22/01/2018

**To**

**Executive Engineer,**

**Kishoregonj WD Division, BWDB, Kishoregonj**

# Subject: Contractor’s Notice of Early Warning as Per GCC Clause 44.1 Increase of Cost and Delay of Execution for Contract Package KISH/PW-09

Dear Sir,

This is to inform you that the work under the above contract have been delayed by following events and they will cause additional cost and extension of intended completion date. Events and particulars are as follows.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Events** | **Additional Cost(Lakh)** | **Time Extension** | **Relevant GCC Clause** | **Remarks** |
| 1.Failure to Hanover Site for Diversion Channel | 15.00 | Up to 30/06/2021 | GCC 13.1& GCC 69.1 |  |

This notice is served to fulfil my contractual obligation of Early Warning as per GCC clause 44.1

Yours sincerely,

# Contractor