## Input_sheet
| Package Name | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
0 | BWDB/Brah/HFMLIP/PW-01 | Regulator Rehablitation | nos | 2 | 87.5 | 0 | BRAH/PW-01 | New | 16 | 0 | R-14 | BRAH
1 | BWDB/Brah/HFMLIP/PW-01 | Regulator Rehablitation | nos | 2 | 87.5 | 0 | BRAH/PW-01 | New | 16 | 0 | R-15 | BRAH
2 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Rehablitation of Submersible Embankment | Km | 0 | 0 | 0 | HOBI/PW-01 | 0 | 1 | 0 | R-8 | HOBI
3 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Construction of Causeway for Aralia (4&6m). | nos. | 1 | 27.05 | Need rehabilitation of existing 3-vent regulator instead of reinstallation of 2-vent regulator. | HOBI/PW-01 | Rehab | 2 |  | R-8 | HOBI
4 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Construction of Causeway for Aralia (4&6m). | nos. | 1 | 300 | Need 6.0 m causeway instead of 4.0 m causeway. | HOBI/PW-01 | Rehab | 2 | 0 | R-8 | HOBI
5 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Irrigation Inlet | Km | 19.695 | 857.52 | 0 | HOBI/PW-01 | Rehab | 8 | 664867.22 | R-8 | HOBI
6 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 4.0m wide Causeway | Km | 16.76 | 385.43 | 2.40 Km length will be increased. | HOBI/PW-01 | Rehab | 10 | 127061.11 | R-8 | HOBI
7 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Re-excavation of Khal/River (Rehab. Khal 2.295 km & River 17.40 km) | nos. | 2 | 456 | 1 no. additional 4 m width Causeway will be needed. | HOBI/PW-02 | Rehab | 5 | 0 | R-7 | HOBI
8 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Replacement of Reg. Gates & other related works | nos. | 0 | 0 | 0 | HOBI/PW-02 | Rehab | 4 | 0 | R-7 | HOBI
9 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 4m Causeway | Km | 3.312 | 54.82 | 0 | HOBI/PW-02 | Rehab | 8 | 124772.75 | R-7 | HOBI
10 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Box Drainage Outlet | Km | 26.952 | 739.82 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10 | 408978.43 | R-7 | HOBI
11 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 6.0m wide Causeway | km | 5.64 | 154.82 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10 | 0 | R-8 | HOBI
12 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Regulator Gate repair | Nos | 4 | 13.77 | 0 | HOBI/PW-02 | 0 | 16 | 0 | R-7 | HOBI
13 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-hab of Regulator | Nos | 9 | 21.23 | 0 | HOBI/PW-02 | 0 | 16 | 0 | R-5 | HOBI
14 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of Khal (New Haor) | Km | 23.815 | 1161.49 | Concerned XEN proposed to raise the height of embkt. | HOBI/PW-04 | New | 11 | 256912.018 | N-10 | HOBI
15 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Const of Box Drainage Outlet | nos. | 1 | 400 | 0 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
16 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Re-excavation of Khal (Rehab. Kairdhala & Aralia Beel ) | nos. | 4 | 460 | 0 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
17 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Rehab. of submersible Embankment (Re-section Kairadhala-16.02 km & Aralia-14.124 km and Const. Aralia-8.36 km) | nos. | 1 | 231.95 | 0 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
18 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Replacement of Reg. Gates & other related works | nos. | 1 | 125 | 0 | HOBI/PW-05 | New | 5 | 0 | N-10 | HOBI
19 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | (a) Re-Inatallation of Reguator((one no.32 vent 1.50mx1.80m ) | nos. | 15 | 134 | 0 | HOBI/PW-06 | New | 1 | 0 | N-10 | HOBI
20 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Rehab. of submersible Embankment ( Aralia-22.484 km) | nos. | 9 | 540 | 0 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
21 | BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Const. of Submersible Embankment | nos. | 2 | 356.4 | Size of pitching block will be enhanced. | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
22 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 4 vent (1.50 mx1.80m) | nos. | 2 | 529.6 | 0 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
23 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 1 vent (1.50 mx1.80m) | Km | 18.048 | 606.84 | 0 | HOBI/PW-07 | New | 7 | 403996.842 | N-10 | HOBI
24 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 2 vent (1.50 mx1.80m) | Km | 12.01 | 319.92 | 0 | HOBI/PW-07 | New | 7 | 208662.994 | N-10 | HOBI
25 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of River (New Haor) | nos. | 1 | 9.69 | 0 | HOBI/PW-07 | New | 12 | 0 | N-10 | HOBI
26 | BWDB/Hobi/HFMLIP/PW-07 | O&M During Construction | LS | 0 | 0 | 0 | HOBI/PW-08 | New | 17 | 0 | A-1 | HOBI
27 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | Km | 1.22 | 52.46 | 0 | KISH/PW-01 | Rehab | 8 | 304227.48 | R-1 | KISH
28 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | Km | 2.151 | 92.47 | 0 | KISH/PW-01 | Rehab | 8 | 304227.48 | R-2 | KISH
29 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | Km | 8.18 | 351.62 | 0 | KISH/PW-01 | Rehab | 8 | 304227.48 | R-3 | KISH
30 | BWDB/Kish/HFMLIP/PW-32 Dakshiner Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 6 | 25.64 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-4 | KISH
31 | BWDB/Kish/HFMLIP/PW-32 Naogaon Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 2 | 8.55 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-3 | KISH
32 | BWDB/Kish/HFMLIP/PW-32 Noapara Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 3 | 12.81 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-2 | KISH
33 | BWDB/Kish/HFMLIP/PW-32 Nunnir Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 2 | 8.55 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-1 | KISH
34 | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 | 0 | KISH/PW-02 | New | 3 | 0 | N-1 | KISH
35 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | Km | 11.095 | 211.74 | 0 | KISH/PW-02 | New | 7 | 211770.02 | N-1 | KISH
36 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | Km | 0.315 | 14.81 | 0 | KISH/PW-02 | New | 11 | 2953 | N-1 | KISH
37 | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | nos. | 1 | 155.52 | 0 | KISH/PW-03 | New | 3 | 0 | N-2 | KISH
38 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 10.383 | 554.48 | 0 | KISH/PW-03 | New | 11 | 109104.8 | N-2 | KISH
39 | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | nos. | 2 | 198 | 0 | KISH/PW-04 | New | 3 | 0 | N-2 | KISH
40 | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 256 | 0 | KISH/PW-04 | New | 3 | 0 | N-2 | KISH
41 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 6.471 | 264 | 0 | KISH/PW-04 | New | 11 | 50421.04 | N-2 | KISH
42 | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | nos. | 1 | 220 | 0 | KISH/PW-05 | New | 3 | 0 | N-2 | KISH
43 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | Km | 12.214 | 580 | 0 | KISH/PW-05 | New | 11 | 98770 | N-2 | KISH
44 | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 243 | 0 | KISH/PW-06 | New | 3 | 0 | N-2 | KISH
45 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 20 | 597 | 0 | KISH/PW-06 | New | 7 | 577707.02 | N-2 | KISH
46 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 25.7 | 680 | 0 | KISH/PW-07 | New | 7 | 945139.04 | N-3 | KISH
47 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | Km | 0.8 | 23 | 0 | KISH/PW-07 | New | 11 | 12696 | N-3 | KISH
48 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 70 | 0 | KISH/PW-09 | New | 4 | 0 | N-2 | KISH
49 | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of 6.00 m causeway | nos. | 1 | 237.5 | 0 | KISH/PW-09 | New | 5 | 0 | N-2 | KISH
50 | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 170 | Regulators are converted to causeway. | KISH/PW-09 | New | 5 | 0 | N-3 | KISH
51 | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 237.5 | 0 | KISH/PW-09 | New | 5 | 0 | N-3 | KISH
52 | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 150 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3 | 0 | N-4 | KISH
53 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 243 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5 | 0 | N-4 | KISH
54 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 11.98 | 623 | 0 | KISH/PW-10 | New | 11 | 121988 | N-4 | KISH
55 | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | nos. | 1 | 326.37 | 0 | KISH/PW-11 | New | 3 | 0 | N-4 | KISH
56 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 10.86 | 540 | 0 | KISH/PW-11 | New | 11 | 109155.3 | N-4 | KISH
57 | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 | 0 | KISH/PW-12 | New | 3 | 0 | N-4 | KISH
58 | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | nos. | 1 | 303.33 | 0 | KISH/PW-12 | New | 3 | 0 | N-4 | KISH
59 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 10.757 | 422.65 | 0 | KISH/PW-12 | New | 7 | 371757.99 | N-4 | KISH
60 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 235 | 0 | KISH/PW-13 | New | 3 | 0 | N-5 | KISH
61 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | nos. | 1 | 175 | 0 | KISH/PW-13 | New | 3 | 0 | N-5 | KISH
62 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | Km | 10 | 490 | 0 | KISH/PW-13 | New | 11 | 215922 | N-5 | KISH
63 | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | nos. | 1 | 219.6 | 0 | KISH/PW-14 | New | 3 | 0 | N-5 | KISH
64 | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | nos. | 0 | 0 | 0 | KISH/PW-14 | New | 3 | 0 | N-5 | KISH
65 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | Km | 16.9 | 705.4 | 0 | KISH/PW-14 | New | 11 | 194853 | N-5 | KISH
66 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 1 | 0 | Regulator c onverted by 6.00 m causeway | KISH/PW-15 | New | 5 | 0 | N-5 | KISH
67 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | Km | 9 | 600 | 0 | KISH/PW-15 | New | 11 | 133316.13 | N-5 | KISH
68 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 404.5 | 0 | KISH/PW-16 | New | 3 | 0 | N-5 | KISH
69 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | Km | 14.12 | 531.3 | 0 | KISH/PW-16 | New | 11 | 143610.85 | N-5 | KISH
70 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 25 | 274.32 | 0 | KISH/PW-17 | New | 1 | 0 | N-5 | KISH
71 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 1 | 675 | 0 | KISH/PW-17 | New | 3 | 0 | N-5 | KISH
72 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 115.24 | 0 | KISH/PW-17 | New | 3 | 0 | N-5 | KISH
73 | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 5 | 177.44 | 0 | KISH/PW-17 | New | 4 | 0 | N-5 | KISH
74 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | Km | 13.17 | 561 | 0 | KISH/PW-17 | New | 11 | 202851.03 | N-5 | KISH
75 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 537 | 0 | KISH/PW-18 | New | 5 | 0 | N-5 | KISH
76 | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 1 | 445 | 0 | KISH/PW-18 | New | 5 | 0 | N-5 | KISH
77 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 26.035 | 615 | 0 | KISH/PW-18 | New | 7 | 453822.6 | N-5 | KISH
78 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 22.933 | 1065 | 0 | KISH/PW-19 | New | 7 | 577753.68 | N-5 | KISH
79 | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 15 | 100.05 | 0 | KISH/PW-20 | New | 1 | 0 | N-2 | KISH
80 | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 7 | 46.6 | 0 | KISH/PW-20 | New | 1 | 0 | N-3 | KISH
81 | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 14 | 93.35 | 0 | KISH/PW-20 | New | 1 | 0 | N-4 | KISH
82 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 3 | 128.25 | 0 | KISH/PW-20 | New | 4 | 0 | N-2 | KISH
83 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | nos. | 0 | 0 | 0 | KISH/PW-20 | New | 4 | 0 | N-3 | KISH
84 | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 42.75 | 0 | KISH/PW-20 | New | 4 | 0 | N-4 | KISH
85 | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 178 | 0 | KISH/PW-20 | New | 5 | 0 | N-2 | KISH
86 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 2 | 356 | 0 | KISH/PW-20 | New | 5 | 0 | N-3 | KISH
87 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 178 | 0 | KISH/PW-20 | New | 5 | 0 | N-4 | KISH
88 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 1 | 225 | 0 | KISH/PW-21 | New | 3 | 0 | N-6 | KISH
89 | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 160 | 0 | KISH/PW-21 | New | 3 | 0 | N-6 | KISH
90 | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 10 | 463.48 | 0 | KISH/PW-21 | New | 11 | 121065.93 | N-6 | KISH
91 | BWDB/Kish/HFMLIP/PW-29 O&M During Construction | O&M During Construction | nos. | 5 | 125 | 0 | KISH/PW-21 | New | 12 | 0 | N-6 | KISH
92 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 6 | 73 | 0 | KISH/PW-22 | New | 1 | 0 | N-6 | KISH
93 | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | nos. | 3 | 116 | 0 | KISH/PW-22 | New | 4 | 0 | N-6 | KISH
94 | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.m width Causeway | nos. | 1 | 195 | 0 | KISH/PW-22 | New | 5 | 0 | N-6 | KISH
95 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 9.92 | 210 | 0 | KISH/PW-22 | New | 7 | 146641.43 | N-6 | KISH
96 | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | Km | 11 | 290 | 0 | KISH/PW-22 | New | 11 | 91984.7 | N-6 | KISH
97 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 4 | 41.87 | 0 | KISH/PW-23 | New | 1 | 0 | N-7 | KISH
98 | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 2 | 640.67 | 0 | KISH/PW-23 | New | 3 | 0 | N-7 | KISH
99 | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 39.54 | 0 | KISH/PW-23 | New | 4 | 0 | N-7 | KISH
100 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | Km | 1.925 | 32.63 | 0 | KISH/PW-23 | New | 7 | 23149.28 | N-7 | KISH
101 | BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | Km | 4.51 | 105.29 | 0 | KISH/PW-23 | New | 11 | 51688.691 | N-7 | KISH
102 | BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | Km | 19.843 | 918.58 | 0 | KISH/PW-24 | New | 11 | 214238.2 | N-8 | KISH
103 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 15 | 125 | 0 | KISH/PW-25 | New | 1 | 0 | N-8 | KISH
104 | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | nos. | 1 | 397 | 0 | KISH/PW-25 | New | 3 | 0 | N-8 | KISH
105 | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 44 | 0 | KISH/PW-25 | New | 4 | 0 | N-8 | KISH
106 | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | nos. | 1 | 200 | 0 | KISH/PW-25 | New | 5 | 0 | N-8 | KISH
107 | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | nos. | 1 | 320 | 0 | KISH/PW-25 | New | 5 | 0 | N-8 | KISH
108 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 11 | 425 | 0 | KISH/PW-25 | New | 7 | 342244.7 | N-8 | KISH
109 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 22.7 | 479 | 0 | KISH/PW-26 | New | 7 | 468821.04 | N-9 | KISH
110 | BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | Km | 0.54 | 23 | 0 | KISH/PW-26 | New | 11 | 11787.77 | N-9 | KISH
111 | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 314 | 0 | KISH/PW-27 | New | 3 | 0 | N-9 | KISH
112 | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | nos. | 0 | 0 | 0 | KISH/PW-27 | New | 3 | 0 | N-9 | KISH
113 | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | nos. | 4 | 49 | 0 | KISH/PW-27 | New | 4 | 0 | N-9 | KISH
114 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 1 | 440 | 0 | KISH/PW-27 | New | 5 | 0 | N-9 | KISH
115 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 1 | 160 | 0 | KISH/PW-27 | New | 5 | 0 | N-9 | KISH
116 | BWDB/Kish/HFMLIP/PW-31 Naogaon Haor Part -B Kishoreganj | Construction of Submersible Embankment with Slope/Crest Protection work (Type-A 0.73 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 55 | 1850 | 0 | KISH/PW-28 | New | 15 | 0 | A-1 | KISH
117 | BWDB/Kish/HFMLIP/PW-33 Threshing Floor Construction | O&M During Construction | L.S. | 1 | 50 | 0 | KISH/PW-29 | New | 17 | 0 | A-1 | KISH
118 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 4.481 | 1566 | 0 | KISH/PW-30 | New | 11 | 0 | N-5 | KISH
119 | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.649 | 1674 | 0 | KISH/PW-31 | New | 11 | 0 | N-5 | KISH
120 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.275 | 1701.95 | 0 | KISH/PW-32 | New | 11 | 0 | N-2 | KISH
121 | BWDB/Kish/HFMLIP/PW-33 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.191 | 1036.79 | 0 | KISH/PW-33-Lot-1 | New | 11 | 0 | N-2 | KISH
122 | BWDB/Kish/HFMLIP/PW-33 Sonair Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 4.845 | 1417 | 0 | KISH/PW-33-Lot-2 | New | 11 | 0 | N-2 | KISH
123 | BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 0 | 0 | 0 | KISH/PW-33-Lot-1 | New | 11 | 0 | N-2 | KISH
124 | BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 0 | 0 | 0 | KISH/PW-33-Lot-1 | New | 11 | 0 | N-2 | KISH
125 | BWDB/Kish/HFMLIP/PW-34 | Construction of threshing floor | Nos | 20 | 225 | 0 | KISH/PW-34 | New | 14 | 0 | N-5 | KISH
126 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 10.69 | 345.15 | 0 | NETR/PW-01 | Rehab | 9 | 0 | R-11 | NETR
127 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | Km | 35.52 | 1146.85 | 0 | NETR/PW-01 | Rehab | 9 | 603554.12 | R-9 | NETR
128 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 30.98 | 507.2842 | 0 | NETR/PW-02 | Rehab | 8 | 914740.64 | R-10 | NETR
129 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 6.133 | 100.4252 | 0 | NETR/PW-02 | Rehab | 8 | 914740.64 | R-11 | NETR
130 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Replacement of Reg. Gates & other related works | Km | 13.27 | 217.2906 | 0 | NETR/PW-02 | Rehab | 8 | 914740.64 | R-9 | NETR
131 | BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal Project (b) Kangsha River Scheme (30.98 Km) | nos. | 1 | 389.57 | 0 | NETR/PW-03 | Rehab | 2 | 0 | R-9 | NETR
132 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Replacement of Reg. Gates & other related works | km | 20.9 | 562.43 | 0 | NETR/PW-03 | 0 | 9 | 312275.643 | R-10 | NETR
133 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of Submersible Embankment | Km | 3.56 | 68 | 0 | NETR/PW-03 | Rehab | 10 | 14852.987 | R-11 | NETR
134 | BWDB/Netra/HFMLIP/PW-07 Dharmapasah Rui Beel | Re-excavation of River (Lower Kongsha River 10.50 km & Gunai River 11.44 Km) | Nos | 16 | 40 | 0 | NETR/PW-03 | 0 | 16 | 0 | R-10 | NETR
135 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Irrigation Inlet | Nos | 6 | 15 | 0 | NETR/PW-03 | 0 | 16 | 0 | R-11 | NETR
136 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Submersible Embankment | Nos | 10 | 25 | 0 | NETR/PW-03 | 0 | 16 | 0 | R-9 | NETR
137 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 10.195 | 484.75 | 0 | NETR/PW-04 | Rehab | 8 | 792075.56 | R-12 | NETR
138 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-Sectioning of Submersible Embankment | Km | 13.838 | 680.25 | 0 | NETR/PW-04 | Rehab | 8 | 792075.56 | R-13 | NETR
139 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Irrigation Inlet | Km | 9.75 | 315 | 0 | NETR/PW-04 | Rehab | 10 | 191943.37 | R-12 | NETR
140 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of New Regulators 2 vent (1.50mx1.80m) | Nos | 16 | 40 | 24.033 | NETR/PW-04 | 0 | 16 | 0 | R-12 | NETR
141 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Box Drainage Outlet | Nos | 8 | 20 | 0 | NETR/PW-04 | 0 | 16 | 0 | R-13 | NETR
142 | BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (c) Singer Beel Scheme (6.133 Km) | nos. | 3 | 712.43 | 0 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
143 | BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (a) Damapara Water Management Project.(13.27 Km) | nos. | 1 | 439.67 | 0 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
144 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Box Drainage Outlet | Km | 3.071 | 57.25 | 0 | NETR/PW-05 | New | 11 | 25797.655 | N-11 | NETR
145 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Singer Beel-10.69) | nos. | 2 | 16.92 | 0 | NETR/PW-06 | New | 1 | 0 | N-11 | NETR
146 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (a) Re-Sectioning of Full Embankment (Kangsha)- 20.90 km. | nos. | 2 | 85.01 | 0 | NETR/PW-06 | New | 4 | 0 | N-11 | NETR
147 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 13.37 | 540 | 0 | NETR/PW-06 | New | 7 | 368599.89 | N-11 | NETR
148 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehabilitation of existing Regulator 4 vent | nos. | 1 | 19.43 | 0 | NETR/PW-06 | New | 12 | 0 | N-11 | NETR
149 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 21.94 | 995 | 0 | NETR/PW-07 | New | 7 | 677328 | N-12 | NETR
150 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Dampara-35.828) | nos. | 3 | 37 | 0 | NETR/PW-08 | New | 1 | 0 | N-12 | NETR
151 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Re-Installation of Regulator 5 vent (1.50mx1.80m, Dampara) | nos. | 2 | 490 | 0 | NETR/PW-08 | New | 3 | 0 | N-12 | NETR
152 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (b) Re-Sectioning of Submersible Embankment (Singer beel)- 3.56 Km. | nos. | 5 | 300 | 0 | NETR/PW-08 | New | 4 | 0 | N-12 | NETR
153 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Re-excavation of Khal (New) | Km | 0 | 0 | 0 | NETR/PW-08 | New | 11 | 0 | N-12 | NETR
154 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Box Drainage Outlet | nos. | 9 | 107.07 | 0 | SUNM/PW-01 | New | 1 | 0 | N-14 | SUNM
155 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 4.0 m width Causeway | nos. | 7 | 301.63 | 0 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
156 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 4.0 m width Causeway | Km | 13.928 | 603.75 | Need more 6 nos. Khal for re-excavation extra cost will remain same. | SUNM/PW-01 | New | 7 | 206690 | N-14 | SUNM
157 | BWDB/Sunam/HFMLIP/PW-07 Dharmapasha Rui Bill Haor | Const of Submersible Embankment with Slope/Crest Protection Work (Type-A -0.700 km,Type-B 2.800 km & Fuse Type-0.025 ) | Km | 16.54 | 550.12 | XEN reported that no need 17.34 km embkt. | SUNM/PW-01 | New | 11 | 399171.48 | N-14 | SUNM
158 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Irrigation Inlet | Km | 36.58 | 1275 | 0 | SUNM/PW-02 | New | 7 | 913100 | N-14 | SUNM
159 | BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Divn-2) | Re-excavation of River (New Haor) (Piain River) | nos. | 1 | 221.62 | 0 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
160 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 345.16 | 0 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
161 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 3 | 578.71 | 0 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
162 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 259.36 | 0 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
163 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Box Drainage Outlet | Km | 34.94 | 1564 | 0 | SUNM/PW-04 | New | 11 | 0 | N-12 | SUNM
164 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Re-excavation of Khal (New Haor)(4 Nos. Khal) | nos. | 1 | 270 | 0 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
165 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Submersible Embankment | nos. | 1 | 318 | 0 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
166 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 6.0 m width Causeway | nos. | 1 | 281 | 0 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
167 | BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Submersible Embankment | nos. | 3 | 722 | 0 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
168 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Irrigation Inlet | nos. | 12 | 131.28 | 0 | SUNM/PW-06 | New | 1 | 0 | N-12 | SUNM
169 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 45.13 | 0 | SUNM/PW-06 | New | 4 | 0 | N-12 | SUNM
170 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 6.0 m width Causeway | Km | 66.043 | 1423.59 | 0 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
171 | Construction of Submersible Embankment with Slope Protection Work | Re-excavation of Khal (New Haor) | Km | 3.405 | 1556.04 | 0 | SUNM/PW-07 | New | 11 | 0 | N-12 | SUNM

## haor_wise_quantity
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | Chandpur Haor Sub-Project | N-1 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1 | Nunnir Haor Sub-Project | N-2 | 15 | 0 | 6 | 4 | 2 | 0 | 20 | 0 | 0 | 0 | 38.379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | Boro Haor Sub-Project | N-3 | 7 | 0 | 0 | 0 | 4 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | Noapara Haor Sub-Project | N-4 | 14 | 0 | 4 | 1 | 2 | 0 | 10.757 | 0 | 0 | 0 | 22.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | Naogaon Haor Sub-Project | N-5 | 25 | 0 | 6 | 5 | 3 | 0 | 48.968 | 0 | 0 | 0 | 70.32 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 6
5 | Badla Haor Sub-Project | N-6 | 6 | 0 | 2 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | Chatal Haor Sub-Project | N-7 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | Dakhshiner Haor Sub-Project | N-8 | 15 | 0 | 1 | 1 | 2 | 0 | 11 | 0 | 0 | 0 | 19.843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | Suniar Haor Sub-Project | N-9 | 0 | 0 | 2 | 4 | 2 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | Mokhar Haor Sub-Project | N-10 | 15 | 0 | 6 | 9 | 5 | 0 | 30.058 | 0 | 0 | 0 | 23.815 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | Ganesh Haor Sub-Project | N-11 | 2 | 0 | 4 | 2 | 0 | 0 | 13.37 | 0 | 0 | 0 | 3.071 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | Dharmapasha Rui Beel Sub-Project | N-12 | 15 | 0 | 4 | 6 | 4 | 0 | 87.983 | 0 | 0 | 0 | 38.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | Dhakua Haor Sub-Project | N-14 | 9 | 0 | 2 | 7 | 4 | 0 | 50.508 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 16
15 | Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 17
16 | Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 18
17 | Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 19
18 | Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 20
19 | Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | Aralia Khal Sub-Project | R-7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3.312 | 0 | 26.952 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 22
21 | Bashira River Re-excavation Sub-Project | R-8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | Dampara Water Management Scheme | R-9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13.27 | 35.52 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 24
23 | Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.98 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 25
24 | Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.133 | 10.69 | 3.56 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 26
25 | Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.195 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 27
26 | Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 28
27 | Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 29
28 | Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 30
29 | All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 1 | 0 | 31

## haor_wise_cost
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | Chandpur Haor Sub-Project | N-1 | 0 | 0 | 123.45 | 0 | 0 | 0 | 211.74 | 0 | 0 | 0 | 14.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1 | Nunnir Haor Sub-Project | N-2 | 100.05 | 0 | 1072.52 | 198.25 | 415.5 | 0 | 597 | 0 | 0 | 0 | 5554.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | Boro Haor Sub-Project | N-3 | 46.6 | 0 | 0 | 0 | 763.5 | 0 | 680 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | Noapara Haor Sub-Project | N-4 | 93.35 | 0 | 1007.19 | 42.75 | 421 | 0 | 422.65 | 0 | 0 | 0 | 1163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | Naogaon Haor Sub-Project | N-5 | 274.32 | 0 | 1824.34 | 177.44 | 982 | 0 | 1680 | 0 | 0 | 0 | 6127.7 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 6
5 | Badla Haor Sub-Project | N-6 | 73 | 0 | 385 | 116 | 195 | 0 | 210 | 0 | 0 | 0 | 753.48 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | Chatal Haor Sub-Project | N-7 | 41.87 | 0 | 640.67 | 39.54 | 0 | 0 | 32.63 | 0 | 0 | 0 | 105.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | Dakhshiner Haor Sub-Project | N-8 | 125 | 0 | 397 | 44 | 520 | 0 | 425 | 0 | 0 | 0 | 918.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | Suniar Haor Sub-Project | N-9 | 0 | 0 | 314 | 49 | 600 | 0 | 479 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | Mokhar Haor Sub-Project | N-10 | 134 | 0 | 1091.95 | 540 | 1011 | 0 | 926.76 | 0 | 0 | 0 | 1161.49 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | Ganesh Haor Sub-Project | N-11 | 16.92 | 0 | 1152.1 | 85.01 | 0 | 0 | 540 | 0 | 0 | 0 | 57.25 | 19.43 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | Dharmapasha Rui Beel Sub-Project | N-12 | 168.28 | 0 | 1078 | 345.13 | 1003 | 0 | 2418.59 | 0 | 0 | 0 | 3120.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | Dhakua Haor Sub-Project | N-14 | 107.07 | 0 | 566.78 | 301.63 | 838.07 | 0 | 1878.75 | 0 | 0 | 0 | 550.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.55 | 0 | 0 | 16
15 | Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.81 | 0 | 0 | 17
16 | Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.55 | 0 | 0 | 18
17 | Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.64 | 0 | 0 | 19
18 | Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.23 | 0 | 0 | 20
19 | Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | Aralia Khal Sub-Project | R-7 | 0 | 0 | 0 | 0 | 456 | 0 | 0 | 54.82 | 0 | 739.82 | 0 | 0 | 0 | 0 | 0 | 13.77 | 0 | 0 | 22
21 | Bashira River Re-excavation Sub-Project | R-8 | 0 | 327.05 | 0 | 0 | 0 | 0 | 0 | 857.52 | 0 | 540.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | Dampara Water Management Scheme | R-9 | 0 | 389.57 | 0 | 0 | 0 | 0 | 0 | 217.2906 | 1146.85 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 24
23 | Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507.2842 | 562.43 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 25
24 | Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.4252 | 345.15 | 68 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 26
25 | Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.75 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 27
26 | Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 28
27 | Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.5 | 0 | 0 | 29
28 | Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.5 | 0 | 0 | 30
29 | All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850 | 0 | 50 | 0 | 31

## Package_wise_quantity
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | KISH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 2
1 | KISH/PW-02 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | KISH/PW-03 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | KISH/PW-04 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | KISH/PW-05 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
5 | KISH/PW-06 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | KISH/PW-09 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | KISH/PW-10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | KISH/PW-11 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | KISH/PW-12 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 10.757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | KISH/PW-13 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | KISH/PW-14 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | KISH/PW-15 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | KISH/PW-16 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
15 | KISH/PW-17 | 0 | 25 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 13.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
16 | KISH/PW-18 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 26.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
17 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
18 | KISH/PW-20 | 0 | 36 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
19 | KISH/PW-21 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | KISH/PW-22 | 0 | 6 | 0 | 0 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
21 | KISH/PW-23 | 0 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
23 | KISH/PW-25 | 0 | 15 | 0 | 1 | 1 | 2 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
24 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
25 | KISH/PW-27 | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
26 | KISH/PW-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 28
27 | KISH/PW-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 29
28 | KISH/PW-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
29 | KISH/PW-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
30 | KISH/PW-32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
31 | KISH/PW-33-Lot-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
32 | KISH/PW-33-Lot-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
33 | KISH/PW-34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 35
34 | HOBI/PW-01 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 16.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
35 | HOBI/PW-02 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3.312 | 0 | 32.592 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 37
36 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38
37 | HOBI/PW-05 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
38 | HOBI/PW-06 | 0 | 15 | 0 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
39 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.058 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 41
40 | HOBI/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
41 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
42 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
43 | NETR/PW-03 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 20.9 | 3.56 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 45
44 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.033 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 46
45 | NETR/PW-05 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47
46 | NETR/PW-06 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 13.37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 48
47 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
48 | NETR/PW-08 | 0 | 3 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
49 | SUNM/PW-01 | 0 | 9 | 0 | 0 | 7 | 0 | 0 | 13.928 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
50 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
51 | SUNM/PW-03 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
52 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
53 | SUNM/PW-05 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
54 | SUNM/PW-06 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 66.043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56
55 | SUNM/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
56 | BRAH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 58

## Package_wise_cost
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | KISH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.55 | 0 | 0 | 2
1 | KISH/PW-02 | 0 | 0 | 0 | 123.45 | 0 | 0 | 0 | 211.74 | 0 | 0 | 0 | 14.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | KISH/PW-03 | 0 | 0 | 0 | 155.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | KISH/PW-04 | 0 | 0 | 0 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | KISH/PW-05 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
5 | KISH/PW-06 | 0 | 0 | 0 | 243 | 0 | 0 | 0 | 597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | KISH/PW-09 | 0 | 0 | 0 | 0 | 70 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | KISH/PW-10 | 0 | 0 | 0 | 150 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | KISH/PW-11 | 0 | 0 | 0 | 326.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | KISH/PW-12 | 0 | 0 | 0 | 530.82 | 0 | 0 | 0 | 422.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | KISH/PW-13 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | KISH/PW-14 | 0 | 0 | 0 | 219.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | KISH/PW-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | KISH/PW-16 | 0 | 0 | 0 | 404.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
15 | KISH/PW-17 | 0 | 274.32 | 0 | 790.24 | 177.44 | 0 | 0 | 0 | 0 | 0 | 0 | 561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
16 | KISH/PW-18 | 0 | 0 | 0 | 0 | 0 | 982 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
17 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
18 | KISH/PW-20 | 0 | 240 | 0 | 0 | 171 | 712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
19 | KISH/PW-21 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463.48 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | KISH/PW-22 | 0 | 73 | 0 | 0 | 116 | 195 | 0 | 210 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
21 | KISH/PW-23 | 0 | 41.87 | 0 | 640.67 | 39.54 | 0 | 0 | 32.63 | 0 | 0 | 0 | 105.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 918.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
23 | KISH/PW-25 | 0 | 125 | 0 | 397 | 44 | 520 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
24 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
25 | KISH/PW-27 | 0 | 0 | 0 | 314 | 49 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
26 | KISH/PW-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850 | 0 | 0 | 0 | 28
27 | KISH/PW-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 29
28 | KISH/PW-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
29 | KISH/PW-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
30 | KISH/PW-32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1701.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
31 | KISH/PW-33-Lot-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
32 | KISH/PW-33-Lot-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
33 | KISH/PW-34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 35
34 | HOBI/PW-01 | 0 | 0 | 327.05 | 0 | 0 | 0 | 0 | 0 | 857.52 | 0 | 385.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
35 | HOBI/PW-02 | 0 | 0 | 0 | 0 | 0 | 456 | 0 | 0 | 54.82 | 0 | 894.64 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 37
36 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38
37 | HOBI/PW-05 | 0 | 0 | 0 | 1091.95 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
38 | HOBI/PW-06 | 0 | 134 | 0 | 0 | 540 | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
39 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926.76 | 0 | 0 | 0 | 0 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 41
40 | HOBI/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
41 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
42 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
43 | NETR/PW-03 | 0 | 0 | 389.57 | 0 | 0 | 0 | 0 | 0 | 0 | 562.43 | 68 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 45
44 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 46
45 | NETR/PW-05 | 0 | 0 | 0 | 1152.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47
46 | NETR/PW-06 | 0 | 16.92 | 0 | 0 | 85.01 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 19.43 | 0 | 0 | 0 | 0 | 0 | 0 | 48
47 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
48 | NETR/PW-08 | 0 | 37 | 0 | 490 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
49 | SUNM/PW-01 | 0 | 107.07 | 0 | 0 | 301.63 | 0 | 0 | 603.75 | 0 | 0 | 0 | 550.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
50 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
51 | SUNM/PW-03 | 0 | 0 | 0 | 566.78 | 0 | 838.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
52 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
53 | SUNM/PW-05 | 0 | 0 | 0 | 588 | 0 | 1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
54 | SUNM/PW-06 | 0 | 131.28 | 0 | 0 | 45.13 | 0 | 0 | 1423.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56
55 | SUNM/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1556.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
56 | BRAH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 58

## Structure_wise_cost
| name | stcode | Dpptransfer | Unit | Quantity | GoB | RPA | DPA | Total | Annex_input_Transfer | Dpp_Transfer_row
0 | Construction of Irrigation Inlet | 1 | 1 | Nos | 127 | 165.2644 | 1015.1956 | 0 | 1180.46 | 0 | 0
1 | Rehab Regulator Rehab Haor | 2 | 2 | Nos | 3 | 100.3268 | 616.2932 | 0 | 716.62 | 0 | 0
2 | Regulator | 3 | 3 | Nos | 40 | 1351.42 | 8301.58 | 0 | 9653 | 0 | 0
3 | Box Drainage Outlet | 4 | 3 | Nos | 43 | 271.425 | 1667.325 | 0 | 1938.75 | 0 | 0
4 | Causeway | 5 | 3 | Nos | 31 | 1008.7098 | 6196.3602 | 0 | 7205.07 | 0 | 0
5 | Bridge | 6 | 3 | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Khal_River Reexcavation(New Haor) | 7 | 4 | Km | 343.984 | 1470.2968 | 9031.8232 | 0 | 10502.12 | 0 | 0
7 | Khal_River Reexcavation(Rehab Haor) | 8 | 5 | Km | 108.974 | 475.8446 | 2923.0454 | 0 | 3398.89 | 0 | 0
8 | Embankment Rehablitation | 9 | 6 | Km | 67.11 | 287.6202 | 1766.8098 | 0 | 2054.43 | 0 | 0
9 | Submersible Embankment Rehabilitation | 10 | 7 | Km | 62.662 | 232.8298 | 1430.2402 | 0 | 1663.07 | 0 | 0
10 | Submersible Embankment Construction | 11 | 8 | Km | 260.318 | 2740.0772 | 16831.9028 | 0 | 19571.98 | 0 | 0
11 | Rehab Regulator New Haor | 12 | 9 | Nos | 7 | 21.5768 | 132.5432 | 0 | 154.12 | 0 | 0
12 | Embankment Slope Protection Work | 13 | 8 | Km | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Thrashing Floor Construction | 14 | 10 | Nos | 20 | 31.5 | 193.5 | 0 | 225 | 0 | 0
14 | Construction of WMG | 15 | 11 | Nos | 55 | 259 | 1591 | 0 | 1850 | 0 | 0
15 | Gate Repair By M&E | 16 | 12 | Nos | 86 | 56.777 | 348.773 | 0 | 405.55 | 0 | 0
16 | O&M During Construction | 17 | 13 | LS | 1 | 50 | 0 | 0 | 50 | 0 | 0

## Civil_Works_Cost
| Code | Description | rindex | unit | Quantity | GOB | RPA | DPA | TOTAL | Unitcost | Tindex
0 | 4111306 | Construction of Irrigation Inlet (New Haors) | 58 | Nos | 127 | 165.2644 | 1015.1956 | 0 | 1180.46 | 9.295 | 2
1 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 59 | Nos | 3 | 100.3268 | 616.2932 | 0 | 716.62 | 238.8733 | 3
2 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 60 | Nos | 114 | 2631.5548 | 16165.2652 | 0 | 18796.82 | 164.8844 | 4
3 | 4111307 | Re-excavation of Khal/River (New Haors) | 61 | Km | 343.984 | 1470.2968 | 9031.8232 | 0 | 10502.12 | 30.5308 | 5
4 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 62 | Km | 108.974 | 475.8446 | 2923.0454 | 0 | 3398.89 | 31.1899 | 6
5 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 63 | Km | 67.11 | 287.6202 | 1766.8098 | 0 | 2054.43 | 30.6129 | 7
6 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 64 | Km | 62.662 | 232.8298 | 1430.2402 | 0 | 1663.07 | 26.5403 | 8
7 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 65 | Km | 260.318 | 2740.0772 | 16831.9028 | 0 | 19571.98 | 75.1849 | 9
8 | 4111201 | Rehabilitation of Regulator (New Haors) | 66 | Nos | 7 | 21.5768 | 132.5432 | 0 | 154.12 | 22.0171 | 10
9 | 4111201 | Threshing Floor Construction | 67 | Nos | 20 | 31.5 | 193.5 | 0 | 225 | 11.25 | 11
10 | 4111201 | Construction of WMG Office | 68 | Nos | 55 | 259 | 1591 | 0 | 1850 | 33.6364 | 12
11 | 3258114 | Gate Repair By M&E | 40 | Nos | 86 | 56.777 | 348.773 | 0 | 405.55 | 4.7157 | 13
12 | 4111201 | O&M During Construction | 69 | LS | 1 | 50 | 0 | 0 | 50 | 50 | 14

## district_wise_quantity
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | rrow_index
0 | Kishoreganj | KISH | 86 | 0 | 24 | 19 | 16 | 0 | 162.065 | 11.551 | 0 | 0 | 178.547 | 5 | 0 | 20 | 55 | 13 | 1 | 0 | 2
1 | Hobiganj | HOBI | 15 | 2 | 6 | 9 | 7 | 0 | 30.058 | 23.007 | 0 | 49.352 | 23.815 | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 3
2 | Netrokona | NETR | 5 | 1 | 6 | 7 | 0 | 0 | 35.31 | 74.416 | 67.11 | 13.31 | 3.071 | 1 | 0 | 0 | 0 | 56 | 0 | 0 | 4
3 | Sunamgonj | SUNM | 21 | 0 | 4 | 8 | 8 | 0 | 116.551 | 0 | 0 | 0 | 54.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | Brahmanbaria | BRAH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 6

## district_wise_cost
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | rrow_index
0 | Kishoreganj | KISH | 754.19 | 0 | 5764.17 | 666.98 | 3897 | 0 | 4738.02 | 496.55 | 0 | 0 | 14683.08 | 125 | 0 | 225 | 1850 | 55.55 | 50 | 33305.54 | 2
1 | Hobiganj | HOBI | 134 | 327.05 | 1091.95 | 540 | 1467 | 0 | 926.76 | 912.34 | 0 | 1280.07 | 1161.49 | 9.69 | 0 | 0 | 0 | 35 | 0 | 7885.35 | 3
2 | Netrokona | NETR | 53.92 | 389.57 | 1642.1 | 385.01 | 0 | 0 | 1535 | 1990 | 2054.43 | 383 | 57.25 | 19.43 | 0 | 0 | 0 | 140 | 0 | 8649.71 | 4
3 | Sunamgonj | SUNM | 238.35 | 0 | 1154.78 | 346.76 | 1841.07 | 0 | 3302.34 | 0 | 0 | 0 | 3670.16 | 0 | 0 | 0 | 0 | 0 | 0 | 10553.46 | 5
4 | Brahmanbaria | BRAH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 175 | 6

## code_wise_costcomaprision
| Code | Description | Quantity_1st | GOB_1st | RPA_1st | DPA_1st | TOTAL_1st | rindex | Quantity_2nd | GOB_2nd | RPA_2nd | DPA_2nd | TOTAL_2nd | Quantity_diff | GOB_Diff | RPA_diff | DPA_diff | TOTAL_diff | Tindex | annex2_input_index | annex9_input_index | UintCost | units | Distribution _code
0 | 3111302 | Conveyance Allowance | 1 Item | 10 | 0 | 0 | 10 | 12 | 1 Item | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 2 | 2 | 2 | 5 | 0 | 1
1 | 3111327 | Overtime Allowance | 1 Item | 10 | 0 | 0 | 10 | 13 | 1 Item | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 10 | 0 | 1
2 | 3111338 | Other Allowance | 1 Item | 140 | 0 | 0 | 140 | 14 | 1 Item | 140 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 140 | 0 | 1
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 1 Item | 100 | 0 | 0 | 100 | 16 | 1 Item | 120 | 0 | 0 | 120 | 0 | 20 | 0 | 0 | 20 | 5 | 5 | 5 | 120 | 0 | 1
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 1 Item | 245 | 0 | 0 | 245 | 17 | 1 Item | 245 | 0 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 245 | 0 | 1
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 1 Item | 2596.27 | 0 | 0 | 2596.27 | 18 | 1 Item | 2596.27 | 0 | 0 | 2596.27 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 2596.27 | 0 | 1
6 | 3211119 | Postage | 1 Item | 25 | 0 | 0 | 25 | 19 | 1 Item | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 8 | 8 | 8 | 5 | 0 | 1
7 | 3211120 | Telephones/Telegram/Teleprinter | 1 Item | 25 | 0 | 0 | 25 | 20 | 1 Item | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 9 | 9 | 9 | 5 | 0 | 1
8 | 3211117 | Telex/Fax/Internet | 1 Item | 25 | 0 | 0 | 25 | 21 | 1 Item | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 10 | 10 | 10 | 5 | 0 | 1
9 | 3221104 | Registration Fee (Vehicles) | 1 Item | 15 | 0 | 0 | 15 | 22 | 1 Item | 20 | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 5 | 11 | 11 | 11 | 20 | 0 | 1
10 | 3211115 | Water | 1 Item | 10 | 0 | 0 | 10 | 23 | 1 Item | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 12 | 12 | 12 | 5 | 0 | 1
11 | 3211113 | Electricity | 1 Item | 15 | 0 | 0 | 15 | 24 | 1 Item | 20 | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 5 | 13 | 13 | 13 | 20 | 0 | 1
12 | 3243102 | Gas & Fuel | 1 Item | 200 | 0 | 0 | 200 | 25 | 1 Item | 40 | 0 | 0 | 40 | 0 | -160 | 0 | 0 | -160 | 14 | 14 | 14 | 40 | 0 | 2
13 | 3243101 | Petrol and Lubricant | 1 Item | 150 | 0 | 0 | 150 | 26 | 1 Item | 170 | 0 | 0 | 170 | 0 | 20 | 0 | 0 | 20 | 15 | 15 | 15 | 170 | 0 | 2
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 1 Item | 3 | 0 | 0 | 3 | 27 | 1 Item | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 3 | 0 | 1
15 | 3255102 | Printing & Binding | 1 Item | 35 | 0 | 0 | 35 | 28 | 1 Item | 50 | 0 | 0 | 50 | 0 | 15 | 0 | 0 | 15 | 17 | 17 | 17 | 50 | 0 | 1
16 | 3255104 | Stationery, Seals & Stamps | 1 Item | 150 | 0 | 0 | 150 | 29 | 1 Item | 120 | 0 | 0 | 120 | 0 | -30 | 0 | 0 | -30 | 18 | 18 | 18 | 120 | 0 | 1
17 | 3211127 | Books & Periodicals | 1 Item | 2 | 0 | 0 | 2 | 30 | 1 Item | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19 | 2 | 0 | 1
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 1 Item | 0 | 238.54 | 0 | 238.54 | 32 | 1 Item | 0 | 238.54 | 0 | 238.54 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 238.54 | 0 | 3
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 1 Item | 47.81 | 350.6 | 0 | 398.41 | 33 | 1 Item | 64.4 | 472.3 | 0 | 536.7 | 0 | 16.59 | 121.7 | 0 | 138.29 | 21 | 21 | 21 | 536.7 | 0 | 3
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 1 Item | 304 | 2229.34 | 0 | 2533.34 | 34 | 1 Item | 373.9 | 2756.2 | 0 | 3130.1 | 0 | 69.9 | 526.86 | 0 | 596.76 | 22 | 22 | 22 | 3130.1 | 0 | 3
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 1 Item | 158.6 | 1163.08 | 0 | 1321.68 | 35 | 1 Item | 159.7 | 1171.5 | 0 | 1331.2 | 0 | 1.1 | 8.42 | 0 | 9.52 | 23 | 23 | 23 | 1331.2 | 0 | 3
22 | 3211109 | Casual labour/Job worker | 1 Item | 15 | 0 | 0 | 15 | 36 | 1 Item | 22 | 0 | 0 | 22 | 0 | 7 | 0 | 0 | 7 | 24 | 24 | 24 | 22 | 0 | 1
23 | 3256103 | Consumable Stores | 1 Item | 25 | 0 | 0 | 25 | 37 | 1 Item | 15 | 0 | 0 | 15 | 0 | -10 | 0 | 0 | -10 | 25 | 25 | 25 | 15 | 0 | 1
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 71+234 | 0 | 0 | 7901.4 | 7901.4 | 38 | 56+532 | 0 | 0 | 7901.4 | 7901.4 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 26 | 0 | MM | 4
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 1 Item | 25 | 0 | 0 | 25 | 39 | 1 Item | 30 | 0 | 0 | 30 | 0 | 5 | 0 | 0 | 5 | 27 | 27 | 27 | 30 | 0 | 1
26 | 3111332 | b) Interim Evaluation | 1 Item | 10 | 0 | 0 | 10 | 40 | 1 Item | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 28 | 10 | 0 | 1
27 | 3111332 | c) Progress Monitoring | 1 Item | 10 | 0 | 0 | 10 | 41 | 1 Item | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 29 | 10 | 0 | 1
28 | 3257104 | Survey | 1 Item | 162 | 0 | 0 | 162 | 42 | 1 Item | 162 | 0 | 0 | 162 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 162 | 0 | 1
29 | 3255101 | Computer Consumables | 1 Item | 50 | 0 | 0 | 50 | 43 | 1 Item | 60 | 0 | 0 | 60 | 0 | 10 | 0 | 0 | 10 | 31 | 31 | 31 | 60 | 0 | 1
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1 Item | 1700 | 0 | 0 | 1700 | 44 | 1 Item | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 1700 | 0 | 1
31 | 3258101 | Motor Vehicles | L.S. | 100 | 0 | 0 | 100 | 46 | L.S. | 125 | 0 | 0 | 125 | 0 | 25 | 0 | 0 | 25 | 33 | 33 | 33 | 125 | 0 | 5
32 | 3258102 | Furnitures & Fixtures | L.S. | 15 | 0 | 0 | 15 | 47 | L.S. | 10 | 0 | 0 | 10 | 0 | -5 | 0 | 0 | -5 | 34 | 34 | 34 | 10 | 0 | 5
33 | 3258103 | Computers & office equipments | L.S. | 25 | 0 | 0 | 25 | 48 | L.S. | 15 | 0 | 0 | 15 | 0 | -10 | 0 | 0 | -10 | 35 | 35 | 35 | 15 | 0 | 5
34 | 3258105 | Machineries & Equipments | L.S. | 25 | 0 | 0 | 25 | 49 | L.S. | 10 | 0 | 0 | 10 | 0 | -15 | 0 | 0 | -15 | 36 | 36 | 36 | 10 | 0 | 5
35 | 3258107 | Office Building : Repair & Maintenance | L.S. | 20 | 0 | 0 | 20 | 50 | L.S. | 25 | 0 | 0 | 25 | 0 | 5 | 0 | 0 | 5 | 37 | 37 | 37 | 25 | 0 | 5
36 | 3258106 | Residential Building : Repair & Maintenance | L.S. | 20 | 0 | 0 | 20 | 51 | L.S. | 40 | 0 | 0 | 40 | 0 | 20 | 0 | 0 | 20 | 38 | 38 | 38 | 40 | 0 | 5
37 | 3258105 | Engineering Equipments | L.S. | 25 | 0 | 0 | 25 | 52 | L.S. | 20 | 0 | 0 | 20 | 0 | -5 | 0 | 0 | -5 | 39 | 39 | 39 | 20 | 0 | 5
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 104 | 43.5 | 319 | 0 | 362.5 | 54 | 86 | 56.777 | 348.773 | 0 | 405.55 | 0 | 13.277 | 29.773 | 0 | 43.05 | 40 | 40 | 40 | 405.55 | 0 | 8
39 | 3258128 | Water Transport : Repair of Speedboat(s) | L.S. | 10 | 0 | 0 | 10 | 55 | L.S. | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 41 | 41 | 41 | 5 | 0 | 5
40 | 3258107 | Others : Repair & Maintenance | L.S. | 25 | 0 | 0 | 25 | 56 | L.S. | 40 | 0 | 0 | 40 | 0 | 15 | 0 | 0 | 15 | 42 | 42 | 42 | 40 | 0 | 5
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 10 | 702.5 | 0 | 0 | 702.5 | 68 | 10 | 702.5 | 0 | 0 | 702.5 | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 43 | 70.25 | Nos | 6
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 35 | 68.25 | 0 | 0 | 68.25 | 69 | 45 | 68.25 | 0 | 0 | 68.25 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 1.52 | Nos | 6
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 6 | 100 | 0 | 0 | 100 | 71 | 5 | 90 | 0 | 0 | 90 | 0 | -10 | 0 | 0 | -10 | 45 | 45 | 45 | 18 | Nos | 6
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 7 | 8.97 | 0 | 0 | 8.97 | 73 | 7 | 8.97 | 0 | 0 | 8.97 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 46 | 1.28 | Nos | 6
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 7 | 5 | 0 | 0 | 5 | 74 | 2 | 1 | 0 | 0 | 1 | 0 | -4 | 0 | 0 | -4 | 47 | 47 | 47 | 0.5 | Nos | 6
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 17 | 20.5 | 0 | 0 | 20.5 | 76 | 17 | 20.5 | 0 | 0 | 20.5 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 48 | 20.5 | Nos | 6
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 6 | 6 | 0 | 0 | 6 | 77 | 3 | 3 | 0 | 0 | 3 | 0 | -3 | 0 | 0 | -3 | 49 | 49 | 49 | 1 | Nos | 6
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | L.S | 50 | 0 | 0 | 50 | 78 | L.S | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 6
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 30 | 19.5 | 0 | 0 | 19.5 | 80 | 37 | 24.5 | 0 | 0 | 24.5 | 0 | 5 | 0 | 0 | 5 | 51 | 51 | 51 | 0.66 | Nos | 6
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 11 | 13.75 | 0 | 0 | 13.75 | 81 | 11 | 13.75 | 0 | 0 | 13.75 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 1.25 | Nos | 6
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 2 | 1.5 | 0 | 0 | 1.5 | 82 | 2 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 53 | 0.75 | Nos | 6
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 11 | 5.25 | 0 | 0 | 5.25 | 83 | 17 | 5.25 | 0 | 0 | 5.25 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 54 | 0.31 | Nos | 6
53 | 4112314 | Furnitures & Fixtures | LS | 50 | 0 | 0 | 50 | 84 | LS | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 50 | 0 | 6
54 | 4112303 | Aircooler | 15 | 15 | 0 | 0 | 15 | 85 | 15 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 56 | 1 | Nos | 6
55 | 4141101 | Land Acquisition ( 470 hectare) | 470 | 24000 | 0 | 0 | 24000 | 87 | 470 | 19725 | 0 | 0 | 19725 | 0 | -4275 | 0 | 0 | -4275 | 57 | 57 | 57 | 41.97 | ha | 7
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 131 | 151.32 | 1109.68 | 0 | 1261 | 90 | 127 | 165.2644 | 1015.1956 | 0 | 1180.46 | 0 | 13.9444 | -94.4844 | 0 | -80.54 | 58 | 58 | 58 | 9.29 | Nos | 8
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 7(2+5) | 181.8 | 1333.2 | 0 | 1515 | 92 | 3 | 100.3268 | 616.2932 | 0 | 716.62 | 0 | -81.4732 | -716.9068 | 0 | -798.38 | 59 | 59 | 59 | 238.87 | Nos | 8
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 137(57+35+14) | 2437.32 | 17873.68 | 0 | 20311 | 93 | 114 | 2631.5548 | 16165.2652 | 0 | 18796.82 | 0 | 194.2348 | -1708.4148 | 0 | -1514.18 | 60 | 60 | 60 | 164.88 | Nos | 8
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 318 | 1167.48 | 8561.52 | 0 | 9729 | 94 | 343.984 | 1470.2968 | 9031.8232 | 0 | 10502.12 | 0 | 302.8168 | 470.3032 | 0 | 773.12 | 61 | 61 | 61 | 30.53 | Km | 8
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 143 | 301.8 | 2213.2 | 0 | 2515 | 96 | 108.974 | 475.8446 | 2923.0454 | 0 | 3398.89 | 0 | 174.0446 | 709.8454 | 0 | 883.89 | 62 | 62 | 62 | 31.19 | Km | 8
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 84.31 | 306 | 2244 | 0 | 2550 | 97 | 67.11 | 287.6202 | 1766.8098 | 0 | 2054.43 | 0 | -18.3798 | -477.1902 | 0 | -495.57 | 63 | 63 | 63 | 30.61 | Km | 8
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 87.03 | 214.2 | 1570.8 | 0 | 1785 | 98 | 62.662 | 232.8298 | 1430.2402 | 0 | 1663.07 | 0 | 18.6298 | -140.5598 | 0 | -121.93 | 64 | 64 | 64 | 26.54 | Km | 8
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 263.24 | 1434.3 | 10518.2 | 0 | 11952.5 | 99 | 260.318 | 7880.3088 | 11691.6712 | 0 | 19571.98 | 0 | 6446.0088 | 1173.4712 | 0 | 7619.48 | 65 | 65 | 65 | 0 | Km | 8
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 8 | 19.92 | 146.08 | 0 | 166 | 100 | 7 | 21.5768 | 132.5432 | 0 | 154.12 | 0 | 1.6568 | -13.5368 | 0 | -11.88 | 66 | 66 | 66 | 22.02 | Nos | 8
65 | 4111201 | Threshing Floor Construction | 0 | 0 | 0 | 0 | 0 | 101 | 20 | 31.5 | 193.5 | 0 | 225 | 0 | 31.5 | 193.5 | 0 | 225 | 67 | 67 | 67 | 11.25 | Nos | 8
66 | 4111201 | Construction of WMG Office | 60 | 165.6 | 1214.4 | 0 | 1380 | 102 | 55 | 259 | 1591 | 0 | 1850 | 0 | 93.4 | 376.6 | 0 | 470 | 68 | 68 | 68 | 33.64 | Nos | 8
67 | 4111201 | O&M During Construction | L.S | 200 | 0 | 0 | 200 | 103 | 1 | 50 | 0 | 0 | 50 | 0 | -150 | 0 | 0 | -150 | 69 | 69 | 69 | 0 | Iten | 8
68 | 0 | (c) Physical Contingency ( Lump sum): | L.S. | 100 | 158 | 0 | 258 | 106 | L.S. | 30.54 | 0 | 0 | 30.54 | 0 | -69.46 | -158 | 0 | -227.46 | 70 | 70 | 70 | 0 | Item | 9
69 | 0 | (d) Price Contingency (Lump sum): | L.S. | 100.76 | 301.38 | 0 | 402.14 | 107 | L.S. | 10 | 0 | 0 | 10 | 0 | -90.76 | -301.38 | 0 | -392.14 | 71 | 71 | 71 | 0 | Item | 9

## Yearwise-cost-projection
| Code | Description | rindex | Unit Cost | Quantity | TotalCost | Weight | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2020-21-P | 2021-22-P | Investment_Cost_Index | Total_upto_19_20 | Remaining | EC_FACTOR
0 | 3111302 | Conveyance Allowance | 10 | 5 | 1 Item | 5 | 5e-05 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.58 | 0.42 | 9 | 1.51 | 3.49 | 0.902
1 | 3111327 | Overtime Allowance | 11 | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.63 | 0.37 | 10 | 0 | 10 | 0.902
2 | 3111338 | Other Allowance | 12 | 140 | 1 Item | 140 | 0.00139 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.6 | 0.4 | 11 | 50.61 | 89.39 | 0.902
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 14 | 120 | 1 Item | 120 | 0.0012 | 0.99 | 11.92 | 14.98 | 17.96 | 12.7 | 15 | 28.799 | 17.651 | 0.62 | 0.38 | 13 | 73.55 | 46.45 | 0.902
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 15 | 245 | 1 Item | 245 | 0.00244 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.25 | 58.3296 | 35.7504 | 0.62 | 0.38 | 14 | 150.92 | 94.08 | 0.812
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 16 | 2596.27 | 1 Item | 2596.27 | 0.02586 | 223.75 | 464.64 | 327.7 | 337.33 | 249.75 | 359.08 | 367.7316 | 266.2884 | 0.58 | 0.42 | 15 | 1962.25 | 634.02 | 0.812
6 | 3211119 | Postage | 17 | 5 | 1 Item | 5 | 5e-05 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.5 | 2.1634 | 1.5666 | 0.58 | 0.42 | 16 | 1.27 | 3.73 | 0.812
7 | 3211120 | Telephones/Telegram/Teleprinter | 18 | 5 | 1 Item | 5 | 5e-05 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.2 | 2.3363 | 1.4937 | 0.61 | 0.39 | 17 | 1.17 | 3.83 | 0.812
8 | 3211117 | Telex/Fax/Internet | 19 | 5 | 1 Item | 5 | 5e-05 | 0.25 | 0.001 | 0.09 | 0.05 | 0.05 | 0.2 | 2.441 | 1.918 | 0.56 | 0.44 | 18 | 0.641 | 4.359 | 0.812
9 | 3221104 | Registration Fee (Vehicles) | 20 | 20 | 1 Item | 20 | 0.0002 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 1 | 4.4604 | 2.6196 | 0.63 | 0.37 | 19 | 12.92 | 7.08 | 0.812
10 | 3211115 | Water | 21 | 5 | 1 Item | 5 | 5e-05 | 0 | 0.12 | 0.23 | 0.37 | 0.4 | 0.45 | 2.0923 | 1.3377 | 0.61 | 0.39 | 20 | 1.57 | 3.43 | 0.812
11 | 3211113 | Electricity | 22 | 20 | 1 Item | 20 | 0.0002 | 0.19 | 1.67 | 1.78 | 2.31 | 2.78 | 3.5 | 4.2735 | 3.4965 | 0.55 | 0.45 | 21 | 12.23 | 7.77 | 0.812
12 | 3243102 | Gas & Fuel | 23 | 40 | 1 Item | 40 | 0.0004 | 0.94 | 3.7 | 3 | 4 | 5.89 | 6 | 10.0467 | 6.4233 | 0.61 | 0.39 | 22 | 23.53 | 16.47 | 0.812
13 | 3243101 | Petrol and Lubricant | 24 | 170 | 1 Item | 170 | 0.00169 | 0.62 | 6.99 | 18.97 | 18 | 20 | 20 | 48.6894 | 36.7306 | 0.57 | 0.43 | 23 | 84.58 | 85.42 | 0.72
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 25 | 3 | 1 Item | 3 | 3e-05 | 0.08 | 0.749 | 0.01 | 0.22 | 0.1 | 0.15 | 0.93005 | 0.76095 | 0.55 | 0.45 | 24 | 1.309 | 1.691 | 0.902
15 | 3255102 | Printing & Binding | 26 | 50 | 1 Item | 50 | 0.0005 | 0.2 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.355 | 5.981 | 0.61 | 0.39 | 25 | 34.664 | 15.336 | 0.812
16 | 3255104 | Stationery, Seals & Stamps | 27 | 120 | 1 Item | 120 | 0.0012 | 0.97 | 6.972 | 11.2 | 12.79 | 17.98 | 20 | 31.5554 | 18.5326 | 0.63 | 0.37 | 26 | 69.912 | 50.088 | 0.812
17 | 3211127 | Books & Periodicals | 28 | 2 | 1 Item | 2 | 2e-05 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.58 | 0.42 | 27 | 0.48 | 1.52 | 0.812
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 30 | 238.54 | 1 Item | 238.54 | 0.00238 | 0 | 0 | 0 | 0 | 0 | 0 | 238.54 | 0 | 1 | 0 | 29 | 0 | 238.54 | 0.902
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 31 | 536.7 | 1 Item | 536.7 | 0.00535 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 196.17 | 23.418 | 15.612 | 0.6 | 0.4 | 30 | 497.67 | 39.03 | 0.902
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 32 | 3130.1 | 1 Item | 3130.1 | 0.03118 | 0 | 0 | 199.49 | 524.89 | 622.25 | 677.14 | 696.9879 | 409.3421 | 0.63 | 0.37 | 31 | 2023.77 | 1106.33 | 0.902
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 33 | 1331.2 | 1 Item | 1331.2 | 0.01326 | 0 | 0 | 119.7 | 224.29 | 234.21 | 246.66 | 278.487 | 227.853 | 0.55 | 0.45 | 32 | 824.86 | 506.34 | 0.902
22 | 3211109 | Casual labour/Job worker | 34 | 22 | 1 Item | 22 | 0.00022 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.5 | 4.6748 | 2.8652 | 0.62 | 0.38 | 33 | 14.46 | 7.54 | 0.902
23 | 3256103 | Consumable Stores | 35 | 15 | 1 Item | 15 | 0.00015 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.58 | 0.42 | 34 | 6.74 | 8.26 | 0.812
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 36 | 0 | 56+532 | 7901.4 | 0.07871 | 849.67 | 1849.425 | 1123.15 | 689.33 | 686.43 | 500 | 1344.071 | 859.324 | 0.61 | 0.39 | 35 | 5698.005 | 2203.395 | 0.902
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 37 | 30 | 1 Item | 30 | 0.0003 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 5 | 7.1166 | 5.1534 | 0.58 | 0.42 | 36 | 17.73 | 12.27 | 0.902
26 | 3111332 | b) Interim Evaluation | 38 | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0.27 | 0.25 | 0.77 | 1 | 7.71 | 0 | 1 | 0 | 37 | 2.29 | 7.71 | 0.902
27 | 3111332 | c) Progress Monitoring | 39 | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0.3 | 0.25 | 0.75 | 1 | 4.774 | 2.926 | 0.62 | 0.38 | 38 | 2.3 | 7.7 | 0.902
28 | 3257104 | Survey | 40 | 162 | 1 Item | 162 | 0.00161 | 0 | 7.62 | 17.47 | 30 | 29.93 | 50 | 15.3786 | 11.6014 | 0.57 | 0.43 | 39 | 135.02 | 26.98 | 0.902
29 | 3255101 | Computer Consumables | 41 | 60 | 1 Item | 60 | 0.0006 | 0.49 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.242 | 13.2889 | 0.55 | 0.45 | 40 | 30.469 | 29.531 | 0.902
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 42 | 1700 | 1 Item | 1700 | 0.01693 | 0 | 84.31 | 227.97 | 263.24 | 299.93 | 300 | 298.9935 | 225.5565 | 0.57 | 0.43 | 41 | 1175.45 | 524.55 | 0.86
31 | 3258101 | Motor Vehicles | 44 | 125 | L.S. | 125 | 0.00125 | 0.98 | 5.967 | 12 | 21.99 | 20.46 | 15 | 26.7317 | 21.8713 | 0.55 | 0.45 | 43 | 76.397 | 48.603 | 0.86
32 | 3258102 | Furnitures & Fixtures | 45 | 10 | L.S. | 10 | 0.0001 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 2 | 2.88 | 1.92 | 0.6 | 0.4 | 44 | 5.2 | 4.8 | 0.86
33 | 3258103 | Computers & office equipments | 46 | 15 | L.S. | 15 | 0.00015 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.59 | 0.41 | 45 | 8.34 | 6.66 | 0.86
34 | 3258105 | Machineries & Equipments | 47 | 10 | L.S. | 10 | 0.0001 | 0 | 0.22 | 0.01 | 0.5 | 0.5 | 2 | 4.1297 | 2.6403 | 0.61 | 0.39 | 46 | 3.23 | 6.77 | 0.86
35 | 3258107 | Office Building : Repair & Maintenance | 48 | 25 | L.S. | 25 | 0.00025 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.59 | 0.41 | 47 | 19.98 | 5.02 | 0.765
36 | 3258106 | Residential Building : Repair & Maintenance | 49 | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 8.95 | 5.58 | 5 | 11.8726 | 8.5974 | 0.58 | 0.42 | 48 | 19.53 | 20.47 | 0.765
37 | 3258105 | Engineering Equipments | 50 | 20 | L.S. | 20 | 0.0002 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.55 | 0.45 | 49 | 3.39 | 16.61 | 0.86
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 52 | 405.55 | 86 | 405.55 | 0.00404 | 0 | 0 | 59.7 | 24.34 | 10.99 | 58.25 | 158.9301 | 93.3399 | 0.63 | 0.37 | 51 | 153.28 | 252.27 | 0.812
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 53 | 5 | L.S. | 5 | 5e-05 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.75 | 1.1346 | 0.7254 | 0.61 | 0.39 | 52 | 3.14 | 1.86 | 0.812
40 | 3258107 | Others : Repair & Maintenance | 54 | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 2.5 | 4.98 | 3 | 16.5312 | 12.9888 | 0.56 | 0.44 | 53 | 10.48 | 29.52 | 0.902
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 59 | 70.25 | 10 | 702.5 | 0.007 | 346.3 | 138.6 | 0 | 122 | 0 | 95.6 | 0 | 0 | 0 | 0 | 58 | 702.5 | 0 | 0.68
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 60 | 1.52 | 45 | 68.25 | 0.00068 | 5.83 | 26.31 | 10.08 | 8 | 0 | 0 | 18.03 | 0 | 1 | 0 | 59 | 50.22 | 18.03 | 0.68
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 62 | 18 | 5 | 90 | 0.0009 | 0 | 0 | 40.29 | 21 | 0 | 0 | 28.71 | 0 | 1 | 0 | 61 | 61.29 | 28.71 | 0.68
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 64 | 1.28 | 7 | 8.97 | 9e-05 | 3.73 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 6.23 | 2.74 | 0.812
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 65 | 0.5 | 2 | 1 | 1e-05 | 0.79 | 2.74 | 0 | 0 | -0.006 | 0 | 0 | 0 | 0 | 0 | 64 | 3.524 | -2.524 | 0.812
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 67 | 20.5 | 17 | 20.5 | 0.0002 | 0 | 5.55 | 11.15 | 3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 20.5 | 0 | 0.68
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 68 | 1 | 3 | 3 | 3e-05 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 3 | 0 | 0.68
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 69 | 0 | L.S | 50 | 0.0005 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 35.51 | 0 | 1 | 0 | 68 | 14.49 | 35.51 | 0.68
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 71 | 0.66 | 37 | 24.5 | 0.00024 | 3.88 | 7.14 | 6.18 | 2.27 | 0 | 0 | 5.03 | 0 | 1 | 0 | 70 | 19.47 | 5.03 | 0.812
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 72 | 1.25 | 11 | 13.75 | 0.00014 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 3.87 | 0 | 1 | 0 | 71 | 9.88 | 3.87 | 0.812
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 73 | 0.75 | 2 | 1.5 | 1e-05 | 0 | 0.2 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1 | 0 | 72 | 0.2 | 1.3 | 0.812
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 74 | 0.31 | 17 | 5.25 | 5e-05 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 1.17 | 0 | 1 | 0 | 73 | 4.08 | 1.17 | 0.812
53 | 4112314 | Furnitures & Fixtures | 75 | 50 | LS | 50 | 0.0005 | 7.96 | 8.45 | 8.99 | 9.96 | 9.97 | 0 | 2.8954 | 1.7746 | 0.62 | 0.38 | 74 | 45.33 | 4.67 | 0.812
54 | 4112303 | Aircooler | 76 | 1 | 15 | 15 | 0.00015 | 0 | 0 | 3.77 | 2 | 3.96 | 4 | 0.7747 | 0.4953 | 0.61 | 0.39 | 75 | 13.73 | 1.27 | 0.812
55 | 4141101 | Land Acquisition ( 470 hectare) | 78 | 41.97 | 470 | 19725 | 0.19649 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 2049.42 | 3351.98 | 0 | 1 | 0 | 77 | 16373.02 | 3351.98 | 0.902
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 81 | 9.29 | 127 | 1180.46 | 0.01176 | 0 | 0 | 0 | 0 | 116.72 | 490.33 | 315.3755 | 258.0345 | 0.55 | 0.45 | 80 | 607.05 | 573.41 | 0.902
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 83 | 238.87 | 3 | 716.62 | 0.00714 | 0 | 0 | 0 | 0 | 0 | 0 | 437.1382 | 279.4818 | 0.61 | 0.39 | 82 | 0 | 716.62 | 0.765
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 84 | 164.88 | 114 | 18796.82 | 0.18724 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 8105.58 | 2774.0238 | 1773.5562 | 0.61 | 0.39 | 83 | 14249.24 | 4547.58 | 0.765
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 85 | 30.53 | 343.984 | 10502.12 | 0.10462 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 3936.68 | 321.2968 | 232.6632 | 0.58 | 0.42 | 84 | 9948.16 | 553.96 | 0.761
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 87 | 31.19 | 108.974 | 3398.89 | 0.03386 | 0 | 0 | 0 | 0 | 455.04 | 900.73 | 1164.5784 | 878.5416 | 0.57 | 0.43 | 86 | 1355.77 | 2043.12 | 0.761
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 88 | 30.61 | 67.11 | 2054.43 | 0.02047 | 0 | 0 | 0 | 0 | 452.46 | 913.26 | 392.5647 | 296.1453 | 0.57 | 0.43 | 87 | 1365.72 | 688.71 | 0.761
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 89 | 26.54 | 62.662 | 1663.07 | 0.01657 | 0 | 0 | 0 | 0 | 341.85 | 657.55 | 418.1121 | 245.5579 | 0.63 | 0.37 | 88 | 999.4 | 663.67 | 0.761
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 90 | 0 | 260.318 | 19571.98 | 0.19493 | 0 | 0 | 336.91 | 3910 | 1880.15 | 4650.77 | 5364.4315 | 3429.7185 | 0.61 | 0.39 | 89 | 10777.83 | 8794.15 | 0.761
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 91 | 22.02 | 7 | 154.12 | 0.00154 | 0 | 0 | 0 | 0 | 73.26 | 0 | 50.1332 | 30.7268 | 0.62 | 0.38 | 90 | 73.26 | 80.86 | 0.761
65 | 4111201 | Threshing Floor Construction | 92 | 11.25 | 20 | 225 | 0.00224 | 0 | 0 | 0 | 0 | 0 | 0 | 137.25 | 87.75 | 0.61 | 0.39 | 91 | 0 | 225 | 2.761
66 | 4111201 | Construction of WMG Office | 93 | 33.64 | 55 | 1850 | 0.01843 | 0 | 0 | 0 | 0 | 42.09 | 348.14 | 861.2643 | 598.5057 | 0.59 | 0.41 | 92 | 390.23 | 1459.77 | 0.765
67 | 4111201 | O&M During Construction | 94 | 0 | 1 | 50 | 0.0005 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5 | 21.5 | 0.57 | 0.43 | 93 | 0 | 50 | 0.761
68 | 0 | (c) Physical Contingency ( Lump sum): | 97 | 0 | L.S. | 30.54 | 0.0003 | 0 | 0 | 0 | 0 | 0 | 0 | 19.2402 | 11.2998 | 0.63 | 0.37 | 96 | 0 | 30.54 | 0.765
69 | 0 | (d) Price Contingency (Lump sum): | 98 | 0 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 4.5 | 0.55 | 0.45 | 97 | 0 | 10 | 0

## Annex-9_detail_phasing
| Code | Description | rindex | Total-cum | GoB-cum | RPA-cum | DPA-cum | Total-19-20 | GoB-19-20 | RPA-19-20 | DPA-19-20 | Total-20-21 | GoB-20-21 | RPA-20-21 | DPA-20-21 | Total-21-22 | GoB-21-22 | RPA-21-22 | DPA-21-22 | Total-DPP-Cost | Total-Phased-Cost-1 | Total-Phased-GoB | Total-Phased-RPA | Total-Phased-DPA | Total-Phased-Cost-2 | Check1 | Check2
0 | 3111302 | Conveyance Allowance | 11 | 1.01 | 1.01 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.0242 | 2.0242 | 0 | 0 | 1.4658 | 1.4658 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
1 | 3111327 | Overtime Allowance | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 6.3 | 0 | 0 | 3.7 | 3.7 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
2 | 3111338 | Other Allowance | 13 | 36.61 | 36.61 | 0 | 0 | 14 | 14 | 0 | 0 | 53.634 | 53.634 | 0 | 0 | 35.756 | 35.756 | 0 | 0 | 140 | 140 | 140 | 0 | 0 | 140 | 0 | 0
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 15 | 58.54 | 58.54 | 0 | 0 | 15 | 15 | 0 | 0 | 28.799 | 28.799 | 0 | 0 | 17.651 | 17.651 | 0 | 0 | 120 | 119.99 | 119.99 | 0 | 0 | 119.99 | 0.01 | 0.01
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 16 | 116.67 | 116.67 | 0 | 0 | 34.25 | 34.25 | 0 | 0 | 58.3296 | 58.3296 | 0 | 0 | 35.7504 | 35.7504 | 0 | 0 | 245 | 245 | 245 | 0 | 0 | 245 | 0 | 0
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 17 | 1603.18 | 1603.18 | 0 | 0 | 359.08 | 359.08 | 0 | 0 | 367.7316 | 367.7316 | 0 | 0 | 266.2884 | 266.2884 | 0 | 0 | 2596.27 | 2596.28 | 2596.28 | 0 | 0 | 2596.28 | -0.01 | -0.01
6 | 3211119 | Postage | 18 | 0.77 | 0.77 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.1634 | 2.1634 | 0 | 0 | 1.5666 | 1.5666 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
7 | 3211120 | Telephones/Telegram/Teleprinter | 19 | 0.97 | 0.97 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 2.3363 | 2.3363 | 0 | 0 | 1.4937 | 1.4937 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
8 | 3211117 | Telex/Fax/Internet | 20 | 0.44 | 0.44 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 2.441 | 2.441 | 0 | 0 | 1.918 | 1.918 | 0 | 0 | 5 | 4.999 | 4.999 | 0 | 0 | 4.999 | 0.001 | 0.001
9 | 3221104 | Registration Fee (Vehicles) | 21 | 11.92 | 11.92 | 0 | 0 | 1 | 1 | 0 | 0 | 4.4604 | 4.4604 | 0 | 0 | 2.6196 | 2.6196 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 3.5527e-15 | 3.5527e-15
10 | 3211115 | Water | 22 | 1.11 | 1.11 | 0 | 0 | 0.45 | 0.45 | 0 | 0 | 2.0923 | 2.0923 | 0 | 0 | 1.3377 | 1.3377 | 0 | 0 | 5 | 4.99 | 4.99 | 0 | 0 | 4.99 | 0.01 | 0.01
11 | 3211113 | Electricity | 23 | 8.74 | 8.74 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 4.2735 | 4.2735 | 0 | 0 | 3.4965 | 3.4965 | 0 | 0 | 20 | 20.01 | 20.01 | 0 | 0 | 20.01 | -0.01 | -0.01
12 | 3243102 | Gas & Fuel | 24 | 17.52 | 17.52 | 0 | 0 | 6 | 6 | 0 | 0 | 10.0467 | 10.0467 | 0 | 0 | 6.4233 | 6.4233 | 0 | 0 | 40 | 39.99 | 39.99 | 0 | 0 | 39.99 | 0.01 | 0.01
13 | 3243101 | Petrol and Lubricant | 25 | 64.59 | 64.59 | 0 | 0 | 20 | 20 | 0 | 0 | 48.6894 | 48.6894 | 0 | 0 | 36.7306 | 36.7306 | 0 | 0 | 170 | 170.01 | 170.01 | 0 | 0 | 170.01 | -0.01 | -0.01
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 26 | 1.16 | 1.16 | 0 | 0 | 0.15 | 0.15 | 0 | 0 | 0.93005 | 0.93005 | 0 | 0 | 0.76095 | 0.76095 | 0 | 0 | 3 | 3.001 | 3.001 | 0 | 0 | 3.001 | -0.001 | -0.001
15 | 3255102 | Printing & Binding | 27 | 34.16 | 34.16 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 9.355 | 9.355 | 0 | 0 | 5.981 | 5.981 | 0 | 0 | 50 | 49.996 | 49.996 | 0 | 0 | 49.996 | 0.004 | 0.004
16 | 3255104 | Stationery, Seals & Stamps | 28 | 49.91 | 49.91 | 0 | 0 | 20 | 20 | 0 | 0 | 31.5554 | 31.5554 | 0 | 0 | 18.5326 | 18.5326 | 0 | 0 | 120 | 119.998 | 119.998 | 0 | 0 | 119.998 | 0.002 | 0.002
17 | 3211127 | Books & Periodicals | 29 | 0.28 | 0.28 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0.8816 | 0.8816 | 0 | 0 | 0.6384 | 0.6384 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.54 | 0 | 238.54 | 0 | 0 | 0 | 0 | 0 | 238.54 | 238.54 | 0 | 238.54 | 0 | 238.54 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 32 | 301.5 | 22.54 | 278.96 | 0 | 196.17 | 21.0294 | 175.1406 | 0 | 23.418 | 2.5104 | 20.9076 | 0 | 15.612 | 1.6736 | 13.9384 | 0 | 536.7 | 536.7 | 47.7534 | 488.9466 | 0 | 536.7 | 0 | 0
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 33 | 1346.63 | 80.34 | 1266.29 | 0 | 677.14 | 72.5894 | 604.5506 | 0 | 696.9879 | 74.7171 | 622.2708 | 0 | 409.3421 | 43.8815 | 365.4606 | 0 | 3130.1 | 3130.1 | 271.528 | 2858.572 | 0 | 3130.1 | 0 | 0
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 34 | 578.2 | 35.47 | 542.73 | 0 | 246.66 | 26.442 | 220.218 | 0 | 278.487 | 29.8538 | 248.6332 | 0 | 227.853 | 24.4258 | 203.4272 | 0 | 1331.2 | 1331.2 | 116.1916 | 1215.0084 | 0 | 1331.2 | 0 | 0
22 | 3211109 | Casual labour/Job worker | 35 | 10.96 | 10.96 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 4.6748 | 4.6748 | 0 | 0 | 2.8652 | 2.8652 | 0 | 0 | 22 | 22 | 22 | 0 | 0 | 22 | 0 | 0
23 | 3256103 | Consumable Stores | 36 | 3.74 | 3.74 | 0 | 0 | 3 | 3 | 0 | 0 | 4.7908 | 4.7908 | 0 | 0 | 3.4692 | 3.4692 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 37 | 5168.01 | 0 | 0 | 5168.01 | 500 | 0 | 0 | 500 | 1344.071 | 0 | 0 | 1344.071 | 859.324 | 0 | 0 | 859.324 | 7901.4 | 7871.405 | 0 | 0 | 7871.405 | 7871.405 | 29.995 | 29.995
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 38 | 12.73 | 12.73 | 0 | 0 | 5 | 5 | 0 | 0 | 7.1166 | 7.1166 | 0 | 0 | 5.1534 | 5.1534 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 0
26 | 3111332 | b) Interim Evaluation | 39 | 1.29 | 1.29 | 0 | 0 | 1 | 1 | 0 | 0 | 7.71 | 7.71 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
27 | 3111332 | c) Progress Monitoring | 40 | 1.3 | 1.3 | 0 | 0 | 1 | 1 | 0 | 0 | 4.774 | 4.774 | 0 | 0 | 2.926 | 2.926 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
28 | 3257104 | Survey | 41 | 85.02 | 85.02 | 0 | 0 | 50 | 50 | 0 | 0 | 15.3786 | 15.3786 | 0 | 0 | 11.6014 | 11.6014 | 0 | 0 | 162 | 162 | 162 | 0 | 0 | 162 | 2.8422e-14 | 2.8422e-14
29 | 3255101 | Computer Consumables | 42 | 20.47 | 20.47 | 0 | 0 | 10 | 10 | 0 | 0 | 16.242 | 16.242 | 0 | 0 | 13.2889 | 13.2889 | 0 | 0 | 60 | 60.001 | 60.001 | 0 | 0 | 60.001 | -0.001 | -0.001
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 43 | 875.46 | 875.46 | 0 | 0 | 300 | 300 | 0 | 0 | 298.9935 | 298.9935 | 0 | 0 | 225.5565 | 225.5565 | 0 | 0 | 1700 | 1700.01 | 1700.01 | 0 | 0 | 1700.01 | -0.01 | -0.01
31 | 3258101 | Motor Vehicles | 45 | 61.4 | 61.4 | 0 | 0 | 15 | 15 | 0 | 0 | 26.7317 | 26.7317 | 0 | 0 | 21.8713 | 21.8713 | 0 | 0 | 125 | 125.003 | 125.003 | 0 | 0 | 125.003 | -0.003 | -0.003
32 | 3258102 | Furnitures & Fixtures | 46 | 3.2 | 3.2 | 0 | 0 | 2 | 2 | 0 | 0 | 2.88 | 2.88 | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
33 | 3258103 | Computers & office equipments | 47 | 5.34 | 5.34 | 0 | 0 | 3 | 3 | 0 | 0 | 3.9294 | 3.9294 | 0 | 0 | 2.7306 | 2.7306 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
34 | 3258105 | Machineries & Equipments | 48 | 1.22 | 1.22 | 0 | 0 | 2 | 2 | 0 | 0 | 4.1297 | 4.1297 | 0 | 0 | 2.6403 | 2.6403 | 0 | 0 | 10 | 9.99 | 9.99 | 0 | 0 | 9.99 | 0.01 | 0.01
35 | 3258107 | Office Building : Repair & Maintenance | 49 | 19.98 | 19.98 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9618 | 2.9618 | 0 | 0 | 2.0582 | 2.0582 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 25 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | 50 | 14.53 | 14.53 | 0 | 0 | 5 | 5 | 0 | 0 | 11.8726 | 11.8726 | 0 | 0 | 8.5974 | 8.5974 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
37 | 3258105 | Engineering Equipments | 51 | 1.39 | 1.39 | 0 | 0 | 2 | 2 | 0 | 0 | 9.1355 | 9.1355 | 0 | 0 | 7.4745 | 7.4745 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 53 | 95.03 | 10.83 | 84.2 | 0 | 58.25 | 8.5744 | 49.6756 | 0 | 158.9301 | 23.3945 | 135.5356 | 0 | 93.3399 | 13.7396 | 79.6003 | 0 | 405.55 | 405.55 | 56.5385 | 349.0115 | 0 | 405.55 | 0 | 0
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 54 | 2.39 | 2.39 | 0 | 0 | 0.75 | 0.75 | 0 | 0 | 1.1346 | 1.1346 | 0 | 0 | 0.7254 | 0.7254 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | -8.8818e-16 | -8.8818e-16
40 | 3258107 | Others : Repair & Maintenance | 55 | 7.48 | 7.48 | 0 | 0 | 3 | 3 | 0 | 0 | 16.5312 | 16.5312 | 0 | 0 | 12.9888 | 12.9888 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 60 | 606.9 | 606.9 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702.5 | 702.5 | 702.5 | 0 | 0 | 702.5 | 0 | 0
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 61 | 50.22 | 50.22 | 0 | 0 | 0 | 0 | 0 | 0 | 18.03 | 18.03 | 0 | 0 | 0 | 0 | 0 | 0 | 68.25 | 68.25 | 68.25 | 0 | 0 | 68.25 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 63 | 61.29 | 61.29 | 0 | 0 | 0 | 0 | 0 | 0 | 28.71 | 28.71 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 90 | 0 | 0 | 90 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 8.97 | 8.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.97 | 8.97 | 8.97 | 0 | 0 | 8.97 | 0 | 0
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 66 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 68 | 20.5 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5 | 20.5 | 20.5 | 0 | 0 | 20.5 | 0 | 0
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 69 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 70 | 9.49 | 9.49 | 0 | 0 | 5 | 5 | 0 | 0 | 35.51 | 35.51 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 0
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 72 | 19.47 | 19.47 | 0 | 0 | 0 | 0 | 0 | 0 | 5.03 | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 | 24.5 | 24.5 | 24.5 | 0 | 0 | 24.5 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 73 | 9.88 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 3.87 | 3.87 | 0 | 0 | 0 | 0 | 0 | 0 | 13.75 | 13.75 | 13.75 | 0 | 0 | 13.75 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 74 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 75 | 4.08 | 4.08 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 5.25 | 5.25 | 0 | 0 | 5.25 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | 76 | 45.32 | 45.32 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8954 | 2.8954 | 0 | 0 | 1.7746 | 1.7746 | 0 | 0 | 50 | 49.99 | 49.99 | 0 | 0 | 49.99 | 0.01 | 0.01
54 | 4112303 | Aircooler | 77 | 9.73 | 9.73 | 0 | 0 | 4 | 4 | 0 | 0 | 0.7747 | 0.7747 | 0 | 0 | 0.4953 | 0.4953 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | 79 | 14323.6 | 14323.6 | 0 | 0 | 2049.42 | 2049.42 | 0 | 0 | 3351.98 | 3351.98 | 0 | 0 | 0 | 0 | 0 | 0 | 19725 | 19725 | 19725 | 0 | 0 | 19725 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 82 | 116.72 | 16.34 | 100.38 | 0 | 490.33 | 68.6462 | 421.6838 | 0 | 315.3755 | 44.1526 | 271.2229 | 0 | 258.0345 | 36.1248 | 221.9097 | 0 | 1180.46 | 1180.46 | 165.2636 | 1015.1964 | 0 | 1180.46 | 0 | 0
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437.1382 | 61.1993 | 375.9389 | 0 | 279.4818 | 39.1275 | 240.3543 | 0 | 716.62 | 716.62 | 100.3268 | 616.2932 | 0 | 716.62 | 0 | -1.1369e-13
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 85 | 6143.66 | 889.49 | 5254.17 | 0 | 8105.58 | 1134.7812 | 6970.7988 | 0 | 2774.0238 | 388.3633 | 2385.6605 | 0 | 1773.5562 | 248.2979 | 1525.2583 | 0 | 18796.82 | 18796.82 | 2660.9324 | 16135.8876 | 0 | 18796.82 | 0 | 0
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 86 | 6011.48 | 791.08 | 5220.4 | 0 | 3936.68 | 551.1352 | 3385.5448 | 0 | 321.2968 | 44.9816 | 276.3152 | 0 | 232.6632 | 32.5728 | 200.0904 | 0 | 10502.12 | 10502.12 | 1419.7696 | 9082.3504 | 0 | 10502.12 | 0 | 0
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 88 | 455.04 | 64.36 | 390.68 | 0 | 900.73 | 126.1022 | 774.6278 | 0 | 1164.5784 | 163.041 | 1001.5374 | 0 | 878.5416 | 122.9958 | 755.5458 | 0 | 3398.89 | 3398.89 | 476.499 | 2922.391 | 0 | 3398.89 | 0 | 0
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 89 | 452.46 | 63.49 | 388.97 | 0 | 913.26 | 127.8564 | 785.4036 | 0 | 392.5647 | 54.9591 | 337.6056 | 0 | 296.1453 | 41.4603 | 254.685 | 0 | 2054.43 | 2054.43 | 287.7658 | 1766.6642 | 0 | 2054.43 | 0 | 0
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 90 | 341.85 | 48.84 | 293.01 | 0 | 657.55 | 92.057 | 565.493 | 0 | 418.1121 | 58.5357 | 359.5764 | 0 | 245.5579 | 34.3781 | 211.1798 | 0 | 1663.07 | 1663.07 | 233.8108 | 1429.2592 | 0 | 1663.07 | 0 | 2.2737e-13
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 91 | 6127.06 | 779.02 | 5348.04 | 0 | 4650.77 | 651.1078 | 3999.6622 | 0 | 5364.4315 | 751.0204 | 4613.4111 | 0 | 3429.7185 | 480.1606 | 2949.5579 | 0 | 19571.98 | 19571.98 | 2661.3088 | 16910.6712 | 0 | 19571.98 | 0 | 0
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 92 | 73.26 | 9.77 | 63.49 | 0 | 0 | 0 | 0 | 0 | 50.1332 | 7.0186 | 43.1146 | 0 | 30.7268 | 4.3018 | 26.425 | 0 | 154.12 | 154.12 | 21.0904 | 133.0296 | 0 | 154.12 | 0 | 0
65 | 4111201 | Threshing Floor Construction | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.25 | 19.215 | 118.035 | 0 | 87.75 | 12.285 | 75.465 | 0 | 225 | 225 | 31.5 | 193.5 | 0 | 225 | 0 | 0
66 | 4111201 | Construction of WMG Office | 94 | 42.09 | 5.47 | 36.62 | 0 | 348.14 | 48.7396 | 299.4004 | 0 | 861.2643 | 120.577 | 740.6873 | 0 | 598.5057 | 83.7908 | 514.7149 | 0 | 1850 | 1850 | 258.5774 | 1591.4226 | 0 | 1850 | 2.2737e-13 | 0
67 | 4111201 | O&M During Construction | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5 | 3.99 | 24.51 | 0 | 21.5 | 3.01 | 18.49 | 0 | 50 | 50 | 7 | 43 | 0 | 50 | 0 | 0
68 | 0 | (c) Physical Contingency ( Lump sum): | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.2402 | 19.2402 | 0 | 0 | 11.2998 | 11.2998 | 0 | 0 | 30.54 | 30.54 | 30.54 | 0 | 0 | 30.54 | 0 | 0
69 | 0 | (d) Price Contingency (Lump sum): | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 5.5 | 0 | 0 | 4.5 | 4.5 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0

## EIRR_INPUT
| Financial_Year | Financial_Cost | Economic_Cost | Financial _Input_Index | Financial _Input_Index.1
0 | Year-1 | 1456.294 | 1212.6888 | 8 | 8
1 | Year-2 | 2682.927 | 2329.3642 | 9 | 9
2 | Year-3 | 7942.686 | 6957.1397 | 10 | 10
3 | Year-4 | 15867.59 | 13168.0538 | 11 | 11
4 | Year-5 | 17642.414 | 14304.0036 | 12 | 12
5 | Year-6 | 24717.06 | 19492.7755 | 13 | 13
6 | Year-7 | 19554.143 | 16131.702 | 14 | 14
7 | Year-8 | 10523.7 | 8503.3383 | 15 | 15

## Distribution_of_cost
| Item | costcode | rindex | 1st Revised | 2nd revised | difference
0 | Office Administration | 1 | 2 | 5403.27 | 5360.27 | -43
1 | Fuel & Lubricant | 2 | 3 | 350 | 210 | -140
2 | Training and Livelihood | 3 | 4 | 4491.97 | 5236.54 | 744.57
3 | Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
4 | Repair & Maintenance | 5 | 6 | 265 | 290 | 25
5 | Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22 | -12
6 | Land Acquisition | 7 | 8 | 24000 | 19725 | -4275
7 | Civilworks | 8 | 9 | 53727 | 60569.06 | 6842.06
8 | contingency | 9 | 10 | 660.14 | 40.54 | -619.6

## quantity_comaprision
| Code | Description | U1 | Q1 | U2 | Q2 | U3 | Q3 | rindex | annex_index
0 | 3111302 | Conveyance Allowance | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 12 | 2
1 | 3111327 | Overtime Allowance | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 13 | 3
2 | 3111338 | Other Allowance | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 14 | 4
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 16 | 5
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 17 | 6
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 18 | 7
6 | 3211119 | Postage | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 19 | 8
7 | 3211120 | Telephones/Telegram/Teleprinter | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 20 | 9
8 | 3211117 | Telex/Fax/Internet | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 21 | 10
9 | 3221104 | Registration Fee (Vehicles) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 22 | 11
10 | 3211115 | Water | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 23 | 12
11 | 3211113 | Electricity | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 24 | 13
12 | 3243102 | Gas & Fuel | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 25 | 14
13 | 3243101 | Petrol and Lubricant | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 26 | 15
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 27 | 16
15 | 3255102 | Printing & Binding | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 28 | 17
16 | 3255104 | Stationery, Seals & Stamps | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 29 | 18
17 | 3211127 | Books & Periodicals | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 30 | 19
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 32 | 20
19 | 0 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 33 | 21
20 | 0 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 34 | 22
21 | 0 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 35 | 23
22 | 3211109 | Casual labour/Job worker | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 36 | 24
23 | 3256103 | Consumable Stores | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 37 | 25
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | MM | 71+234 | MM | 56+532 | 0 | 0 | 38 | 26
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 39 | 27
26 | 0 | b) Interim Evaluation | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 40 | 28
27 | 0 | c) Progress Monitoring | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 41 | 29
28 | 3257104 | Survey | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 42 | 30
29 | 3255101 | Computer Consumables | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 43 | 31
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 44 | 32
31 | 3258101 | Motor Vehicles | 0 | L.S. | 0 | L.S. | 0 | 0 | 46 | 33
32 | 3258102 | Furnitures & Fixtures | 0 | L.S. | 0 | L.S. | 0 | 0 | 47 | 34
33 | 3258103 | Computers & office equipments | 0 | L.S. | 0 | L.S. | 0 | 0 | 48 | 35
34 | 3258105 | Machineries & Equipments | 0 | L.S. | 0 | L.S. | 0 | 0 | 49 | 36
35 | 3258107 | Office Building : Repair & Maintenance | 0 | L.S. | 0 | L.S. | 0 | 0 | 50 | 37
36 | 3258106 | Residential Building : Repair & Maintenance | 0 | L.S. | 0 | L.S. | 0 | 0 | 51 | 38
37 | 3258105 | Engineering Equipments | 0 | L.S. | 0 | L.S. | 0 | 0 | 52 | 39
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 0 | 104 | 0 | 86 | 0 | 0 | 54 | 40
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 0 | L.S. | 0 | L.S. | 0 | 0 | 55 | 41
40 | 3258107 | Others : Repair & Maintenance | 0 | L.S. | 0 | L.S. | 0 | 0 | 56 | 42
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos | 10 | Nos | 10 | Nos | 0 | 68 | 43
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos | 35 | Nos | 45 | Nos | 0 | 69 | 44
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | Nos | 6 | Nos | 5 | Nos | 0 | 71 | 45
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | Nos | 7 | Nos | 0 | 73 | 46
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | Nos | 2 | Nos | 0 | 74 | 47
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos | 17 | Nos | 17 | Nos | 0 | 76 | 48
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 6 | Nos | 3 | Nos | 0 | 77 | 49
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 0 | L.S | 0 | L.S | 0 | 0 | 78 | 50
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos | 30 | Nos | 37 | Nos | 0 | 80 | 51
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 11 | Nos | 11 | Nos | 0 | 81 | 52
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | Nos | 2 | Nos | 2 | Nos | 0 | 82 | 53
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos | 11 | Nos | 17 | Nos | 0 | 83 | 54
53 | 4112314 | Furnitures & Fixtures | 0 | LS | 0 | LS | 0 | 0 | 84 | 55
54 | 4112303 | Aircooler | Nos | 15 | Nos | 15 | Nos | 0 | 85 | 56
55 | 4141101 | Land Acquisition ( 470 hectare) | ha | 470 | ha | 470 | ha | 0 | 87 | 57
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | Nos | 131 | Nos | 127 | Nos | 0 | 90 | 58
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos | 7(2+5) | Nos | 3 | Nos | 0 | 92 | 59
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos | 137(57+35+14) | Nos | 114 | Nos | 0 | 93 | 60
59 | 4111307 | Re-excavation of Khal/River (New Haors) | Km | 318 | Km | 343.984 | Km | 0 | 94 | 61
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | Km | 143 | Km | 108.974 | Km | 0 | 96 | 62
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | Km | 84.31 | Km | 67.11 | Km | 0 | 97 | 63
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | Km | 87.03 | Km | 62.662 | Km | 0 | 98 | 64
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | Km | 260.318 | Km | 0 | 99 | 65
64 | 4111201 | Rehabilitation of Regulator (New Haors) | Nos | 8 | Nos | 7 | Nos | 0 | 100 | 66
65 | 4111201 | Threshing Floor Construction | Nos | 0 | Nos | 20 | Nos | 0 | 102 | 67
66 | 4111201 | Construction of WMG Office | Nos | 60 | Nos | 55 | Nos | 0 | 103 | 68
67 | 4111201 | O&M During Construction | Iten | L.S | Nos | 1 | 0 | 0 | 104 | 69
68 | 0 | (c) Physical Contingency ( Lump sum): | Item | L.S. | Item | L.S. | 0 | 0 | 107 | 0
69 | 0 | (d) Price Contingency (Lump sum): | Item | L.S. | Item | L.S. | 0 | 0 | 108 | 0

## Annex-9_detail_phasing_modified
| Code | Description | rindex | Total-cum | GoB-cum | RPA-cum | DPA-cum | Total-19-20 | GoB-19-20 | RPA-19-20 | DPA-19-20 | Total-20-21 | GoB-20-21 | RPA-20-21 | DPA-20-21 | Total-21-22 | GoB-21-22 | RPA-21-22 | DPA-21-22 | Total-DPP-Cost | Total-Phased-Cost-1 | Total-Phased-GoB | Total-Phased-RPA | Total-Phased-DPA | Total-Phased-Cost-2 | Check1 | Check2
0 | 3111302 | Conveyance Allowance | 11 | 1.51 | 1.51 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.0242 | 2.0242 | 0 | 0 | 1.4658 | 1.4658 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
1 | 3111327 | Overtime Allowance | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 6.3 | 0 | 0 | 3.7 | 3.7 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
2 | 3111338 | Other Allowance | 13 | 50.61 | 50.61 | 0 | 0 | 14 | 14 | 0 | 0 | 53.634 | 53.634 | 0 | 0 | 35.756 | 35.756 | 0 | 0 | 140 | 140 | 140 | 0 | 0 | 140 | 0 | 0
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 15 | 73.54 | 73.54 | 0 | 0 | 15 | 15 | 0 | 0 | 28.799 | 28.799 | 0 | 0 | 17.651 | 17.651 | 0 | 0 | 120 | 119.99 | 119.99 | 0 | 0 | 119.99 | 0.01 | 0.01
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 16 | 150.92 | 150.92 | 0 | 0 | 34.25 | 34.25 | 0 | 0 | 58.3296 | 58.3296 | 0 | 0 | 35.7504 | 35.7504 | 0 | 0 | 245 | 245 | 245 | 0 | 0 | 245 | 0 | 0
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 17 | 1962.26 | 1962.26 | 0 | 0 | 359.08 | 359.08 | 0 | 0 | 367.7316 | 367.7316 | 0 | 0 | 266.2884 | 266.2884 | 0 | 0 | 2596.27 | 2596.28 | 2596.28 | 0 | 0 | 2596.28 | -0.01 | -0.01
6 | 3211119 | Postage | 18 | 1.27 | 1.27 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.1634 | 2.1634 | 0 | 0 | 1.5666 | 1.5666 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
7 | 3211120 | Telephones/Telegram/Teleprinter | 19 | 1.17 | 1.17 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 2.3363 | 2.3363 | 0 | 0 | 1.4937 | 1.4937 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
8 | 3211117 | Telex/Fax/Internet | 20 | 0.64 | 0.64 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 2.441 | 2.441 | 0 | 0 | 1.918 | 1.918 | 0 | 0 | 5 | 4.999 | 4.999 | 0 | 0 | 4.999 | 0.001 | 0.001
9 | 3221104 | Registration Fee (Vehicles) | 21 | 12.92 | 12.92 | 0 | 0 | 1 | 1 | 0 | 0 | 4.4604 | 4.4604 | 0 | 0 | 2.6196 | 2.6196 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 3.5527e-15 | 3.5527e-15
10 | 3211115 | Water | 22 | 1.56 | 1.56 | 0 | 0 | 0.45 | 0.45 | 0 | 0 | 2.0923 | 2.0923 | 0 | 0 | 1.3377 | 1.3377 | 0 | 0 | 5 | 4.99 | 4.99 | 0 | 0 | 4.99 | 0.01 | 0.01
11 | 3211113 | Electricity | 23 | 12.24 | 12.24 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 4.2735 | 4.2735 | 0 | 0 | 3.4965 | 3.4965 | 0 | 0 | 20 | 20.01 | 20.01 | 0 | 0 | 20.01 | -0.01 | -0.01
12 | 3243102 | Gas & Fuel | 24 | 23.52 | 23.52 | 0 | 0 | 6 | 6 | 0 | 0 | 10.0467 | 10.0467 | 0 | 0 | 6.4233 | 6.4233 | 0 | 0 | 40 | 39.99 | 39.99 | 0 | 0 | 39.99 | 0.01 | 0.01
13 | 3243101 | Petrol and Lubricant | 25 | 84.59 | 84.59 | 0 | 0 | 20 | 20 | 0 | 0 | 48.6894 | 48.6894 | 0 | 0 | 36.7306 | 36.7306 | 0 | 0 | 170 | 170.01 | 170.01 | 0 | 0 | 170.01 | -0.01 | -0.01
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 26 | 1.31 | 1.31 | 0 | 0 | 0.15 | 0.15 | 0 | 0 | 0.93005 | 0.93005 | 0 | 0 | 0.76095 | 0.76095 | 0 | 0 | 3 | 3.001 | 3.001 | 0 | 0 | 3.001 | -0.001 | -0.001
15 | 3255102 | Printing & Binding | 27 | 34.66 | 34.66 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 9.355 | 9.355 | 0 | 0 | 5.981 | 5.981 | 0 | 0 | 50 | 49.996 | 49.996 | 0 | 0 | 49.996 | 0.004 | 0.004
16 | 3255104 | Stationery, Seals & Stamps | 28 | 69.91 | 69.91 | 0 | 0 | 20 | 20 | 0 | 0 | 31.5554 | 31.5554 | 0 | 0 | 18.5326 | 18.5326 | 0 | 0 | 120 | 119.998 | 119.998 | 0 | 0 | 119.998 | 0.002 | 0.002
17 | 3211127 | Books & Periodicals | 29 | 0.48 | 0.48 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0.8816 | 0.8816 | 0 | 0 | 0.6384 | 0.6384 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.54 | 0 | 238.54 | 0 | 0 | 0 | 0 | 0 | 238.54 | 238.54 | 0 | 238.54 | 0 | 238.54 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 32 | 497.67 | 43.5694 | 454.1006 | 0 | 196.17 | 21.0294 | 175.1406 | 0 | 23.418 | 2.5104 | 20.9076 | 0 | 15.612 | 1.6736 | 13.9384 | 0 | 536.7 | 536.7 | 47.7534 | 488.9466 | 0 | 536.7 | 0 | 0
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 33 | 2023.77 | 152.9294 | 1870.8406 | 0 | 677.14 | 72.5894 | 604.5506 | 0 | 696.9879 | 74.7171 | 622.2708 | 0 | 409.3421 | 43.8815 | 365.4606 | 0 | 3130.1 | 3130.1 | 271.528 | 2858.572 | 0 | 3130.1 | 0 | 0
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 34 | 824.86 | 61.912 | 762.948 | 0 | 246.66 | 26.442 | 220.218 | 0 | 278.487 | 29.8538 | 248.6332 | 0 | 227.853 | 24.4258 | 203.4272 | 0 | 1331.2 | 1331.2 | 116.1916 | 1215.0084 | 0 | 1331.2 | 0 | 0
22 | 3211109 | Casual labour/Job worker | 35 | 14.46 | 14.46 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 4.6748 | 4.6748 | 0 | 0 | 2.8652 | 2.8652 | 0 | 0 | 22 | 22 | 22 | 0 | 0 | 22 | 0 | 0
23 | 3256103 | Consumable Stores | 36 | 6.74 | 6.74 | 0 | 0 | 3 | 3 | 0 | 0 | 4.7908 | 4.7908 | 0 | 0 | 3.4692 | 3.4692 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 37 | 5668.01 | 0 | 0 | 5668.01 | 500 | 0 | 0 | 500 | 1344.071 | 0 | 0 | 1344.071 | 859.324 | 0 | 0 | 859.324 | 7901.4 | 7871.405 | 0 | 0 | 7871.405 | 7871.405 | 29.995 | 29.995
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 38 | 17.73 | 17.73 | 0 | 0 | 5 | 5 | 0 | 0 | 7.1166 | 7.1166 | 0 | 0 | 5.1534 | 5.1534 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 0
26 | 3111332 | b) Interim Evaluation | 39 | 2.29 | 2.29 | 0 | 0 | 1 | 1 | 0 | 0 | 7.71 | 7.71 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
27 | 3111332 | c) Progress Monitoring | 40 | 2.3 | 2.3 | 0 | 0 | 1 | 1 | 0 | 0 | 4.774 | 4.774 | 0 | 0 | 2.926 | 2.926 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
28 | 3257104 | Survey | 41 | 135.02 | 135.02 | 0 | 0 | 50 | 50 | 0 | 0 | 15.3786 | 15.3786 | 0 | 0 | 11.6014 | 11.6014 | 0 | 0 | 162 | 162 | 162 | 0 | 0 | 162 | 2.8422e-14 | 2.8422e-14
29 | 3255101 | Computer Consumables | 42 | 30.47 | 30.47 | 0 | 0 | 10 | 10 | 0 | 0 | 16.242 | 16.242 | 0 | 0 | 13.2889 | 13.2889 | 0 | 0 | 60 | 60.001 | 60.001 | 0 | 0 | 60.001 | -0.001 | -0.001
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 43 | 1175.46 | 1175.46 | 0 | 0 | 300 | 300 | 0 | 0 | 298.9935 | 298.9935 | 0 | 0 | 225.5565 | 225.5565 | 0 | 0 | 1700 | 1700.01 | 1700.01 | 0 | 0 | 1700.01 | -0.01 | -0.01
31 | 3258101 | Motor Vehicles | 45 | 76.4 | 76.4 | 0 | 0 | 15 | 15 | 0 | 0 | 26.7317 | 26.7317 | 0 | 0 | 21.8713 | 21.8713 | 0 | 0 | 125 | 125.003 | 125.003 | 0 | 0 | 125.003 | -0.003 | -0.003
32 | 3258102 | Furnitures & Fixtures | 46 | 5.2 | 5.2 | 0 | 0 | 2 | 2 | 0 | 0 | 2.88 | 2.88 | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
33 | 3258103 | Computers & office equipments | 47 | 8.34 | 8.34 | 0 | 0 | 3 | 3 | 0 | 0 | 3.9294 | 3.9294 | 0 | 0 | 2.7306 | 2.7306 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
34 | 3258105 | Machineries & Equipments | 48 | 3.22 | 3.22 | 0 | 0 | 2 | 2 | 0 | 0 | 4.1297 | 4.1297 | 0 | 0 | 2.6403 | 2.6403 | 0 | 0 | 10 | 9.99 | 9.99 | 0 | 0 | 9.99 | 0.01 | 0.01
35 | 3258107 | Office Building : Repair & Maintenance | 49 | 19.98 | 19.98 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9618 | 2.9618 | 0 | 0 | 2.0582 | 2.0582 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 25 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | 50 | 19.53 | 19.53 | 0 | 0 | 5 | 5 | 0 | 0 | 11.8726 | 11.8726 | 0 | 0 | 8.5974 | 8.5974 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
37 | 3258105 | Engineering Equipments | 51 | 3.39 | 3.39 | 0 | 0 | 2 | 2 | 0 | 0 | 9.1355 | 9.1355 | 0 | 0 | 7.4745 | 7.4745 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 53 | 153.28 | 19.4044 | 133.8756 | 0 | 58.25 | 8.5744 | 49.6756 | 0 | 158.9301 | 23.3945 | 135.5356 | 0 | 93.3399 | 13.7396 | 79.6003 | 0 | 405.55 | 405.55 | 56.5385 | 349.0115 | 0 | 405.55 | 0 | 0
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 54 | 3.14 | 3.14 | 0 | 0 | 0.75 | 0.75 | 0 | 0 | 1.1346 | 1.1346 | 0 | 0 | 0.7254 | 0.7254 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | -8.8818e-16 | -8.8818e-16
40 | 3258107 | Others : Repair & Maintenance | 55 | 10.48 | 10.48 | 0 | 0 | 3 | 3 | 0 | 0 | 16.5312 | 16.5312 | 0 | 0 | 12.9888 | 12.9888 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 60 | 702.5 | 702.5 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702.5 | 702.5 | 702.5 | 0 | 0 | 702.5 | 0 | 0
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 61 | 50.22 | 50.22 | 0 | 0 | 0 | 0 | 0 | 0 | 18.03 | 18.03 | 0 | 0 | 0 | 0 | 0 | 0 | 68.25 | 68.25 | 68.25 | 0 | 0 | 68.25 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 63 | 61.29 | 61.29 | 0 | 0 | 0 | 0 | 0 | 0 | 28.71 | 28.71 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 90 | 0 | 0 | 90 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 8.97 | 8.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.97 | 8.97 | 8.97 | 0 | 0 | 8.97 | 0 | 0
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 66 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 68 | 20.5 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5 | 20.5 | 20.5 | 0 | 0 | 20.5 | 0 | 0
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 69 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 70 | 14.49 | 14.49 | 0 | 0 | 5 | 5 | 0 | 0 | 35.51 | 35.51 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 0
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 72 | 19.47 | 19.47 | 0 | 0 | 0 | 0 | 0 | 0 | 5.03 | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 | 24.5 | 24.5 | 24.5 | 0 | 0 | 24.5 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 73 | 9.88 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 3.87 | 3.87 | 0 | 0 | 0 | 0 | 0 | 0 | 13.75 | 13.75 | 13.75 | 0 | 0 | 13.75 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 74 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 75 | 4.08 | 4.08 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 5.25 | 5.25 | 0 | 0 | 5.25 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | 76 | 45.32 | 45.32 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8954 | 2.8954 | 0 | 0 | 1.7746 | 1.7746 | 0 | 0 | 50 | 49.99 | 49.99 | 0 | 0 | 49.99 | 0.01 | 0.01
54 | 4112303 | Aircooler | 77 | 13.73 | 13.73 | 0 | 0 | 4 | 4 | 0 | 0 | 0.7747 | 0.7747 | 0 | 0 | 0.4953 | 0.4953 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | 79 | 16373.02 | 16373.02 | 0 | 0 | 2049.42 | 2049.42 | 0 | 0 | 3351.98 | 3351.98 | 0 | 0 | 0 | 0 | 0 | 0 | 19725 | 19725 | 19725 | 0 | 0 | 19725 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 82 | 607.05 | 84.9862 | 522.0638 | 0 | 490.33 | 68.6462 | 421.6838 | 0 | 315.3755 | 44.1526 | 271.2229 | 0 | 258.0345 | 36.1248 | 221.9097 | 0 | 1180.46 | 1180.46 | 165.2636 | 1015.1964 | 0 | 1180.46 | 0 | 0
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437.1382 | 61.1993 | 375.9389 | 0 | 279.4818 | 39.1275 | 240.3543 | 0 | 716.62 | 716.62 | 100.3268 | 616.2932 | 0 | 716.62 | 0 | -1.1369e-13
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 85 | 14249.24 | 2024.2712 | 12224.9688 | 0 | 8105.58 | 1134.7812 | 6970.7988 | 0 | 2774.0238 | 388.3633 | 2385.6605 | 0 | 1773.5562 | 248.2979 | 1525.2583 | 0 | 18796.82 | 18796.82 | 2660.9324 | 16135.8876 | 0 | 18796.82 | 0 | 0
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 86 | 9948.16 | 1342.2152 | 8605.9448 | 0 | 3936.68 | 551.1352 | 3385.5448 | 0 | 321.2968 | 44.9816 | 276.3152 | 0 | 232.6632 | 32.5728 | 200.0904 | 0 | 10502.12 | 10502.12 | 1419.7696 | 9082.3504 | 0 | 10502.12 | 0 | 0
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 88 | 1355.77 | 190.4622 | 1165.3078 | 0 | 900.73 | 126.1022 | 774.6278 | 0 | 1164.5784 | 163.041 | 1001.5374 | 0 | 878.5416 | 122.9958 | 755.5458 | 0 | 3398.89 | 3398.89 | 476.499 | 2922.391 | 0 | 3398.89 | 0 | 0
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 89 | 1365.72 | 191.3464 | 1174.3736 | 0 | 913.26 | 127.8564 | 785.4036 | 0 | 392.5647 | 54.9591 | 337.6056 | 0 | 296.1453 | 41.4603 | 254.685 | 0 | 2054.43 | 2054.43 | 287.7658 | 1766.6642 | 0 | 2054.43 | 0 | 0
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 90 | 999.4 | 140.897 | 858.503 | 0 | 657.55 | 92.057 | 565.493 | 0 | 418.1121 | 58.5357 | 359.5764 | 0 | 245.5579 | 34.3781 | 211.1798 | 0 | 1663.07 | 1663.07 | 233.8108 | 1429.2592 | 0 | 1663.07 | 0 | 2.2737e-13
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 91 | 10777.83 | 1430.1278 | 9347.7022 | 0 | 4650.77 | 651.1078 | 3999.6622 | 0 | 5364.4315 | 751.0204 | 4613.4111 | 0 | 3429.7185 | 480.1606 | 2949.5579 | 0 | 19571.98 | 19571.98 | 2661.3088 | 16910.6712 | 0 | 19571.98 | 0 | 0
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 92 | 73.26 | 9.77 | 63.49 | 0 | 0 | 0 | 0 | 0 | 50.1332 | 7.0186 | 43.1146 | 0 | 30.7268 | 4.3018 | 26.425 | 0 | 154.12 | 154.12 | 21.0904 | 133.0296 | 0 | 154.12 | 0 | 0
65 | 4111201 | Threshing Floor Construction | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137.25 | 19.215 | 118.035 | 0 | 87.75 | 12.285 | 75.465 | 0 | 225 | 225 | 31.5 | 193.5 | 0 | 225 | 0 | 0
66 | 4111201 | Construction of WMG Office | 94 | 390.23 | 54.2096 | 336.0204 | 0 | 348.14 | 48.7396 | 299.4004 | 0 | 861.2643 | 120.577 | 740.6873 | 0 | 598.5057 | 83.7908 | 514.7149 | 0 | 1850 | 1850 | 258.5774 | 1591.4226 | 0 | 1850 | 2.2737e-13 | 0
67 | 4111201 | O&M During Construction | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5 | 3.99 | 24.51 | 0 | 21.5 | 3.01 | 18.49 | 0 | 50 | 50 | 7 | 43 | 0 | 50 | 0 | 0
68 | 0 | (c) Physical Contingency ( Lump sum): | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.2402 | 19.2402 | 0 | 0 | 11.2998 | 11.2998 | 0 | 0 | 30.54 | 30.54 | 30.54 | 0 | 0 | 30.54 | 0 | 0
69 | 0 | (d) Price Contingency (Lump sum): | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 5.5 | 0 | 0 | 4.5 | 4.5 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0