## All Abstruct
Abstruct cost ofestimate for slope protection work of submersible embankment around ( A) Dakshiner Haor sub project from km.0.480 to km 0.524 = 44.00m, km 1.210 to km 1.245 = 35.00m , km. 8.760 to km 8.797= 37.00m, km 9.175 to km 9.600 =425.00m, km. 9.785 to km 9.952= 167.00m, km. 10.100 to km 10.400 = 300.00m, km. 12.075 to km 12.440 = 365.00m, km. 12.712 to km 12.784 = 72.00m, km. 21.600 to km 21.733 = 133.00m, km 22.375 to km 22.480 =105.00m, km. 24.950 to km 25.100= 150.00m, km 25.170 to km 25.270 =100.00m , km. 25.720 to km 25.900 = 180.00m & km. 25.925 to km 26.003 = 78.00m Total = 2.191 km & B) 1 no. Flood Fuse from km. 5.560 to km.5.750=15.00m & 1 no. Flood Fuse from km. 33.925 to km.33.955 = 30.00m of Noagaon Haor (Part-B), Grand total= 2.236 km. in C/W Haor Flood Management & Livelihood Improvement Project under Kishoregonj WD Division BWDB, Kishoregonj during the year 2020-21. (Package no. BWDB/Kish/HFMLIP/PW-34)
Sl No./ Code no | Description of Items | Quantity | Unit | Rate | Amount
1 | 2 | 3 | 4 | 5 | 6
1/16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | #REF! | nos | 367.41 | #REF!
2/16-450 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ringbundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | #REF! | Cum | 198.79 | #REF!
3/16-220 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-220-10 . 300m to 1.00 km.(85% compaction) | #REF! | Cum | 429.88 | #REF!
4/16-240 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping /ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-240-10 : Equipment; ht: 0 to 4m; 85% comp. | #REF! | Cum | 157.7 | #REF!
5/16-510 | Earth work in excavation of foundation trenches in all kinds of soil as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. 16-510-10 : For moving spoil earth upto a distance of 100m from the centre of the pit. | #REF! | Cum | 341.37 | #REF!
6/16-180 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | #REF! | Cum | 16.97 | #REF!
7/16-160 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3m neglected) for all kinds of earth work. Nos of lead = 2 nos leads |  |  | 29.69x2= | 0
|  | #REF! | Cum | 59.38 | #REF!
8/16-170 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm neglected) for all kinds of earth work. Nos of lifts= 2 nos lifts |  |  | 15.36x2= | 0
|  | #REF! | Cum | 30.72 | #REF!
9/40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550-30 : FM : 1.0 to 1.5 | #REF! | Cum | 1267.96 | #REF!
10/40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric). 40-500-40 : Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm, EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N. (Quantiy relating turfing item code 48-100 will be measurable and payable simultaneously. As such full grown continuous turfing over Geo-textile fabric inevitable/necessary) | #REF! | Sqm | 250.13 | #REF!
11/40-380 | Supplying filling and placing of geo-textile bags of different sizes and capacity at project/work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordancewith the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in measurable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical specification, approved design and direction of Engineer in charge. [fill volume and weight will be measured after filling with dry sand]" A) 40-380-20 : Geo-bag; inner size:1075mmx850mm, outer size:1125mm x900mmgeo-fabric th.=>3.0mm, Fill Vol: 0.1164cum; wt: 175kg | #REF! | Nos | 439.81 | #REF!
| B) 40-380-30 : Geo-bag; inner size:950mmx750mm, outer size:1000mmx800mm geo-fabric th.=>3.0mm, Fill Vol: 0.0840cum; wt: 125kg | #REF! | Nos | 339.8 | #REF!
12/40-530 | Supplying and laying shingles and peagravels as filter in two layers (top and bottom) as per specific size ranges and gradation including grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: (A)40-530-20: Well graded between 40mm to 20mm size. | #REF! | Cum | 5771.61 | #REF!
| (B) 40-530-30: Well graded between 20mm to 5mm size. | #REF! | Cum | 6135.23 | #REF!
13/40-190 | Manufacturing and supplying C.C. blocks in leanest mix. 1:2.5:5 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a 28 days cylinder strength of 12 N/mm² including grading, washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering (steel shutter to be used) and stacking in measurable stacks, cost of all materials and charges, etc. complete as per direction of Engineer in charge . (A)40-190-15 : Block Size: 50cmx50cmx50cm | #REF! | Nos. | 1708.4 | #REF!
| (B )40-190-05 : Block Size: 50cmx50cmx30cm | #REF! | Nos | 1044.04 | #REF!
| (C )40-190-06 : Block Size: 40cmx40cmx30cm | #REF! | Nos | 684.23 | #REF!
| (D) 40-190-35 : Block Size: 40cmx40cmx40cm | #REF! | Nos. | 891.24 | #REF!
| (E) 40-190-40 : Block Size: 40cmx40cmx20cm | #REF! | Nos | 457.33 | #REF!
| (F) 40-190-45 : Block Size: 30cmx30cmx30cm | #REF! | Nos | 380.95 | #REF!
14/40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge. A) 40-270-10 . Within 200 m | #REF! | Cum | 1395.03 | #REF!
| B) 40-270-20 . 200 m to 500 m. | #REF! | Cum | 2185.1 | #REF!
15/28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-120-20 : With 25mm down graded stone chips. | #REF! | Cum | 12907.66 | #REF!
17/36-150 | Formwork for centering and water tight shuttering as per drawing with14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charg. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrackbamboo props. | #REF! | Sqm | 1143.84 | #REF!
18/76-120 | M.S. Work for reinforcement with deformed M.S. bar, fy=400 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10 : 8mm dia to 30mm dia. | #REF! | Kg. | 102.44 | #REF!
19/20-100 | Single brick flat soling including preparation of bed, sand filling (FM>=0.50), levelling, dressing and sand blinding in foundation or floor with supply of all materials etc. complete and as per direction of Engineer in charge 20-100-10: With 1st class bricks | #REF! | Sqm | 445.19 | #REF!
20/28-200 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10 : with stone chips.consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10 : With stone chips. | #REF! | Cum | 14581.84 | #REF!
21/16-120 | Earth work by manual labour in constructing/ resectioning of embankment / canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 . 0 m to 3 m height with 85% compaction. | #REF! | Cum | 245.6 | #REF!
22/48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only). as per direction of Engineer in charge. (Quantiy relating item code 40-500-40 will be measurable and payable simultaneously. As such full grown continuous turfing over Geo-textile fabric inevitable/necessary). | #REF! | Sqm | 32.97 | #REF!
22/16-470 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge. | #REF! | Cum | 198.84 | #REF!
23/ Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge. | 1 | 1 Item | 967050.85 | 967050.85
24/ Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 4 nos. of tube well and sanitation facilities by installing 6 nos. of sanitary latrines for usage of labours, Officials and others for prevailing the hygenic and healthy environment at allover the working sithe as per direction of the engineer in charge. | 1 | 1 Item | 111148.95 | 111148.95
25/ Approved Analysis Rate | Operate, maintain of plant and equipment such as generator for site electrification for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | 1 Item | 110909.92 | 110909.92
26/ Approved Analysis Rate | Provide and maintain 1 (one) no. engine boat with boatmen having sun and rainproof cover to facilitate supervision by the eEngineer/Engineer's Representative during whole construction period of the work as per Technical Specication, Contractor's Method statement and as per direction of Engineer in charge | 120 | Days | 2497.86 | 299743.2
27/ Approved Analysis Rate | Mobilize, Strengthen required land based construction equipment such as excavator, dump truck, chain dozer, vibro-compactor and plants such as generator for site electrification, digital camera for taking photographs and digital vedio camera for recording/Taking Photograph as sequences of works etc for keeping records of the works by providing following information including transfer to site, complete for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer -in- Charge | 1 | 1 Item | 92026.55 | 92026.55
28/ Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | 1 Item | 112344.1 | 112344.1
29/ NSI | Environmental Monitoring through Sample Collection and analysis such as Air quality test, Surface water test, Sound Level monitoring, Traffic signs and road navigation, safety provisions with first aid and medical Assistant as per direction of Engineer in charge. | 1 | 1 Item | 250000 | 250000
| Total= |  |  |  | #REF!
#REF!
#REF!
18325750.4611
1943223.57
#REF!
Ok

## All Qnty. Abstruct
Quantity Abstruct of Detail estimate for slope protection work of submersible embankment around ( A) Dakshiner Haor sub project from km.0.480 to km 0.524 = 44.00m, km 1.210 to km 1.245 = 35.00m , km. 8.760 to km 8.797= 37.00m, km 9.175 to km 9.600 =425.00m, km. 9.785 to km 9.952= 167.00m, km. 10.100 to km 10.400 = 300.00m, km. 12.075 to km 12.440 = 365.00m, km. 12.712 to km 12.784 = 72.00m, km. 21.600 to km 21.733 = 133.00m, km 22.375 to km 22.480 =105.00m, km. 24.950 to km 25.100= 150.00 m, km 25.170 to km 25.270 =100.00m , km. 25.720 to km 25.900 = 180.00m & km. 25.925 to km 26.003 = 78.00m Total = 2.191 km & (B) 1 no. Flood Fuse from km. 5.560 to km.5.750=15.00m of Noagaon Haor, Grand total= 2.206 km. in C/W Haor Flood Management & Livelihood Improvement Project under Kishoregonj WD Division BWDB, Kishoregonj during the year 2020-21. (Package no. BWDB/Kish/HFMLIP/PW-34)
Sl No. Code no | Description of Items | [6 empty] | Quantity
1/16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge.
| For Protective works |  |  |  | = | #REF! | Nos
| For Flood fuse of at km 33.925 |  |  |  | = | 0
| For Flood fuse of at km 5.56 |  |  |  | = | 0 |  | #REF!
|  |  |  | Total | = | #REF! | Nos | Nos
2/16-450 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ringbundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge.
| For Flood fuse of at km 33.925 |  |  |  | = | 2052 | Cum
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | Cum | #REF!
|  |  |  | Total | = | #REF! |  | Cum
3/16-220 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-220-10 . 300m to 1.00 km.(85% compaction)
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 0
| For Flood fuse of at km 5.56 |  |  |  | = | 0 |  | Cum
|  |  |  | Total | = | #REF! | Cum
4/16-240 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping /ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-240-10 : Equipment; ht: 0 to 4m; 85% comp.
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 0
| For Flood fuse of at km 5.56 |  |  |  | = | 0 |  | Cum
|  |  |  | Total | = | #REF! | Cum
5/16-510 | Earth work in excavation of foundation trenches in all kinds of soil as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. 16-510-10 : For moving spoil earth upto a distance of 100m from the centre of the pit.
| For Protective works |  |  |  | = | 0 | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1590.3
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ' | Cum
|  |  |  | Total | = | #REF! | Cum
6/16-180 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement.
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1725.75
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
7/16-160 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3m neglected) for all kinds of earth work.
2 Nos lead
| For Protective works |  |  |  | = | 0 | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1725.75
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
8/16-170 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm neglected) for all kinds of earth work.
2 Nos lifts
| For Protective works |  |  |  | = | 0 | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1725.75
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
9/40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550-30 : FM : 1.0 to 1.5
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 297.3339
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
10/40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric). 40-500-40 : Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm, EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N. (Quantiy relating turfing item code 48-100 will be measurable and payable simultaneously. As such full grown continuous turfing over Geo-textile fabric inevitable/necessary)
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 2038.2259
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! |  | Cum
|  |  |  | Total | = | #REF! | Cum
11/40-380 | Supplying filling and placing of geo-textile bags of different sizes and capacity at project/work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordancewith the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in measurable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical specification, approved design and direction of Engineer in charge. [fill volume and weight will be measured after filling with dry sand]" A) 40-380-20 : Geo-bag; inner size:1075mmx850mm, outer size:1125mm x900mmgeo-fabric th.=>3.0mm, Fill Vol: 0.1164cum; wt: 175kg
| For Protective works |  |  |  | = | 0 | Nos | #REF!
2195.096
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Nos
|  |  |  | Total | = | #REF! | Nos
B) 40-380-30 : Geo-bag; inner size:950mmx750mm, outer size:1000mmx800mm geo-fabric th.=>3.0mm, Fill Vol: 0.0840cum; wt: 125kg
| For Protective works |  |  |  | = | #REF! | Nos | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 0
| For Flood fuse of at km 5.56 |  |  |  | = | 0 | ,,
|  |  |  | Total | = | #REF! | Nos
12/40-530 | Supplying and laying shingles and peagravels as filter in two layers (top and bottom) as per specific size ranges and gradation including grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: (A)40-530-20: Well graded between 40mm to 20mm size.
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 198.2226
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
(B) 40-530-30: Well graded between 20mm to 5mm size.
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 198.2226
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! |  | Cum
|  |  |  | Total | = | #REF! | Cum
13/40-190 | Manufacturing and supplying C.C. blocks in leanest mix. 1:2.5:5 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a 28 days cylinder strength of 12 N/mm² including grading, washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering (steel shutter to be used) and stacking in measurable stacks, cost of all materials and charges, etc. complete as per direction of Engineer in charge . (A)40-190-15 : Block Size: 50cmx50cmx50cm
| For Protective works |  |  |  | = | 0 | Nos | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1736.6
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Nos
|  |  |  | Total | = | #REF! | Nos
(B )40-190-05 : Block Size: 50cmx50cmx30cm
| For Protective works |  |  |  | = | 0 | Nos | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 3330.8744
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Nos.
|  |  |  | Total | = | #REF! | Nos
(C )40-190-06 : Block Size: 40cmx40cmx30cm
| For Protective works |  |  |  | = | #REF! | Nos | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 0
| For Flood fuse of at km 5.56 |  |  |  | = | 0 | ,, | Nos.
|  |  |  | Total | = | #REF! | Nos
.(D) 40-190-35 : Block Size: 40cmx40cmx40cm
| For Protective works |  |  |  | = | 0 | Nos. | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 2375
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Nos.
|  |  |  | Total | = | #REF! | Nos.
.(E) 40-190-40 : Block Size: 40cmx40cmx20cm
| For Protective works |  |  |  | = | #REF! | Nos. | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 3875.2875
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Nos.
|  |  |  | Total | = | #REF! | nos.
.(F) 40-190-45 : Block Size: 30cmx30cmx30cm
| For Protective works |  |  |  | = | #REF! | Nos. | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 0
| For Flood fuse of at km 5.56 |  |  |  | = | 0 | ,, | Nos.
|  |  |  | Total | = | #REF! | Nos.
14/40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge. A) 40-270-10 . Within 200 m
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 371.4499
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
B) 40-270-20 . 200 m to 500 m.
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 371.4499
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
15/28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-120-20 : With 25mm down graded stone chips.
| For Protective works |  |  |  | = | #REF! | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 30.64
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
16/36-150 | Formwork for centering and water tight shuttering as per drawing with14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charg. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrackbamboo props.
| For Protective works |  |  |  | = | 0 | Sqm | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 118.236
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Sqm
|  |  |  | Total | = | #REF! | Sqm
17/76-120 | M.S. Work for reinforcement with deformed M.S. bar, fy=400 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10 : 8mm dia to 30mm dia.
| For Protective works |  |  |  | = | 0 | Kg | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 142.6724
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Kg
|  |  |  | Total | = | #REF! | Kg
18/20-100 | Single brick flat soling including preparation of bed, sand filling (FM>=0.50), levelling, dressing and sand blinding in foundation or floor with supply of all materials etc. complete and as per direction of Engineer in charge 20-100-10: With 1st class bricks
| For Protective works |  |  |  | = | 0 | Sqm | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 2
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Sqm
|  |  |  | Total | = | #REF! | Sqm
19/28-200 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10 : with stone chips.consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10 : With stone chips.
| For Protective works |  |  |  | = | 0 | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1.2362
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
20/16-120 | Earth work by manual labour in constructing/ resectioning of embankment / canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 . 0 m to 3 m height with 85% compaction.
| For Protective works |  |  |  | = | 0 | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1725.75
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
21/48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only). as per direction of Engineer in charge. (Quantiy relating item code 40-500-40 will be measurable and payable simultaneously. As such full grown continuous turfing over Geo-textile fabric inevitable/necessary).
| For Protective works |  |  |  | = | #REF! | Sqm | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 0
| For Flood fuse of at km 5.56 |  |  |  | = | 0 | ,, | Sqm
|  |  |  | Total | = | #REF! | Sqm
22/16-470 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge.
| For Protective works |  |  |  | = | 0 | Cum | #REF!
| For Flood fuse of at km 33.925 |  |  |  | = | 1641.6
| For Flood fuse of at km 5.56 |  |  |  | = | #REF! | ,, | Cum
|  |  |  | Total | = | #REF! | Cum
23/ Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge. | [6 empty] | 1 Item
|  |  | = | L.S. | 1 Items
24/ Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 4 nos. of tube well and sanitation facilities by installing 6 nos. of sanitary latrines for usage of labours, Officials and others for prevailing the hygenic and healthy environment at allover the working sithe as per direction of the engineer in charge. | [6 empty] | 1 Item
|  |  | = | L.S. | 1 Items
25/ Approved Analysis Rate | Operate, maintain of plant and equipment such as generator for site electrification for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | [6 empty] | 1 Item
|  |  | = | L.S. | 1 Items
26/ Approved Analysis Rate | Provide and maintain 1 (one) no. engine boat with boatmen having sun and rainproof cover to facilitate supervision by the eEngineer/Engineer's Representative during whole construction period of the work as per Technical Specication, Contractor's Method statement and as per direction of Engineer in charge | [6 empty] | 120
|  |  | = | 120 | 1 Items |  |  | days
27/ Approved Analysis Rate | Mobilize, Strengthen required land based construction equipment such as excavator, dump truck, chain dozer, vibro-compactor and plants such as generator for site electrification, digital camera for taking photographs and digital vedio camera for recording/Taking Photograph as sequences of works etc for keeping records of the works by providing following information including transfer to site, complete for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer -in- Charge | [6 empty] | 1 Item
|  |  | = | L.S. | 1 Items
28/ Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | [6 empty] | 1 Item
|  |  | = | L.S. | 1 Items
29/ NSI | Environmental Monitoring through Sample Collection and analysis such as Air quality test, Surface water test, Sound Level monitoring, Traffic signs and road navigation, safety provisions with first aid and medical Assistant as per direction of Engineer in charge. | [6 empty] | 1 Item
|  |  | = | L.S. | 1 Items

## Protective Abstruct
Abstruct cost ofestimate for slope protection work of submersible embankment around ( A) Dakshiner Haor sub project from km.0.480 to km 0.524 = 44.00m, km 1.210 to km 1.245 = 35.00m , km. 8.760 to km 8.797= 37.00m, km 9.175 to km 9.600 =425.00m, km. 9.785 to km 9.952= 167.00m, km. 10.100 to km 10.400 = 300.00m, km. 12.075 to km 12.440 = 365.00m, km. 12.712 to km 12.784 = 72.00m, km. 21.600 to km 21.733 = 133.00m, km 22.375 to km 22.480 =105.00m, km. 24.950 to km 25.100= 150.00m, km 25.170 to km 25.270 =100.00m , km. 25.720 to km 25.900 = 180.00m & km. 25.925 to km 26.003 = 78.00m Total = 2.191 km & B) 1 no. Flood Fuse from km. 5.560 to km.5.750=15.00m of Noagaon Haor, Grand total= 2.206 km. in C/W Haor Flood Management & Livelihood Improvement Project under Kishoregonj WD Division BWDB, Kishoregonj during the year 2020-21. (Package no. BWDB/Kish/HFMLIP/PW-34)
Sl. No/ code no | Description of Items | Quantity | Unit | Rate | Amount Tk.
1 | 2 | 3 | 4 | 5 | 6
1/16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | #REF! | No | 367.41 | #REF!
2./16-220 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-220-10 . 300m to 1.00 km.(85% compaction) | #REF! | Cum | 429.88 | #REF!
3/16-240 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-240-10 : Equipment; ht: 0 to 4m; 85% comp. | #REF! | Cum | 157.7 | #REF!
4/16-180 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | #REF! |  | 16.97 | #REF!
5/40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550-30: FM : FM : 1.0 to 1.5 | #REF! | Cum | 1267.96 | #REF!
6/40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric). 40-500-40 : Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm, EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N. (Quantiy relating turfing item code 48-100 will be measurable and payable simultaneously. As such full grown continuous turfing over Geo-textile fabric inevitable/necessary) | #REF! | Sqm | 250.13 | #REF!
7/40-530 | Supplying and laying shingles and peagravels as filter in two layers (top and bottom) as per specific size ranges and gradation including grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: (A) 40-530-20. :Well graded between 40mm to 20mm size. . | #REF! | Cum | 5771.61 | #REF!
| (B) 40-530-30. :. Well graded between 20mm to 5mm size. (Combination of sub-item 10 & 30 or 20 & 30 shall be used) | #REF! | Cum | 6135.23 | #REF!
8/40-190 | Manufacturing and supplying C.C. blocks in leanest mix. 1:2.5:5 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a 28 days cylinder strength of 12 N/mm² including grading, washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering (steel shutter to be used) and stacking in measurable stacks, cost of all materials and charges, etc. complete as per direction of Engineer incharge. (A) 40-190-40. : Block Size: 40cmx40cmx20cm | #REF! | Nos | 457.33 | #REF!
| (B)40-190-50. : Block Size: 30cmx30cmx30cm | #REF! | Nos | 380.95 | #REF!
| (C)40-190-06. : Block Size: 40cmx40cmx30cm | #REF! | Nos | 684.23 | #REF!
9/40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge. (A) 40-270 -10. Within 200 m. cum | #REF! | Cum | 1395.03 | #REF!
| (B)40-270 -10. 200 m to 500 m. | #REF! | Cum | 2185.1 | #REF!
10/40-380 | Supplying filling and placing of geo-textile bags of different sizes and capacity at project/ work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg /m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordance with the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in easurable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical specification, approved design and direction of Engineer in charge.[fill volume and weight will be measured after filling with dry sand]" 40-380-30 : Geo-bag; inner size:950mmx750mm, outer size:1000mmx800mm geo-fabric th.=>3.0mm, Fill Vol: 0.0840cum; wt: 125kg | #REF! | N o. | 339.8 | #REF!
11/28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. cum28-120 . With 25mm down graded picked jhama or 1st. class brick chips. 28-120-20.: With 25mm down graded stone chips | #REF! | Cum | 12907.66 | #REF!
12/48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only). as per direction of Engineer in charge. (Quantiy relating item code 40-500-40 will be measurable and payable simultaneously. As such full grown continuous turfing over Geo-textile fabric inevitable/necessary). | #REF! | Sqm | 32.97 | #REF!
|  | Total Tk. |  |  | #REF!

## Fuse Abs.12.380
Abstruct cost of Estimate for Detail Estimate for Construction of 20 .00 m width Flood Fuse on Submersible Embankment/Low Depression at Km. 12.380 (at Joishiddhi) of Dakshiner Haor in c/w Haor Flood Management & Livelihood Improvement Project under Kishoregonj WD. Division, BWDB, Kishoregonj, during the year 2020-2021. (Package no. BWDB/Kish/HFMLIP/PW-25)
Sl No | Code No | Item Description | Quantity | Unit | Rate (Tk) | Amount (Tk)
1 | 40-450 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ringbundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | 2052 | Cum | 198.79 | 407917.08
2 | 16-510 | Earth work in excavation of foundation trenches in all kinds of soil as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. 16-510-10 : For moving spoil earth upto a distance of 100m from the centre of the pit. | 1590.3 | Cum | 341.37 | 542880.711
3 | 40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550-30 : FM : 1.0 to 1.5 | 297.3339 | Cum | 1267.96 | 377007.4728
4 | 04-620 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x 10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric) 40-500-40: :Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm,EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N. | 2038.2259 | Sqm | 250.13 | 509821.4444
5 | 40-380 | Supplying filling and placing of geo-textile bags of different sizes and capacity at project/work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordancewith the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in measurable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical specification, approved design and direction of Engineer in charge. [fill volume and weight will be measured after filling with dry sand]" 40-380-20 : Geo-bag; inner size:1075mmx850mm, outer size:1125mm x900mmgeo-fabric th.=>3.0mm, Fill Vol: 0.1164cum; wt: 175kg | 2195.096 | Nos | 439.81 | 965425.1929
6 | 40-530 | Supplying and laying shingles and peagravels as filter in two layers (top and bottom) as per specific size ranges and gradation including grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: (A)40-530-20: Well graded between 40mm to 20mm size. | 198.2226 | cum | 5771.61 | 1144063.4827
|  | (B) 40-530-30: Well graded between 20mm to 5mm size. | 198.2226 | sqm | 6135.23 | 1216141.1808
7 | 40-190 | Manufacturing and supplying C.C. blocks in leanest mix. 1:2.5:5 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a 28 days cylinder strength of 12 N/mm² including grading, washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering (steel shutter to be used) and stacking in measurable stacks, cost of all materials and charges, etc. complete as per direction of Engineer in charge . (A)40-190-10 : Block Size: 50cmx50cmx50cm | 1736.6 | Nos | 1708.4 | 2966807.44
|  | (B )40-190-15 : Block Size: 50cmx50cmx30cm | 3330.8744 | Nos | 1044.04 | 3477566.1295
|  | .(C) 40-190-35 : Block Size: 40cmx40cmx40cm | 2375 | Nos | 891.24 | 2116695
|  | .(D) 40-190-40 : Block Size: 40cmx40cmx20cm | 3875.2875 | Nos | 457.33 | 1772285.2324
8 | 40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge. 40-270-10 . Within 200 m | 371.4499 | Cum | 1395.03 | 518183.7411
|  | 40-270-20 . 200 m to 500 m. | 371.4499 | Cum | 2185.1 | 811655.1563
9 | 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-120-20 : With 25mm down graded stone chips. | 30.64 | Cum | 12907.66 | 395490.7024
10 | 36-150 | Formwork for centering and water tight shuttering as per drawing with14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charg. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrackbamboo props. | 118.236 | sqm | 1143.84 | 135243.0662
11 | 76-120 | M.S. Work for reinforcement with deformed M.S. bar, fy=400 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10 : 8mm dia to 30mm dia. | 142.6724 | Kg | 102.44 | 14615.3607
12 | 20-100 | Single brick flat soling including preparation of bed, sand filling (FM>=0.50), levelling, dressing and sand blinding in foundation or floor with supply of all materials etc. complete and as per direction of Engineer in charge 20-100-10: With 1st class bricks | 2 | Sqm | 445.19 | 890.38
13 | 28-200 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10 : with stone chips.consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. With stone chips. | 1.2362 | cum | 14581.84 | 18025.6915
14 | 16-120 | Earth work by manual labour in constructing/ resectioning of embankment / canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 . 0 m to 3 m height with 85% compaction. | 1725.75 | Cum | 245.6 | 423844.2
15 | 16-180 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | 1725.75 | Cum | 16.97 | 29285.9775
16 | 16-160 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3m neglected) for all kinds of earth work. | 1725.75 | Cum | 29.69 x 2 =
|  | Nos of lead = 2 nos. |  |  | 59.38 | 102475.035
17 | 16-170 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm neglected) for all kinds of earth work. | 1725.75 | Cum | 15.36x2=
|  | Nos of Lift = 2 nos. |  |  | 30.72 | 53015.04
18 | 16-470 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge. | 1641.6 | Cum | 198.84 | 326415.744
18325750.4611

## Fuse detail 12.380
Detail Estimate for Construction of 20 .00 m width Flood Fuse on Submersible Embankment/Low Depression at Km. 12.380 (at Joishiddhi) of Dakshiner Haor in c/w Haor Flood Management & Livelihood Improvement Project under Kishoregonj WD. Division, BWDB, Kishoregonj, during the year 2020-2021. (Package no. BWDB/Kish/HFMLIP/PW-25)
7.9057
Sl No | Code No | Item Description |  |  | Detail measurement | [8 empty] | Quantity | Unit
1 | 16-450 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ringbundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge.
Construction of Cross bundh
|  |  | C/S & R/S | =
[5 empty] | 2 | x( | 16 | + | 3 | )/2
|  |  |  | x( | 30 | + | 42 | )/2 | x |  | 3 | = | 2052 | 2052 | Cum
Cum
2 | 16-510 | Earth work in excavation of foundation trenches in all kinds of soil as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. 16-510-10 : For moving spoil earth upto a distance of 100m from the centre of the pit. | Height of Embankment |  |  |  |  | = | 2.5 | m |  |  |  | 1590.3 | Cum
|  |  | Base Width |  |  |  |  | = | 20 | m
Total Base width =
|  |  | = | ( | 6 | x | 2.5 | )+ | 4.3 | = | 19.3 | m
|  |  | C/S Appron | [6 empty] | = | 17 | m
|  |  | R/S Appron | [6 empty] | = | 15 | m
[9 empty] | Total = |  | 51.3 | m
|  |  | Earth Cutting = |  | 1 | x | 51.3 | x | 20 | x | 1.55 | = | 1590.3
3 | 40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550-30 : FM : 1.0 to 1.5 | Bed = | = | 1 | x | 51.3 | [6 empty] | 297.3339 | Cum
|  |  | 51.3 | . -(( | 2 | x | 5 | )+( | 2 | x | 0.6 | ))
[10 empty] | = | 40.1 | m
|  |  | Volume | = | 1 | x | 40.1 | x | 20 | x | 0.15 | = | 120.3
|  |  | Slope | =
|  |  | Incloned length= |  | (2.50)² | + | (7.50)² | = | 7.906 | m
|  |  | Volume | = | 2 | x | 7.906 | x | 4.3 | x | 0.15 | = | 10.1987
|  |  | Toe Length of circle portion |  |  |  |  | = | ½ x2ԈR
|  |  | 0.5 | x | 2 | x | 3.14 | x | 7.5 | = | 23.55 | m
|  |  | Top length | [6 empty] | = | 0 | m
|  |  | Average length= ( |  | 23.55 | + | 0 | ÷ | 2 | = | 11.775 | m
|  |  | Volume | = | 2 | x | 11.775 | x | 7.906 | x | 0.15 | = | 27.9279
|  |  | Crest | = | 2 | x | 7 | x | 4.3 | x | 0.15 | = | 9.03
|  |  | Embkt slope | = | 4 | x | 7 | x | 7.906 | x | 0.15 | = | 33.2052
Loose appron Top portion, C/S=
|  |  | 2 | x( | 7 | + | 3 | )x | 12 | x | 0.15 | = | 18
2
Loose appron Top portion, R/S=
|  |  | 2 | x( | 7 | + | 3 | )x | 10 | x | 0.15 | = | 15
2
|  |  | C/S & R/S | = | 4 | x | 5 | x | 1 | x | 0.15 | = | 3
Slope of Channel Sec. C-C
|  |  | Inclined length= |  |  |  | (2.00)² | + | (6.00)² | = | 6.32 | m
|  |  | C/S | = | 2 | x | 17 | x | 6.32 | x | 0.15 | = | 32.232
|  |  | R/S | = | 2 | x | 15 | x | 6.32 | x | 0.15 | = | 28.44
[11 empty] | Total | = | 297.3339
4 | 40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric) 40-500-40: :Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm,EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N.
|  |  | Bed | = |  |  | 1 | x | 40.1 | x | 20 | = | 802
|  |  | Slope | = |  |  | 2 | x | 7.906 | x | 4.3 | = | 67.9916
|  |  | Slope circle | = |  |  | 2 | x | 11.775 | x | 7.906 | = | 186.1863
|  |  | Top of Embkt |  |  | = | 2 | x | 7 | x | 4.3 | = | 60.2
|  |  | Slope ,, | = |  |  | 4 | x | 7 | x | 9.906 | = | 277.368
Loose appron Top of channel
|  |  | C/S | = | 2 | x( | 7 | + | 3 | )x | 12 | = | 120
2
|  |  | R/S | = | 2 | x( | 7 | + | 3 | )x | 10 | = | 100
2
|  |  | C/S & R/S | = | 2 | x | 2 | x | 5 | x | 1 | = | 20
Slope of Channel Sec. C-C
|  |  | Inclined length= |  |  |  | (2.00)² | + | (6.00)² | = | 6.32 | m |  | 2038.2259 | Sqm
|  |  | C/S | = |  |  | 2 | x | 17 | x | 6.32 | = | 214.88
|  |  | R/S | = |  |  | 2 | x | 15 | x | 6.32 | = | 189.6
[11 empty] | Total | = | 2038.2259
5 | 40-380 | Supplying filling and placing of geo-textile bags of different sizes and capacity at project/work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordancewith the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in measurable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical specification, approved design and direction of Engineer in charge. [fill volume and weight will be measured after filling with dry sand]" 40-380-20 : Geo-bag; inner size:1075mmx850mm, outer size:1125mm x900mmgeo-fabric th.=>3.0mm, Fill Vol: 0.1164cum; wt: 175kg
|  |  | Bed | = | 1 | x | 40.1 | x | 20 | x | 0.2 | = | 160.4
|  |  | Slope | = | 2 | x | 7.906 | x | 4.3 | x | 0.2 | = | 13.5983
|  |  | ,, Circle | = | 2 | x | 11.775 | x | 7.906 | x | 0.2 | = | 37.2373
|  |  | Side of Embk. | = | 4 | x | 7 | x | 7.906 | x | 0.2 | = | 44.2736
[11 empty] | Total | = | 255.5092
Cum
|  |  | Nos of bag | = |  |  |  |  | 255.5092 | ÷ | 0.1164 | = | 2195.096 | 2195.096 | Nos
6 | 40-530 | Supplying and laying shingles and peagravels as filter in two layers (top and bottom) as per specific size ranges and gradation including grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: (A)40-530-20: Well graded between 40mm to 20mm size.
|  |  | Bed | = | 1 | x | 40.1 | x | 20 | x | 0.2 | = | 160.4
|  |  | Slope | = | 2 | x | 7.906 | x | 4.3 | x | 0.2 | = | 13.5983
|  |  | ,, Circle | = | 2 | x | 11.775 | x | 7.906 | x | 0.2 | = | 37.2373
|  |  | Top of Embk. | = | 2 | x | 7 | x | 4.3 | x | 0.2 | = | 12.04
|  |  | Side of Embk. | = | 4 | x | 7 | x | 7.906 | x | 0.2 | = | 44.2736
Loose appron Top portion, C/S=
|  |  | 2 | x( | 7 | + | 3 | )x | 12 | x | 0.2 | = | 24
2
Loose appron Top portion, R/S=
|  |  | 2 | x( | 7 | + | 3 | )x | 10 | x | 0.2 | = | 20
2
|  |  | C/S & R/S | = | 4 | x | 5 | x | 1 | x | 0.2 | = | 4
Slope of Channel Sec. C-C
|  |  | Inclined length= |  |  |  | (2.00)² | + | (6.00)² | = | 6.32 | m
|  |  | C/S | = | 2 | x | 17 | x | 6.32 | x | 0.2 | = | 42.976
|  |  | R/S | = | 2 | x | 15 | x | 6.32 | x | 0.2 | = | 37.92
396.4452
|  |  | 40mm to 20 mm = 50% of total quantity |  |  |  |  | = | 396.4452 | x | 0.5 | = | 198.2226 | 198.2226 | Cum
Cum
|  | (B) 40-530-30: Well graded between 20mm to 5mm size. | 40mm to 20 mm = 50% of total quantity |  |  |  |  | = | 396.4452 | x | 0.5 | = | 198.2226 | 198.2226 | Cum
Cum
7 | 40-190 | Manufacturing and supplying C.C. blocks in leanest mix. 1:2.5:5 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a 28 days cylinder strength of 12 N/mm² including grading, washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering (steel shutter to be used) and stacking in measurable stacks, cost of all materials and charges, etc. complete as per direction of Engineer in charge . (A)40-190-15 : Block Size: 50cmx50cmx50cm | [11 empty] | 1736.6 | Nos
Block area
|  |  | Bed & Apron= |  |  |  | 1 | x | 40.1 | x | 20 | = | 802
|  |  | 50% of total Area = |  |  |  | 802 | x | 0.5 |  |  | = | 401
|  |  | Guide wall | = |  |  | 4 | x | 7 | x | 2 | = | 56
[11 empty] | Total | = | 457
|  |  | Area of each block |  |  | = | 0.5 | x | 0.5 | = | 0.25 | Sqm
|  |  | Nos of blocks for bed = |  |  |  | 457 | ÷ | 0.25 |  |  | = | 1828
|  |  | Deduction 5% for gap | [5 empty] | 1828 | x | 0.05 | = | 91.4
[11 empty] | Total = |  | 1736.6
|  | (B )40-190-05 : Block Size: 50cmx50cmx30cm | Block area
|  |  | Bed | = |  |  | 1 | x | 40.1 | x | 20 | = | 802
|  |  | 50% of total Area = |  |  |  | 802 | x | 0.5 |  |  | = | 401
|  |  | Slope | = |  |  | 2 | x | 7.906 | x | 4.3 | = | 67.9916
|  |  | Slope circle | = |  |  | 2 | x | 11.775 | x | 7.906 | = | 186.1863
|  |  | Slope ,, | = |  |  | 4 | x | 7 | x | 7.906 | = | 221.368
[11 empty] | Total | = | 876.5459
|  |  | Area of each block |  |  | = | 0.5 | x | 0.5 | = | 0.25 | Sqm
|  |  | Nos of block = | [5 empty] | 876.5459 | ÷ | 0.25 | = | 3506.1836
|  |  | Deduction 5% for gap | [5 empty] | 3506.1836 | x | 0.05 | = | 175.3092
[11 empty] | Total | = | 3330.8744 | 3330.8744 | Nos
.(C) 40-190-35 : Block Size: 40cmx40cmx40cm
Loose Appron C/S & R/S.
|  |  | Area= | = | 4 | x | 20 | x | 5 | = | 400 | Sqm
|  |  | Area of each block |  |  | = | 0.4 | x | 0.4 | = | 0.16 | Sqm
|  |  | Nos of block = | [5 empty] | 400 | ÷ | 0.16 | = | 2500
[11 empty] | Total | = | 2500
|  |  | Deduction 5% for gap | [5 empty] | 2500 | x | 0.05 | = | 125
[11 empty] | Total | = | 2375 | 2375 | Nos
Nos
.(D) 40-190-40 : Block Size: 40cmx40cmx20cm
|  |  | Top of Embankment |  |  | = | 2 | x | 7 | x | 4.3 | = | 60.2
Loose appron on the bank
|  |  | C/S | = | 2 | x( | 10 | + | 3 | )x | 7 | = | 91
2
[6 empty] | = | 2 | x | 5 | x | 1 | = | 10
|  |  | R/S | = | 2 | x( | 8 | + | 3 | )x | 7 | = | 77
2
[6 empty] | = | 2 | x | 5 | x | 1 | = | 10
Slope of Channel Sec. C-C
|  |  | Inclined length= |  |  |  | (2.00)² | + | (6.00)² | = | 6.32 | m
|  |  | C/S |  |  | = | 2 | x | 17 | x | 6.32 | = | 214.88
|  |  | R/S |  |  | = | 2 | x | 15 | x | 6.32 | = | 189.6
[11 empty] | Total | = | 652.68
|  |  | Area of each block |  |  | = | 0.4 | x | 0.4 | = | 0.16 | Sqm
|  |  | Nos of block = | [5 empty] | 652.68 | ÷ | 0.16 | = | 4079.25
|  |  | Deduction 5% for gap | [5 empty] | 4079.25 | x | 0.05 | = | 203.9625
[11 empty] | Total | = | 3875.2875 | 3875.2875 | Nos
Nos
8 | 40-274 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge. 40-270-10 . Within 200 m | Volume
Block size 50 cm x 50 cm x 50 cm
|  |  |  | = | 1736.6 | x | 0.5 | x | 0.5 | x | 0.5 | = | 217.075
Block size 50 cm x 50 cm x 50 cm
|  |  |  | = | 3330.8744 | x | 0.5 | x | 0.5 | x | 0.3 | = | 249.8156
Block size 40 cm x 40 cm x 40 cm
|  |  |  | = | 2375 | x | 0.4 | x | 0.4 | x | 0.4 | = | 152
Block size 40 cm x 40 cm x 20 cm
|  |  |  | = | 3875.2875 | x | 0.4 | x | 0.4 | x | 0.2 | = | 124.0092
[11 empty] | Total | = | 742.8998
40-270-10 . Within 200 m
|  |  | 50% of Total quantity |  |  | = | 742.8998 | x | 0.5 | = |  | = | 371.4499 | 371.4499 | Cum
Cum
|  | 40-270-20 . 200 m to 500 m. | 40-270-10 . Within 200 m
|  |  | 50% of Total quantity |  |  | = | 742.8998 | x | 0.5 | = |  | = | 371.4499 | 371.4499 | Cum
Cum
9 | 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-120-20 : With 25mm down graded stone chips.
|  |  | For Guide wall = |  | 2 | x | 20 | x | 0.6 | x | 1.2 | = | 28.8
Gap filling of block placing
|  |  | 4 | x | 7 | x | 0.5 | x | 0.2 | x | 0.2 | = | 0.56
Top of channel
|  |  | 2 | x | 32 | x | 0.5 | x | 0.2 | x | 0.2 | = | 1.28
[11 empty] | Total | = | 30.64 | 30.64 | Cum
Cum
10 | 36-150 | Formwork for centering and water tight shuttering as per drawing with14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charg. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrackbamboo props.
|  |  | For Guide wall = |  | 2 | x | 2 | x | 20 | x | 1.2 | = | 96
|  |  | Side | = | 2 | x | 2 | x | 0.6 | x | 1.2 | = | 2.88
Location Post base
|  |  |  | = | 2 | x | 4 | x | 1 | x | 0.3 | = | 2.4
|  |  | Do Ver. | = | 2 | x | 3.14 | x | 0.3 | x | 9 | = | 16.956
[11 empty] | Total | = | 118.236 | 118.236 | Sqm
Sqm
11 | 76-120 | M.S. Work for reinforcement with deformed M.S. bar, fy=400 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10 : 8mm dia to 30mm dia. | 12 mm dia rod
For base @ 150 mm c/c
|  |  |  | = | 2 | x | 2 | x | 8 | x | 0.88 | = | 28.16
|  |  | Ver. |  |  |  | 2 | x | 4 | x | 9.7 | = | 77.6
[11 empty] | Total | = | 105.76
[6 empty] | @ | 0.89 | Kg /m |  |  |  | = | 94.1264
|  |  | 10 mm dia rod | [9 empty] | Kg
For Ring @ 200 mm c/c
|  |  | Ver. |  |  |  | 2 | x | 45 | x | 0.87 | = | 78.3
[6 empty] | @ | 0.62 | Kg /m |  |  |  | = | 48.546
[11 empty] | Total | = | 142.6724 | 142.6724 | Kg.
Kg
12 | 20-100 | Single brick flat soling including preparation of bed, sand filling (FM>=0.50), levelling, dressing and sand blinding in foundation or floor with supply of all materials etc. complete and as per direction of Engineer in charge .20-100-10: With 1st class bricks
|  |  | For base of location Post | = |  |  | 2 | x | 1 | x | 1 | = | 2 | 2 | Sqm
Sqm
13 | 28-200 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10 : with stone chips.
For location Post
|  |  | Base | = | 2 | x | 1 | x | 1 | x | 0.3 | = | 0.6
Post
|  |  | 2 | x | 9 | x | 0.7854 | x | 0.3 | x | 0.3 | = | 0.63617
[11 empty] | Total | = | 1.2362 | 1.2362 | cum
Cum
14 | 16-110 | Earth work by manual labour in constructing/ resectioning of embankment / canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 . 0 m to 3 m height with 85% compaction.
For closing the Flood Fuse
|  |  | 1 | x( | 20 | + | 35 | )x( | 4.3 | + | 19.3 | )
[6 empty] | 2 |  |  |  | 2
[10 empty] | x | 3.5 | = | 1135.75 | 1725.75 | Cum
For Embankment construction
|  |  | 2 | x | 10 | x( | 4.3 | + | 19.3 | )x | 2.5 | = | 590
2
[11 empty] | Total | = | 1725.75
15 | 16-180 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement.
|  |  | Quantity same as item no.-13 |  |  |  |  | = | 1725.75 |  | Cum |  |  | 1725.75 | Cum
16 | 16-160 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3m neglected) for all kinds of earth work.
|  |  | Lead calculation |  |  | = | ((20/2 +50+22/2) -30)/15 = |  |  |  | 2.06 nos
Say 2 nos. lead
|  |  | Quantity same as item no.-13 |  |  |  |  | = | 1725.75 |  | Cum |  |  | 1725.75 | Cum
17 | 16-170 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm neglected) for all kinds of earth work.
Lift calculation
[5 empty] | (3.00/2 +3.00/2 -1.5)/1.00 = |  |  |  | 1.5 nos | say 2 nos Lift
|  |  | Quantity same as item no.-13 |  |  |  |  | = | 1725.75 |  | Cum |  |  | 1725.75 | Cum
18 | 16-470 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge.
|  |  |  | Total quantity of Cross bundh = quantity Same as item no. 1 = | [8 empty] | 2052
Cum
|  |  | Remove 80% of total quantity |  |  |  |  | = | 2052 | x | 0.8 | = | 1641.6 | 1641.6 | Cum
#REF!
[18 empty] | #REF! | #REF!
[16 empty] | 0 | 0
0