## Prev_Data
Code | Description | Imed_Code | Dpp_allocation | Weight | Prev_Progress_Fin | Prev_Progress_Phy | Cur_Tar_Fin | Cur_Tar_Phy
3111302 | Conveyance Allowance | REV_1 | 10 | 0.02 | 1.01 | 0.00202 | 0.5 | 0.001
3111327 | Overtime Allowance | REV_1 | 10 | 0.02 | 0 | 0 | 0 | 0
3111338 | Other Allowance | REV_1 | 140 | 0.23 | 36.61 | 0.060145 | 14 | 0.023
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 100 | 0.17 | 58.54 | 0.099518 | 15 | 0.0255
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 245 | 0.41 | 116.67 | 0.19524 | 34.25 | 0.057316
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 2596.27 | 4.33 | 1603.18 | 2.6737 | 269.16 | 0.4489
3211119 | Postage | REV_5 | 25 | 0.04 | 0.77 | 0.001232 | 0.5 | 0.0008
3211120 | Telephones/Telegram/Teleprinter | REV_5 | 25 | 0.04 | 0.97 | 0.001552 | 0.2 | 0.00032
3211117 | Telex/Fax/Internet | REV_5 | 25 | 0.04 | 0.44 | 0.000704 | 0.2 | 0.00032
3221104 | Registration Fee (Vehicles) | REV_6 | 15 | 0.03 | 11.92 | 0.02384 | 1 | 0.002
3211115 | Water | REV_7 | 10 | 0.02 | 1.11 | 0.00222 | 0.45 | 0.0009
3211113 | Electricity | REV_7 | 15 | 0.03 | 8.74 | 0.01748 | 3.5 | 0.007
3243102 | Gas & Fuel | REV_8 | 200 | 0.33 | 17.52 | 0.028908 | 6 | 0.0099
3243101 | Petrol and Lubricant | REV_8 | 150 | 0.25 | 64.59 | 0.10765 | 20 | 0.033333
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 3 | 0.01 | 1.16 | 0.0038667 | 0.15 | 0.0005
3255102 | Printing & Binding | REV_10 | 35 | 0.06 | 34.16 | 0.05856 | 0.5 | 0.00085714
3255104 | Stationery, Seals & Stamps | REV_11 | 150 | 0.25 | 49.91 | 0.083183 | 20 | 0.033333
3211127 | Books & Periodicals | REV_12 | 2 | 0 | 0.28 | 0 | 0.2 | 0
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 238.54 | 0.53 |  | 0 |  | 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 398.41 | 0.89 | 301.5 | 0.67351 | 202.05 | 0.45136
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 2533.34 | 5.64 | 1346.63 | 2.998 | 695.47 | 1.5483
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 1321.68 | 2.94 | 578.2 | 1.2862 | 252.37 | 0.56138
3211109 | Casual labour/Job worker | REV_15 | 15 | 0.25 | 10.96 | 0.18267 | 3.5 | 0.058333
3256103 | Consumable Stores | REV_16 | 25 | 0.42 | 3.74 | 0.062832 | 3 | 0.0504
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 7901.4 | 10 | 5168.01 | 6.5406 | 500 | 0.6328
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 25 | 0.42 | 12.73 | 0.21386 | 5 | 0.084
3111332 | b) Interim Evaluation | REV_18 | 10 | 0.17 | 1.22 | 0.02074 | 1 | 0.017
3111332 | c) Progress Monitoring | REV_18 | 10 | 0.17 | 1.23 | 0.02091 | 1 | 0.017
3257104 | Survey | REV_19 | 162 | 2.7 | 85.02 | 1.417 | 50 | 0.83333
3255101 | Computer Consumables | REV_20 | 50 | 0.83 | 20.47 | 0.3398 | 10 | 0.166
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 1700 | 2.84 | 875.46 | 1.4625 | 300 | 0.50118
3258101 | Motor Vehicles | REV_22 | 100 | 0.48 | 61.4 | 0.29472 | 15 | 0.072
3258102 | Furnitures & Fixtures | REV_22 | 15 | 0.07 | 3.2 | 0.014933 | 2 | 0.0093333
3258103 | Computers & office equipments | REV_22 | 25 | 0.12 | 5.34 | 0.025632 | 3 | 0.0144
3258105 | Machineries & Equipments | REV_22 | 25 | 0.12 | 1.22 | 0.005856 | 2 | 0.0096
3258107 | Office Building : Repair & Maintenance | REV_22 | 20 | 0.1 | 19.98 | 0.0999 | 0 | 0
3258106 | Residential Building : Repair & Maintenance | REV_22 | 20 | 0.1 | 14.53 | 0.07265 | 5 | 0.025
3258105 | Engineering Equipments | REV_22 | 25 | 0.12 | 1.39 | 0.006672 | 2 | 0.0096
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 362.5 | 1.73 | 95.03 | 0.45352 | 58.25 | 0.27799
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 10 | 0.05 | 2.4 | 0.012 | 0.75 | 0.00375
3258107 | Others : Repair & Maintenance | REV_22 | 25 | 0.12 | 7.48 | 0.035904 | 3 | 0.0144
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 702.5 | 2.73 | 606.9 | 2.3585 | 95.6 | 0.37151
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 68.25 | 0.27 | 50.22 | 0.19867 | 0 | 0
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 100 | 1 | 61.29 | 0.6129 | 0 | 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 8.97 | 0.21 | 8.95 | 0.20953 | 0 | 0
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 5 | 0.11 | 0.79 | 0.01738 | 0 | 0
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 20.5 | 0.47 | 20.18 | 0.46266 | 0 | 0
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 6 | 0.14 | 2.13 | 0.0497 | 0 | 0
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 50 | 1.15 | 9.49 | 0.21827 | 5 | 0.115
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 19.5 | 0.45 | 19.47 | 0.44931 | 0 | 0
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 13.75 | 0.32 | 9.88 | 0.22993 | 0 | 0
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 1.5 | 0.03 | 0.2 | 0.004 | 0 | 0
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 5.25 | 0.12 | 4.08 | 0.093257 | 0 | 0
4112314 | Furnitures & Fixtures | CAP_6 | 50 | 0.77 | 45.32 | 0.69793 | 0 | 0
4112303 | Aircooler | CAP_6 | 15 | 0.23 | 9.74 | 0.14935 | 4 | 0.061333
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 24000 | 10 | 14323.6 | 5.9682 | 2139.42 | 0.89143
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 1261 | 1.06 |  | 0 | 490.33 | 0.41217
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 1515 | 1.27 |  | 0 | 0 | 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 20311 | 17.09 | 6143.66 | 5.1694 | 8105.58 | 6.8202
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 9729 | 8.19 | 6011.48 | 5.0605 | 3956.08 | 3.3303
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 2515 | 2.12 |  | 0 | 900.73 | 0.75926
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 2550 | 2.15 |  | 0 | 913.26 | 0.77
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 1785 | 1.5 |  | 0 | 657.55 | 0.55256
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 11952.5 | 10.06 | 6127.06 | 5.1569 | 4914.31 | 4.1362
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 166 | 0.14 |  | 0 | 0 | 0
4111201 | Construction of WMG Office | CAP_8 | 1380 | 1.16 |  | 0 | 318.14 | 0.26742
4111201 | O&M During Construction | CAP_8 | 200 | 0.17 | 0 | 0 | 0 | 0