## Up to June 2019
Cumulative Expenditure of 47 nos Packages up to 30.06.2020 (Including Gate)
SL No. | Item | As Per RDPP |  | Up to June 2018 |  |  | July'18 to June'19 |  |  | Total Cumulative up to June'19 Amount |  |  | July'2019 to June'2020 |  |  | Total Cumulative up to June'20 Amount
|  | Quantity | Cost | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA
New Haor Sub-Project
1 | Construction of Irrigation Inlet | 131 nos. | 1261 | 5.27 | 0.68721 | 4.5828 | 116.72 | 16.3408 | 100.3792 | 121.99 | 17.028 | 104.962 | 151.91 | 18.9887 | 132.9212 | 273.9 | 36.0168 | 237.8832
2 | Construction of Submersible Embankment | 263.24 km | 11952.5 | 3895.91 | 506.01 | 3389.9 | 2007.04 | 280.9856 | 1726.0544 | 5902.95 | 786.9956 | 5115.9544 | 1932 | 241.5 | 1690.5 | 7834.95 | 1028.4956 | 6806.4544
3 | Construction of Regulator/ Causeway/Drainage Box Outler | 137 nos. | 20311 | 2581.71 | 332.56 | 2249.15 | 3413.2 | 471.78 | 2941.42 | 5994.91 | 804.34 | 5190.57 | 4329.57 | 541.1962 | 3788.3737 | 10324.48 | 1345.5362 | 8978.9437
4 | Re-excavation of Khal/River | 318.20km | 3729 | 1958.04 | 252.78 | 1705.26 | 2875.01 | 402.5014 | 2472.5086 | 4833.05 | 655.2814 | 4177.7686 | 1805.24 | 225.655 | 1579.585 | 6638.29 | 880.9364 | 5757.3536
5 | Rehablitation of Regulator (New Haor) | 8 nos | 166 | 0 | 0 | 0 | 178.46 | 24.9844 | 153.4756 | 178.46 | 24.9844 | 153.4756 | 12.48 | 1.56 | 10.92 | 190.94 | 26.5444 | 164.3956
Rehabilitation Sub-Project
6 | Re-excavation of Khal/River (Rehab) | 143.00km | 2515 | 0 | 0 | 0 | 1517.6 | 212.464 | 1305.136 | 1517.6 | 212.464 | 1305.136 | 365.52 | 45.69 | 319.83 | 1883.12 | 258.154 | 1624.966
7 | Re-installation/Construction of regulator/ Causeway (Rehablitation Sub-project) | 7 nos | 1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733.34 | 91.6675 | 641.6725 | 733.34 | 91.6675 | 641.6725
8 | Construction of Full Embankment | 84.31km | 2550 | 62.18 | 8.85 | 53.33 | 477.32 | 66.8248 | 410.4952 | 539.5 | 75.6748 | 463.8252 | 361.19 | 45.1488 | 316.0413 | 900.69 | 120.8236 | 779.8664
9 | Construction of Submersible Embankment (Rehab) | 87.03km | 1785 | 0 | 0 | 0 | 633.06 | 85.63 | 547.43 | 633.06 | 85.63 | 547.43 | 738.02 | 92.2525 | 645.7675 | 1371.08 | 177.8825 | 1193.1975
10 | Replecement of Gate (Netrokona & Kishoregonj) | 104 nos | 362.5 | 84.04 | 9.84 | 74.2 | 10.99 | 0.99 | 10 | 95.03 | 10.83 | 84.2 | 33.17 | 4.1462 | 29.0237 | 128.2 | 14.9762 | 113.2237
11 | Construction of WMG office | 60 nos | 1380 | 0 | 0 | 0 | 42.09 | 5.4717 | 36.6183 | 42.09 | 5.4717 | 36.6183 | 93.32 | 11.665 | 81.655 | 135.41 | 17.1367 | 118.2733
12 | O&M during Construction | L.S | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 8587.15 | 1110.7272 | 7476.4228 | 11271.49 | 1567.9727 | 9703.5173 | 19858.64 | 2678.6999 | 17179.9401 | 10555.76 | 1319.47 | 9236.29 | 30414.4 | 3998.1699 | 26416.2301

## Sheet1
Package No. | Construction of Irrigation Inlet | Construction of Submersible Embankment | Construction of Regulator/ Causeway/ Drainage Box Outler | Re-excavation of Khal/River | Rehablitation of Regulator (New Haor) | Re-excavation of Khal/River (Rehab) | Re-installation/ Construction of regulator/ Causeway (Rehablitation Sub-project) | Construction of Full Embankment | Construction of Submersible Embankment (Rehab) | Replecement of Gate (Netrokona & Kishoregonj) | Construction of WMG office | Package wise Total (In Lac Taka) |  | Physical Progress | Contract Amount
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Kishoregonj
PW-02 |  | 14.01 | 137.44 | 196.26 | [7 empty] | 347.71 | 357.78 | 89 | 402
PW-03 |  | 473.29 | 152.64 | [8 empty] | 625.93 | 668.7762 | 97 | 689.46
PW-04 |  | 263.82 | 450.87 | [8 empty] | 714.69 | 706.9674 | 99.5 | 710.52
PW-05 |  | 425.81 | 149.34 | [8 empty] | 575.15 | 662.931 | 86 | 770.85
PW-06 |  |  | 224.43 | 612.82 | [7 empty] | 837.25 | 786.4679 | 99.5 | 790.42
PW-07 |  |  |  | 565.07 | [7 empty] | 565.07 | 567.15 | 60 | 945.25
PW-13 |  | 235.97 | 411.23 | [8 empty] | 647.2 | 762.9032 | 76 | 1003.82
PW-14 |  | 638.29 | 168.6 | [8 empty] | 806.89 | 745.59 | 87 | 857
PW-15 |  | 333.94 | [9 empty] | 333.94 | 470.292 | 60 | 783.82
PW-09 |  |  | 712.33 | [8 empty] | 712.33 | 719.1044 | 98 | 733.78
PW-10 |  | 302.15 | 107.53 | [8 empty] | 409.68 | 530.382 | 60 | 883.97
PW-11 |  | 320.79 | 202.07 | [8 empty] | 522.86 | 540.8845 | 65 | 832.13
PW-16 |  | 398.08 | 323.54 | [8 empty] | 721.62 | 824.22 | 90 | 915.8
PW-17 | 246.59 | 522.11 | 683.25 | [8 empty] | 1451.95 | 1489.7425 | 95 | 1568.15
PW-24 |  | 890.42 | [9 empty] | 890.42 | 881.8368 | 96 | 918.58
PW-12 |  |  | 455.25 | 250.34 | [7 empty] | 705.59 | 810.4495 | 85 | 953.47
PW-18 |  |  | 349.21 | 361.81 | [7 empty] | 711.02 | 722.436 | 52 | 1389.3
PW-19 |  |  |  | 331.35 | [7 empty] | 331.35 | 474.5699 | 49 | 968.51
PW-20 | 4.91 |  | 739.81 | [8 empty] | 744.72 | 833.85 | 75 | 1111.8
PW-26 |  | 22.52 | 478.6 | [8 empty] | 501.12 | 506.2243 | 99.4 | 509.28
PW-25 |  |  | 467.31 | 282.06 | [7 empty] | 749.37 | 795.225 | 50 | 1590.45
PW-22 |  | 190.6 | 29.94 | 60.51 | [7 empty] | 281.05 | 296.163 | 35 | 846.18
PW-23 | 40.31 | 102.27 | 577.75 | [8 empty] | 720.33 | 668.4825 | 85 | 786.45
PW-01 | [5 empty] | 51.09 | [5 empty] | 51.09 | 64.5502 | 13 | 496.54
PW-21 |  | 76.84 | 191.4 | [8 empty] | 268.24 | 311.5136 | 32 | 973.48
PW-27 | [12 empty] | 0 |  | 929.77
PW-28 | [10 empty] | 135.41 | 135.41 | 220.796 | 17 | 1298.8
Hobigonj | [12 empty] | 0
PW-04 |  | 655.94 | [9 empty] | 655.94 | 847.8877 | 73 | 1161.49
PW-05 |  |  | 307.8 | [8 empty] | 307.8 | 522.9919 | 41 | 1275.59
PW-06 | 22.4 |  | 1071.91 | [8 empty] | 1094.31 | 1343.8992 | 84 | 1599.88
PW-07 |  |  |  | 673.81 | [7 empty] | 673.81 | 769.2108 | 83 | 926.76
PW-01 | [5 empty] | 646.97 |  |  | 291.3 |  |  | 938.27 | 1136.6261 | 73.5 | 1546.43
PW-02 | [5 empty] | 120 | 98 |  | 861.52 |  |  | 1079.52 | 1192.8136 | 88 | 1355.47
Netrokona | [12 empty] | 0
PW-01 | [7 empty] | 817.97 |  |  |  | 817.97 | 953.771 | 70 | 1362.53
PW-07 |  |  |  | 567.71 | [7 empty] | 567.71 | 901.8481 | 99.5 | 906.38
PW-02 | [5 empty] | 475.86 | [5 empty] | 475.86 | 621.8745 | 65 | 956.73
PW-03 |  |  |  |  | 310.37 |  | 0 | 402.36 |  |  |  | 712.73 | 776.4334 | 82 | 946.87
PW-04 | [5 empty] | 625.91 |  |  | 218.26 |  |  | 844.17 | 1020.6438 | 66 | 1546.43
PW-05 | [6 empty] | 635.34 |  |  |  |  | 635.34 | 725.5218 | 61 | 1189.38
PW-06 |  |  | 44.77 | 318.57 | 12.48 | [6 empty] | 375.82 | 590.1836 | 90.75 | 650.34
PW-08 |  |  | 136.46 | [8 empty] | 136.46 | 216.9496 | 28 | 774.82
Sunamgonj | [12 empty] | 0
PW-01 |  | 459.73 | 195.82 | 89.53 | [7 empty] | 745.08 | 922.8839 | 59 | 1564.21
PW-02 |  |  |  | 1094.77 | [7 empty] | 1094.77 | 955 | 80 | 1193.75
PW-03 |  |  | 511.73 | [8 empty] | 511.73 | 601.3254 | 39 | 1541.86
PW-04 |  | 1521.41 | [9 empty] | 1521.41 | 1533.0336 | 98 | 1564.32
PW-05 |  |  | 1061.82 | [8 empty] | 1061.82 | 1130.7375 | 75 | 1507.65
PW-06 |  |  |  | 1268.67 | [7 empty] | 1268.67 | 1341.7845 | 85 | 1578.57
Gate Repleacement | [9 empty] | 128.2
Total | 314.21 | 7847.99 | 10342.85 | 6673.28 | 322.85 | 1919.83 | 733.34 | 1220.33 | 1371.08 | 128.2 | 135.41 | 30881.17

## 08.11.2020
SL No. | Item | As Per 2nd RDPP |  | Year-1 (2014-15) |  | Year-2 (2015-16) |  | Year-3 (2016-17) |  | Year-4 (2017-18) |  | Year-5 (2018-19) |  | Year-6 (2019-20) |  | Year-7 (2020-21) |  | Year-8 (2021-22) |  | Up to June 2018 |  |  | July'18 to June'19 |  |  | Total Cumulative up to June'19 Amount |  |  | July'2019 to June'2020 |  |  | Total Cumulative up to June'20 Amount |  |  | Budget 2019-20 |  |  | Balance Budget
|  | Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA | GoB | RPA | Total
Irrigation Structure
1 | Construction of Irrigation Inlet | 116 nos. | 1089.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 Nos (Full) & 8 nos (Part) | 116.72 | 31 Nos (Full) & 17 nos (Part) | 192.22 | 0 | 0 | 0 | 0 | 5.27 | 0.68721 | 4.5828 | 116.72 | 16.3408 | 100.3792 | 121.99 | 17.028 | 104.962 | 192.22 | 24.0275 | 168.1925 | 314.21 | 41.0555 | 273.1545 | 30.93 | 354 | 384.93 | 192.71
Drainage Structure
2 | Re-installation/Construction of regulator/ Causeway (Rehablitation Sub-project) | 5 nos | 1175.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1No. (Part) | 0 | 1No. (Full) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Construction of Regulator/ Causeway/Drainage Box Outler | 112 nos. | 18686.36 | 0 | 0 | 0 | 0 | 7 Nos (Part) | 293.15 | 7 Nos (Full) & 20 nos (Part) | 2774.9 | 30 Nos (Full) & 50 nos (Part) | 3076.61 | 50 Nos (Full) & 30 nos (Part) | 4075.22 | 0 | 0 | 0 | 0 | 2581.71 | 332.56 | 2249.15 | 3413.2 | 471.78 | 2941.42 | 5994.91 | 804.34 | 5190.57 | 4075.22 | 512.09 | 3563.13 | 10070.13 | 1316.43 | 8753.7 | 523.12 | 5857 | 6380.12 | 2304.9
4 | Re-excavation of Khal/River | 337.954 km | 10223.64 | 0 | 0 | 0 | 0 | 50 km (Full) & 50 km (Part) | 349.16 | 100 km (Full) & 50 km (Part) | 840 | 150 km (Full) & 100 km (Part) | 4822.32 | 187 km (Full) & 73 km (Part) | 2667.18 | 0 | 0 | 0 | 0 | 1958.04 | 252.78 | 1705.26 | 2875.01 | 402.5014 | 2472.5086 | 4833.05 | 655.2814 | 4177.7686 | 2667.19 | 319.57 | 2347.62 | 7500.24 | 974.8514 | 6525.3886 | 322.33 | 2858 | 3180.33 | 513.14
Others Structure
5 | Re-excavation of Khal/River (Rehab) | 108.974km | 3397.9416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 km (Full) & 30 km (Part) | 455.04 | 65 km (Full) & 15 km (Part) | 726.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517.6 | 212.464 | 1305.136 | 1517.6 | 212.464 | 1305.136 | 726.54 | 94.32 | 632.22 | 2244.14 | 306.784 | 1937.356 | 150.74 | 650 | 800.74 | 74.2
6 | Construction of Full Embankment | 67.110km | 2035.4302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 km (Full) & 23 km (Part) | 452.46 | 53 km (Full) & 12 km (Part) | 253.65 | 0 | 0 | 0 | 0 | 62.18 | 8.85 | 53.33 | 477.32 | 66.8248 | 410.4952 | 539.5 | 75.6748 | 463.8252 | 253.6512 | 35.79 | 217.8612 | 793.1513 | 111.4648 | 681.6864 | 36.79 | 660 | 696.79 | 443.1387
7 | Construction of Submersible Embankment (Rehab) | 61.210km | 1747.8134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 km (Full) & 21 km (Part) | 341.85 | 51 km (Full) & 4km (Part) | 179.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633.06 | 85.63 | 547.43 | 633.06 | 85.63 | 547.43 | 179.6775 | 26.02 | 153.6575 | 812.7375 | 111.65 | 701.0875 | 27.02 | 475 | 502.02 | 322.3425
8 | Construction of Submersible Embankment (New Haor) | 261.653 km | 19669.7082 | 0 | 0 | 0 | 0 | 10 km (Full) & 30 km (Part) | 336.9 | 20 km (Full) & 80 km (Part) | 3910 | 110 km (Full) & 90 km (Part) | 1880.15 | 156 km (Full) & 54 km (Part) | 2923.61 | 0 | 0 | 0 | 0 | 3895.91 | 506.01 | 3389.9 | 2007.04 | 280.9856 | 1726.0544 | 5902.95 | 786.9956 | 5115.9544 | 2923.61 | 365.4513 | 2558.1588 | 8826.56 | 1152.4469 | 7674.1132 | 378.79 | 3591 | 3969.79 | 1046.18
9 | Rehablitation of Regulator (New Haor) | 7 nos | 160.7906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1no. (Part) | 73.26 | 1 Nos (Full) & 3 nos (Part) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178.46 | 24.9844 | 153.4756 | 178.46 | 24.9844 | 153.4756 | 0 | 0 | 0 | 178.46 | 24.9844 | 153.4756 | 0 | 0 | 0 | 0
10 | Construction of WMG office | 30 nos | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5nos. (Part) | 42.09 | 4 Nos (Full) & 4 nos (Part) | 93.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.09 | 5.4717 | 36.6183 | 42.09 | 5.4717 | 36.6183 | 93.32 | 11.665 | 81.655 | 135.41 | 17.1367 | 118.2733 | 16.28 | 255 | 271.28 | 177.96
11 | O&M during Construction | L.S | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Threshing Floor Construction | 5 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Physical Work |  | 59561.444 | 0 | 0 | 0 | 0 | 0 | 979.21 | 0 | 7524.9 | 0 | 11260.5 | 0 | 11111.43 | 0 | 0 | 0 | 0 | 8503.11 | 1100.8872 | 7402.2228 | 11260.5 | 1566.9827 | 9693.5173 | 19763.61 | 2667.8699 | 17095.7401 | 11111.4288 | 1388.9337 | 9722.495 | 30875.0387 | 4056.8037 | 26818.2351 | 1486 | 14700 | 16186 | 5074.5712
| Gate Replacement | [36 empty] | 0
13 | Replecement of Gate (Netrokona & Kishoregonj) | 86 nos | 404.24 | 0 | 0 | 0 | 0 | 26 nos | 59.7 | 26 nos. | 24.35 | L.S | 10.99 | L.S | 33.17 | 0 | 0 | 0 | 0 | 84.04 | 9.84 | 74.2 | 10.99 | 0.99 | 10 | 95.03 | 10.83 | 84.2 | 33.17 | 3.71 | 29.46 | 128.2 | 14.54 | 113.66 | 4.12 | 50 | 54.12 | 20.95
| Total |  | 59965.684 | [5 empty] | 1038.91 |  | 7549.25 |  | 11271.49 |  | 11144.6 |  |  |  |  | 8587.15 | 1110.7272 | 7476.4228 | 11271.49 | 1567.9727 | 9703.5173 | 19858.64 | 2678.6999 | 17179.9401 | 11144.5988 | 1392.6437 | 9751.955 | 31003.2387 | 4071.3437 | 26931.8951 | 1490.12 | 14750 | 16240.12 | 10170.0925

## Sheet2
SL No. | Item | Unit | As Per 2nd RDPP | Year-1 (2014-15) | Year-2 (2015-16) | Year-3 (2016-17) | Year-4 (2017-18) | Year-5 (2018-19) | Year-6 (2019-20) | Year-7 (2020-21) | Year-8 (2021-22) | Up to June 2018 |  |  | July'18 to June'19 |  |  | Total Cumulative up to June'19 Amount |  |  | July'2019 to June'2020 |  |  | Total Cumulative up to June'20 Amount |  |  | Budget 2019-20 |  |  | Balance Budget
1 | Inlet | No. | 116 | 0 | 0 | 0 | 0 | 17 | 45 | 95 | 116 | 5.27 | 0.68721 | 4.5828 | 116.72 | 16.3408 | 100.3792 | 121.99 | 17.028 | 104.962 | 192.22 | 24.0275 | 168.1925 | 314.21 | 41.0555 | 273.1545 | 30.93 | 354 | 384.93 | 192.71
|  |  | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116
|  |  |  | 0 Of 116 | 0 Of 116 | 0 Of 116 | 0 Of 116 | 17 Of 116 | 45 Of 116 | 95 Of 116 | 116 Of 116
2 | Re-installation/Construction of regulator/ Causeway (Rehablitation Sub-project) | No. | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Construction of Regulator/ Causeway/Drainage Box Outler | No. | 112 | 0 | 0 | 2 | 19 | 60 | 68 | 98 | 112 | 2581.71 | 332.56 | 2249.15 | 3413.2 | 471.78 | 2941.42 | 5994.91 | 804.34 | 5190.57 | 4075.22 | 512.09 | 3563.13 | 10070.13 | 1316.43 | 8753.7 | 523.12 | 5857 | 6380.12 | 2304.9
4 | Re-excavation of Khal/River | Km | 337.954 | 0 | 0 | 80 | 130 | 210 | 231 | 306 | 337.95 | 1958.04 | 252.78 | 1705.26 | 2875.01 | 402.5014 | 2472.5086 | 4833.05 | 655.2814 | 4177.7686 | 2667.19 | 319.57 | 2347.62 | 7500.24 | 974.8514 | 6525.3886 | 322.33 | 2858 | 3180.33 | 513.14
5 | Re-excavation of Khal/River (Rehab) | Km | 108.974 | 0 | 0 | 0 | 0 | 48 | 74 | 108.97 | 108.97 | 0 | 0 | 0 | 1517.6 | 212.464 | 1305.136 | 1517.6 | 212.464 | 1305.136 | 726.54 | 94.32 | 632.22 | 2244.14 | 306.784 | 1937.356 | 150.74 | 650 | 800.74 | 74.2
6 | Construction of Full Embankment | Km | 67.11 | 0 | 0 | 0 | 0 | 44 | 60 | 67.11 | 67.11 | 62.18 | 8.85 | 53.33 | 477.32 | 66.8248 | 410.4952 | 539.5 | 75.6748 | 463.8252 | 253.6512 | 35.79 | 217.8612 | 793.1513 | 111.4648 | 681.6864 | 36.79 | 660 | 696.79 | 443.1387
7 | Construction of Submersible Embankment (Rehab) | Km | 61.21 | 0 | 0 | 0 | 0 | 43 | 53 | 61.21 | 61.31 | 0 | 0 | 0 | 633.06 | 85.63 | 547.43 | 633.06 | 85.63 | 547.43 | 179.6775 | 26.02 | 153.6575 | 812.7375 | 111.65 | 701.0875 | 27.02 | 475 | 502.02 | 322.3425
8 | Construction of Submersible Embankment (New Haor) | Km | 261.653 | 0 | 0 | 28 | 68 | 164 | 188 | 238 | 261.65 | 3895.91 | 506.01 | 3389.9 | 2007.04 | 280.9856 | 1726.0544 | 5902.95 | 786.9956 | 5115.9544 | 2923.61 | 365.4513 | 2558.1588 | 8826.56 | 1152.4469 | 7674.1132 | 378.79 | 3591 | 3969.79 | 1046.18
9 | Rehablitation of Regulator (New Haor) | No. | 7 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 7 | 0 | 0 | 0 | 178.46 | 24.9844 | 153.4756 | 178.46 | 24.9844 | 153.4756 | 0 | 0 | 0 | 178.46 | 24.9844 | 153.4756 | 0 | 0 | 0 | 0
10 | Construction of WMG office | No. | 30 | 0 | 0 | 0 | 0 | 3 | 6 | 19 | 30 | 0 | 0 | 0 | 42.09 | 5.4717 | 36.6183 | 42.09 | 5.4717 | 36.6183 | 93.32 | 11.665 | 81.655 | 135.41 | 17.1367 | 118.2733 | 16.28 | 255 | 271.28 | 177.96
11 | O&M during Construction | L.S | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Threshing Floor Construction | No. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5
13 | Replecement of Gate (Netrokona & Kishoregonj) | No. | 86 | 0 | 0 | 26 | 52 | 53 | 54 | 73 | 13 | 84.04 | 9.84 | 74.2 | 10.99 | 0.99 | 10 | 95.03 | 10.83 | 84.2 | 33.17 | 3.71 | 29.46 | 128.2 | 14.54 | 113.66 | 4.12 | 50 | 54.12 | 20.95

## Input_data
StructureName | Unit | As Per 2nd RDPP | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
Construction of Irrigation Inlet | Nos | 116 | 0 | 0 | 0 | 0 | 17 | 45 | 95 | 116
Regulator Re-installation (Rehablitation Sub-project) | Nos | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5
Construction of Regulator/ Causeway/Drainage Box Outler (New Haor) | Nos | 112 | 0 | 0 | 2 | 19 | 60 | 68 | 98 | 112
Re-excavation of Khal/River (New Haor) | Km | 337.954 | 0 | 0 | 80 | 130 | 210 | 231 | 306 | 337.95
Re-excavation of Khal/River (Rehab Haor) | Km | 108.974 | 0 | 0 | 0 | 0 | 48 | 74 | 108.97 | 108.97
Construction of Full Embankment (Rehab Haor) | Km | 67.11 | 0 | 0 | 0 | 0 | 44 | 60 | 67.11 | 67.11
Construction of Submersible Embankment (Rehab Haor) | Km | 61.21 | 0 | 0 | 0 | 0 | 43 | 53 | 61.21 | 61.31
Construction of Submersible Embankment (New Haor) | Km | 261.653 | 0 | 0 | 28 | 68 | 164 | 188 | 238 | 261.65
Rehablitation of Regulator (New Haor) | Nos | 7 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 7
Construction of WMG office | Nos | 30 | 0 | 0 | 0 | 0 | 3 | 6 | 19 | 30
Construction of Threshing Floor | Nos | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5
Replecement of Gate (Netrokona & Kishoregonj) | Nos | 86 | 0 | 0 | 26 | 52 | 53 | 54 | 73 | 86

## Input_Data2
StructureName | Unit | As Per 2nd RDPP | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
Total | Nos | 599 | 0 | 0 | 9.12 | 74.75 | 171.79 | 269.3 | 429.3 | 599

## This Years Physical Work Progra
StructureName | Unit | As Per 2nd RDPP | 2020-21
Inlet | Nos | 116 | 50
Reg Re-inst | Nos | 5 | 3
Reg/ CW/BDO | Nos | 112 | 30
Khal/River (New) | Km | 338 | 75
Khal/River (Rehab ) | Km | 109 | 34
Full Emb | Km | 68 | 7
Subm Emb (Rehab) | Km | 62 | 8
Subm Emb (New) | Km | 263 | 50
Rehabof Reg | Nos | 7 | 4
WMG office | Nos | 30 | 13
Threshing Floor | Nos | 5 | 3
Gate | Nos | 86 | 19