## Resource_List
Code | Name | Unit
101 | Mixture Machine | Nos
102 | Excavator | Nos
103 | Compaction Ruller | Nos
104 | Form Work | Nos
201 | Cement | Bag
202 | Sand 1.5 FM | cum
203 | Stone Chips | cum
204 | Geotextile Filter | sqm
205 | Filter Sand | cum
206 | Peagravel | cum
207 | CC Block | Nos
301 | Labor | m-day
401 | Labor payment | BDT Lac

## Resources_Consumption
Code | Name | Unit | NS101 | 40-190-05 | 40-190-15 | 40-190-35 | 40-190-40 | 40-190-50 | NS105 | 16-240 | 40-550-10 | 40-500-40 | 40-530-30 | NS106 | NS102 | 16-510 | 40-450 | 16-470 | 40-380-20 | 48-100 | 40-670-30
101 | Mixture Machine | Nos | 0 | 0.0037037 | 0.0061728 | 0.0031546 | 0.0015798 | 0.0013333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Excavator | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0033 | 0 | 0 | 0 | 0 | 0 | 0.0033 | 0.0033 | 0.0033 | 0.0033 | 0 | 0
103 | Compaction Roller | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0013158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Form Work | Nos | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | Cement | Bag | 0 | 0.38448 | 0.6408 | 0.32809 | 0.16404 | 0.13841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21
202 | Sand 1.5 FM | cum | 0 | 0.033375 | 0.055625 | 0.02848 | 0.01424 | 0.012015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031
203 | Stone Chips | cum | 0 | 0.073209 | 0.12202 | 0.062472 | 0.031236 | 0.026355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | Filter Sand | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | Geotextile Filter | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | Peagravel | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | CC Block | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | Geobag | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
209 | Turfing Sod | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
301 | Labor | m-day | 0.7 | 0.11111 | 0.18519 | 0.094637 | 0.047393 | 0.04 | 0.4 | 0.1 | 0.18 | 0.018 | 0.18 | 0.0057143 | 0.7 | 0.1 | 0.1 | 0.1 | 0.016327 | 0.02 | 0.06
401 | Labor payment | BDT Thousand | 210 | 33 | 56 | 29 | 14 | 12 | 120 | 60 | 54 | 5.4 | 54 | 1.72 | 210 | 60 | 60 | 60 | 5 | 6 | 18

## WBS3
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | -1 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9

## Main
Name | Start | Finish | Allocation_Sheet_Name | Site Name
Type_A_665M_M2950_TO_M3615 | 1 | 87 | Type_A_665M_M2950_TO_M3615 | Type A slope protection work of the Noapara Hao Submergible Embankment from M2950 to M3615=665M under HFMLIP
Type_B5_30M_M6900_TO_M6930 | 1 | 87 | T_B5_30M_M6900_TO_M6930 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M6900 to M6930=30M under HFMLIP
Type_B5_210M_M8550_TO_M8760 | 1 | 87 | T_B5_210M_M8550_TO_M8760 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M8550 to M8760=210M under HFMLIP
Type_B5_353M_M8822_TO_M9175 | 1 | 87 | T_B5_353M_M8822_TO_M9175 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M8822 to M9175=353M under HFMLIP
Type_B5_212M_M12440_TO_M12652 | 1 | 87 | T_B5_212M_M12440_TO_M12652 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M12440 to M12652=212M under HFMLIP
Type_B5_30M_M13925_TO_M13955 | 1 | 87 | T_B5_30M_M13925_TO_M13955 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M13925 to M13955=30M under HFMLIP
Type_B5_170M_M17500_TO_M17670 | 1 | 87 | T_B5_170M_M17500_TO_M17670 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M17500 to M17670=170M under HFMLIP
Type_B5_357M_M21733_TO_M22090 | 1 | 87 | T_B5_357M_M21733_TO_M22090 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M21733 to M22090=357M under HFMLIP
Type_B5_95M_M25625_TO_M25720 | 1 | 87 | T_B5_95M_M25625_TO_M25720 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M25625 to M25720=95M under HFMLIP
Type_B5_88M_M33100_TO_M33188 | 1 | 87 | T_B5_88M_M33100_TO_M33188 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M33100 to M33188=88M under HFMLIP
Type_B5_450M_M15600_TO_M16050 | 1 | 87 | T_B5_450M_M15600_TO_M16050 | Type B5 slope protection work of the Noapara Haor Submergible Embankment from M15600 to M16050=450M under HFMLIP
Type_B5_2035M_M3615_TO_M5650 | 1 | 87 | T_B5_2035M_M3615_TO_M5650 | Type B5 slope protection work of the Noapara Haor Submergible Embankment from M3615 to M5650=2035M under HFMLIP
Type_B5_350M_M13350_TO_M13700 | 1 | 87 | T_B5_350M_M13350_TO_M13700 | Type B5 slope protection work of the Nunnir Haor Submergible Embankment from M13350 to M13700=350M under HFMLIP

## Type_A_665M_M2950_TO_M3615
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 21 | 1 | Nos | 21058 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 21 | 1 | Nos | 55449 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 40 | 1 | Cum | 7388 | 16-240
6 | Placing Sand Filter | 17 | 4,5 | Cum | 918 | 40-550-10
7 | Placing Geotextile Filter | 17 | 4,5 | sqm | 10767 | 40-500-40
8 | Placing Pea Gravel Filter | 17 | 4,5 | Cum | 917 | 40-530-30
9 | Placing CC Block | 17 | 4,5 | Nos | 76507 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_B5_30M_M6900_TO_M6930
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 7 | 1 | Cum | 355 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 486 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 7 | 2 | Nos | 120 | 40-380-20
5 | Close Turfing | 7 | 2 | sqm | 414 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_210M_M8550_TO_M8760
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 2479 | 16-240
3 | Placing Geotextile Filter | 15 | 2 | sqm | 3400 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 15 | 2 | Nos | 840 | 40-380-20
5 | Close Turfing | 15 | 2 | percent | 2896 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_353M_M8822_TO_M9175
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 4166 | 16-240
3 | Placing Geotextile Filter | 15 | 2 | sqm | 5716 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 15 | 2 | Nos | 1412 | 40-380-20
5 | Close Turfing | 15 | 2 | percent | 4868 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_212M_M12440_TO_M12652
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 2502 | 16-240
3 | Placing Geotextile Filter | 15 | 2 | sqm | 3433 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 15 | 2 | Nos | 848 | 40-380-20
5 | Close Turfing | 15 | 2 | percent | 2924 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_30M_M13925_TO_M13955
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 355 | 16-240
3 | Placing Geotextile Filter | 3 | 2 | sqm | 486 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 3 | 2 | Nos | 120 | 40-380-20
5 | Close Turfing | 3 | 2 | percent | 414 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_170M_M17500_TO_M17670
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 2007 | 16-240
3 | Placing Geotextile Filter | 10 | 2 | sqm | 2753 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 10 | 2 | Nos | 680 | 40-380-20
5 | Close Turfing | 10 | 2 | percent | 2345 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_357M_M21733_TO_M22090
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 4214 | 16-240
3 | Placing Geotextile Filter | 15 | 2 | sqm | 5780 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 15 | 2 | Nos | 1428 | 40-380-20
5 | Close Turfing | 15 | 2 | sqm | 4924 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_95M_M25625_TO_M25720
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 1122 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 1539 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 7 | 2 | Nos | 380 | 40-380-20
5 | Close Turfing | 7 | 2 | percent | 1311 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_88M_M33100_TO_M33188
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 1039 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 1425 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 7 | 2 | Nos | 352 | 40-380-20
5 | Close Turfing | 7 | 2 | sqm | 1214 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_450M_M15600_TO_M16050
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 20 | 1 | Cum | 5311 | 16-240
3 | Placing Geotextile Filter | 17 | 2 | sqm | 7286 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 17 | 2 | Nos | 1800 | 40-380-20
5 | Close Turfing | 17 | 2 | sqm | 6206 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_2035M_M3615_TO_M5650
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 30 | 1 | Cum | 24016 | 16-240
3 | Placing Geotextile Filter | 30 | 2 | sqm | 32947 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 30 | 2 | Nos | 8140 | 40-380-20
5 | Close Turfing | 30 | 2 | percent | 28063 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_350M_M13350_TO_M13700
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 4131 | 16-240
3 | Placing Geotextile Filter | 15 | 2 | sqm | 5667 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 15 | 2 | Nos | 1400 | 40-380-20
5 | Close Turfing | 15 | 2 | sqm | 4827 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## Equipment Production Rate
CC Bock | L | B | H | Relative Size wrt 30X30X30 | Standard Production Rate | Block/machine |  | code
50X50X50 | 50 | 50 | 50 | 4.6296 | 750 | 162 | 0.0061728 | 40-190-15
50X50X30 | 50 | 50 | 30 | 2.7778 | 750 | 270 | 0.0037037 | 40-190-05
40X40X40 | 40 | 40 | 40 | 2.3704 | 750 | 317 | 0.0031546 | 40-190-35
40X40X20 | 40 | 40 | 20 | 1.1852 | 750 | 633 | 0.0015798 | 40-190-40
30X30X30 | 30 | 30 | 30 | 1 | 750 | 750 | 0.0013333 | 40-190-50
|  |  |  | Equipment |  | Daily Prod(8hrs)
|  |  |  | Excavator |  | 300
|  |  |  | Roller |  | 760 | 0.0013158
|  |  |  | Mixuture Machie |  | 17
CC Block Placing
Block Size | L | B | H | Realtive Area | Standard Prod/Day | Daily Production
50X50X30 | 50 | 50 | 30 | 1.5625 | 1400 | 896
50X50X20 | 50 | 50 | 30 | 1.5625 | 1400 | 896
40X40X40 | 40 | 40 | 40 | 1 | 1400 | 1400
40X40X20 | 40 | 40 | 20 | 1 | 1400 | 1400
30X30X30 | 30 | 30 | 30 | 0.5625 | 1400 | 2489
175 kg geobag |  |  |  | 245/day by group 20 incld bed prep

## Block Placing Production Rate
1 Group | 20 Labour
Dayliy Placing Including Bed Preparation for 40X40X20 CC Block | 1400 | Nos
unit area of block | 0.16 | sqm
Bed Area | 224 | sqm
Sand Filter 100mm thick | 22.4 | cum
Geo Textile Filter | 224 | sqm
Gravel Filter | 22.4 | cum

## Project_name
Name
Submersible Embankment Slope Protection Work at Kishoregonj PW-35