## 14-15 to 19-20
Item wise Physical & Financial Progress
Economic Code | Item | As per 1st RDPP |  |  |  | As per 2nd RDPP |  |  |  |  | Physical & Financial Progress from 01-07-2014 to 30-06-2015) |  |  |  |  | Cumulative Physical & Financial Progress (up to June, 2015) |  |  |  |  | Physical & Financial Progress from 01-07-2015 to 30-06-2016) |  |  |  |  | Cumulative Physical & Financial Progress (up to June, 2016) |  |  |  |  | Physical & Financial Progress from 01-07-2016 to 30-06-2017) |  |  |  |  | Cumulative Physical & Financial Progress (up to June, 2017) |  |  |  |  | Physical & Financial Progress from 01-07-2017 to 30-06-2018) |  |  |  |  | Cumulative Physical & Financial Progress (up to June, 2018) |  |  |  |  | Physical & Financial Progress from 01-07-2018 to 30-06-2019) |  |  |  |  | Cumulative Physical & Financial Progress (up to June, 2019) |  |  |  |  | Physical & Financial Progress from 01-07-2019 to 30-06-2020) |  |  |  |  | Cumulative Physical & Financial Progress (up to June, 2020)
|  | GOB (FE) | PA |  | Total | Physical | GOB (FE) | PA |  | Total | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial
|  |  | RPA | DPA |  |  |  | RPA | DPA |  |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total
(a) Revenue Component:
4700 | Salary & Allowance
4765 | Conveyance Allowance | 10 |  |  | 10 |  | 5 |  |  | 5 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.13 |  |  | 0.13 | L.S. | 0.43 |  |  | 0.43 | L.S. | 0.28 |  |  | 0.28 | L.S. | 0.71 |  |  | 0.71 | L.S. | 0.3 |  |  | 0.3 | L.S. | 1.01 |  |  | 1.01 | L.S. | 0.5 |  |  | 0.5 | L.S. | 1.51 |  |  | 1.51
4769 | Overtime Allowance | 10 |  |  | 10 |  | 10 |  |  | 10 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. |  |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. |  |  |  | 0 | L.S. | 0 |  |  | 0
4795 | Other Allowance | 140 |  |  | 140 |  | 140 |  |  | 140 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 25 |  |  | 25 | L.S. | 25 |  |  | 25 | L.S. | 11.61 |  |  | 11.61 | L.S. | 36.61 |  |  | 36.61 | L.S. | 14 |  |  | 14 | L.S. | 50.61 |  |  | 50.61
4700 | Supplies and Services
4801 | Travel Expenses (TA & DA for PMO & PIU) | 100 |  |  | 100 |  | 120 |  |  | 120 | L.S. | 0.99 |  |  | 0.99 | L.S. | 0.99 |  |  | 0.99 | L.S. | 11.92 |  |  | 11.92 | L.S. | 12.91 |  |  | 12.91 | L.S. | 14.98 |  |  | 14.98 | L.S. | 27.89 |  |  | 27.89 | L.S. | 17.96 |  |  | 17.96 | L.S. | 45.85 |  |  | 45.85 | L.S. | 12.7 |  |  | 12.7 | L.S. | 58.55 |  |  | 58.55 | L.S. | 14.98 |  |  | 14.98 | L.S. | 73.53 |  |  | 73.53
4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 |  |  | 245 |  | 245 |  |  | 245 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 16.25 |  |  | 16.25 | L.S. | 16.25 |  |  | 16.25 | L.S. | 31.35 |  |  | 31.35 | L.S. | 47.6 |  |  | 47.6 | L.S. | 34.86 |  |  | 34.86 | L.S. | 82.46 |  |  | 82.46 | L.S. | 34.21 |  |  | 34.21 | L.S. | 116.67 |  |  | 116.67 | L.S. | 34.21 |  |  | 34.21 | L.S. | 150.88 |  |  | 150.88
4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 |  |  | 2596.27 |  | 2874.35 |  |  | 2874.35 | L.S. | 223.75 |  |  | 223.75 | L.S. | 223.75 |  |  | 223.75 | L.S. | 464.64 |  |  | 464.64 | L.S. | 688.39 |  |  | 688.39 | L.S. | 327.7 |  |  | 327.7 | L.S. | 1016.09 |  |  | 1016.09 | L.S. | 337.33 |  |  | 337.33 | L.S. | 1353.42 |  |  | 1353.42 | L.S. | 249.75 |  |  | 249.75 | L.S. | 1603.17 |  |  | 1603.17 | L.S. | 177.18 |  |  | 177.18 | L.S. | 1780.35 |  |  | 1780.35
4815 | Postage | 25 |  |  | 25 |  | 5 |  |  | 5 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.13 |  |  | 0.13 | L.S. | 0.18 |  |  | 0.18 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.37 |  |  | 0.37 | L.S. | 0.77 |  |  | 0.77 | L.S. | 0.48 |  |  | 0.48 | L.S. | 1.25 |  |  | 1.25
4816 | Telephones/Telegram/Teleprinter | 25 |  |  | 25 |  | 5 |  |  | 5 | L.S. | 0.21 |  |  | 0.21 | L.S. | 0.21 |  |  | 0.21 | L.S. | 0.24 |  |  | 0.24 | L.S. | 0.45 |  |  | 0.45 | L.S. | 0.29 |  |  | 0.29 | L.S. | 0.74 |  |  | 0.74 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.89 |  |  | 0.89 | L.S. | 0.08 |  |  | 0.08 | L.S. | 0.97 |  |  | 0.97 | L.S. | 0.07 |  |  | 0.07 | L.S. | 1.04 |  |  | 1.04
4817 | Telex/Fax/Internet | 25 |  |  | 25 |  | 5 |  |  | 5 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0 |  |  | 0 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.09 |  |  | 0.09 | L.S. | 0.34 |  |  | 0.34 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.39 |  |  | 0.39 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.44 |  |  | 0.44 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.54 |  |  | 0.54
4818 | Registration Fee (Vehicles) | 15 |  |  | 15 |  | 20 |  |  | 20 | L.S. | 1.1 |  |  | 1.1 | L.S. | 1.1 |  |  | 1.1 | L.S. | 8.37 |  |  | 8.37 | L.S. | 9.47 |  |  | 9.47 | L.S. | 0.08 |  |  | 0.08 | L.S. | 9.55 |  |  | 9.55 | L.S. | 0 |  |  | 0 | L.S. | 9.55 |  |  | 9.55 | L.S. | 2.37 |  |  | 2.37 | L.S. | 11.92 |  |  | 11.92 | L.S. | 0.17 |  |  | 0.17 | L.S. | 12.09 |  |  | 12.09
4819 | Water | 10 |  |  | 10 |  | 5 |  |  | 5 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.12 |  |  | 0.12 | L.S. | 0.12 |  |  | 0.12 | L.S. | 0.23 |  |  | 0.23 | L.S. | 0.35 |  |  | 0.35 | L.S. | 0.37 |  |  | 0.37 | L.S. | 0.72 |  |  | 0.72 | L.S. | 0.4 |  |  | 0.4 | L.S. | 1.12 |  |  | 1.12 | L.S. | 0.55 |  |  | 0.55 | L.S. | 1.67 |  |  | 1.67
4821 | Electricity | 15 |  |  | 15 |  | 20 |  |  | 20 | L.S. | 0.19 |  |  | 0.19 | L.S. | 0.19 |  |  | 0.19 | L.S. | 1.67 |  |  | 1.67 | L.S. | 1.86 |  |  | 1.86 | L.S. | 1.78 |  |  | 1.78 | L.S. | 3.64 |  |  | 3.64 | L.S. | 2.31 |  |  | 2.31 | L.S. | 5.95 |  |  | 5.95 | L.S. | 2.78 |  |  | 2.78 | L.S. | 8.73 |  |  | 8.73 | L.S. | 2.89 |  |  | 2.89 | L.S. | 11.62 |  |  | 11.62
4822 | Gas & Fuel | 200 |  |  | 200 |  | 40 |  |  | 40 | L.S. | 0.94 |  |  | 0.94 | L.S. | 0.94 |  |  | 0.94 | L.S. | 3.7 |  |  | 3.7 | L.S. | 4.64 |  |  | 4.64 | L.S. | 3 |  |  | 3 | L.S. | 7.64 |  |  | 7.64 | L.S. | 4 |  |  | 4 | L.S. | 11.64 |  |  | 11.64 | L.S. | 5.89 |  |  | 5.89 | L.S. | 17.53 |  |  | 17.53 | L.S. | 4.02 |  |  | 4.02 | L.S. | 21.55 |  |  | 21.55
4823 | Petrol and Lubricant | 150 |  |  | 150 |  | 170 |  |  | 170 | L.S. | 0.62 |  |  | 0.62 | L.S. | 0.62 |  |  | 0.62 | L.S. | 6.99 |  |  | 6.99 | L.S. | 7.61 |  |  | 7.61 | L.S. | 18.97 |  |  | 18.97 | L.S. | 26.58 |  |  | 26.58 | L.S. | 18 |  |  | 18 | L.S. | 44.58 |  |  | 44.58 | L.S. | 20 |  |  | 20 | L.S. | 64.58 |  |  | 64.58 | L.S. | 24.18 |  |  | 24.18 | L.S. | 88.76 |  |  | 88.76
4824 | Insurance/Bank Charges (including Vehicles) | 3 |  |  | 3 |  | 3 |  |  | 3 | L.S. | 0.08 |  |  | 0.08 | L.S. | 0.08 |  |  | 0.08 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.83 |  |  | 0.83 | L.S. | 0 |  |  | 0 | L.S. | 0.83 |  |  | 0.83 | L.S. | 0.22 |  |  | 0.22 | L.S. | 1.05 |  |  | 1.05 | L.S. | 0.1 |  |  | 0.1 | L.S. | 1.15 |  |  | 1.15 | L.S. | 0.91 |  |  | 0.91 | L.S. | 2.06 |  |  | 2.06
4827 | Printing & Binding | 35 |  |  | 35 |  | 50 |  |  | 50 | L.S. | 0.2 |  |  | 0.2 | L.S. | 0.2 |  |  | 0.2 | L.S. | 6.99 |  |  | 6.99 | L.S. | 7.19 |  |  | 7.19 | L.S. | 16.99 |  |  | 16.99 | L.S. | 24.18 |  |  | 24.18 | L.S. | 6 |  |  | 6 | L.S. | 30.18 |  |  | 30.18 | L.S. | 3.98 |  |  | 3.98 | L.S. | 34.16 |  |  | 34.16 | L.S. | 0.5 |  |  | 0.5 | L.S. | 34.66 |  |  | 34.66
4828 | Stationery, Seals & Stamps | 150 |  |  | 150 |  | 120 |  |  | 120 | L.S. | 0.97 |  |  | 0.97 | L.S. | 0.97 |  |  | 0.97 | L.S. | 6.97 |  |  | 6.97 | L.S. | 7.94 |  |  | 7.94 | L.S. | 12 |  |  | 12 | L.S. | 19.94 |  |  | 19.94 | L.S. | 11.99 |  |  | 11.99 | L.S. | 31.93 |  |  | 31.93 | L.S. | 17.98 |  |  | 17.98 | L.S. | 49.91 |  |  | 49.91 | L.S. | 19.95 |  |  | 19.95 | L.S. | 69.86 |  |  | 69.86
4831 | Books & Periodicals | 2 |  |  | 2 |  | 2 |  |  | 2 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.03 |  |  | 0.03 | L.S. | 0.13 |  |  | 0.13 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.18 |  |  | 0.18 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.28 |  |  | 0.28 | L.S. | 0.2 |  |  | 0.2 | L.S. | 0.48 |  |  | 0.48
4840 | Training Expenditure | [15 empty] | 0
| Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 238.54 |  | 238.54 |  | 0 | 100 |  | 100 | [6 empty] | 0 | [8 empty] | L.S. |  |  |  | 0 | [5 empty] | L.S. |  |  |  | 0 | [5 empty] | L.S. | [9 empty] | L.S. | [9 empty] | L.S.
| Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 47.81 | 350.6 |  | 398.41 |  | 64.4 | 472.3 |  | 536.7 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 9.22 |  | 9.22 | L.S. | 0 | 9.22 |  | 9.22 | L.S. | 0 | 29.86 |  | 29.86 | L.S. | 0 | 39.08 |  | 39.08 | L.S. | 6.8 | 79.75 |  | 86.55 | L.S. | 6.8 | 118.83 |  | 125.63 | L.S. | 15.74 | 160.13 |  | 175.87 | L.S. | 22.54 | 278.96 |  | 301.5 | L.S. | 2.71 | 19.5 |  | 22.21 | L.S. | 25.25 | 298.46 |  | 323.71
| Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 304 | 2229.34 |  | 2533.34 |  | 354.92 | 2602.71 |  | 2957.63 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 199.49 |  | 199.49 | L.S. | 0 | 199.49 |  | 199.49 | L.S. | 24.64 | 500.25 |  | 524.89 | L.S. | 24.64 | 699.74 |  | 724.38 | L.S. | 55.7 | 566.55 |  | 622.25 | L.S. | 80.34 | 1266.29 |  | 1346.63 | L.S. | 34.46 | 303.65 |  | 338.11 | L.S. | 114.8 | 1569.94 |  | 1684.74
| Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 158.6 | 1163.08 |  | 1321.68 |  | 125.23 | 918.38 |  | 1043.61 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 119.7 |  | 119.7 | L.S. | 0 | 119.7 |  | 119.7 | L.S. | 14.5 | 209.79 |  | 224.29 | L.S. | 14.5 | 329.49 |  | 343.99 | L.S. | 20.97 | 213.24 |  | 234.21 | L.S. | 35.47 | 542.73 |  | 578.2 | L.S. | 7.97 | 75.01 |  | 82.98 | L.S. | 43.44 | 617.74 |  | 661.18
4851 | Casual labour/Job worker | 15 |  |  | 15 |  | 22 |  |  | 22 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.25 |  |  | 0.25 | L.S. | 2.11 |  |  | 2.11 | L.S. | 2.36 |  |  | 2.36 | L.S. | 2.35 |  |  | 2.35 | L.S. | 4.71 |  |  | 4.71 | L.S. | 2 |  |  | 2 | L.S. | 6.71 |  |  | 6.71 | L.S. | 4.25 |  |  | 4.25 | L.S. | 10.96 |  |  | 10.96 | L.S. | 3.49 |  |  | 3.49 | L.S. | 14.45 |  |  | 14.45
4854 | Consumable Stores | 25 |  |  | 25 |  | 15 |  |  | 15 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.99 |  |  | 0.99 | L.S. | 0.99 |  |  | 0.99 | L.S. | 0.75 |  |  | 0.75 | L.S. | 1.74 |  |  | 1.74 | L.S. | 1 |  |  | 1 | L.S. | 2.74 |  |  | 2.74 | L.S. | 1 |  |  | 1 | L.S. | 3.74 |  |  | 3.74 | L.S. | 3 |  |  | 3 | L.S. | 6.74 |  |  | 6.74
4874 | Consultancy : International - 71 M/M National - 324 M/M |  |  | 7901.4 | 7901.4 |  | 0 |  | 7901.4 | 7901.4 | L.S. |  |  | 849.67 | 849.67 | L.S. |  |  | 849.67 | 849.67 | L.S. |  |  | 1849.43 | 1849.43 | L.S. |  |  | 2699.1 | 2699.1 | L.S. |  |  | 1093.15 | 1093.15 | L.S. |  |  | 3792.25 | 3792.25 | L.S. |  |  | 689.33 | 689.33 | L.S. |  |  | 4481.58 | 4481.58 | L.S. |  |  | 686.43 | 686.43 | L.S. |  |  | 5168.01 | 5168.01 | L.S. |  |  | 450 | 450 | L.S. |  |  | 5618.01 | 5618.01
4883 | a) Honorarium/Fees/Remuneration (for different Committee) | 25 |  |  | 25 |  | 30 |  |  | 30 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.4 |  |  | 0.4 | L.S. | 1.33 |  |  | 1.33 | L.S. | 1.73 |  |  | 1.73 | L.S. | 1.5 |  |  | 1.5 | L.S. | 3.23 |  |  | 3.23 | L.S. | 4.5 |  |  | 4.5 | L.S. | 7.73 |  |  | 7.73 | L.S. | 5 |  |  | 5 | L.S. | 12.73 |  |  | 12.73 | L.S. | 3 |  |  | 3 | L.S. | 15.73 |  |  | 15.73
| b) Interim Evaluation | 10 |  |  | 10 |  | 10 |  |  | 10 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.27 |  |  | 0.27 | L.S. | 0.27 |  |  | 0.27 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.52 |  |  | 0.52 | L.S. | 0.77 |  |  | 0.77 | L.S. | 1.29 |  |  | 1.29 | L.S. | 0.41 |  |  | 0.41 | L.S. | 1.7 |  |  | 1.7
| c) Progress Monitoring | 10 |  |  | 10 |  | 10 |  |  | 10 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.55 |  |  | 0.55 | L.S. | 0.75 |  |  | 0.75 | L.S. | 1.3 |  |  | 1.3 | L.S. | 0.41 |  |  | 0.41 | L.S. | 1.71 |  |  | 1.71
4886 | Survey | 162 |  |  | 162 |  | 162 |  |  | 162 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 7.62 |  |  | 7.62 | L.S. | 7.62 |  |  | 7.62 | L.S. | 17.47 |  |  | 17.47 | L.S. | 25.09 |  |  | 25.09 | L.S. | 30 |  |  | 30 | L.S. | 55.09 |  |  | 55.09 | L.S. | 29.93 |  |  | 29.93 | L.S. | 85.02 |  |  | 85.02 | L.S. | 30 |  |  | 30 | L.S. | 115.02 |  |  | 115.02
4888 | Computer Consumables | 50 |  |  | 50 |  | 60 |  |  | 60 | L.S. | 0.49 |  |  | 0.49 | L.S. | 0.49 |  |  | 0.49 | L.S. | 1.5 |  |  | 1.5 | L.S. | 1.99 |  |  | 1.99 | L.S. | 4.5 |  |  | 4.5 | L.S. | 6.49 |  |  | 6.49 | L.S. | 6.48 |  |  | 6.48 | L.S. | 12.97 |  |  | 12.97 | L.S. | 7.5 |  |  | 7.5 | L.S. | 20.47 |  |  | 20.47 | L.S. | 10 |  |  | 10 | L.S. | 30.47 |  |  | 30.47
4899 | Other Expenses: Salary of Manpower through Outsourcing | 1700 |  |  | 1700 |  | 1700 |  |  | 1700 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 84.31 |  |  | 84.31 | L.S. | 84.31 |  |  | 84.31 | L.S. | 227.96 |  |  | 227.96 | L.S. | 312.27 |  |  | 312.27 | L.S. | 263.24 |  |  | 263.24 | L.S. | 575.51 |  |  | 575.51 | L.S. | 299.93 |  |  | 299.93 | L.S. | 875.44 |  |  | 875.44 | L.S. | 299.96 |  |  | 299.96 | L.S. | 1175.4 |  |  | 1175.4
4900 | Repair, Maintenance & Rehabilitation
4901 | Motor Vehicles | 100 |  |  | 100 |  | 125 |  |  | 125 | L.S. | 0.98 |  |  | 0.98 | L.S. | 0.98 |  |  | 0.98 | L.S. | 5.97 |  |  | 5.97 | L.S. | 6.95 |  |  | 6.95 | L.S. | 12 |  |  | 12 | L.S. | 18.95 |  |  | 18.95 | L.S. | 21.99 |  |  | 21.99 | L.S. | 40.94 |  |  | 40.94 | L.S. | 20.46 |  |  | 20.46 | L.S. | 61.4 |  |  | 61.4 | L.S. | 14.97 |  |  | 14.97 | L.S. | 76.37 |  |  | 76.37
4906 | Furnitures & Fixtures | 15 |  |  | 15 |  | 10 |  |  | 10 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.49 |  |  | 0.49 | L.S. | 0.49 |  |  | 0.49 | L.S. | 0.74 |  |  | 0.74 | L.S. | 1.23 |  |  | 1.23 | L.S. | 0.98 |  |  | 0.98 | L.S. | 2.21 |  |  | 2.21 | L.S. | 0.99 |  |  | 0.99 | L.S. | 3.2 |  |  | 3.2 | L.S. | 1.11 |  |  | 1.11 | L.S. | 4.31 |  |  | 4.31
4911 | Computers & office equipments | 25 |  |  | 25 |  | 15 |  |  | 15 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.85 |  |  | 0.85 | L.S. | 1.35 |  |  | 1.35 | L.S. | 2 |  |  | 2 | L.S. | 3.35 |  |  | 3.35 | L.S. | 1.99 |  |  | 1.99 | L.S. | 5.34 |  |  | 5.34 | L.S. | 3 |  |  | 3 | L.S. | 8.34 |  |  | 8.34
4916 | Machineries & Equipments | 25 |  |  | 25 |  | 10 |  |  | 10 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.01 |  |  | 0.01 | L.S. | 0.23 |  |  | 0.23 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.73 |  |  | 0.73 | L.S. | 0.5 |  |  | 0.5 | L.S. | 1.23 |  |  | 1.23 | L.S. | 1.99 |  |  | 1.99 | L.S. | 3.22 |  |  | 3.22
4921 | Office Building : Repair & Maintenance | 20 |  |  | 20 |  | 25 |  |  | 25 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 9.98 |  |  | 9.98 | L.S. | 9.98 |  |  | 9.98 | L.S. | 10 |  |  | 10 | L.S. | 19.98 |  |  | 19.98 | L.S. |  |  |  | 0 | L.S. | 19.98 |  |  | 19.98
4923 | Residential Building : Repair & Maintenance | 20 |  |  | 20 |  | 40 |  |  | 40 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 8.95 |  |  | 8.95 | L.S. | 8.95 |  |  | 8.95 | L.S. | 5.58 |  |  | 5.58 | L.S. | 14.53 |  |  | 14.53 | L.S. | 4.95 |  |  | 4.95 | L.S. | 19.48 |  |  | 19.48
4932 | Engineering Equipments | 25 |  |  | 25 |  | 20 |  |  | 20 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.09 |  |  | 0.09 | L.S. | 0.09 |  |  | 0.09 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.39 |  |  | 0.39 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.89 |  |  | 0.89 | L.S. | 0.5 |  |  | 0.5 | L.S. | 1.39 |  |  | 1.39 | L.S. | 2 |  |  | 2 | L.S. | 3.39 |  |  | 3.39
4947 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 43.5 | 319 |  | 362.5 |  | 56.5936 | 347.6464 |  | 404.24 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 0 | 0 |  | 0 | L.S. | 7.16 | 52.54 |  | 59.7 | L.S. | 7.16 | 52.54 |  | 59.7 | L.S. | 2.68 | 21.67 |  | 24.35 | L.S. | 9.84 | 74.21 |  | 84.05 | L.S. | 0.99 | 10 |  | 10.99 | L.S. | 10.83 | 84.21 |  | 95.04 | L.S. | 3.71 | 29.46 |  | 33.17 | L.S. | 14.54 | 113.67 |  | 128.21
4976 | Water Transport : Repair of Speedboat(s) | 10 |  |  | 10 |  | 5 |  |  | 5 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0.9 |  |  | 0.9 | L.S. | 0.9 |  |  | 0.9 | L.S. | 0 |  |  | 0 | L.S. | 0.9 |  |  | 0.9 | L.S. | 0.75 |  |  | 0.75 | L.S. | 1.65 |  |  | 1.65 | L.S. | 0.74 |  |  | 0.74 | L.S. | 2.39 |  |  | 2.39 | L.S. | 0.38 |  |  | 0.38 | L.S. | 2.77 |  |  | 2.77
4991 | Others : Repair & Maintenance | 25 |  |  | 25 |  | 40 |  |  | 40 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 2.49 |  |  | 2.49 | L.S. | 2.49 |  |  | 2.49 | L.S. | 4.98 |  |  | 4.98 | L.S. | 7.47 |  |  | 7.47 | L.S. | 1.49 |  |  | 1.49 | L.S. | 8.96 |  |  | 8.96
| Sub-total : (a) Revenue Component: | 6572.18 | 4300.56 | 7901.4 | 18774.14 |  | 6739.4936 | 4441.0364 | 7901.4 | 19081.93 |  | 231.42 | 0 | 849.67 | 1081.09 |  | 231.42 | 0 | 849.67 | 1081.09 |  | 635.09 | 9.22 | 1849.43 | 2493.74 |  | 866.51 | 9.22 | 2699.1 | 3574.83 |  | 703.91 | 401.59 | 1093.15 | 2198.65 |  | 1570.42 | 410.81 | 3792.25 | 5773.48 |  | 863.27 | 811.46 | 689.33 | 2364.06 |  | 2433.69 | 1222.27 | 4481.58 | 8137.54 |  | 850.94 | 949.92 | 686.43 | 2487.29 |  | 3284.63 | 2172.19 | 5168.01 | 10624.83 |  | 723.9 | 427.62 | 450 | 1601.52 |  | 4008.53 | 2599.81 | 5618.01 | 12226.35
(b) Capital Component:
6800 | Acquisition of Assets:
6807 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 |  |  | 702.5 |  | 702.5 |  |  | 702.5 |  | 346.3 |  |  | 346.3 |  | 346.3 |  |  | 346.3 |  | 138.6 |  |  | 138.6 | 7 nos. | 484.9 |  |  | 484.9 |  | 0 |  |  | 0 | 7 nos. | 484.9 |  |  | 484.9 |  | 122 |  |  | 122 | 7 nos. | 606.9 |  |  | 606.9 | 1 no. |  |  |  | 0 | 7 nos. | 606.9 |  |  | 606.9 | 1 no. |  |  |  | 0 | 7 nos. | 606.9 |  |  | 606.9
| Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 68.25 |  |  | 68.25 |  | 68.25 |  |  | 68.25 |  | 5.83 |  |  | 5.83 |  | 5.83 |  |  | 5.83 |  | 26.31 |  |  | 26.31 | 30 nos. | 32.14 |  |  | 32.14 |  | 10.08 |  |  | 10.08 | 30 nos. | 42.22 |  |  | 42.22 | 3 nos. | 8 |  |  | 8 | 33 nos. | 50.22 |  |  | 50.22 |  |  |  |  | 0 | 33 nos. | 50.22 |  |  | 50.22 |  |  |  |  | 0 | 33 nos. | 50.22 |  |  | 50.22
6809 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 100 |  |  | 100 |  | 90 |  |  | 90 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 3 nos. | 0 |  |  | 0 |  | 40.29 |  |  | 40.29 | 3 nos. | 40.29 |  |  | 40.29 | 1 no. | 21 |  |  | 21 | 4 nos. | 61.29 |  |  | 61.29 |  |  |  |  | 0 | 4 nos. | 61.29 |  |  | 61.29 |  |  |  |  | 0 | 4 nos. | 61.29 |  |  | 61.29
6813 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 |  |  | 8.97 |  | 8.97 |  |  | 8.97 |  | 3.73 |  |  | 3.73 |  | 3.73 |  |  | 3.73 |  | 2.74 |  |  | 2.74 | 7 nos. | 6.47 |  |  | 6.47 |  | 2.48 |  |  | 2.48 | 7 nos. | 8.95 |  |  | 8.95 |  | 0 |  |  | 0 | 7 nos. | 8.95 |  |  | 8.95 |  |  |  |  | 0 | 7 nos. | 8.95 |  |  | 8.95 |  |  |  |  | 0 | 7 nos. | 8.95 |  |  | 8.95
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 5 |  |  | 5 |  | 1 |  |  | 1 |  | 0.79 |  |  | 0.79 |  | 0.79 |  |  | 0.79 |  | 0 |  |  | 0 | 2 nos. | 0.79 |  |  | 0.79 |  | 0 |  |  | 0 | 2 nos. | 0.79 |  |  | 0.79 |  | 0 |  |  | 0 | 2 nos. | 0.79 |  |  | 0.79 |  |  |  |  | 0 | 2 nos. | 0.79 |  |  | 0.79 |  |  |  |  | 0 | 2 nos. | 0.79 |  |  | 0.79
6814 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 |  |  | 20.5 |  | 20.5 |  |  | 20.5 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 5.55 |  |  | 5.55 | 11 nos. | 5.55 |  |  | 5.55 |  | 11.15 |  |  | 11.15 | 11 nos. | 16.7 |  |  | 16.7 |  | 3.48 |  |  | 3.48 | 11 nos. | 20.18 |  |  | 20.18 |  |  |  |  | 0 | 11 nos. | 20.18 |  |  | 20.18 |  |  |  |  | 0 | 11 nos. | 20.18 |  |  | 20.18
| Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 |  |  | 6 |  | 3 |  |  | 3 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 1 no. | 2.13 |  |  | 2.13 | 1 no. | 2.13 |  |  | 2.13 |  |  |  |  | 0 | 1 no. | 2.13 |  |  | 2.13 |  |  |  |  | 0 | 1 no. | 2.13 |  |  | 2.13
| Engineering Laboratory Equipments for Kishoregonj WD Division | 50 |  |  | 50 |  | 50 |  |  | 50 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | L.S. | 7.89 |  |  | 7.89 | L.S. | 7.89 |  |  | 7.89 | L.S. | 1.6 |  |  | 1.6 | L.S. | 9.49 |  |  | 9.49 | L.S. | 5 |  |  | 5 | L.S. | 14.49 |  |  | 14.49
6815 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.5 |  |  | 19.5 |  | 22.5 |  |  | 22.5 |  | 3.88 |  |  | 3.88 |  | 3.88 |  |  | 3.88 |  | 7.34 |  |  | 7.34 | 27 nos. | 11.22 |  |  | 11.22 |  | 6.17 |  |  | 6.17 | 27 nos. | 17.39 |  |  | 17.39 | 3 no. | 2.08 |  |  | 2.08 | 30 nos. | 19.47 |  |  | 19.47 |  |  |  |  | 0 | 30 nos. | 19.47 |  |  | 19.47 |  |  |  |  | 0 | 30 nos. | 19.47 |  |  | 19.47
| Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 |  |  | 13.75 |  | 13.75 |  |  | 13.75 |  | 3.74 |  |  | 3.74 |  | 3.74 |  |  | 3.74 |  | 0 |  |  | 0 | 7 nos. | 3.74 |  |  | 3.74 |  | 2.98 |  |  | 2.98 | 7 nos. | 6.72 |  |  | 6.72 | 4 no. | 3.15 |  |  | 3.15 | 11 nos. | 9.87 |  |  | 9.87 |  |  |  |  | 0 | 11 nos. | 9.87 |  |  | 9.87 |  |  |  |  | 0 | 11 nos. | 9.87 |  |  | 9.87
| A3 Combo Printer 2 no ( PMO) | 1.5 |  |  | 1.5 |  | 1.5 |  |  | 1.5 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0.2 |  |  | 0.2 | 1 no. | 0.2 |  |  | 0.2 |  |  |  |  | 0 | 1 no. | 0.2 |  |  | 0.2 |  |  |  |  | 0 | 1 no. | 0.2 |  |  | 0.2 |  |  |  |  | 0 | 1 no. | 0.2 |  |  | 0.2 |  |  |  |  | 0 | 1 no. | 0.2 |  |  | 0.2
| Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 |  |  | 5.25 |  | 5.25 |  |  | 5.25 |  | 2.97 |  |  | 2.97 |  | 2.97 |  |  | 2.97 |  | 0 |  |  | 0 | 7 nos. | 2.97 |  |  | 2.97 |  | 0 |  |  | 0 | 7 nos. | 2.97 |  |  | 2.97 | 4 no. | 1.1 |  |  | 1.1 | 11 nos. | 4.07 |  |  | 4.07 |  |  |  |  | 0 | 11 nos. | 4.07 |  |  | 4.07 |  |  |  |  | 0 | 11 nos. | 4.07 |  |  | 4.07
6821 | Furnitures & Fixtures | 50 |  |  | 50 |  | 50 |  |  | 50 | L.S. | 7.96 |  |  | 7.96 | L.S. | 7.96 |  |  | 7.96 | L.S. | 8.45 |  |  | 8.45 | L.S. | 16.41 |  |  | 16.41 | L.S. | 8.99 |  |  | 8.99 | L.S. | 25.4 |  |  | 25.4 | L.S. | 9.96 |  |  | 9.96 | L.S. | 35.36 |  |  | 35.36 | L.S. | 9.97 |  |  | 9.97 | L.S. | 45.33 |  |  | 45.33 | L.S. |  |  |  | 0 | L.S. | 45.33 |  |  | 45.33
6869 | Aircooler | 15 |  |  | 15 |  | 15 |  |  | 15 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | 4 nos. | 0 |  |  | 0 | L.S. | 3.77 |  |  | 3.77 | 4 nos. | 3.77 |  |  | 3.77 | L.S. | 2 |  |  | 2 | 4 nos. | 5.77 |  |  | 5.77 | L.S. | 3.96 |  |  | 3.96 | 4 nos. | 9.73 |  |  | 9.73 | L.S. | 2.99 |  |  | 2.99 | 4 nos. | 12.72 |  |  | 12.72
6900 | Acquisition/Purchase of lands and landed properties of Assets: | [15 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0
6901 | Land Acquisition ( 408 hectare) | 24000 |  |  | 24000 |  | 20000 |  |  | 20000 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 4649.65 |  |  | 4649.65 | L.S. | 4649.65 |  |  | 4649.65 | L.S. | 5794.05 |  |  | 5794.05 | L.S. | 10443.7 |  |  | 10443.7 | L.S. | 3879.9 |  |  | 3879.9 | L.S. | 14323.6 |  |  | 14323.6 | L.S. | 1000 |  |  | 1000 | L.S. | 15323.6 |  |  | 15323.6
7000 | Construction and Works:
7036 | Irrigation Infrastructures :
7036 | Construction of Irrigation Inlet (New Haors) | 151.32 | 1109.68 |  | 1261 |  | 169.3356 | 1040.2 |  | 1209.5356 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 12 nos. (Part) | 16.34 | 100.38 |  | 116.72 |  | 16.34 | 100.38 |  | 116.72 | 12 nos. (Part) | 24.03 | 168.19 |  | 192.22 |  | 40.37 | 268.57 |  | 308.94
7041 | Drainage Structures : | [28 empty] | 0 | [9 empty] | 0
7041 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 181.8 | 1333.2 |  | 1515 |  | 164.57 | 1010.93 |  | 1175.5 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 1 no. (Part) | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 1 no. (Part) |  |  |  | 0 |  | 0 | 0 |  | 0
7041 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 2437.32 | 17873.68 |  | 20311 |  | 2603.3686 | 15992.12 |  | 18595.4886 | 7 nos. (Part) | 0 | 0 |  | 0 | 7 nos. (Part) | 0 | 0 |  | 0 | 7 nos. (Part) | 0 | 0 |  | 0 | 5 nos. (Part) | 0 | 0 |  | 0 | 7 nos. (Part) | 38.11 | 255.04 |  | 293.15 | 5 nos. (Part) | 38.11 | 255.04 |  | 293.15 | 7 nos. (Part) | 411.86 | 2362.04 |  | 2773.9 | 15 nos. (Part) | 449.97 | 2617.08 |  | 3067.05 | 7 nos. (Part) | 439.52 | 2637.09 |  | 3076.61 | 15 nos. (Part) | 889.49 | 5254.17 |  | 6143.66 | 7 nos. (Part) | 512.09 | 3563.13 |  | 4075.22 | 15 nos. (Part) | 1401.58 | 8817.3 |  | 10218.88
7041 | Re-excavation of Khal/River (New Haors) | 1167.48 | 8561.52 |  | 9729 |  | 1427.1782 | 8766.95 |  | 10194.1282 | 112 Km. (Part) | 0 | 0 |  | 0 | 112 Km. (Part) | 0 | 0 |  | 0 | 112 Km. (Part) | 0 | 0 |  | 0 | 8 Km. | 0 | 0 |  | 0 | 112 Km. (Part) | 40.49 | 308.67 |  | 349.16 | 8 Km. | 40.49 | 308.67 |  | 349.16 | 112 Km. (Part) | 100 | 740 |  | 840 | 108 Km. (Part) | 140.49 | 1048.67 |  | 1189.16 | 112 Km. (Part) | 650.59 | 4171.73 |  | 4822.32 | 108 Km. (Part) | 791.08 | 5220.4 |  | 6011.48 | 112 Km. (Part) | 319.56 | 2347.62 |  | 2667.18 | 108 Km. (Part) | 1110.64 | 7568.02 |  | 8678.66
Others
7081 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 301.8 | 2213.2 |  | 2515 |  | 475.7116 | 2922.23 |  | 3397.9416 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 50 Km. (Part) | 64.36 | 390.68 |  | 455.04 |  | 64.36 | 390.68 |  | 455.04 | 50 Km. (Part) | 94.32 | 632.22 |  | 726.54 |  | 158.68 | 1022.9 |  | 1181.58
7081 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 306 | 2244 |  | 2550 |  | 284.9602 | 1750.47 |  | 2035.4302 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 5 Km. (Part) | 63.49 | 388.97 |  | 452.46 |  | 63.49 | 388.97 |  | 452.46 | 5 Km. (Part) | 35.79 | 217.86 |  | 253.65 |  | 99.28 | 606.83 |  | 706.11
7081 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 214.2 | 1570.8 |  | 1785 |  | 244.6934 | 1503.12 |  | 1747.8134 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 15 Km. (Part) | 48.84 | 293.01 |  | 341.85 |  | 48.84 | 293.01 |  | 341.85 | 15 Km. (Part) | 26.02 | 153.66 |  | 179.68 |  | 74.86 | 446.67 |  | 521.53
7081 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 1434.3 | 10518.2 |  | 11952.5 |  | 6786.8482 | 12882.86 |  | 19669.7082 | 90 Km. (Part) | 0 | 0 |  | 0 | 90 Km. (Part) | 0 | 0 |  | 0 | 90 Km. (Part) | 0 | 0 |  | 0 | 10 Km. | 0 | 0 |  | 0 | 90 Km. (Part) | 40.42 | 296.48 |  | 336.9 | 10 Km. | 40.42 | 296.48 |  | 336.9 | 90 Km. (Part) | 470 | 3440 |  | 3910 | 90 Km. (Part) | 510.42 | 3736.48 |  | 4246.9 | 90 Km. (Part) | 268.59 | 1611.56 |  | 1880.15 | 90 Km. (Part) | 779.01 | 5348.04 |  | 6127.05 | 90 Km. (Part) | 365.45 | 2558.16 |  | 2923.61 | 90 Km. (Part) | 1144.46 | 7906.2 |  | 9050.66
7081 | Rehabilitation of Regulator (New Haors) | 19.92 | 146.08 |  | 166 |  | 22.5106 | 138.28 |  | 160.7906 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 3 nos. (Part) | 9.77 | 63.49 |  | 73.26 |  | 9.77 | 63.49 |  | 73.26 | 3 nos. (Part) | 0 | 0 |  | 0 |  | 9.77 | 63.49 |  | 73.26
| Threshing Floor Construction | [5 empty] | 31.5 | 193.5 |  | 225
7081 | Construction of WMG Office | 165.6 | 1214.4 |  | 1380 |  | 147 | 903 |  | 1050 | [6 empty] | 0 | 0 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 5 nos. (Part) | 5.47 | 36.62 |  | 42.09 |  | 5.47 | 36.62 |  | 42.09 | 5 nos. (Part) | 11.67 | 81.66 |  | 93.33 |  | 17.14 | 118.28 |  | 135.42
7081 | O & M during Construction | 200 |  |  | 200 |  | 100 | 0 |  | 100 | [6 empty] | 0 | [9 empty] | 0 |  |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | 0 | [9 empty] | 0 |  |  | 0 | [6 empty] | 0 |  |  | 0
| Sub-total : (b) Capital Component: | 31645.96 | 46784.76 | 0 | 78430.72 |  | 33509.8964 | 47103.66 | 0 | 80613.5564 |  | 375.2 | 0 | 0 | 375.2 |  | 375.2 | 0 | 0 | 375.2 |  | 189.19 | 0 | 0 | 189.19 |  | 564.39 | 0 | 0 | 564.39 |  | 4854.58 | 860.19 | 0 | 5714.77 |  | 5418.97 | 860.19 | 0 | 6279.16 |  | 6958.7 | 6542.04 | 0 | 13500.74 |  | 12377.67 | 7402.23 | 0 | 19779.9 |  | 5462.4 | 9693.53 | 0 | 15155.93 |  | 17840.07 | 17095.76 | 0 | 34935.83 |  | 2396.92 | 9722.5 | 0 | 12119.42 |  | 20236.99 | 26818.26 | 0 | 47055.25
| Total Cost (a+b) : | 38218.14 | 51085.32 | 7901.4 | 97204.86 |  | 33549.8964 | 51544.6964 | 7901.4 | 99695.4864 |  | 606.62 | 0 | 849.67 | 1456.29 |  | 606.62 | 0 | 849.67 | 1456.29 |  | 824.28 | 9.22 | 1849.43 | 2682.93 |  | 1430.9 | 9.22 | 2699.1 | 4139.22 |  | 5558.49 | 1261.78 | 1093.15 | 7913.42 |  | 6989.39 | 1271 | 3792.25 | 12052.64 |  | 7821.97 | 7353.5 | 689.33 | 15864.8 |  | 14811.36 | 8624.5 | 4481.58 | 27917.44 |  | 6313.34 | 10643.45 | 686.43 | 17643.22 |  | 21124.7 | 19267.95 | 5168.01 | 45560.66 |  | 3120.82 | 10150.12 | 450 | 13720.94 |  | 24245.52 | 29418.07 | 5618.01 | 59281.6
| (c) Physical Contingency ( Lump sum): | 100 | 158 |  | 258 |  | 49.51 |  |  | 49.51
| (d) Price Contingency (Lump sum): | 100.76 | 301.38 |  | 402.14 |  | 10 |  |  | 10
| Grand Total : (a)+(b)+(c)+(d): | 38418.9 | 51544.7 | 7901.4 | 97865 |  | 33609.4064 | 51544.6964 | 7901.4 | 99754.9964 |  | 606.62 | 0 | 849.67 | 1456.29 |  | 606.62 | 0 | 849.67 | 1456.29 |  | 824.28 | 9.22 | 1849.43 | 2682.93 |  | 1430.9 | 9.22 | 2699.1 | 4139.22 |  | 5558.49 | 1261.78 | 1093.15 | 7913.42 |  | 6989.39 | 1271 | 3792.25 | 12052.64 |  | 7821.97 | 7353.5 | 689.33 | 15864.8 |  | 14811.36 | 8624.5 | 4481.58 | 27917.44 |  | 6313.34 | 10643.45 | 686.43 | 17643.22 |  | 21124.7 | 19267.95 | 5168.01 | 45560.66 |  | 3120.82 | 10150.12 | 450 | 13720.94 |  | 24245.52 | 29418.07 | 5618.01 | 59281.6
[52 empty] | 42.62% | 123.4% | 15.32% | 63.2% | [6 empty] | 14.77% | 52.68% | 8.707% | 30.12%
[12 empty] | 1.805% | 0% | 10.75% | 1.46% | [6 empty] | 2.453% | 0.01789% | 23.41% | 2.69% | [6 empty] | 916.3% | #DIV/0! | 128.7% | 543.4%
| Ph W | 6623.24 | 47103.76 |  | 53527 | Ph W | 12514.27 | 47451.3064 |  | 59865.5764 | Ph W | 0 | 0 |  | 0 | [5 empty] | Ph W | 0 | 0 |  | 0 | [5 empty] | Ph W | 126.18 | 912.73 |  | 1038.91 | [5 empty] | Ph W | 984.54 | 6563.71 |  | 7548.25 | [5 empty] | Ph W | 1567.96 | 9703.53 |  | 11271.49 | [5 empty] | Ph W | 1392.64 | 9751.96 |  | 11144.6 | Ph W | 349564.9328 | 26931.93 |  | 31003.25
| Train | 510.41 | 4440.94 |  | 4253.43 | Train | 544.55 | 4093.39 |  | 4537.94 | Train | 0 | 0 |  | 0 | [5 empty] | Train | 0 | 9.22 |  | 9.22 | [5 empty] | Train | 0 | 349.05 |  | 349.05 | [5 empty] | Train | 45.94 | 789.79 |  | 835.73 | [5 empty] | Train | 92.41 | 939.92 |  | 1032.33 | [5 empty] | Train | 45.14 | 398.16 |  | 443.3 | Train | 183.49 | 2486.14 |  | 2669.63

## 18-19
Item wise Physical & Financial Progress
Economic Code | Item | As per 1st RDPP |  |  |  | Cumulative Physical & Financial Progress (up to June, 2018) |  |  |  |  | Physical & Financial Target during 2019-20 as per ADP |  |  |  |  | Physical & Financial Target during 2018-19 as per RADP |  |  |  |  | Physical & Financial Progress from 01-07-2018 to 30-06-2019) |  |  |  |  | Cumulative Physical & Financial Progress up to current month (up to November, 2018) |  |  |  |  | IMED 05
|  | GOB (FE) | PA |  | Total | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Terget | Expend | RPA | DPA | Remainig GOB
|  |  | RPA | DPA |  |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total
(a) Revenue Component:
| Salary & Allowance | [29 empty] | 12.3 | 11.91
3111302 | Conveyance Allowance | 10 |  |  | 10 | L.S. | 0.71 | 0 | 0 | 0.71 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.3 |  |  | 0.3 | L.S. | 1.01 | 0 | 0 | 1.01 |  |  |  |  | 0
3111327 | Overtime Allowance | 10 |  |  | 10 | L.S. | 0 | 0 | 0 | 0 | L.S. |  |  |  | 0 | L.S. |  |  |  | 0 | L.S. |  |  |  | 0 | L.S. | 0 | 0 | 0 | 0
3111338 | Other Allowance | 140 |  |  | 140 | L.S. | 25 | 0 | 0 | 25 | L.S. | 14 |  |  | 14 | L.S. | 12 |  |  | 12 | L.S. | 11.61 |  |  | 11.61 | L.S. | 36.61 | 0 | 0 | 36.61 |  |  |  |  | 0.39
Supplies and Services
3241101 | Travel Expenses (TA & DA for PMO & PIU) | 100 |  |  | 100 | L.S. | 45.84 | 0 | 0 | 45.84 | L.S. | 18 |  |  | 18 | L.S. | 15 |  |  | 15 | L.S. | 12.7 |  |  | 12.7 | L.S. | 58.54 | 0 | 0 | 58.54 | 15 | 12.7 |  |  | 2.3
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 |  |  | 245 | L.S. | 82.46 | 0 | 0 | 82.46 | L.S. | 34.25 |  |  | 34.25 | L.S. | 34.25 |  |  | 34.25 | L.S. | 34.21 |  |  | 34.21 | L.S. | 116.67 | 0 | 0 | 116.67 | 34.25 | 34.21 |  |  | 0.04
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 |  |  | 2596.27 | L.S. | 1353.43 | 0 | 0 | 1353.43 | L.S. | 252.44 |  |  | 252.44 | L.S. | 255.57 |  |  | 255.57 | L.S. | 249.75 |  |  | 249.75 | L.S. | 1603.18 | 0 | 0 | 1603.18 | 255.57 | 249.75 |  |  | 5.82
3211119 | Postage | 25 |  |  | 25 | L.S. | 0.4 | 0 | 0 | 0.4 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.37 |  |  | 0.37 | L.S. | 0.77 | 0 | 0 | 0.77 | 0.65 | 0.5 |  |  | 0.03
3211120 | Telephones/Telegram/Teleprinter | 25 |  |  | 25 | L.S. | 0.89 | 0 | 0 | 0.89 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.08 |  |  | 0.08 | L.S. | 0.97 | 0 | 0 | 0.97 |  |  |  |  | 0.07
3211117 | Telex/Fax/Internet | 25 |  |  | 25 | L.S. | 0.39 | 0 | 0 | 0.39 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.44 | 0 | 0 | 0.44 |  |  |  |  | 0.05
3221104 | Registration Fee (Vehicles) | 15 |  |  | 15 | L.S. | 9.55 | 0 | 0 | 9.55 | L.S. | 5.45 |  |  | 5.45 | L.S. | 4 |  |  | 4 | L.S. | 2.37 |  |  | 2.37 | L.S. | 11.92 | 0 | 0 | 11.92 | 4 | 2.37 |  |  | 1.63
3211115 | Water | 10 |  |  | 10 | L.S. | 0.71 | 0 | 0 | 0.71 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.4 |  |  | 0.4 | L.S. | 1.11 | 0 | 0 | 1.11 | 3.6 | 3.18 |  |  | 0
3211113 | Electricity | 15 |  |  | 15 | L.S. | 5.96 | 0 | 0 | 5.96 | L.S. | 2.5 |  |  | 2.5 | L.S. | 3.2 |  |  | 3.2 | L.S. | 2.78 |  |  | 2.78 | L.S. | 8.74 | 0 | 0 | 8.74 |  |  |  |  | 0.42
3243102 | Gas & Fuel | 200 |  |  | 200 | L.S. | 11.63 | 0 | 0 | 11.63 | L.S. | 4 |  |  | 4 | L.S. | 6 |  |  | 6 | L.S. | 5.89 |  |  | 5.89 | L.S. | 17.52 | 0 | 0 | 17.52 | 26 | 25.89 |  |  | 0.11
3243101 | Petrol and Lubricant | 150 |  |  | 150 | L.S. | 44.59 | 0 | 0 | 44.59 | L.S. | 18 |  |  | 18 | L.S. | 20 |  |  | 20 | L.S. | 20 |  |  | 20 | L.S. | 64.59 | 0 | 0 | 64.59 |  |  |  |  | 0
3221108 | Insurance/Bank Charges (including Vehicles) | 3 |  |  | 3 | L.S. | 1.06 | 0 | 0 | 1.06 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.1 |  |  | 0.1 | L.S. | 1.16 | 0 | 0 | 1.16 | 0.15 | 0.1 |  |  | 0.05
3255102 | Printing & Binding | 35 |  |  | 35 | L.S. | 30.18 | 0 | 0 | 30.18 | L.S. | 4 |  |  | 4 | L.S. | 4 |  |  | 4 | L.S. | 3.98 |  |  | 3.98 | L.S. | 34.16 | 0 | 0 | 34.16 | 4 | 3.98 |  |  | 0.02
3255104 | Stationery, Seals & Stamps | 150 |  |  | 150 | L.S. | 31.93 | 0 | 0 | 31.93 | L.S. | 15 |  |  | 15 | L.S. | 18 |  |  | 18 | L.S. | 17.98 |  |  | 17.98 | L.S. | 49.91 | 0 | 0 | 49.91 | 18 | 17.98 |  |  | 0.02
3211127 | Books & Periodicals | 2 |  |  | 2 | L.S. | 0.18 | 0 | 0 | 0.18 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.28 | 0 | 0 | 0.28 | 0.1 | 0.1 |  |  | 0
3231201 | Training Expenditure
| Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 238.54 |  | 238.54 | L.S. |  |  |  | 0 | L.S. |  |  |  |  | L.S. | [9 empty] | L.S.
| Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 47.81 | 350.6 |  | 398.41 | L.S. | 6.8 | 118.83 | 0 | 125.63 | L.S. | 10.41 | 93.68 |  | 104.09 | L.S. | 21.84 | 160.18 |  | 182.02 | L.S. | 15.74 | 160.13 |  | 175.87 | L.S. | 22.54 | 278.96 | 0 | 301.5 | 1068.18 | 1032.33 | 939.92 |  | 6.1 | 181.9659 | 21.8359
| Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 304 | 2229.34 |  | 2533.34 | L.S. | 24.64 | 699.74 | 0 | 724.38 | L.S. | 59.38 | 534.47 |  | 593.85 | L.S. | 77.26 | 566.57 |  | 643.83 | L.S. | 55.7 | 566.55 |  | 622.25 | L.S. | 80.34 | 1266.29 | 0 | 1346.63 |  |  |  |  | 21.56 | 643.8068 | 77.2568
| Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 158.6 | 1163.08 |  | 1321.68 | L.S. | 14.5 | 329.49 | 0 | 343.99 | L.S. | 23.54 | 211.85 |  | 235.39 | L.S. | 29.08 | 213.25 |  | 242.33 | L.S. | 20.97 | 213.24 |  | 234.21 | L.S. | 35.47 | 542.73 | 0 | 578.2 |  |  |  |  | 8.11 | 242.3182 | 29.0782
3211109 | Casual labour/Job worker | 15 |  |  | 15 | L.S. | 6.71 | 0 | 0 | 6.71 | L.S. | 4 |  |  | 4 | L.S. | 4.25 |  |  | 4.25 | L.S. | 4.25 |  |  | 4.25 | L.S. | 10.96 | 0 | 0 | 10.96 | 4.25 | 4.25 |  |  | 0
3256103 | Consumable Stores | 25 |  |  | 25 | L.S. | 2.74 | 0 | 0 | 2.74 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. | 3.74 | 0 | 0 | 3.74 | 1 | 1 |  |  | 0
3257101 | Consultancy : International - 71 M/M National - 324 M/M |  |  | 7901.4 | 7901.4 | L.S. | 0 | 0 | 4481.58 | 4481.58 | L.S. |  |  | 500 | 500 | L.S. |  |  | 700 | 700 | L.S. |  |  | 686.43 | 686.43 | L.S. | 0 | 0 | 5168.01 | 5168.01 | 700 | 686.43 |  | 686.43
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 25 |  |  | 25 | L.S. | 7.73 | 0 | 0 | 7.73 | L.S. | 5 |  |  | 5 | L.S. | 5 |  |  | 5 | L.S. | 5 |  |  | 5 | L.S. | 12.73 | 0 | 0 | 12.73 | 7 | 6.52 |  |  | 0
| b) Interim Evaluation | 10 |  |  | 10 | L.S. | 0.52 | 0 | 0 | 0.52 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. | 0.77 |  |  | 0.77 | L.S. | 1.29 | 0 | 0 | 1.29 |  |  |  |  | 0.23
| c) Progress Monitoring | 10 |  |  | 10 | L.S. | 0.55 | 0 | 0 | 0.55 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. | 0.75 |  |  | 0.75 | L.S. | 1.3 | 0 | 0 | 1.3 |  |  |  |  | 0.25
3257104 | Survey | 162 |  |  | 162 | L.S. | 55.09 | 0 | 0 | 55.09 | L.S. | 30 |  |  | 30 | L.S. | 30 |  |  | 30 | L.S. | 29.93 |  |  | 29.93 | L.S. | 85.02 | 0 | 0 | 85.02 | 30 | 29.93 |  |  | 0.07
3255101 | Computer Consumables | 50 |  |  | 50 | L.S. | 12.97 | 0 | 0 | 12.97 | L.S. | 6.5 |  |  | 6.5 | L.S. | 7.5 |  |  | 7.5 | L.S. | 7.5 |  |  | 7.5 | L.S. | 20.47 | 0 | 0 | 20.47 | 7.5 | 7.5 |  |  | 0
3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 |  |  | 1700 | L.S. | 575.53 | 0 | 0 | 575.53 | L.S. | 300 |  |  | 300 | L.S. | 300 |  |  | 300 | L.S. | 299.93 |  |  | 299.93 | L.S. | 875.46 | 0 | 0 | 875.46 | 300 | 299.93 |  |  | 0.07
Repair, Maintenance & Rehabilitation
3258101 | Motor Vehicles | 100 |  |  | 100 | L.S. | 40.94 | 0 | 0 | 40.94 | L.S. | 20 |  |  | 20 | L.S. | 21 |  |  | 21 | L.S. | 20.46 |  |  | 20.46 | L.S. | 61.4 | 0 | 0 | 61.4 | 58.45 | 56.73 |  |  | 0.54
3258102 | Furnitures & Fixtures | 15 |  |  | 15 | L.S. | 2.21 | 0 | 0 | 2.21 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. | 0.99 |  |  | 0.99 | L.S. | 3.2 | 0 | 0 | 3.2 |  |  |  |  | 0.01
3258103 | Computers & office equipments | 25 |  |  | 25 | L.S. | 3.35 | 0 | 0 | 3.35 | L.S. | 2 |  |  | 2 | L.S. | 2 |  |  | 2 | L.S. | 1.99 |  |  | 1.99 | L.S. | 5.34 | 0 | 0 | 5.34 |  |  |  |  | 0.01
3258105 | Machineries & Equipments | 25 |  |  | 25 | L.S. | 0.72 | 0 | 0 | 0.72 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 1.22 | 0 | 0 | 1.22 |  |  |  |  | 0
3258107 | Office Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 9.98 | 0 | 0 | 9.98 | L.S. | 5 |  |  | 5 | L.S. | 10 |  |  | 10 | L.S. | 10 |  |  | 10 | L.S. | 19.98 | 0 | 0 | 19.98 |  |  |  |  | 0
3258106 | Residential Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 8.95 | 0 | 0 | 8.95 | L.S. | 5 |  |  | 5 | L.S. | 6 |  |  | 6 | L.S. | 5.58 |  |  | 5.58 | L.S. | 14.53 | 0 | 0 | 14.53 |  |  |  |  | 0.42
3258105 | Engineering Equipments | 25 |  |  | 25 | L.S. | 0.89 | 0 | 0 | 0.89 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 1.39 | 0 | 0 | 1.39 |  |  |  |  | 0
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 43.5 | 319 |  | 362.5 | L.S. | 9.84 | 74.2 | 0 | 84.04 | L.S. | 1.36 | 10 |  | 11.36 | L.S. | 1.7 | 10 |  | 11.7 | L.S. | 0.99 | 10 |  | 10.99 | L.S. | 10.83 | 84.2 | 0 | 95.03 |  |  | 10 |  | 0.71
3258128 | Water Transport : Repair of Speedboat(s) | 10 |  |  | 10 | L.S. | 1.65 | 0 | 0 | 1.65 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.74 |  |  | 0.74 | L.S. | 2.39 | 0 | 0 | 2.39 |  |  |  |  | 0.01
3258107 | Others : Repair & Maintenance | 25 |  |  | 25 | L.S. | 2.5 | 0 | 0 | 2.5 | L.S. | 3 |  |  | 3 | L.S. | 5 |  |  | 5 | L.S. | 4.98 |  |  | 4.98 | L.S. | 7.48 | 0 | 0 | 7.48 |  |  |  |  | 0.02
| Sub-total : (a) Revenue Component: | 6572.18 | 4300.56 | 7901.4 | 18774.14 |  | 2433.72 | 1222.26 | 4481.58 | 8137.56 |  | 850 | 850 | 500 | 2200 |  | 900 | 950 | 700 | 2550 |  | 850.94 | 949.92 | 686.43 | 2487.29 |  | 3284.66 | 2172.18 | 5168.01 | 10624.85 | 2550 | 2487.29 | 949.92 | 686.43 | 49.06
(b) Capital Component:
Acquisition of Assets:
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 |  |  | 702.5 | 9 nos. | 606.9 | 0 | 0 | 606.9 | 1 no. | 95.6 |  |  | 95.6 | 1 no. | 95.6 |  |  | 95.6 | 1 no. |  |  |  | 0 | 7 nos. | 606.9 | 0 | 0 | 606.9 | 95.6 | 0
| Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 68.25 |  |  | 68.25 | 35 nos. | 50.22 | 0 | 0 | 50.22 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 33 nos. | 50.22 | 0 | 0 | 50.22
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 100 |  |  | 100 | 4 nos. | 61.29 | 0 | 0 | 61.29 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4 nos. | 61.29 | 0 | 0 | 61.29 | 0 | 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 |  |  | 8.97 | 7 nos. | 8.95 | 0 | 0 | 8.95 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 7 nos. | 8.95 | 0 | 0 | 8.95 | 0 | 0
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 5 |  |  | 5 | 2 nos. | 0.79 | 0 | 0 | 0.79 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2 nos. | 0.79 | 0 | 0 | 0.79
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 |  |  | 20.5 | 11 nos. | 20.18 | 0 | 0 | 20.18 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 20.18 | 0 | 0 | 20.18 | 2 | 1.6
| Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 |  |  | 6 | 1 no. | 2.13 | 0 | 0 | 2.13 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. | 2.13 | 0 | 0 | 2.13
| Engineering Laboratory Equipments for Kishoregonj WD Division | 50 |  |  | 50 | L.S. | 7.89 | 0 | 0 | 7.89 | L.S. | 2 |  |  | 2 | L.S. | 2 |  |  | 2 | L.S. | 1.6 |  |  | 1.6 | L.S. | 9.49 | 0 | 0 | 9.49
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.5 |  |  | 19.5 | 30 nos. | 19.47 | 0 | 0 | 19.47 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 30 nos. | 19.47 | 0 | 0 | 19.47 | 0 | 0
| Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 |  |  | 13.75 | 11 nos. | 9.88 | 0 | 0 | 9.88 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 9.88 | 0 | 0 | 9.88
| A3 Combo Printer 2 no ( PMO) | 1.5 |  |  | 1.5 | 1 no. | 0.2 | 0 | 0 | 0.2 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. | 0.2 | 0 | 0 | 0.2
| Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 |  |  | 5.25 | 11 nos. | 4.08 | 0 | 0 | 4.08 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 4.08 | 0 | 0 | 4.08
4112314 | Furnitures & Fixtures | 50 |  |  | 50 | L.S. | 35.35 | 0 | 0 | 35.35 | L.S. | 10 |  |  | 10 | L.S. | 10 |  |  | 10 | L.S. | 9.97 |  |  | 9.97 | L.S. | 45.32 | 0 | 0 | 45.32 | 14 | 13.93
4112303 | Aircooler | 15 |  |  | 15 | 4 nos. | 5.77 | 0 | 0 | 5.77 | 4 nos. | 4 |  |  | 4 | 4 nos. | 4 |  |  | 4 | L.S. | 3.96 |  |  | 3.96 | 4 nos. | 9.73 | 0 | 0 | 9.73
Acquisition/Purchase of lands and landed properties of Assets:
4141101 | Land Acquisition ( 470 hectare) | 24000 |  |  | 24000 | L.S. | 10443.7 | 0 | 0 | 10443.7 | L.S. | 7852.4 |  |  | 7852.4 | L.S. | 3879.9 |  |  | 3879.9 | L.S. | 3879.9 |  |  | 3879.9 | L.S. | 14323.6 | 0 | 0 | 14323.6 | 3879.9 | 3879.9
Construction and Works:
4111306 | Irrigation Infrastructures : | [29 empty] | 12051.5 | 11260.5 | 9693.53
4111306 | Construction of Irrigation Inlet (New Haors) | 151.32 | 1109.68 |  | 1261 |  |  |  |  | 0 | 50 (F)+25 (P) nos. | 90 | 610 |  | 700 | 50 (F)+25 (P) nos. | 45 | 105 |  | 150 | 12 nos. (Part) | 16.34 | 100.38 |  | 116.72 | [10 empty] | 11260.51
4111307 | Drainage Structures : | [8 empty] | 0
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 181.8 | 1333.2 |  | 1515 |  |  |  |  | 0 | 5 nos. (Part) | 90 | 610 |  | 700 | 5 nos. (Part) | 75 | 450 |  | 525 | 1 no. (Part) | 0 | 0 |  | 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 2437.32 | 17873.68 |  | 20311 | 15 nos. (Part) | 449.97 | 2617.08 | 0 | 3067.05 | 20 (F)+40 (P) nos. | 600 | 4000 |  | 4600 | 20 (F)+40 (P) nos. | 422 | 2700 |  | 3122 | 7 nos. (Part) | 439.52 | 2637.09 |  | 3076.61 | 15 nos. (Part) | 889.49 | 5254.17 | 0 | 6143.66
4111307 | Re-excavation of Khal/River (New Haors) | 1167.48 | 8561.52 |  | 9729 | 108 Km. (Part) | 140.49 | 1048.67 | 0 | 1189.16 | 100 (F)+100 (P) Km. | 750 | 5000 |  | 5750 | 100 (F)+100 (P) Km. | 683.5 | 4205 |  | 4888.5 | 112 Km. (Part) | 650.59 | 4171.73 |  | 4822.32 | 108 Km. (Part) | 791.08 | 5220.4 | 0 | 6011.48
Others
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 301.8 | 2213.2 |  | 2515 |  |  |  |  | 0 | 50 (F)+60 (P) Km. | 100 | 700 |  | 800 | 50 (F)+60 (P) Km. | 65 | 400 |  | 465 | 50 Km. (Part) | 64.36 | 390.68 |  | 455.04
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 306 | 2244 |  | 2550 |  |  |  |  | 0 | 35 (F)+30 (P) Km. | 90 | 610 |  | 700 | 35 (F)+30 (P) Km. | 65 | 400 |  | 465 | 5 Km. (Part) | 63.49 | 388.97 |  | 452.46
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 214.2 | 1570.8 |  | 1785 |  |  |  |  | 0 | 25 (F)+25 (P) Km. | 75 | 525 |  | 600 | 25 (F)+25 (P) Km. | 50 | 300 |  | 350 | 15 Km. (Part) | 48.84 | 293.01 |  | 341.85
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 1434.3 | 10518.2 |  | 11952.5 | 90 Km. (Part) | 510.43 | 3736.48 | 0 | 4246.91 | 80 (F)+110 (P) Km. | 370 | 2455 |  | 2825 | 80 (F)+110 (P) Km. | 275 | 1650 |  | 1925 | 90 Km. (Part) | 268.59 | 1611.56 |  | 1880.15 | 90 Km. (Part) | 779.02 | 5348.04 | 0 | 6127.06
4111201 | Rehabilitation of Regulator (New Haors) | 19.92 | 146.08 |  | 166 |  |  |  |  | 0 | 3 (F)+2 (P) nos. | 10 | 65 |  | 75 | 3 (F)+2 (P) nos. | 10 | 65 |  | 75 | 3 nos. (Part) | 9.77 | 63.49 |  | 73.26
4111201 | Construction of WMG Office | 165.6 | 1214.4 |  | 1380 |  |  |  |  | 0 | 5 (F)+5 (P) nos. | 11 | 75 |  | 86 | 5 (F)+5 (P) nos. | 11 | 75 |  | 86 | 5 nos. (Part) | 5.47 | 36.62 |  | 42.09
4111201 | O & M during Construction | 200 |  |  | 200 |  |  |  |  | 0
| Sub-total : (b) Capital Component: | 31645.96 | 46784.76 | 0 | 78430.72 |  | 12377.69 | 7402.23 | 0 | 19779.92 |  | 10150 | 14650 | 0 | 24800 |  | 5693 | 10350 | 0 | 16043 |  | 5462.4 | 9693.53 | 0 | 15155.93 |  | 17840.09 | 17095.76 | 0 | 34935.85 | 16043 | 15155.93 | 9693.53 | 0
| Total Cost (a+b) : | 38218.14 | 51085.32 | 7901.4 | 97204.86 |  | 14811.41 | 8624.49 | 4481.58 | 27917.48 |  | 11000 | 15500 | 500 | 27000 |  | 6593 | 11300 | 700 | 18593 |  | 6313.34 | 10643.45 | 686.43 | 17643.22 |  | 21124.75 | 19267.94 | 5168.01 | 45560.7 | 18593 | 17643.22 | 10643.45 | 686.43
| (c) Physical Contingency ( Lump sum): | 100 | 158 |  | 258
| (d) Price Contingency (Lump sum): | 100.76 | 301.38 |  | 402.14 | [27 empty] | 11329.88
| Grand Total : (a)+(b)+(c)+(d): | 38418.9 | 51544.7 | 7901.4 | 97865 |  | 14811.41 | 8624.49 | 4481.58 | 27917.48 |  | 11000 | 15500 | 500 | 27000 |  | 6593 | 11300 | 700 | 18593 |  | 6313.34 | 10643.45 | 686.43 | 17643.22 |  | 21124.75 | 19267.94 | 5168.01 | 45560.7
[22 empty] | 95.76% | 94.19% | 98.06% | 94.89%
45560.7

## Sheet3
Code | Description | Budget_Gob | Budget_RPA | Budget_DPA | Budget_Total | Exp_Gob | Exp_RPA | Exp_DPA | Exp_Total
4111307 | Reg/CW/Bridge/Box outlet | 312200000 | 2700000 | 0 | 312200000 | 52677027.2 | 327000355.01 | 0 | 379677382.21
|  | 3122 | 27 | 0 | 3122 | 526.7703 | 3270.0036 | 0 | 3796.7738

## 19-20
Item wise Physical & Financial Progress
Economic Code | Item | As per 1st RDPP |  |  |  | Physical & Financial Revised Target during 2019-20 as per RADP(Rescheduled) |  |  |  |  | Physical & Financial Progress from 01-07-2019 to 30-06-2020 |  |  |  |  | Cumulative Physical & Financial Progress up to current month (up to November, 2018) |  |  |  |  | Physical & Financial Target during 2020-21 as per ADP |  |  |  |  | Physical & Financial Progress from 01-07-2019 to 30-04-2020 |  |  |  |  | IMED 05 |  |  |  |  | Physical & Financial Progress cumulative till date
|  | GOB (FE) | PA |  | Total | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Terget | Expend | RPA | DPA | Remainig GOB | Physical | Financial
|  |  | RPA | DPA |  |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total | [6 empty] | GOB | RPA | DPA | Total
(a) Revenue Component:
| Salary & Allowance | [29 empty] | 14.5 | 14.5
3111302 | Conveyance Allowance | 10 |  |  | 10 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.5 |  |  | 0.5 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
3111327 | Overtime Allowance | 10 |  |  | 10 | L.S. |  |  |  |  | L.S. |  |  |  | 0 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. |  |  |  |  | L.S. |  |  |  | 0 | [5 empty] | L.S. | #REF! |  |  | #REF!
3111338 | Other Allowance | 140 |  |  | 140 | L.S. | 14 |  |  | 14 | L.S. | 14 |  |  | 14 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 13 |  |  | 13 | L.S. | 14 |  |  | 14 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
Supplies and Services
3241101 | Travel Expenses (TA & DA for PMO & PIU) | 100 |  |  | 100 | L.S. | 15 |  |  | 15 | L.S. | 14.98 |  |  | 14.98 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 6 |  |  | 6 | L.S. | 14.98 |  |  | 14.98 | 15 | 14.98 |  |  | 0.02 | L.S. | #REF! |  |  | #REF!
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 |  |  | 245 | L.S. | 34.25 |  |  | 34.25 | L.S. | 34.21 |  |  | 34.21 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 34.25 |  |  | 34.25 | L.S. | 34.21 |  |  | 34.21 | 34.25 | 34.21 |  |  | 0.04 | L.S. | #REF! |  |  | #REF!
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 |  |  | 2596.27 | L.S. | 179.54 |  |  | 179.54 | L.S. | 177.18 |  |  | 177.18 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 140 |  |  | 140 | L.S. | 177.18 |  |  | 177.18 | 179.54 | 177.18 |  |  | 2.36 | L.S. | #REF! |  |  | #REF!
3211119 | Postage | 25 |  |  | 25 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.48 |  |  | 0.48 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.2 |  |  | 0.2 | L.S. | 0.48 |  |  | 0.48 | 0.7 | 0.65 |  |  | 0.02 | L.S. | #REF! |  |  | #REF!
3211120 | Telephones/Telegram/Teleprinter | 25 |  |  | 25 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.07 |  |  | 0.07 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.07 |  |  | 0.07 |  |  |  |  | 0.03 | L.S. | #REF! |  |  | #REF!
3211117 | Telex/Fax/Internet | 25 |  |  | 25 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.1 |  |  | 0.1 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.1 |  |  | 0.1 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
3221104 | Registration Fee (Vehicles) | 15 |  |  | 15 | L.S. | 1 |  |  | 1 | L.S. | 0.17 |  |  | 0.17 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.17 |  |  | 0.17 | 1 | 0.17 |  |  | 0.83 | L.S. | #REF! |  |  | #REF!
3211115 | Water | 10 |  |  | 10 | L.S. | 0.7 |  |  | 0.7 | L.S. | 0.55 |  |  | 0.55 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.55 |  |  | 0.55 | 4.7 | 3.44 |  |  | 0.15 | L.S. | #REF! |  |  | #REF!
3211113 | Electricity | 15 |  |  | 15 | L.S. | 4 |  |  | 4 | L.S. | 2.89 |  |  | 2.89 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 3 |  |  | 3 | L.S. | 2.89 |  |  | 2.89 |  |  |  |  | 1.11 | L.S. | #REF! |  |  | #REF!
3243102 | Gas & Fuel | 200 |  |  | 200 | L.S. | 6 |  |  | 6 | L.S. | 4.02 |  |  | 4.02 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 2 |  |  | 2 | L.S. | 4.02 |  |  | 4.02 | 31 | 28.2 |  |  | 1.98 | L.S. | #REF! |  |  | #REF!
3243101 | Petrol and Lubricant | 150 |  |  | 150 | L.S. | 25 |  |  | 25 | L.S. | 24.18 |  |  | 24.18 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 10 |  |  | 10 | L.S. | 24.18 |  |  | 24.18 |  |  |  |  | 0.82 | L.S. | #REF! |  |  | #REF!
3221108 | Insurance/Bank Charges (including Vehicles) | 3 |  |  | 3 | L.S. | 1 |  |  | 1 | L.S. | 0.91 |  |  | 0.91 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.91 |  |  | 0.91 | 1 | 0.91 |  |  | 0.09 | L.S. | #REF! |  |  | #REF!
3255102 | Printing & Binding | 35 |  |  | 35 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0 |  |  | 0 | L.S. | 0.5 |  |  | 0.5 | 0.5 | 0.5 |  |  | 0 | L.S. | #REF! |  |  | #REF!
3255104 | Stationery, Seals & Stamps | 150 |  |  | 150 | L.S. | 20 |  |  | 20 | L.S. | 19.95 |  |  | 19.95 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 7 |  |  | 7 | L.S. | 19.95 |  |  | 19.95 | 20 | 19.95 |  |  | 0.05 | L.S. | #REF! |  |  | #REF!
3211127 | Books & Periodicals | 2 |  |  | 2 | L.S. | 0.2 |  |  | 0.2 | L.S. | 0.2 |  |  | 0.2 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.2 |  |  | 0.2 | 0.2 | 0.2 |  |  | 0 | L.S. | #REF! |  |  | #REF!
3231201 | Training Expenditure | [35 empty] | #REF! | #REF!
| Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 238.54 |  | 238.54 | L.S. | [9 empty] | L.S. | [20 empty] | #REF! | #REF!
| Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 47.81 | 350.6 |  | 398.41 | L.S. | 10.52 | 125.15 |  | 135.67 | L.S. | 2.71 | 19.5 |  | 22.21 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 3 | 30 |  | 33 | L.S. | 2.71 | 19.5 |  | 22.21 | 810 | 443.3 | 398.16 |  | 7.81 | L.S. | #REF! | #REF! |  | #REF!
| Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 304 | 2229.34 |  | 2533.34 | L.S. | 36.28 | 504.59 |  | 540.87 | L.S. | 34.46 | 303.65 |  | 338.11 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 9 | 90 |  | 99 | L.S. | 34.46 | 303.65 |  | 338.11 |  |  |  |  | 1.82 | L.S. | #REF! | #REF! |  | #REF!
| Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 158.6 | 1163.08 |  | 1321.68 | L.S. | 13.2 | 120.26 |  | 133.46 | L.S. | 7.97 | 75.01 |  | 82.98 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 3 | 30 |  | 33 | L.S. | 7.97 | 75.01 |  | 82.98 |  |  |  |  | 5.23 | L.S. | #REF! | #REF! |  | #REF!
3211109 | Casual labour/Job worker | 15 |  |  | 15 | L.S. | 3.5 |  |  | 3.5 | L.S. | 3.49 |  |  | 3.49 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 1.5 |  |  | 1.5 | L.S. | 3.49 |  |  | 3.49 | 3.5 | 3.49 |  |  | 0.01 | L.S. | #REF! | #REF! | #REF! | #REF!
3256103 | Consumable Stores | 25 |  |  | 25 | L.S. | 3 |  |  | 3 | L.S. | 3 |  |  | 3 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 1 |  |  | 1 | L.S. | 3 |  |  | 3 | 3 | 3 |  |  | 0 | L.S. | #REF! | #REF! | #REF! | #REF!
3257101 | Consultancy : International - 71 M/M National - 324 M/M |  |  | 7901.4 | 7901.4 | L.S. |  |  | 700 | 700 | L.S. |  |  | 450 | 450 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. |  |  | 558 | 558 | L.S. |  |  | 450 | 450 | 700 | 450 |  | 450 |  | L.S. |  |  | #REF! | #REF!
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 25 |  |  | 25 | L.S. | 5.5 |  |  | 5.5 | L.S. | 3 |  |  | 3 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 3 |  |  | 3 | L.S. | 3 |  |  | 3 | 7 | 3.82 |  |  | 2.5 | L.S. | #REF! |  |  | #REF!
| b) Interim Evaluation | 10 |  |  | 10 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.41 |  |  | 0.41 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.41 |  |  | 0.41 |  |  |  |  | 0.34 | L.S. | #REF! |  |  | #REF!
| c) Progress Monitoring | 10 |  |  | 10 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.41 |  |  | 0.41 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.41 |  |  | 0.41 |  |  |  |  | 0.34 | L.S. | #REF! |  |  | #REF!
3257104 | Survey | 162 |  |  | 162 | L.S. | 30 |  |  | 30 | L.S. | 30 |  |  | 30 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 10 |  |  | 10 | L.S. | 30 |  |  | 30 | 30 | 30 |  |  | 0 | L.S. | #REF! |  |  | #REF!
3255101 | Computer Consumables | 50 |  |  | 50 | L.S. | 10 |  |  | 10 | L.S. | 10 |  |  | 10 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 5 |  |  | 5 | L.S. | 10 |  |  | 10 | 10 | 10 |  |  | 0 | L.S. | #REF! |  |  | #REF!
3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 |  |  | 1700 | L.S. | 250 |  |  | 250 | L.S. | 299.96 |  |  | 299.96 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 230 |  |  | 230 | L.S. | 299.96 |  |  | 299.96 | 250 | 299.96 |  |  | -49.96 | L.S. | #REF! |  |  | #REF!
Repair, Maintenance & Rehabilitation
3258101 | Motor Vehicles | 100 |  |  | 100 | L.S. | 15 |  |  | 15 | L.S. | 14.97 |  |  | 14.97 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 7 |  |  | 7 | L.S. | 14.97 |  |  | 14.97 | 84.11 | 63.06 |  |  | 0.03 | L.S. | #REF! |  |  | #REF!
3258102 | Furnitures & Fixtures | 15 |  |  | 15 | L.S. | 1.11 |  |  | 1.11 | L.S. | 1.11 |  |  | 1.11 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0 |  |  | 0 | L.S. | 1.11 |  |  | 1.11 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
3258103 | Computers & office equipments | 25 |  |  | 25 | L.S. | 3 |  |  | 3 | L.S. | 3 |  |  | 3 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 1.5 |  |  | 1.5 | L.S. | 3 |  |  | 3 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
3258105 | Machineries & Equipments | 25 |  |  | 25 | L.S. | 2 |  |  | 2 | L.S. | 1.99 |  |  | 1.99 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 1 |  |  | 1 | L.S. | 1.99 |  |  | 1.99 |  |  |  |  | 0.01 | L.S. | #REF! |  |  | #REF!
3258107 | Office Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 0 |  |  | 0 | L.S. |  |  |  | 0 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0 |  |  | 0 | L.S. |  |  |  | 0 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
3258106 | Residential Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 5 |  |  | 5 | L.S. | 4.95 |  |  | 4.95 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0 |  |  | 0 | L.S. | 4.95 |  |  | 4.95 |  |  |  |  | 0.05 | L.S. | #REF! |  |  | #REF!
3258105 | Engineering Equipments | 25 |  |  | 25 | L.S. | 2 |  |  | 2 | L.S. | 2 |  |  | 2 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0 |  |  | 0 | L.S. | 2 |  |  | 2 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 43.5 | 319 |  | 362.5 | L.S. | 4.12 | 50 |  | 54.12 | L.S. | 3.71 | 29.46 |  | 33.17 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 6.1 | 50 |  | 56.1 | L.S. | 3.71 | 29.46 |  | 33.17 |  |  | 29.46 |  | 0.41 | L.S. | #REF! | #REF! | #REF! | #REF!
3258128 | Water Transport : Repair of Speedboat(s) | 10 |  |  | 10 | L.S. | 0.38 |  |  | 0.38 | L.S. | 0.38 |  |  | 0.38 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 0 |  |  | 0 | L.S. | 0.38 |  |  | 0.38 |  |  |  |  | 0 | L.S. | #REF! |  |  | #REF!
3258107 | Others : Repair & Maintenance | 25 |  |  | 25 | L.S. | 1.5 |  |  | 1.5 | L.S. | 1.49 |  |  | 1.49 | L.S. | #REF! | #REF! | #REF! | #REF! | L.S. | 1 |  |  | 1 | L.S. | 1.49 |  |  | 1.49 |  |  |  |  | 0.01 | L.S. | #REF! |  |  | #REF!
| Sub-total : (a) Revenue Component: | 6572.18 | 4300.56 | 7901.4 | 18774.14 |  | 700 | 800 | 700 | 2200 |  | 723.9 | 427.62 | 450 | 1601.52 |  | #REF! | #REF! | #REF! | #REF! |  | 500 | 200 | 558 | 1258 |  | 723.9 | 427.62 | 450 | 1601.52 | 2200 | 1601.52 | 427.62 | 450 | -23.9 |  | #REF! | #REF! | #REF! | #REF!
(b) Capital Component:
Acquisition of Assets:
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 |  |  | 702.5 | 1 no. | 0 |  |  | 0 |  |  |  |  | 0 | 7 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  | 1 no. | #REF! |  |  | #REF!
| Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 68.25 |  |  | 68.25 |  |  |  |  | 0 |  |  |  |  | 0 | 33 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | #REF! |  |  | #REF!
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 100 |  |  | 100 |  |  |  |  | 0 |  |  |  |  | 0 | 4 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | #REF! |  |  | #REF!
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 |  |  | 8.97 |  |  |  |  | 0 |  |  |  |  | 0 | 7 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | #REF! |  |  | #REF!
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 5 |  |  | 5 |  |  |  |  | 0 |  |  |  |  | 0 | 2 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | #REF! |  |  | #REF!
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 |  |  | 20.5 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | 5 | 5 |  |  |  |  | #REF! |  |  | #REF!
| Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 |  |  | 6 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | #REF! |  |  | #REF!
| Engineering Laboratory Equipments for Kishoregonj WD Division | 50 |  |  | 50 | L.S. | 5 |  |  | 5 | L.S. | 5 |  |  | 5 | L.S. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 | L.S. | 5 |  |  | 5 | [5 empty] | L.S. | #REF! |  |  | #REF!
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.5 |  |  | 19.5 |  |  |  |  | 0 |  |  |  |  | 0 | 30 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | #REF! |  |  | #REF!
| Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 |  |  | 13.75 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | #REF! |  |  | #REF!
| A3 Combo Printer 2 no ( PMO) | 1.5 |  |  | 1.5 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | #REF! |  |  | #REF!
| Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 |  |  | 5.25 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | #REF! |  |  | #REF!
4112314 | Furnitures & Fixtures | 50 |  |  | 50 | L.S. | 0 |  |  | 0 | L.S. |  |  |  | 0 | L.S. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 | L.S. |  |  |  | 0 | 4 | 2.99 |  |  |  | L.S. | #REF! |  |  | #REF!
4112303 | Aircooler | 15 |  |  | 15 | 4 nos. | 4 |  |  | 4 | L.S. | 2.99 |  |  | 2.99 | 4 nos. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 | L.S. | 2.99 |  |  | 2.99 | [5 empty] | L.S. | #REF! |  |  | #REF!
Acquisition/Purchase of lands and landed properties of Assets:
4141101 | Land Acquisition ( 470 hectare) | 24000 |  |  | 24000 | L.S. | 1000 |  |  | 1000 | L.S. | 1000 |  |  | 1000 | L.S. | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 0 | L.S. | 1000 |  |  | 1000 | 1000 | 1000 |  |  |  | L.S. | #REF! |  |  | #REF!
Construction and Works:
4111306 | Irrigation Infrastructures : |  |  |  |  | 50 (F)+25 (P) nos. | [24 empty] | 16186 | 11111.43 | 9722.5
4111306 | Construction of Irrigation Inlet (New Haors) | 151.32 | 1109.68 |  | 1261 |  | 30.93 | 354 |  | 384.93 | 12 nos. (Part) | 24.03 | 168.19 |  | 192.22 | [5 empty] | 50 (F)+25 (P) nos. | 30.93 | 354 |  | 384.93 | 12 nos. (Part) | 24.03 | 168.19 |  | 192.22 | [5 empty] | 12 nos. (Part) | #REF! | #REF! |  | #REF!
4111307 | Drainage Structures :
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 181.8 | 1333.2 |  | 1515 | 5 nos. (Part) | 0 | 0 |  | 0 | 1 no. (Part) |  |  |  | 0 | [5 empty] | 5 nos. (Part) | 0 | 0 |  | 0 | 1 no. (Part) |  |  |  | 0 | [5 empty] | 1 no. (Part) | #REF! | #REF! |  | #REF!
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 2437.32 | 17873.68 |  | 20311 | 20 (F)+40 (P) nos. | 523.12 | 5857 |  | 6380.12 | 7 nos. (Part) | 512.09 | 3563.13 |  | 4075.22 | 15 nos. (Part) | #REF! | #REF! | #REF! | #REF! | 20 (F)+40 (P) nos. | 523.12 | 5857 |  | 6380.12 | 7 nos. (Part) | 512.09 | 3563.13 |  | 4075.22 | [5 empty] | 7 nos. (Part) | #REF! | #REF! |  | #REF!
4111307 | Re-excavation of Khal/River (New Haors) | 1167.48 | 8561.52 |  | 9729 | 100 (F)+100 (P) Km. | 322.33 | 2858 |  | 3180.33 | 112 Km. (Part) | 319.56 | 2347.62 |  | 2667.18 | 108 Km. (Part) | #REF! | #REF! | #REF! | #REF! | 100 (F)+100 (P) Km. | 322.33 | 2858 |  | 3180.33 | 112 Km. (Part) | 319.56 | 2347.62 |  | 2667.18 | [5 empty] | 112 Km. (Part) | #REF! | #REF! |  | #REF!
Others
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 301.8 | 2213.2 |  | 2515 | 50 (F)+60 (P) Km. | 150.74 | 650 |  | 800.74 | 50 Km. (Part) | 94.32 | 632.22 |  | 726.54 | [5 empty] | 50 (F)+60 (P) Km. | 150.74 | 650 |  | 800.74 | 50 Km. (Part) | 94.32 | 632.22 |  | 726.54 | [5 empty] | 50 Km. (Part) | #REF! | #REF! |  | #REF!
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 306 | 2244 |  | 2550 | 35 (F)+30 (P) Km. | 36.79 | 660 |  | 696.79 | 5 Km. (Part) | 35.79 | 217.86 |  | 253.65 | [5 empty] | 35 (F)+30 (P) Km. | 36.79 | 660 |  | 696.79 | 5 Km. (Part) | 35.79 | 217.86 |  | 253.65 | [5 empty] | 5 Km. (Part) | #REF! | #REF! |  | #REF!
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 214.2 | 1570.8 |  | 1785 | 25 (F)+25 (P) Km. | 27.02 | 475 |  | 502.02 | 15 Km. (Part) | 26.02 | 153.66 |  | 179.68 | [5 empty] | 25 (F)+25 (P) Km. | 27.02 | 475 |  | 502.02 | 15 Km. (Part) | 26.02 | 153.66 |  | 179.68 | [5 empty] | 15 Km. (Part) | #REF! | #REF! |  | #REF!
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 1434.3 | 10518.2 |  | 11952.5 | 80 (F)+110 (P) Km. | 378.79 | 3591 |  | 3969.79 | 90 Km. (Part) | 365.45 | 2558.16 |  | 2923.61 | 90 Km. (Part) | #REF! | #REF! | #REF! | #REF! | 80 (F)+110 (P) Km. | 378.79 | 3591 |  | 3969.79 | 90 Km. (Part) | 365.45 | 2558.16 |  | 2923.61 | [5 empty] | 90 Km. (Part) | #REF! | #REF! |  | #REF!
4111201 | Rehabilitation of Regulator (New Haors) | 19.92 | 146.08 |  | 166 | 3 (F)+2 (P) nos. | 0 | 0 |  | 0 | 3 nos. (Part) | 0 | 0 |  | 0 | [5 empty] | 3 (F)+2 (P) nos. | 0 | 0 |  | 0 | 3 nos. (Part) | 0 | 0 |  | 0 | [5 empty] | 3 nos. (Part) | #REF! | #REF! |  | #REF!
4111201 | Construction of WMG Office | 165.6 | 1214.4 |  | 1380 | 5 (F)+5 (P) nos. | 16.28 | 255 |  | 271.28 | 5 nos. (Part) | 11.67 | 81.66 |  | 93.33 | [5 empty] | 5 (F)+5 (P) nos. | 16.28 | 255 |  | 271.28 | 5 nos. (Part) | 11.67 | 81.66 |  | 93.33 | [5 empty] | 5 nos. (Part) | #REF! | #REF! |  | #REF!
4111201 | O & M during Construction | 200 |  |  | 200
| Sub-total : (b) Capital Component: | 31645.96 | 46784.76 | 0 | 78430.72 |  | 2495 | 14700 | 0 | 17195 |  | 2396.92 | 9722.5 | 0 | 12119.42 |  | #REF! | #REF! | #REF! | #REF! |  | 1486 | 14700 | 0 | 16186 |  | 2396.92 | 9722.5 | 0 | 12119.42 | 17195 | 12119.42 | 9722.5 | 0 |  |  | #REF! | #REF! | 0 | #REF!
| Total Cost (a+b) : | 38218.14 | 51085.32 | 7901.4 | 97204.86 |  | 3195 | 15500 | 700 | 19395 |  | 3120.82 | 10150.12 | 450 | 13720.94 |  | #REF! | #REF! | #REF! | #REF! |  | 1986 | 14900 | 558 | 17444 |  | 3120.82 | 10150.12 | 450 | 13720.94 | 19395 | 13720.94 | 10150.12 | 450 |  |  | #REF! | #REF! | #REF! | #REF!
| (c) Physical Contingency ( Lump sum): | 100 | 158 |  | 258
| (d) Price Contingency (Lump sum): | 100.76 | 301.38 |  | 402.14 | [27 empty] | 10600.12
| Grand Total : (a)+(b)+(c)+(d): | 38418.9 | 51544.7 | 7901.4 | 97865 |  | 3195 | 15500 | 700 | 19395 |  | 3120.82 | 10150.12 | 450 | 13720.94 |  | #REF! | #REF! | #REF! | #REF! |  | 1986 | 14900 | 558 | 17444 |  | 3120.82 | 10150.12 | 450 | 13720.94 | [6 empty] | #REF! | #REF! | #REF! | #REF!
[12 empty] | 97.68% | 65.48% | 64.29% | 70.74% | [11 empty] | 157.1% | 68.12% | 80.65% | 78.66%
[11 empty] | Livelihood | 45.14 | 398.16 | 0 | 443.3 | [10 empty] | Livelihood | 45.14 | 398.16 | 0 | 443.3
[11 empty] | Ph.Work+gate | 1392.64 | 9751.96 | 0 | 11144.6 | [10 empty] | Ph.Work+gate | 1392.64 | 9751.96 | 0 | 11144.6
[11 empty] | Proc.G | 7.99 |  |  | 7.99 | [10 empty] | Proc.G | 7.99 |  |  | 7.99

## Sheet4
Cumulative Expenditure of 47 nos Packages up to 30.06.2020 (Including Gate)
SL No. | Item | As Per RDPP |  | Up to June 2018 |  |  | July'18 to June'19 |  |  | Total Cumulative up to June'19 Amount |  |  | July'2019 to June'2020 |  |  | Total Cumulative up to June'20 Amount
|  | Quantity | Cost | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA | Total | GoB | RPA
Irrigation Structure
1 | Construction of Irrigation Inlet | 131 nos. | 1261 | 5.27 | 0.68721 | 4.5828 | 116.72 | 16.3408 | 100.3792 | 116.72 | 16.34 | 100.38 | 151.91 | 30.93 | 132.9212 | 273.9 | 47.27 | 233.3012 | 216.51 | 247.44
Drainage Structure
7 | Re-installation/Construction of regulator/ Causeway (Rehablitation Sub-project) | 7 nos | 1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733.34 | 0 | 0
3 | Construction of Regulator/ Causeway/Drainage Box Outler | 137 nos. | 20311 | 2581.71 | 332.56 | 2249.15 | 3413.2 | 471.78 | 2941.42 | 5994.91 | 889.49 | 5254.17 | 4182.88 | 522.86 | 3660.02 | 10324.48 | 1412.35 | 8914.19 | 3660.02 | 4182.88
4 | Re-excavation of Khal/River | 318.20km | 9729 | 1958.04 | 252.78 | 1705.26 | 2875.01 | 402.5014 | 2472.5086 | 4833.05 | 791.08 | 5220.4 | 1805.24 | 322.33 | 1579.585 | 6638.29 | 1113.41 | 6799.985 | 2256.31 | 2578.64
Other Structure
6 | Re-excavation of Khal/River (Rehab) | 143.00km | 2515 | 0 | 0 | 0 | 1517.6 | 212.464 | 1305.136 | 1517.6 | 64.36 | 390.68 | 365.52 | 45.69 | 319.83 | 1883.12 | 110.05 | 710.51 | 319.83 | 365.52
8 | Construction of Full Embankment | 84.31km | 2550 | 62.18 | 8.85 | 53.33 | 477.32 | 66.8248 | 410.4952 | 539.5 | 63.49 | 388.97 | 361.19 | 45.1488 | 316.0413 | 900.69 | 108.6388 | 705.0113 | 316.0413 | 361.19
9 | Construction of Submersible Embankment (Rehab) | 87.03km | 1785 | 0 | 0 | 0 | 633.06 | 85.63 | 547.43 | 633.06 | 48.84 | 293.01 | 738.02 | 92.2525 | 645.7675 | 1371.08 | 141.0925 | 938.7775 | 645.7675 | 738.02
2 | Construction of Submersible Embankment | 263.24 km | 11952.5 | 3895.91 | 506.01 | 3389.9 | 2007.04 | 280.9856 | 1726.0544 | 5902.95 | 779.02 | 5348.04 | 1932 | 241.5 | 1690.5 | 7834.95 | 1020.52 | 7038.54 | 1690.5 | 1932
5 | Rehablitation of Regulator (New Haor) | 8 nos | 166 | 0 | 0 | 0 | 178.46 | 24.9844 | 153.4756 | 178.46 | 9.77 | 63.49 | 12.48 | 1.56 | 10.92 | 190.94 | 11.33 | 74.41 | 10.92 | 12.48
11 | Construction of WMG office | 60 nos | 1380 | 0 | 0 | 0 | 42.09 | 5.4717 | 36.6183 | 42.09 | 5.47 | 36.62 | 93.32 | 11.665 | 81.655 | 135.41 | 17.135 | 118.275 | 81.655 | 93.32
12 | O&M during Construction | L.S | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Physical Works |  |  | 53364.5 | [6 empty] | 19758.34 | 2667.86 | 17095.76 | 9642.56 | 1313.9362 | 8437.24 | 30286.2 | 3981.7963 | 25533
Gate Replacement
10 | Replecement of Gate (Netrokona & Kishoregonj) | 104 nos | 362.5 | 84.04 | 9.84 | 74.2 | 10.99 | 0.99 | 10 | 95.03 | 10.83 | 84.2 | 33.17 | 4.1462 | 29.0237 | 128.2 | 14.9762 | 113.2237
Total Civil Works |  |  | 53727 | 8587.15 | 1110.7272 | 7476.4228 | 11271.49 | 1567.9727 | 9703.5173 | 19853.37 | 2678.69 | 17179.96 | 9675.73 | 1318.0825 | 8466.2638 | 30414.4 | 3996.7725 | 25646.2238

## Sheet1
| Exchange Rate : 30-01-2020(buy) |  |  | 0.7788
Sl. No. | Item | Upto June '19 |  |  | Jul'19 - Feb'20 |  |  | Cumulative |  |  | Cumulative in m JPY
|  | GoB | JICA/PA | Total | GoB | JICA/RPA | Total | GoB | JICA/RPA | Total | GoB | JICA/RPA | Total
|  | Lakh BDT | Lakh BDT | Lakh BDT | Lakh BDT | Lakh BDT | Lakh BDT | Lakh BDT | Lakh BDT | Lakh BDT | M JPY | M JPY | M JPY
1 | Consultant | 0 | #REF! | #REF! | 0 | 450 | 450 | 0 | #REF! | #REF! | 0 | #REF! | #REF!
2 | Physical work with gate | #REF! | #REF! | #REF! | 1392.64 | 9751.96 | 11144.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Livelihood | #REF! | #REF! | #REF! | 45.14 | 398.16 | 443.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | Land Acquisition | #REF! | 0 | #REF! | 1000 | 0 | 1000 | #REF! | 0 | #REF! | #REF! | 0 | #REF!
5 | Tax & Vat | #REF! | 0 | #REF! | 177.18 | 0 | 177.18 | #REF! | 0 | #REF! | #REF! | 0 | #REF!
6 | Procurement goods & Vehicles | #REF! | 0 | #REF! | 7.99 | 0 | 7.99 | #REF! | 0 | #REF! | #REF! | 0 | #REF!
7 | Office administration | #REF! | 0 | #REF! | 497.87 |  | 497.87 | #REF! | 0 | #REF! | #REF! | 0 | #REF!
8 | Contingency | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | #REF! | #REF! | #REF! | 3120.82 | 10600.12 | 13720.94 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Sheet2
Item wise Physical & Financial Progress
Economic Code | Item | Fund Release 1st Qrt. |  |  |  | Physical & Financial Target during 2019-20 as per RADP |  |  |  |  | Fund Release 2nd Qrt. |  |  |  | Total Fund Release |  |  |  | Fund Release 2nd Qrt. |  |  |  | Physical & Financial Progress from 01-07-2019 to 29-02-2020) |  |  |  |  | Cumulative Physical & Financial Progress up to current month (up to November, 2018) |  |  |  |  | IMED 05 |  |  |  |  | Physical & Financial Progress cumulative till date
|  | Financial |  |  |  | Physical | Financial |  |  |  | Financial |  |  |  | Financial |  |  |  | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Terget | Expend | RPA | DPA | Remainig GOB | Physical | Financial
|  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total | GOB | RPA | DPA | Total | GOB | RPA | DPA | Total | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total | [6 empty] | GOB | RPA | DPA | Total
(a) Revenue Component:
| Salary & Allowance | [31 empty] | 14.5 | 9.1
3111302 | Conveyance Allowance | 1.01 | 0 | 0 | 1.01 | L.S. | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | L.S. | 0.3 |  |  | 0.3 | L.S. | 1.31 | 0 | 0 | 1.31 |  |  |  |  | 0.2 | L.S. | 1.31 |  |  | 1.31
3111327 | Overtime Allowance |  |  |  |  | L.S. | [16 empty] | L.S. |  |  |  | 0 | L.S. | 0 | 0 | 0 | 0 | [5 empty] | L.S. | 0 |  |  | 0
3111338 | Other Allowance | 36.61 | 0 | 0 | 36.61 | L.S. | 14 |  |  | 14 | 14 |  |  | 14 | 14 |  |  | 14 | 14 |  |  | 14 | L.S. | 8.8 |  |  | 8.8 | L.S. | 45.41 | 0 | 0 | 45.41 |  |  |  |  | 5.2 | L.S. | 45.41 |  |  | 45.41
Supplies and Services
3241101 | Travel Expenses (TA & DA for PMO & PIU) | 58.54 | 0 | 0 | 58.54 | L.S. | 15 |  |  | 15 | 15 |  |  | 15 | 15 |  |  | 15 | 15 |  |  | 15 | L.S. | 7.42 |  |  | 7.42 | L.S. | 65.96 | 0 | 0 | 65.96 | 15 | 7.42 |  |  | 7.58 | L.S. | 65.96 |  |  | 65.96
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 116.67 | 0 | 0 | 116.67 | L.S. | 34.25 |  |  | 34.25 | 34.25 |  |  | 34.25 | 34.25 |  |  | 34.25 | 34.25 |  |  | 34.25 | L.S. | 19.96 |  |  | 19.96 | L.S. | 136.63 | 0 | 0 | 136.63 | 34.25 | 19.96 |  |  | 14.29 | L.S. | 136.63 |  |  | 136.63
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 1603.18 | 0 | 0 | 1603.18 | L.S. | 359.08 |  |  | 359.08 | 359.08 |  |  | 359.08 | 359.08 |  |  | 359.08 | 359.08 |  |  | 359.08 | L.S. | 79.14 |  |  | 79.14 | L.S. | 1682.32 | 0 | 0 | 1682.32 | 359.08 | 79.14 |  |  | 279.94 | L.S. | 1682.32 |  |  | 1682.32
3211119 | Postage | 0.77 | 0 | 0 | 0.77 | L.S. | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | L.S. | 0.2 |  |  | 0.2 | L.S. | 0.97 | 0 | 0 | 0.97 | 0.9 | 0.25 |  |  | 0.3 | L.S. | 0.97 |  |  | 0.97
3211120 | Telephones/Telegram/Teleprinter | 0.97 | 0 | 0 | 0.97 | L.S. | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | L.S. | 0.03 |  |  | 0.03 | L.S. | 1 | 0 | 0 | 1 |  |  |  |  | 0.17 | L.S. | 1 |  |  | 1
3211117 | Telex/Fax/Internet | 0.44 | 0 | 0 | 0.44 | L.S. | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | L.S. | 0.02 |  |  | 0.02 | L.S. | 0.46 | 0 | 0 | 0.46 |  |  |  |  | 0.18 | L.S. | 0.46 |  |  | 0.46
3221104 | Registration Fee (Vehicles) | 11.92 | 0 | 0 | 11.92 | L.S. | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | L.S. | 0.14 |  |  | 0.14 | L.S. | 12.06 | 0 | 0 | 12.06 | 1 | 0.14 |  |  | 0.86 | L.S. | 12.06 |  |  | 12.06
3211115 | Water | 1.11 | 0 | 0 | 1.11 | L.S. | 0.45 |  |  | 0.45 | 0.7 |  |  | 0.7 | 0.7 |  |  | 0.7 | 0.7 |  |  | 0.7 | L.S. | 0.33 |  |  | 0.33 | L.S. | 1.44 | 0 | 0 | 1.44 | 4.7 | 2.31 |  |  | 0.37 | L.S. | 1.44 |  |  | 1.44
3211113 | Electricity | 8.74 | 0 | 0 | 8.74 | L.S. | 3.5 |  |  | 3.5 | 4 |  |  | 4 | 4 |  |  | 4 | 4 |  |  | 4 | L.S. | 1.98 |  |  | 1.98 | L.S. | 10.72 | 0 | 0 | 10.72 |  |  |  |  | 2.02 | L.S. | 10.72 |  |  | 10.72
3243102 | Gas & Fuel | 17.52 | 0 | 0 | 17.52 | L.S. | 6 |  |  | 6 | 6 |  |  | 6 | 6 |  |  | 6 | 6 |  |  | 6 | L.S. | 2.41 |  |  | 2.41 | L.S. | 19.93 | 0 | 0 | 19.93 | 31 | 17.2 |  |  | 3.59 | L.S. | 19.93 |  |  | 19.93
3243101 | Petrol and Lubricant | 64.59 | 0 | 0 | 64.59 | L.S. | 20 |  |  | 20 | 25 |  |  | 25 | 25 |  |  | 25 | 25 |  |  | 25 | L.S. | 14.79 |  |  | 14.79 | L.S. | 79.38 | 0 | 0 | 79.38 |  |  |  |  | 10.21 | L.S. | 79.38 |  |  | 79.38
3221108 | Insurance/Bank Charges (including Vehicles) | 1.16 | 0 | 0 | 1.16 | L.S. | 0.15 |  |  | 0.15 | 0.7 |  |  | 0.7 | 0.7 |  |  | 0.7 | 0.7 |  |  | 0.7 | L.S. | 0.41 |  |  | 0.41 | L.S. | 1.57 | 0 | 0 | 1.57 | 0.7 | 0.41 |  |  | 0.29 | L.S. | 1.57 |  |  | 1.57
3255102 | Printing & Binding | 34.16 | 0 | 0 | 34.16 | L.S. | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 | L.S. | 0.42 |  |  | 0.42 | L.S. | 34.58 | 0 | 0 | 34.58 | 0.5 | 0.42 |  |  | 0.08 | L.S. | 34.58 |  |  | 34.58
3255104 | Stationery, Seals & Stamps | 49.91 | 0 | 0 | 49.91 | L.S. | 20 |  |  | 20 | 20 |  |  | 20 | 20 |  |  | 20 | 20 |  |  | 20 | L.S. | 11.31 |  |  | 11.31 | L.S. | 61.22 | 0 | 0 | 61.22 | 20 | 11.31 |  |  | 8.69 | L.S. | 61.22 |  |  | 61.22
3211127 | Books & Periodicals | 0.28 | 0 | 0 | 0.28 | L.S. | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | 0.2 |  |  | 0.2 | L.S. | 0.03 |  |  | 0.03 | L.S. | 0.31 | 0 | 0 | 0.31 | 0.2 | 0.03 |  |  | 0.17 | L.S. | 0.31 |  |  | 0.31
3231201 | Training Expenditure | [37 empty] | 0 | 0
| Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  |  | 0 | L.S. | [21 empty] | L.S. | [10 empty] | 0 | 0
| Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 22.54 | 278.96 | 0 | 301.5 | L.S. | 17.06 | 125.15 |  | 142.21 | 16.46 | 125.15 |  | 141.61 | 16.46 | 125.15 |  | 141.61 | 16.46 | 125.15 |  | 141.61 | L.S. | 2.19 | 23.34 |  | 25.53 | L.S. | 24.73 | 302.3 | 0 | 327.03 | 848.67 | 253.55 | 219.57 |  | 14.27 | L.S. | 24.73 | 302.3 |  | 327.03
| Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 80.34 | 1266.29 | 0 | 1346.63 | L.S. | 68.8 | 504.59 |  | 573.39 | 66.38 | 504.59 |  | 570.97 | 66.38 | 504.59 |  | 570.97 | 66.38 | 504.59 |  | 570.97 | L.S. | 27.68 | 185.87 |  | 213.55 | L.S. | 108.02 | 1452.16 | 0 | 1560.18 |  |  |  |  | 38.7 | L.S. | 108.02 | 1452.16 |  | 1560.18
| Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 35.47 | 542.73 | 0 | 578.2 | L.S. | 16.4 | 120.26 |  | 136.66 | 15.83 | 120.26 |  | 136.09 | 15.83 | 120.26 |  | 136.09 | 15.83 | 120.26 |  | 136.09 | L.S. | 4.11 | 10.36 |  | 14.47 | L.S. | 39.58 | 553.09 | 0 | 592.67 |  |  |  |  | 11.72 | L.S. | 39.58 | 553.09 |  | 592.67
3211109 | Casual labour/Job worker | 10.96 | 0 | 0 | 10.96 | L.S. | 3.5 |  |  | 3.5 | 3.5 |  |  | 3.5 | 3.5 |  |  | 3.5 | 3.5 |  |  | 3.5 | L.S. | 2.11 |  |  | 2.11 | L.S. | 13.07 | 0 | 0 | 13.07 | 3.5 | 2.11 |  |  | 1.39 | L.S. | 13.07 | 0 | 0 | 13.07
3256103 | Consumable Stores | 3.74 | 0 | 0 | 3.74 | L.S. | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | L.S. |  |  |  | 0 | L.S. | 3.74 | 0 | 0 | 3.74 | 3 | 0 |  |  | 3 | L.S. | 3.74 | 0 | 0 | 3.74
3257101 | Consultancy : International - 71 M/M National - 324 M/M | 0 | 0 | 5168.01 | 5168.01 | L.S. |  |  | 500 | 500 |  |  | 700 | 700 |  |  | 700 | 700 |  |  | 700 | 700 | L.S. |  |  | 262.38 | 262.38 | L.S. | 0 | 0 | 5430.39 | 5430.39 | 700 | 262.38 |  | 262.38 |  | L.S. |  |  | 5430.39 | 5430.39
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 12.73 | 0 | 0 | 12.73 | L.S. | 5 |  |  | 5 | 5 |  |  | 5 | 5 |  |  | 5 | 5 |  |  | 5 | L.S. | 2.2 |  |  | 2.2 | L.S. | 14.93 | 0 | 0 | 14.93 | 7 | 2.2 |  |  | 2.8 | L.S. | 14.93 |  |  | 14.93
| b) Interim Evaluation | 1.29 | 0 | 0 | 1.29 | L.S. | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | L.S. |  |  |  | 0 | L.S. | 1.29 | 0 | 0 | 1.29 |  |  |  |  | 1 | L.S. | 1.29 |  |  | 1.29
| c) Progress Monitoring | 1.3 | 0 | 0 | 1.3 | L.S. | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | L.S. |  |  |  | 0 | L.S. | 1.3 | 0 | 0 | 1.3 |  |  |  |  | 1 | L.S. | 1.3 |  |  | 1.3
3257104 | Survey | 85.02 | 0 | 0 | 85.02 | L.S. | 50 |  |  | 50 | 30 |  |  | 30 | 30 |  |  | 30 | 30 |  |  | 30 | L.S. | 6.02 |  |  | 6.02 | L.S. | 91.04 | 0 | 0 | 91.04 | 30 | 6.02 |  |  | 23.98 | L.S. | 91.04 |  |  | 91.04
3255101 | Computer Consumables | 20.47 | 0 | 0 | 20.47 | L.S. | 10 |  |  | 10 | 10 |  |  | 10 | 10 |  |  | 10 | 10 |  |  | 10 | L.S. | 6.14 |  |  | 6.14 | L.S. | 26.61 | 0 | 0 | 26.61 | 10 | 6.14 |  |  | 3.86 | L.S. | 26.61 |  |  | 26.61
3256101 | Other Expenses: Salary of Manpower through Outsourcing | 875.46 | 0 | 0 | 875.46 | L.S. | 300 |  |  | 300 | 300 |  |  | 300 | 300 |  |  | 300 | 300 |  |  | 300 | L.S. | 205.66 |  |  | 205.66 | L.S. | 1081.12 | 0 | 0 | 1081.12 | 300 | 205.66 |  |  | 94.34 | L.S. | 1081.12 |  |  | 1081.12
Repair, Maintenance & Rehabilitation
3258101 | Motor Vehicles | 61.4 | 0 | 0 | 61.4 | L.S. | 15 |  |  | 15 | 15 |  |  | 15 | 15 |  |  | 15 | 15 |  |  | 15 | L.S. | 3.62 |  |  | 3.62 | L.S. | 65.02 | 0 | 0 | 65.02 | 91 | 40.11 |  |  | 11.38 | L.S. | 65.02 |  |  | 65.02
3258102 | Furnitures & Fixtures | 3.2 | 0 | 0 | 3.2 | L.S. | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | L.S. |  |  |  | 0 | L.S. | 3.2 | 0 | 0 | 3.2 |  |  |  |  | 2 | L.S. | 3.2 |  |  | 3.2
3258103 | Computers & office equipments | 5.34 | 0 | 0 | 5.34 | L.S. | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | L.S. | 2.29 |  |  | 2.29 | L.S. | 7.63 | 0 | 0 | 7.63 |  |  |  |  | 0.71 | L.S. | 7.63 |  |  | 7.63
3258105 | Machineries & Equipments | 1.22 | 0 | 0 | 1.22 | L.S. | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | L.S. | 0.47 |  |  | 0.47 | L.S. | 1.69 | 0 | 0 | 1.69 |  |  |  |  | 1.53 | L.S. | 1.69 |  |  | 1.69
3258107 | Office Building : Repair & Maintenance | 19.98 | 0 | 0 | 19.98 | L.S. | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | L.S. |  |  |  | 0 | L.S. | 19.98 | 0 | 0 | 19.98 |  |  |  |  | 0 | L.S. | 19.98 |  |  | 19.98
3258106 | Residential Building : Repair & Maintenance | 14.53 | 0 | 0 | 14.53 | L.S. | 5 |  |  | 5 | 5 |  |  | 5 | 5 |  |  | 5 | 5 |  |  | 5 | L.S. |  |  |  | 0 | L.S. | 14.53 | 0 | 0 | 14.53 |  |  |  |  | 5 | L.S. | 14.53 |  |  | 14.53
3258105 | Engineering Equipments | 1.39 | 0 | 0 | 1.39 | L.S. | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 2 | L.S. | 0.56 |  |  | 0.56 | L.S. | 1.95 | 0 | 0 | 1.95 |  |  |  |  | 1.44 | L.S. | 1.95 |  |  | 1.95
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 10.83 | 84.2 | 0 | 95.03 | L.S. | 8.25 | 50 |  | 58.25 | 8.25 | 50 |  | 58.25 | 8.25 | 50 |  | 58.25 | 8.25 | 50 |  | 58.25 | L.S. | 3.71 | 29.46 |  | 33.17 | L.S. | 14.54 | 113.66 | 0 | 128.2 |  |  | 29.46 |  | 4.54 | L.S. | 14.54 | 113.66 | 0 | 128.2
3258128 | Water Transport : Repair of Speedboat(s) | 2.39 | 0 | 0 | 2.39 | L.S. | 0.75 |  |  | 0.75 | 0.75 |  |  | 0.75 | 0.75 |  |  | 0.75 | 0.75 |  |  | 0.75 | L.S. |  |  |  | 0 | L.S. | 2.39 | 0 | 0 | 2.39 |  |  |  |  | 0.75 | L.S. | 2.39 |  |  | 2.39
3258107 | Others : Repair & Maintenance | 7.48 | 0 | 0 | 7.48 | L.S. | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | 3 |  |  | 3 | L.S. |  |  |  | 0 | L.S. | 7.48 | 0 | 0 | 7.48 |  |  |  |  | 3 | L.S. | 7.48 |  |  | 7.48
| Sub-total : (a) Revenue Component: | 3284.66 | 2172.18 | 5168.01 | 10624.85 |  | 992.29 | 800 | 500 | 2292.29 | 975 | 800 | 700 | 2475 | 975 | 800 | 700 | 2475 | 975 | 800 | 700 | 2475 |  | 414.45 | 249.03 | 262.38 | 925.86 |  | 3699.11 | 2421.21 | 5430.39 | 11550.71 | 2475 | 925.86 | 249.03 | 262.38 | 560.55 |  | 3699.11 | 2421.21 | 5430.39 | 11550.71
(b) Capital Component:
Acquisition of Assets:
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 606.9 | 0 | 0 | 606.9 | 1 no. | 95.6 |  |  | 95.6 | 95.6 |  |  | 95.6 | 95.6 |  |  | 95.6 | 95.6 |  |  | 95.6 | 1 no. |  |  |  | 0 | 7 nos. | 606.9 | 0 | 0 | 606.9 | 95.6 | 0 |  |  |  | 1 no. | 606.9 |  |  | 606.9
| Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 50.22 | 0 | 0 | 50.22 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 33 nos. | 50.22 | 0 | 0 | 50.22 | [6 empty] | 50.22 |  |  | 50.22
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 61.29 | 0 | 0 | 61.29 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 4 nos. | 61.29 | 0 | 0 | 61.29 | 0 | 0 |  |  |  |  | 61.29 |  |  | 61.29
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.95 | 0 | 0 | 8.95 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 7 nos. | 8.95 | 0 | 0 | 8.95 | 0 | 0 |  |  |  |  | 8.95 |  |  | 8.95
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 0.79 | 0 | 0 | 0.79 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 2 nos. | 0.79 | 0 | 0 | 0.79 | [6 empty] | 0.79 |  |  | 0.79
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.18 | 0 | 0 | 20.18 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 20.18 | 0 | 0 | 20.18 | 5 | 0 |  |  |  |  | 20.18 |  |  | 20.18
| Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 2.13 | 0 | 0 | 2.13 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 1 no. | 2.13 | 0 | 0 | 2.13 | [6 empty] | 2.13 |  |  | 2.13
| Engineering Laboratory Equipments for Kishoregonj WD Division | 9.49 | 0 | 0 | 9.49 | L.S. | 5 |  |  | 5 | 5 |  |  | 5 | 5 |  |  | 5 | 5 |  |  | 5 | L.S. |  |  |  | 0 | L.S. | 9.49 | 0 | 0 | 9.49 | [5 empty] | L.S. | 9.49 |  |  | 9.49
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.47 | 0 | 0 | 19.47 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 30 nos. | 19.47 | 0 | 0 | 19.47 | 0 | 0 |  |  |  |  | 19.47 |  |  | 19.47
| Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 9.88 | 0 | 0 | 9.88 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 9.88 | 0 | 0 | 9.88 | [6 empty] | 9.88 |  |  | 9.88
| A3 Combo Printer 2 no ( PMO) | 0.2 | 0 | 0 | 0.2 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 1 no. | 0.2 | 0 | 0 | 0.2 | [6 empty] | 0.2 |  |  | 0.2
| Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 4.08 | 0 | 0 | 4.08 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 4.08 | 0 | 0 | 4.08 | [6 empty] | 4.08 |  |  | 4.08
4112314 | Furnitures & Fixtures | 45.32 | 0 | 0 | 45.32 | L.S. | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | L.S. |  |  |  | 0 | L.S. | 45.32 | 0 | 0 | 45.32 | 4 | 0 |  |  |  | L.S. | 45.32 |  |  | 45.32
4112303 | Aircooler | 9.73 | 0 | 0 | 9.73 | 4 nos. | 4 |  |  | 4 | 4 |  |  | 4 | 4 |  |  | 4 | 4 |  |  | 4 | L.S. |  |  |  | 0 | 4 nos. | 9.73 | 0 | 0 | 9.73 | [5 empty] | L.S. | 9.73 |  |  | 9.73
| Acquisition/Purchase of lands and landed properties of Assets: | 0 | 0 | 0
4141101 | Land Acquisition ( 470 hectare) | 14323.6 | 0 | 0 | 14323.6 | L.S. | 2049.42 |  |  | 2049.42 | 327.39 |  |  | 327.39 | 327.39 |  |  | 327.39 | 327.39 |  |  | 327.39 | L.S. |  |  |  | 0 | L.S. | 14323.6 | 0 | 0 | 14323.6 | 327.39 | 0 |  |  |  | L.S. | 14323.6 |  |  | 14323.6
Construction and Works:
4111306 | Irrigation Infrastructures : | [31 empty] | 17093.01 | 1752.06 | 1382.33
4111306 | Construction of Irrigation Inlet (New Haors) | 16.34 | 100.38 | 0 | 116.72 | 50 (F)+25 (P) nos. | 68.65 | 421.68 |  | 490.33 | 57.63 | 354 |  | 411.63 | 57.63 | 354 |  | 411.63 | 57.63 | 354 |  | 411.63 | 12 nos. (Part) |  |  |  | 0 | [10 empty] | 12 nos. (Part) | 16.34 | 100.38 |  | 116.72
4111307 | Drainage Structures :
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 0 | 0 | 0 | 0 | 5 nos. (Part) | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 no. (Part) | 15.39 | 94.54 |  | 109.93 | [10 empty] | 1 no. (Part) | 15.39 | 94.54 |  | 109.93
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 889.49 | 5254.17 | 0 | 6143.66 | 20 (F)+40 (P) nos. | 1134.84 | 6970.74 |  | 8105.58 | 953.46 | 5857 |  | 6810.46 | 953.46 | 5857 |  | 6810.46 | 953.46 | 5857 |  | 6810.46 | 7 nos. (Part) | 209.64 | 1287.79 |  | 1497.43 | 15 nos. (Part) | 1099.13 | 6541.96 | 0 | 7641.09 | [5 empty] | 7 nos. (Part) | 1099.13 | 6541.96 |  | 7641.09
4111307 | Re-excavation of Khal/River (New Haors) | 791.08 | 5220.4 | 0 | 6011.48 | 100 (F)+100 (P) Km. | 553.88 | 3402.2 |  | 3956.08 | 465.26 | 2858 |  | 3323.26 | 465.26 | 2858 |  | 3323.26 | 465.26 | 2858 |  | 3323.26 | 112 Km. (Part) | 35.75 |  |  | 35.75 | 108 Km. (Part) | 826.83 | 5220.4 | 0 | 6047.23 | [5 empty] | 112 Km. (Part) | 826.83 | 5220.4 |  | 6047.23
| Others | [22 empty] | 13.59 |  |  | 13.59
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 64.36 | 390.68 | 0 | 455.04 | 50 (F)+60 (P) Km. | 126.11 | 774.62 |  | 900.73 | 105.81 | 650 |  | 755.81 | 105.81 | 650 |  | 755.81 | 105.81 | 650 |  | 755.81 | 50 Km. (Part) | 8.07 |  |  | 8.07 | [10 empty] | 50 Km. (Part) | 72.43 | 390.68 |  | 463.11
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 63.49 | 388.97 | 0 | 452.46 | 35 (F)+30 (P) Km. | 127.86 | 785.4 |  | 913.26 | 107.44 | 660 |  | 767.44 | 107.44 | 660 |  | 767.44 | 107.44 | 660 |  | 767.44 | 5 Km. (Part) |  |  |  | 0 | [10 empty] | 5 Km. (Part) | 63.49 | 388.97 |  | 452.46
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 48.84 | 293.01 | 0 | 341.85 | 25 (F)+25 (P) Km. | 92.06 | 565.49 |  | 657.55 | 77.32 | 475 |  | 552.32 | 77.32 | 475 |  | 552.32 | 77.32 | 475 |  | 552.32 | 15 Km. (Part) |  |  |  | 0 | [10 empty] | 15 Km. (Part) | 48.84 | 293.01 |  | 341.85
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 779.02 | 5348.04 | 0 | 6127.06 | 80 (F)+110 (P) Km. | 688.04 | 4226.27 |  | 4914.31 | 584.58 | 3591 |  | 4175.58 | 584.58 | 3591 |  | 4175.58 | 584.58 | 3591 |  | 4175.58 | 90 Km. (Part) | 87.29 |  |  | 87.29 | 90 Km. (Part) | 866.31 | 5348.04 | 0 | 6214.35 | [5 empty] | 90 Km. (Part) | 866.31 | 5348.04 |  | 6214.35
4111201 | Rehabilitation of Regulator (New Haors) | 9.77 | 63.49 | 0 | 73.26 | 3 (F)+2 (P) nos. | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3 nos. (Part) |  |  |  | 0 | [10 empty] | 3 nos. (Part) | 9.77 | 63.49 |  | 73.26
4111201 | Construction of WMG Office | 5.47 | 36.62 | 0 | 42.09 | 5 (F)+5 (P) nos. | 44.54 | 303.6 |  | 348.14 | 41.51 | 255 |  | 296.51 | 41.51 | 255 |  | 296.51 | 41.51 | 255 |  | 296.51 | 5 nos. (Part) |  |  |  | 0 | [10 empty] | 5 nos. (Part) | 5.47 | 36.62 |  | 42.09
4111201 | O & M during Construction
| Sub-total : (b) Capital Component: | 17840.09 | 17095.76 | 0 | 34935.85 |  | 4990 | 17450 | 0 | 22440 | 2825 | 14700 | 0 | 17525 | 2825 | 14700 | 0 | 17525 | 2825 | 14700 | 0 | 17525 |  | 369.73 | 1382.33 | 0 | 1752.06 |  | 18209.82 | 18478.09 | 0 | 36687.91 | 17525 | 1752.06 | 1382.33 | 0 |  |  | 18196.23 | 18478.09 | 0 | 36674.32
| Total Cost (a+b) : | 21124.75 | 19267.94 | 5168.01 | 45560.7 |  | 5982.29 | 18250 | 500 | 24732.29 | 3800 | 15500 | 700 | 20000 | 3800 | 15500 | 700 | 20000 | 3800 | 15500 | 700 | 20000 |  | 784.18 | 1631.36 | 262.38 | 2677.92 |  | 21908.93 | 20899.3 | 5430.39 | 48238.62 | 20000 | 2677.92 | 1631.36 | 262.38 |  |  | 21895.34 | 20899.3 | 5430.39 | 48225.03
(c) Physical Contingency ( Lump sum):
| (d) Price Contingency (Lump sum): | [33 empty] | 1893.74
| Grand Total : (a)+(b)+(c)+(d): | 21124.75 | 19267.94 | 5168.01 | 45560.7 |  | 5982.29 | 18250 | 500 | 24732.29 | 3800 | 15500 | 700 | 20000 | 3800 | 15500 | 700 | 20000 | 3800 | 15500 | 700 | 20000 |  | 784.18 | 1631.36 | 262.38 | 2677.92 |  | 21908.93 | 20899.3 | 5430.39 | 48238.62 | [6 empty] | 21895.34 | 20899.3 | 5430.39 | 48225.03
[24 empty] | 20.64% | 10.52% | 37.48% | 13.39%
|  | 138.35 | 2087.98 | 0 | 2226.33 | [17 empty] | Livelihood | 33.98 | 219.57 | 0 | 253.55
|  | 2678.69 | 17179.96 | 0 | 19858.65 | [17 empty] | Ph.Work+gate | 373.44 | 1411.79 | 0 | 1785.23
|  | 848.63 |  |  | 848.63 | [17 empty] | Proc.G | 0 |  |  | 0

## 20-21
Item wise Physical & Financial Progress
Economic Code | Item | As per 1st RDPP |  |  |  | Cumulative Physical & Financial Progress June 20 (up to June, 2018) |  |  |  |  | Physical & Financial Target during 2020-21 as per ADP |  |  |  |  | Physical & Financial Revised Target during 2020-21 as per ADP |  |  |  |  | Physical & Financial Progress from 01-07-2019 to 19-11-2020 |  |  |  |  | Cumulative Physical & Financial Progress up to current month (up to November, 2018) |  |  |  |  | IMED 05 |  |  |  |  | Physical & Financial Progress cumulative till date
|  | GOB (FE) | PA |  | Total | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Terget | Expend | RPA | DPA | Remainig GOB | Physical | Financial
|  |  | RPA | DPA |  |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total | [6 empty] | GOB | RPA | DPA | Total
(a) Revenue Component:
| Salary & Allowance | [29 empty] | 16.25 | 6.9
3111302 | Conveyance Allowance | 10 |  |  | 10 | L.S. | 1.01 | 0 | 0 | 1.01 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.12 |  |  | 0.12 | L.S. | 1.13 | 0 | 0 | 1.13 |  |  |  |  | #REF! | L.S. | 1.13 |  |  | 1.13
3111327 | Overtime Allowance | 10 |  |  | 10 | L.S. |  |  |  |  | L.S. |  |  |  |  | L.S. |  |  |  |  | L.S. |  |  |  | 0 | L.S. | 0 | 0 | 0 | 0 | [5 empty] | L.S. | 0 |  |  | 0
3111338 | Other Allowance | 140 |  |  | 140 | L.S. | 36.61 | 0 | 0 | 36.61 | L.S. | 14.1 |  |  | 14.1 | L.S. | 15.5 |  |  | 15.5 | L.S. | 6.78 |  |  | 6.78 | L.S. | 43.39 | 0 | 0 | 43.39 |  |  |  |  | #REF! | L.S. | 43.39 |  |  | 43.39
Supplies and Services
3241101 | Travel Expenses (TA & DA for PMO & PIU) | 100 |  |  | 100 | L.S. | 58.54 | 0 | 0 | 58.54 | L.S. | 12 |  |  | 12 | L.S. | 15 |  |  | 15 | L.S. | 1.56 |  |  | 1.56 | L.S. | 60.1 | 0 | 0 | 60.1 | #REF! | 1.56 |  |  | #REF! | L.S. | 60.1 |  |  | 60.1
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 |  |  | 245 | L.S. | 116.67 | 0 | 0 | 116.67 | L.S. | 34.25 |  |  | 34.25 | L.S. | 34.25 |  |  | 34.25 | L.S. | 14.25 |  |  | 14.25 | L.S. | 130.92 | 0 | 0 | 130.92 | #REF! | 14.25 |  |  | #REF! | L.S. | 130.92 |  |  | 130.92
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 |  |  | 2596.27 | L.S. | 1603.18 | 0 | 0 | 1603.18 | L.S. | 115 |  |  | 115 | L.S. | 365.45 |  |  | 365.45 | L.S. | 41.27 |  |  | 41.27 | L.S. | 1644.45 | 0 | 0 | 1644.45 | #REF! | 41.27 |  |  | #REF! | L.S. | 1644.45 |  |  | 1644.45
3211119 | Postage | 25 |  |  | 25 | L.S. | 0.77 | 0 | 0 | 0.77 | L.S. | 0.2 |  |  | 0.2 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.02 |  |  | 0.02 | L.S. | 0.79 | 0 | 0 | 0.79 | #REF! | 0.05 |  |  | #REF! | L.S. | 0.79 |  |  | 0.79
3211120 | Telephones/Telegram/Teleprinter | 25 |  |  | 25 | L.S. | 0.97 | 0 | 0 | 0.97 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0 |  |  | 0 | L.S. | 0.97 | 0 | 0 | 0.97 |  |  |  |  | #REF! | L.S. | 0.97 |  |  | 0.97
3211117 | Telex/Fax/Internet | 25 |  |  | 25 | L.S. | 0.44 | 0 | 0 | 0.44 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.03 |  |  | 0.03 | L.S. | 0.47 | 0 | 0 | 0.47 |  |  |  |  | #REF! | L.S. | 0.47 |  |  | 0.47
3221104 | Registration Fee (Vehicles) | 15 |  |  | 15 | L.S. | 11.92 | 0 | 0 | 11.92 | L.S. | 0.5 |  |  | 0.5 | L.S. | 2.5 |  |  | 2.5 | L.S. | 0 |  |  | 0 | L.S. | 11.92 | 0 | 0 | 11.92 | #REF! | 0 |  |  | #REF! | L.S. | 11.92 |  |  | 11.92
3211115 | Water | 10 |  |  | 10 | L.S. | 1.11 | 0 | 0 | 1.11 | L.S. | 0.5 |  |  | 0.5 | L.S. | 1 |  |  | 1 | L.S. | 0.12 |  |  | 0.12 | L.S. | 1.23 | 0 | 0 | 1.23 | #REF! | 1.22 |  |  | #REF! | L.S. | 1.23 |  |  | 1.23
3211113 | Electricity | 15 |  |  | 15 | L.S. | 8.74 | 0 | 0 | 8.74 | L.S. | 3 |  |  | 3 | L.S. | 5 |  |  | 5 | L.S. | 1.1 |  |  | 1.1 | L.S. | 9.84 | 0 | 0 | 9.84 |  |  |  |  | #REF! | L.S. | 9.84 |  |  | 9.84
3243102 | Gas & Fuel | 200 |  |  | 200 | L.S. | 17.52 | 0 | 0 | 17.52 | L.S. | 1 |  |  | 1 | L.S. | 3 |  |  | 3 | L.S. | 0.29 |  |  | 0.29 | L.S. | 17.81 | 0 | 0 | 17.81 | #REF! | 5.03 |  |  | #REF! | L.S. | 17.81 |  |  | 17.81
3243101 | Petrol and Lubricant | 150 |  |  | 150 | L.S. | 64.59 | 0 | 0 | 64.59 | L.S. | 11 |  |  | 11 | L.S. | 25 |  |  | 25 | L.S. | 4.74 |  |  | 4.74 | L.S. | 69.33 | 0 | 0 | 69.33 |  |  |  |  | #REF! | L.S. | 69.33 |  |  | 69.33
3221108 | Insurance/Bank Charges (including Vehicles) | 3 |  |  | 3 | L.S. | 1.16 | 0 | 0 | 1.16 | L.S. | 0.5 |  |  | 0.5 | L.S. | 1 |  |  | 1 | L.S. | 0.11 |  |  | 0.11 | L.S. | 1.27 | 0 | 0 | 1.27 | #REF! | 0.11 |  |  | #REF! | L.S. | 1.27 |  |  | 1.27
3255102 | Printing & Binding | 35 |  |  | 35 | L.S. | 34.16 | 0 | 0 | 34.16 | L.S. | 0 |  |  | 0 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.02 |  |  | 0.02 | L.S. | 34.18 | 0 | 0 | 34.18 | #REF! | 0.02 |  |  | #REF! | L.S. | 34.18 |  |  | 34.18
3255104 | Stationery, Seals & Stamps | 150 |  |  | 150 | L.S. | 49.91 | 0 | 0 | 49.91 | L.S. | 7 |  |  | 7 | L.S. | 20 |  |  | 20 | L.S. | 4.12 |  |  | 4.12 | L.S. | 54.03 | 0 | 0 | 54.03 | #REF! | 4.12 |  |  | #REF! | L.S. | 54.03 |  |  | 54.03
3211127 | Books & Periodicals | 2 |  |  | 2 | L.S. | 0.28 | 0 | 0 | 0.28 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.2 |  |  | 0.2 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.33 | 0 | 0 | 0.33 | #REF! | 0.05 |  |  | #REF! | L.S. | 0.33 |  |  | 0.33
3231201 | Training Expenditure | [35 empty] | 0 | 0
| Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 238.54 |  | 238.54 | L.S. |  |  |  | 0 | [15 empty] | L.S. | [10 empty] | 0 | 0
| Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 47.81 | 350.6 |  | 398.41 | L.S. | 22.54 | 278.96 | 0 | 301.5 | L.S. |  |  |  | 0 | L.S. | 10.33 | 83.58 |  | 93.91 | L.S. |  |  |  | 0 | L.S. | 22.54 | 278.96 | 0 | 301.5 | #REF! | 0 | 0 |  | #REF! | L.S. | 22.54 | 278.96 |  | 301.5
| Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 304 | 2229.34 |  | 2533.34 | L.S. | 80.34 | 1266.29 | 0 | 1346.63 | L.S. |  |  |  | 0 | L.S. | 77.6 | 627.92 |  | 705.52 | L.S. |  |  |  | 0 | L.S. | 80.34 | 1266.29 | 0 | 1346.63 |  |  |  |  | #REF! | L.S. | 80.34 | 1266.29 |  | 1346.63
| Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 158.6 | 1163.08 |  | 1321.68 | L.S. | 35.47 | 542.73 | 0 | 578.2 | L.S. |  |  |  | 0 | L.S. | 17.12 | 138.5 |  | 155.62 | L.S. |  |  |  | 0 | L.S. | 35.47 | 542.73 | 0 | 578.2 |  |  |  |  | #REF! | L.S. | 35.47 | 542.73 |  | 578.2
3211109 | Casual labour/Job worker | 15 |  |  | 15 | L.S. | 10.96 | 0 | 0 | 10.96 | L.S. | 0.5 |  |  | 0.5 | L.S. | 3.5 |  |  | 3.5 | L.S. | 0.21 |  |  | 0.21 | L.S. | 11.17 | 0 | 0 | 11.17 | #REF! | 0.21 |  |  | #REF! | L.S. | 11.17 | 0 | 0 | 11.17
3256103 | Consumable Stores | 25 |  |  | 25 | L.S. | 3.74 | 0 | 0 | 3.74 | L.S. | 1 |  |  | 1 | L.S. | 3 |  |  | 3 | L.S. | 0 |  |  | 0 | L.S. | 3.74 | 0 | 0 | 3.74 | #REF! | 0 |  |  | #REF! | L.S. | 3.74 | 0 | 0 | 3.74
3257101 | Consultancy : International - 71 M/M National - 324 M/M |  |  | 7901.4 | 7901.4 | L.S. | 0 | 0 | 5168.01 | 5168.01 | L.S. |  |  | 558 | 558 | L.S. |  |  | 1100 | 1100 | L.S. |  |  | 237.64 | 237.64 | L.S. | 0 | 0 | 5405.65 | 5405.65 | #REF! | 237.64 |  | 237.64 |  | L.S. |  |  | 5405.65 | 5405.65
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 25 |  |  | 25 | L.S. | 12.73 | 0 | 0 | 12.73 | L.S. | 3 |  |  | 3 | L.S. | 5.5 |  |  | 5.5 | L.S. | 0.76 |  |  | 0.76 | L.S. | 13.49 | 0 | 0 | 13.49 | #REF! | 0.76 |  |  | #REF! | L.S. | 13.49 |  |  | 13.49
| b) Interim Evaluation | 10 |  |  | 10 | L.S. | 1.29 | 0 | 0 | 1.29 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0 |  |  | 0 | L.S. | 1.29 | 0 | 0 | 1.29 |  |  |  |  | #REF! | L.S. | 1.29 |  |  | 1.29
| c) Progress Monitoring | 10 |  |  | 10 | L.S. | 1.3 | 0 | 0 | 1.3 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0 |  |  | 0 | L.S. | 1.3 | 0 | 0 | 1.3 |  |  |  |  | #REF! | L.S. | 1.3 |  |  | 1.3
3257104 | Survey | 162 |  |  | 162 | L.S. | 85.02 | 0 | 0 | 85.02 | L.S. | 15 |  |  | 15 | L.S. | 50 |  |  | 50 | L.S. | 0 |  |  | 0 | L.S. | 85.02 | 0 | 0 | 85.02 | #REF! | 0 |  |  | #REF! | L.S. | 85.02 |  |  | 85.02
3255101 | Computer Consumables | 50 |  |  | 50 | L.S. | 20.47 | 0 | 0 | 20.47 | L.S. | 5 |  |  | 5 | L.S. | 10 |  |  | 10 | L.S. | 4.78 |  |  | 4.78 | L.S. | 25.25 | 0 | 0 | 25.25 | #REF! | 4.78 |  |  | #REF! | L.S. | 25.25 |  |  | 25.25
3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 |  |  | 1700 | L.S. | 875.46 | 0 | 0 | 875.46 | L.S. | 265 |  |  | 265 | L.S. | 300 |  |  | 300 | L.S. | 97.5 |  |  | 97.5 | L.S. | 972.96 | 0 | 0 | 972.96 | #REF! | 97.5 |  |  | #REF! | L.S. | 972.96 |  |  | 972.96
Repair, Maintenance & Rehabilitation
3258101 | Motor Vehicles | 100 |  |  | 100 | L.S. | 61.4 | 0 | 0 | 61.4 | L.S. | 7 |  |  | 7 | L.S. | 20 |  |  | 20 | L.S. | 2.92 |  |  | 2.92 | L.S. | 64.32 | 0 | 0 | 64.32 | #REF! | 3.07 |  |  | #REF! | L.S. | 64.32 |  |  | 64.32
3258102 | Furnitures & Fixtures | 15 |  |  | 15 | L.S. | 3.2 | 0 | 0 | 3.2 | L.S. | 0 |  |  | 0 | L.S. | 2 |  |  | 2 | L.S. | 0 |  |  | 0 | L.S. | 3.2 | 0 | 0 | 3.2 |  |  |  |  | #REF! | L.S. | 3.2 |  |  | 3.2
3258103 | Computers & office equipments | 25 |  |  | 25 | L.S. | 5.34 | 0 | 0 | 5.34 | L.S. | 1.5 |  |  | 1.5 | L.S. | 3 |  |  | 3 | L.S. | 0.02 |  |  | 0.02 | L.S. | 5.36 | 0 | 0 | 5.36 |  |  |  |  | #REF! | L.S. | 5.36 |  |  | 5.36
3258105 | Machineries & Equipments | 25 |  |  | 25 | L.S. | 1.22 | 0 | 0 | 1.22 | L.S. | 1 |  |  | 1 | L.S. | 2 |  |  | 2 | L.S. | 0.13 |  |  | 0.13 | L.S. | 1.35 | 0 | 0 | 1.35 |  |  |  |  | #REF! | L.S. | 1.35 |  |  | 1.35
3258107 | Office Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 19.98 | 0 | 0 | 19.98 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. |  |  |  | 0 | L.S. | 19.98 | 0 | 0 | 19.98 |  |  |  |  | #REF! | L.S. | 19.98 |  |  | 19.98
3258106 | Residential Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 14.53 | 0 | 0 | 14.53 | L.S. | 0 |  |  | 0 | L.S. | 5 |  |  | 5 | L.S. | 0 |  |  | 0 | L.S. | 14.53 | 0 | 0 | 14.53 |  |  |  |  | #REF! | L.S. | 14.53 |  |  | 14.53
3258105 | Engineering Equipments | 25 |  |  | 25 | L.S. | 1.39 | 0 | 0 | 1.39 | L.S. | 0 |  |  | 0 | L.S. | 2 |  |  | 2 | L.S. | 0 |  |  | 0 | L.S. | 1.39 | 0 | 0 | 1.39 |  |  |  |  | #REF! | L.S. | 1.39 |  |  | 1.39
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 43.5 | 319 |  | 362.5 | L.S. | 10.83 | 84.2 | 0 | 95.03 | L.S. | 6.1 | 50 |  | 56.1 | L.S. | 8.25 | 50 |  | 58.25 | L.S. | 0 | 0 |  | 0 | L.S. | 10.83 | 84.2 | 0 | 95.03 |  |  | 0 |  | #REF! | L.S. | 10.83 | 84.2 | 0 | 95.03
3258128 | Water Transport : Repair of Speedboat(s) | 10 |  |  | 10 | L.S. | 2.39 | 0 | 0 | 2.39 | L.S. | 0 |  |  | 0 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0 |  |  | 0 | L.S. | 2.39 | 0 | 0 | 2.39 |  |  |  |  | #REF! | L.S. | 2.39 |  |  | 2.39
3258107 | Others : Repair & Maintenance | 25 |  |  | 25 | L.S. | 7.48 | 0 | 0 | 7.48 | L.S. | 1 |  |  | 1 | L.S. | 3 |  |  | 3 | L.S. | 0 |  |  | 0 | L.S. | 7.48 | 0 | 0 | 7.48 |  |  |  |  | #REF! | L.S. | 7.48 |  |  | 7.48
| Sub-total : (a) Revenue Component: | 6572.18 | 4300.56 | 7901.4 | 18774.14 |  | 3284.66 | 2172.18 | 5168.01 | 10624.85 |  | 506.1 | 50 | 558 | 1114.1 |  | 1015 | 900 | 1100 | 3015 |  | 180.9 | 0 | 237.64 | 418.54 |  | 3465.56 | 2172.18 | 5405.65 | 11043.39 | #REF! | 418.54 | 0 | 237.64 | #REF! |  | 3465.56 | 2172.18 | 5405.65 | 11043.39
(b) Capital Component:
Acquisition of Assets:
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 |  |  | 702.5 | 9 nos. | 606.9 | 0 | 0 | 606.9 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 7 nos. | 606.9 | 0 | 0 | 606.9 | #REF! | 0 |  |  |  | 1 no. | 606.9 |  |  | 606.9
| Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 68.25 |  |  | 68.25 | 35 nos. | 50.22 | 0 | 0 | 50.22 |  |  |  |  | 0 | 10 | 18.03 |  |  | 18.03 |  |  |  |  | 0 | 33 nos. | 50.22 | 0 | 0 | 50.22 | [6 empty] | 50.22 |  |  | 50.22
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 100 |  |  | 100 | 4 nos. | 61.29 | 0 | 0 | 61.29 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4 nos. | 61.29 | 0 | 0 | 61.29 | 0 | 0 |  |  |  |  | 61.29 |  |  | 61.29
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 |  |  | 8.97 | 7 nos. | 8.95 | 0 | 0 | 8.95 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 7 nos. | 8.95 | 0 | 0 | 8.95 | #REF! | 0 |  |  |  |  | 8.95 |  |  | 8.95
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 5 |  |  | 5 | 2 nos. | 0.79 | 0 | 0 | 0.79 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2 nos. | 0.79 | 0 | 0 | 0.79 | [6 empty] | 0.79 |  |  | 0.79
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 |  |  | 20.5 | 11 nos. | 20.18 | 0 | 0 | 20.18 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 20.18 | 0 | 0 | 20.18 | #REF! | 0 |  |  |  |  | 20.18 |  |  | 20.18
| Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 |  |  | 6 | 1 no. | 2.13 | 0 | 0 | 2.13 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. | 2.13 | 0 | 0 | 2.13 | [6 empty] | 2.13 |  |  | 2.13
| Engineering Laboratory Equipments for Kishoregonj WD Division | 50 |  |  | 50 | L.S. | 9.49 | 0 | 0 | 9.49 |  | 35 |  |  | 35 | L.S. | 35 |  |  | 35 |  | 0 |  |  | 0 | L.S. | 9.49 | 0 | 0 | 9.49 | [5 empty] | L.S. | 9.49 |  |  | 9.49
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.5 |  |  | 19.5 | 30 nos. | 19.47 | 0 | 0 | 19.47 |  |  |  |  | 0 | 3 | 3.03 |  |  | 3.03 |  |  |  |  | 0 | 30 nos. | 19.47 | 0 | 0 | 19.47 | #REF! | 0 |  |  |  |  | 19.47 |  |  | 19.47
| Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 |  |  | 13.75 | 11 nos. | 9.88 | 0 | 0 | 9.88 |  |  |  |  | 0 | 3 | 3.87 |  |  | 3.87 |  |  |  |  | 0 | 11 nos. | 9.88 | 0 | 0 | 9.88 | [6 empty] | 9.88 |  |  | 9.88
| A3 Combo Printer 2 no ( PMO) | 1.5 |  |  | 1.5 | 1 no. | 0.2 | 0 | 0 | 0.2 |  |  |  |  | 0 | 1 | 1.3 |  |  | 1.3 |  |  |  |  | 0 | 1 no. | 0.2 | 0 | 0 | 0.2 | [6 empty] | 0.2 |  |  | 0.2
| Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 |  |  | 5.25 | 11 nos. | 4.08 | 0 | 0 | 4.08 |  |  |  |  | 0 | 5 | 1.17 |  |  | 1.17 |  |  |  |  | 0 | 11 nos. | 4.08 | 0 | 0 | 4.08 | [6 empty] | 4.08 |  |  | 4.08
4112314 | Furnitures & Fixtures | 50 |  |  | 50 | L.S. | 45.32 | 0 | 0 | 45.32 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | L.S. | 45.32 | 0 | 0 | 45.32 | #REF! | 0 |  |  |  | L.S. | 45.32 |  |  | 45.32
4112303 | Aircooler | 15 |  |  | 15 | 4 nos. | 9.73 | 0 | 0 | 9.73 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4 nos. | 9.73 | 0 | 0 | 9.73 | [5 empty] | L.S. | 9.73 |  |  | 9.73
| Acquisition/Purchase of lands and landed properties of Assets: | [5 empty] | 0 | 0 | 0
4141101 | Land Acquisition ( 470 hectare) | 24000 |  |  | 24000 | L.S. | 14323.6 | 0 | 0 | 14323.6 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | L.S. | 14323.6 | 0 | 0 | 14323.6 | #REF! | 0 |  |  |  | L.S. | 14323.6 |  |  | 14323.6
Construction and Works:
4111306 | Irrigation Infrastructures : | [29 empty] | #REF! | 46.96 | 41.09
4111306 | Construction of Irrigation Inlet (New Haors) | 151.32 | 1109.68 |  | 1261 |  | 16.34 | 100.38 | 0 | 116.72 | 50 (F)+25 (P) nos. | 70 | 430 |  | 500 | 50 (F)+25 (P) nos. | 70 | 430 |  | 500 | 12 nos. (Part) | 0 | 0 |  | 0 | [10 empty] | 12 nos. (Part) | 16.34 | 100.38 |  | 116.72
4111307 | Drainage Structures : | [20 empty] | 0 | 0
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 181.8 | 1333.2 |  | 1515 |  | 0 | 0 | 0 | 0 | 5 nos. (Part) | 56 | 344 |  | 400 | 5 nos. (Part) | 56 | 344 |  | 400 | 1 no. (Part) | 0 | 0 |  | 0 | [10 empty] | 1 no. (Part) | 0 | 0 |  | 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 2437.32 | 17873.68 |  | 20311 | 15 nos. (Part) | 889.49 | 5254.17 | 0 | 6143.66 | 20 (F)+40 (P) nos. | 346.5 | 2128.5 |  | 2475 | 20 (F)+40 (P) nos. | 346.5 | 2128.5 |  | 2475 | 7 nos. (Part) | 0 | 0 |  | 0 | 15 nos. (Part) | 889.49 | 5254.17 | 0 | 6143.66 | [5 empty] | 7 nos. (Part) | 889.49 | 5254.17 |  | 6143.66
4111307 | Re-excavation of Khal/River (New Haors) | 1167.48 | 8561.52 |  | 9729 | 108 Km. (Part) | 791.08 | 5220.4 | 0 | 6011.48 | 100 (F)+100 (P) Km. | 50 | 430 |  | 480 | 100 (F)+100 (P) Km. | 50 | 430 |  | 480 | 112 Km. (Part) | 0 | 0 |  | 0 | 108 Km. (Part) | 791.08 | 5220.4 | 0 | 6011.48 | [5 empty] | 112 Km. (Part) | 791.08 | 5220.4 |  | 6011.48
| Others | [20 empty] | 0 | 0
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 301.8 | 2213.2 |  | 2515 |  | 64.36 | 390.68 | 0 | 455.04 | 50 (F)+60 (P) Km. | 63 | 387 |  | 450 | 50 (F)+60 (P) Km. | 63 | 387 |  | 450 | 50 Km. (Part) | 0 | 0 |  | 0 | [10 empty] | 50 Km. (Part) | 64.36 | 390.68 |  | 455.04
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 306 | 2244 |  | 2550 |  | 63.49 | 388.97 | 0 | 452.46 | 35 (F)+30 (P) Km. | 70 | 430 |  | 500 | 35 (F)+30 (P) Km. | 70 | 430 |  | 500 | 5 Km. (Part) | 0 | 0 |  | 0 | [10 empty] | 5 Km. (Part) | 63.49 | 388.97 |  | 452.46
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 214.2 | 1570.8 |  | 1785 |  | 48.84 | 293.01 | 0 | 341.85 | 25 (F)+25 (P) Km. | 70 | 430 |  | 500 | 25 (F)+25 (P) Km. | 70 | 430 |  | 500 | 15 Km. (Part) | 0 | 0 |  | 0 | [10 empty] | 15 Km. (Part) | 48.84 | 293.01 |  | 341.85
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 1434.3 | 10518.2 |  | 11952.5 | 90 Km. (Part) | 779.02 | 5348.04 | 0 | 6127.06 | 80 (F)+110 (P) Km. | 644 | 941 |  | 1585 | 80 (F)+110 (P) Km. | 644 | 941 |  | 1585 | 90 Km. (Part) | 0 | 0 |  | 0 | 90 Km. (Part) | 779.02 | 5348.04 | 0 | 6127.06 | [5 empty] | 90 Km. (Part) | 779.02 | 5348.04 |  | 6127.06
4111201 | Rehabilitation of Regulator (New Haors) | 19.92 | 146.08 |  | 166 |  | 9.77 | 63.49 | 0 | 73.26 | 3 (F)+2 (P) nos. | 10.5 | 64.5 |  | 75 | 3 (F)+2 (P) nos. | 10.5 | 64.5 |  | 75 | 3 nos. (Part) | 0 | 0 |  | 0 | [10 empty] | 3 nos. (Part) | 9.77 | 63.49 |  | 73.26
4111201 | Construction of WMG Office | 165.6 | 1214.4 |  | 1380 |  | 5.47 | 36.62 | 0 | 42.09 | 5 (F)+5 (P) nos. | 35 | 215 |  | 250 | 5 (F)+5 (P) nos. | 35 | 215 |  | 250 | 5 nos. (Part) | 5.87 | 41.09 |  | 46.96 | [10 empty] | 5 nos. (Part) | 11.34 | 77.71 |  | 89.05
4111201 | O & M during Construction | 200 |  |  | 200
| Sub-total : (b) Capital Component: | 31645.96 | 46784.76 | 0 | 78430.72 |  | 17840.09 | 17095.76 | 0 | 34935.85 |  | 1450 | 5800 | 0 | 7250 |  | 1477.4 | 5800 | 0 | 7277.4 |  | 5.87 | 41.09 | 0 | 46.96 |  | 17845.96 | 17136.85 | 0 | 34982.81 | #REF! | 46.96 | 41.09 | 0 |  |  | 17845.96 | 17136.85 | 0 | 34982.81
| Total Cost (a+b) : | 38218.14 | 51085.32 | 7901.4 | 97204.86 |  | 21124.75 | 19267.94 | 5168.01 | 45560.7 |  | 1956.1 | 5850 | 558 | 8364.1 |  | 2492.4 | 6700 | 1100 | 10292.4 |  | 186.77 | 41.09 | 237.64 | 465.5 |  | 21311.52 | 19309.03 | 5405.65 | 46026.2 | #REF! | 465.5 | 41.09 | 237.64 |  |  | 21311.52 | 19309.03 | 5405.65 | 46026.2
| (c) Physical Contingency ( Lump sum): | 100 | 158 |  | 258
| (d) Price Contingency (Lump sum): | 100.76 | 301.38 |  | 402.14 | [27 empty] | 278.73
| Grand Total : (a)+(b)+(c)+(d): | 38418.9 | 51544.7 | 7901.4 | 97865 |  | 21124.75 | 19267.94 | 5168.01 | 45560.7 |  | 1956.1 | 5850 | 558 | 8364.1 |  | 2492.4 | 6700 | 1100 | 10292.4 |  | 186.77 | 41.09 | 237.64 | 465.5 |  | 21311.52 | 19309.03 | 5405.65 | 46026.2 | [6 empty] | 21311.52 | 19309.03 | 5405.65 | 46026.2
[22 empty] | 7.494% | 0.6133% | 21.6% | 4.523%
[6 empty] | Livelihood | 138.35 | 2087.98 | 0 | 2226.33 | [10 empty] | Livelihood | 0 | 0 | 0 | 0
[6 empty] | Ph.Work+gate | 2678.69 | 17179.96 | 0 | 19858.65 | [10 empty] | Ph.Work+gate | 5.87 | 41.09 | 0 | 46.96
[6 empty] | Proc.G | 848.63 |  |  | 848.63 | [10 empty] | Proc.G | 0 |  |  | 0

## Sheet5
| 600 | 4000 |  | 4600
| 60000000 | 400000000 | 0 | 460000000
| 60000000 | 400000000 | 0 | 460000000
khal new | 750 | 5000 |  | 5750
| 75000000 | 500000000 | 0 | 575000000
khal rehab
| 4111306 | Irrigation Infrastructures : | Gob Lakh | RPA Lakh | Total Lakh | Gob | RPA | Total
| 4111306 | Construction of Irrigation Inlet (New Haors) | 45 | 105 | 150 | 4500000 | 10500000 | 15000000
| 4111307 | Drainage Structures : |  |  |  | 0 | 0 | 0
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 75 | 450 | 525 | 7500000 | 45000000 | 52500000
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 422 | 2700 | 3122 | 42200000 | 270000000 | 312200000
| 4111307 | Re-excavation of Khal/River (New Haors) | 683.5 | 4205 | 4888.5 | 68350000 | 420500000 | 488850000
|  | Others |  |  |  | 0 | 0 | 0
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 65 | 400 | 465 | 6500000 | 40000000 | 46500000
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 65 | 400 | 465 | 6500000 | 40000000 | 46500000
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 50 | 300 | 350 | 5000000 | 30000000 | 35000000
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 275 | 1650 | 1925 | 27500000 | 165000000 | 192500000
| 4111201 | Rehabilitation of Regulator (New Haors) | 10 | 65 | 75 | 1000000 | 6500000 | 7500000
| 4111201 | Construction of WMG Office | 11 | 75 | 86 | 1100000 | 7500000 | 8600000

## Sheet6
Code | Description | Budget_Gob | Budget_RPA | Budget_DPA | Budget_Total | Exp_Gob | Exp_RPA | Exp_DPA | Exp_Total |  |  |  |  | Gob | RPA | Total
4111306 | Irrigation Inlet | 4500000 | 10500000 | 0 | 15000000 | 2496064.23 | 15332965.91 | 0 | 17829030.14 | Revise | 200 | 28 | 172 | 2800000 | 17200000 | 20000000
4111307 | Regulaor Reinstallation Rehab Haor | 7500000 | 45000000 | 0 | 52500000 | 12552.4 | 77107.6 | 0 | 89660 |  |  | 0 | 0 | 0 | 0 | 0
4111307 | Reg/CW/Bridge/Box outlet | 56000000 | 344000000 | 0 | 400000000 | 53328394.91 | 331001613.69 | 0 | 384330008.6 |  | 4000 | 560 | 3440 | 56000000 | 344000000 | 400000000
4111307 | Re-excavation of Khal New Haor | 35000000 | 215000000 | 0 | 250000000 | 28876568.93 | 184045932.56 | 0 | 212922501.49 |  | 2500 | 350 | 2150 | 35000000 | 215000000 | 250000000
4111201 | Re-excavation of Khal Rehab Haor | 6500000 | 40000000 | 0 | 46500000 | 8431016.65 | 51792742.2 | 0 | 60223758.85 | Revise | 700 | 98 | 602 | 9800000 | 60200000 | 70000000
4111201 | Full Embnk Reahab (Rehab Haor) | 46500000 | 400000 | 0 | 46500000 | 5148108.42 | 31624094.58 | 0 | 36772203 |  |  | 0 | 0 | 0 | 0 | 0
4111201 | Submersible Embnk Reahab (Rehab Haor) | 5000000 | 30000000 | 0 | 35000000 | 17907743.82 | 110004712.04 | 0 | 127912455.86 | Revise | 1300 | 182 | 1118 | 18200000 | 111800000 | 130000000
4111201 | Submersible Embnk construction | 27500000 | 165000000 | 0 | 192500000 | 33131193.3 | 202786581.28 | 0 | 235917774.58 | Revise | 2400 | 336 | 2064 | 33600000 | 206400000 | 240000000
4111201 | Regulaor Reinstallation New Haor | 1000000 | 6500000 | 0 | 7500000 | 0 | 0 | 0 | 0
4111201 | Const:WMG Office | 1100000 | 7500000 | 0 | 8600000 | 547239.29 | 3662293.71 | 0 | 4209533
[6 empty] | 149878881.95 | 930328043.57 | 0 | 1080206925.52