## Yearly_EXP
Code | Description | rindex | Unit Cost | Quantity | TotalCost | Weight | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2020-21-P | 2021-22-P
3111302 | Conveyance Allowance | 10 | 5 |  | 5 |  | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 |  |  | 0.58 | 0.42
3111327 | Overtime Allowance | 11 | 10 |  | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.63 | 0.37
3111338 | Other Allowance | 12 | 140 |  | 140 |  | 0 | 0 | 0 | 25 | 11.61 | 14 |  |  | 0.6 | 0.4
3241101 | Travel Expenses (TA & DA for PMO & PIU) | 14 | 120 |  | 120 |  | 0.991 | 11.909 | 14.98 | 17.96 | 12.7 | 14.98 |  |  | 0.62 | 0.38
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 15 | 245 |  | 245 |  | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.21 |  |  | 0.62 | 0.38
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 16 | 2596.27 |  | 2596.27 |  | 223.746 | 464.654 | 327.7 | 337.33 | 249.75 | 177.18 |  |  | 0.58 | 0.42
3211119 | Postage | 17 | 5 |  | 5 |  | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.48 |  |  | 0.58 | 0.42
3211120 | Telephones/Telegram/Teleprinter | 18 | 5 |  | 5 |  | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.07 |  |  | 0.61 | 0.39
3211117 | Telex/Fax/Internet | 19 | 5 |  | 5 |  | 0.249 | 0.001 | 0.09 | 0.05 | 0.05 | 0.1 |  |  | 0.56 | 0.44
3221104 | Registration Fee (Vehicles) | 20 | 20 |  | 20 |  | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 0.17 |  |  | 0.63 | 0.37
3211115 | Water | 21 | 5 |  | 5 |  | 0 | 0.11 | 0.23 | 0.37 | 0.4 | 0.55 |  |  | 0.61 | 0.39
3211113 | Electricity | 22 | 20 |  | 20 |  | 0.187 | 1.683 | 1.78 | 2.31 | 2.78 | 2.89 |  |  | 0.55 | 0.45
3243102 | Gas & Fuel | 23 | 100 |  | 100 |  | 0.938 | 3.692 | 3 | 4 | 5.89 | 4.02 |  |  | 0.61 | 0.39
3243101 | Petrol and Lubricant | 24 | 200 |  | 200 |  | 0.625 | 6.995 | 18.97 | 18 | 20 | 24.18 |  |  | 0.57 | 0.43
3221108 | Insurance/Bank Charges (including Vehicles) | 25 | 3 |  | 3 |  | 0.081 | 0.749 | 0.01 | 0.22 | 0.1 | 0.91 |  |  | 0.55 | 0.45
3255102 | Printing & Binding | 26 | 50 |  | 50 |  | 0.196 | 6.994 | 16.99 | 6 | 3.98 | 0.5 |  |  | 0.61 | 0.39
3255104 | Stationery, Seals & Stamps | 27 | 120 |  | 120 |  | 0.968 | 6.972 | 11.2 | 12.79 | 17.98 | 19.95 |  |  | 0.63 | 0.37
3211127 | Books & Periodicals | 28 | 2 |  | 2 |  | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 |  |  | 0.58 | 0.42
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 30 | 238.54 |  | 238.54 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.58 | 0.42
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 31 | 536.58 |  | 536.58 |  | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 22.21 |  |  | 0.6 | 0.4
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 32 | 3139.8 |  | 3139.8 |  | 0 | 0 | 199.49 | 524.89 | 622.25 | 338.12 |  |  | 0.63 | 0.37
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 33 | 1321.68 |  | 1321.68 |  | 0 | 0 | 119.7 | 224.29 | 234.21 | 82.97 |  |  | 0.55 | 0.45
3211109 | Casual labour/Job worker | 34 | 22 |  | 22 |  | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.49 |  |  | 0.62 | 0.38
3256103 | Consumable Stores | 35 | 15 |  | 15 |  | 0 | 0.99 | 0.75 | 1 | 1 | 3 |  |  | 0.58 | 0.42
3257101 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | 36 | - | 71+234 | 7901.4 |  | 849.675 | 1819.425 | 1123.15 | 689.33 | 686.43 | 450 |  |  | 0.61 | 0.39
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 37 | 30 |  | 30 |  | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 3 |  |  | 0.58 | 0.42
3111332 | b) Interim Evaluation | 38 | 10 |  | 10 |  | 0 | 0 | 0.27 | 0.25 | 0.77 | 0.41 |  |  | 0.56 | 0.44
3111332 | c) Progress Monitoring | 39 | 10 |  | 10 |  | 0 | 0 | 0.3 | 0.25 | 0.75 | 0.41 |  |  | 0.62 | 0.38
3257104 | Survey | 40 | 200 |  | 200 |  | 0 | 7.62 | 17.47 | 30 | 29.93 | 30 |  |  | 0.57 | 0.43
3255101 | Computer Consumables | 41 | 60 |  | 60 |  | 0.491 | 1.499 | 4.5 | 6.48 | 7.5 | 10 |  |  | 0.55 | 0.45
3256101 | Other Expenses: Salary of Manpower through Outsourcing | 42 | 1800 |  | 1800 |  | 0 | 84.32 | 227.97 | 263.24 | 299.93 | 299.96 |  |  | 0.57 | 0.43
3258101 | Motor Vehicles | 44 | - |  | 125 |  | 0.983 | 5.967 | 12 | 21.99 | 20.46 | 14.97 |  |  | 0.55 | 0.45
3258102 | Furnitures & Fixtures | 45 | - |  | 10 |  | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 1.11 |  |  | 0.6 | 0.4
3258103 | Computers & office equipments | 46 | - |  | 15 |  | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 |  |  | 0.59 | 0.41
3258105 | Machineries & Equipments | 47 | - |  | 10 |  | 0 | 0.21 | 0.01 | 0.5 | 0.5 | 1.99 |  |  | 0.61 | 0.39
3258107 | Office Building : Repair & Maintenance | 48 | 25 |  | 25 |  | 0 | 0 | 0 | 9.98 | 10 | 0 |  |  | 0.59 | 0.41
3258106 | Residential Building : Repair & Maintenance | 49 | - |  | 40 |  | 0 | 0 | 0 | 8.95 | 5.58 | 4.95 |  |  | 0.58 | 0.42
3258105 | Engineering Equipments | 50 | - |  | 20 |  | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 |  |  | 0.55 | 0.45
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 52 | 4.7005 | 86 | 404.24 |  | 0 | 0 | 59.7 | 24.34 | 10.99 | 33.17 |  |  | 0.63 | 0.37
3258128 | Water Transport : Repair of Speedboat(s) | 53 | - |  | 5 |  | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.38 |  |  | 0.61 | 0.39
3258107 | Others : Repair & Maintenance | 54 | - |  | 40 |  | 0 | 0 | 0 | 2.5 | 4.98 | 1.49 |  |  | 0.56 | 0.44
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 59 | 70.25 | 10 | 702.5 |  | 346.3 | 138.6 | 0 | 122 | 0 | 0 |  |  | 0.56 | 0.44
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 60 | 1.36 | 50 | 68.25 |  | 5.825 | 26.315 | 10.08 | 8 | 0 | 0 |  |  | 0.56 | 0.44
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 62 | 16.67 | 6 | 100 |  | 0 | 0 | 40.29 | 21 | 0 | 0 |  |  | 0.59 | 0.41
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 64 | 1.28 | 7 | 8.97 |  | 3.726 | 2.744 | 2.48 | 0 | 0 | 0 |  |  | 0.57 | 0.43
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 0.71 | 7 | 5 |  | 0.796 | 0 | 0 | 0 | -0.006 | 0 |  |  | 0.58 | 0.42
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 67 | 1.21 | 17 | 20.5 |  | 0 | 5.55 | 11.15 | 3.48 | 0 | 0 |  |  | 0.57 | 0.43
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 68 | 1 | 6 | 6 |  | 0 | 0 | 0 | 2.13 | 0 | 0 |  |  | 0.63 | 0.37
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 69 | 50 | L.S | 50 |  | 0 | 0 | 0 | 7.89 | 1.6 | 5 |  |  | 0.55 | 0.45
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 71 | 0.65 | 30 | 19.5 |  | 3.879 | 7.141 | 6.18 | 2.27 | 0 | 0 |  |  | 0.6 | 0.4
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 72 | 1.25 | 11 | 13.75 |  | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 |  |  | 0.62 | 0.38
4112202 | A3 Combo Printer 2 nos ( PMO) | 73 | 0.75 | 2 | 1.5 |  | 0 | 0.2 | 0 | 0 | 0 | 0 |  |  | 0.55 | 0.45
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 74 | 0.48 | 11 | 5.25 |  | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 |  |  | 0.56 | 0.44
4112314 | Furnitures & Fixtures | 75 | 50 | LS | 50 |  | 7.96 | 8.44 | 8.99 | 9.96 | 9.97 | 0 |  |  | 0.62 | 0.38
4112303 | Aircooler | 76 | 1 | 15 | 15 |  | 0 | 0 | 3.77 | 2 | 3.96 | 2.99 |  |  | 0.61 | 0.39
4141101 | Land Acquisition ( 470 hectare) | 78 | 51.06 | 470 | 24000 |  | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 1000 |  |  | 0.59 | 0.41
4111306 | Construction of Irrigation Inlet (New Haors) | 81 | 10.3379 | 117 | 1209.54 |  | 0 | 0 | 0 | 0 | 116.72 | 192.22 |  |  | 0.55 | 0.45
4111307 | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 83 | 235.1 | 5 | 1175.5 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.61 | 0.39
4111307 | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 84 | 167.5269 | 111 | 18595.49 |  | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 4075.22 |  |  | 0.61 | 0.39
4111307 | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | 85 | 30.3972 | 335.364 | 10194.13 |  | 0 | 0 | 349.16 | 840.8 | 4821.52 | 2673.22 |  |  | 0.58 | 0.42
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | 87 | 31.1812 | 108.974 | 3397.94 |  | 0 | 0 | 0 | 0 | 455.04 | 726.54 |  |  | 0.57 | 0.43
4111201 | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | 88 | 30.3298 | 67.11 | 2035.43 |  | 0 | 0 | 0 | 0 | 452.46 | 253.65 |  |  | 0.57 | 0.43
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | 89 | 28.5543 | 61.21 | 1747.81 |  | 0 | 0 | 0 | 0 | 341.85 | 179.68 |  |  | 0.63 | 0.37
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 90 | 75.1748 | 261.653 | 19669.71 |  | 0 | 0 | 336.91 | 3910 | 1880.15 | 2923.61 |  |  | 0.61 | 0.39
4111201 | Rehabilitation of Regulator (New Haors) | 91 | 22.97 | 7 | 160.79 |  | 0 | 0 | 0 | 0 | 73.26 | 0 |  |  | 0.62 | 0.38
4111201 | Embankment Slope Protection Work | 92 | 45 | 5 | 225 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.56 | 0.44
4111201 | Threshing Floor Construction | 93 | 35 | 30 | 1050 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.61 | 0.39
4111201 | Construction of WMG Office | 94 | 100 | 1 | 100 |  | 0 | 0 | 0 | 0 | 42.09 | 93.33 |  |  | 0.59 | 0.41
4111201 | O & M during Construction | 95 | 200 | L.S | 200 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.57 | 0.43
| (c) Physical Contingency ( Lump sum): | 98 | 258 |  | 258 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.63 | 0.37
| (d) Price Contingency (Lump sum): | 99 | 402.14 |  | 402.14 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.55 | 0.45

## Cum_EXP
Code | Description | rindex | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
3111302 | Conveyance Allowance |  |  | 0.3 | 0.43 | 0.71 | 1.01 | 1.51
3111327 | Overtime Allowance |  | 2019-20: 0
3111338 | Other Allowance |  | 2017-18: 25; 2018-19: 36.61; 2019-20: 50.61
3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | 0.991 | 12.9 | 27.88 | 45.84 | 58.54 | 73.54
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  |  | 16.25 | 47.6 | 82.46 | 116.67 | 150.92
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 223.746 | 688.4 | 1016.1 | 1353.43 | 1603.18 | 1962.26
3211119 | Postage |  |  | 0.05 | 0.18 | 0.4 | 0.77 | 1.27
3211120 | Telephones/Telegram/Teleprinter |  | 0.21 | 0.45 | 0.74 | 0.89 | 0.97 | 1.17
3211117 | Telex/Fax/Internet |  | 0.249 | 0.25 | 0.34 | 0.39 | 0.44 | 0.64
3221104 | Registration Fee (Vehicles) |  | 1.1 | 9.47 | 9.55 | 9.55 | 11.92 | 12.92
3211115 | Water |  |  | 0.11 | 0.34 | 0.71 | 1.11 | 1.56
3211113 | Electricity |  | 0.187 | 1.87 | 3.65 | 5.96 | 8.74 | 12.24
3243102 | Gas & Fuel |  | 0.938 | 4.63 | 7.63 | 11.63 | 17.52 | 23.52
3243101 | Petrol and Lubricant |  | 0.625 | 7.62 | 26.59 | 44.59 | 64.59 | 84.59
3221108 | Insurance/Bank Charges (including Vehicles) |  | 0.081 | 0.83 | 0.84 | 1.06 | 1.16 | 1.31
3255102 | Printing & Binding |  | 0.196 | 7.19 | 24.18 | 30.18 | 34.16 | 34.66
3255104 | Stationery, Seals & Stamps |  | 0.968 | 7.94 | 19.14 | 31.93 | 49.91 | 69.91
3211127 | Books & Periodicals |  |  | 0.1 | 0.13 | 0.18 | 0.28 | 0.48
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 2019-20: 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  |  | 9.22 | 39.08 | 125.63 | 301.5 | 497.67
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 2016-17: 199.49; 2017-18: 724.38; 2018-19: 1346.63; 2019-20: 2023.77
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 2016-17: 119.7; 2017-18: 343.99; 2018-19: 578.2; 2019-20: 824.86
3211109 | Casual labour/Job worker |  | 0.25 | 2.36 | 4.71 | 6.71 | 10.96 | 14.46
3256103 | Consumable Stores |  |  | 0.99 | 1.74 | 2.74 | 3.74 | 6.74
3257101 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) |  | 849.675 | 2669.1 | 3792.25 | 4481.58 | 5168.01 | 5668.01
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 0.4 | 1.73 | 3.23 | 7.73 | 12.73 | 17.73
3111332 | b) Interim Evaluation |  | 2016-17: 0.27; 2017-18: 0.52; 2018-19: 1.29; 2019-20: 2.29
3111332 | c) Progress Monitoring |  | 2016-17: 0.3; 2017-18: 0.55; 2018-19: 1.3; 2019-20: 2.3
3257104 | Survey |  |  | 7.62 | 25.09 | 55.09 | 85.02 | 135.02
3255101 | Computer Consumables |  | 0.491 | 1.99 | 6.49 | 12.97 | 20.47 | 30.47
3256101 | Other Expenses: Salary of Manpower through Outsourcing |  |  | 84.32 | 312.29 | 575.53 | 875.46 | 1175.46
3258101 | Motor Vehicles |  | 0.983 | 6.95 | 18.95 | 40.94 | 61.4 | 76.4
3258102 | Furnitures & Fixtures |  |  | 0.49 | 1.23 | 2.21 | 3.2 | 5.2
3258103 | Computers & office equipments |  |  | 0.5 | 1.35 | 3.35 | 5.34 | 8.34
3258105 | Machineries & Equipments |  |  | 0.21 | 0.22 | 0.72 | 1.22 | 3.22
3258107 | Office Building : Repair & Maintenance |  | 2017-18: 9.98; 2018-19: 19.98; 2019-20: 19.98
3258106 | Residential Building : Repair & Maintenance |  | 2017-18: 8.95; 2018-19: 14.53; 2019-20: 19.53
3258105 | Engineering Equipments |  |  | 0.09 | 0.39 | 0.89 | 1.39 | 3.39
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) |  | 2016-17: 59.7; 2017-18: 84.04; 2018-19: 95.03; 2019-20: 153.28
3258128 | Water Transport : Repair of Speedboat(s) |  |  | 0.9 | 0.9 | 1.65 | 2.39 | 3.14
3258107 | Others : Repair & Maintenance |  | 2017-18: 2.5; 2018-19: 7.48; 2019-20: 10.48
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. |  | 346.3 | 484.9 | 484.9 | 606.9 | 606.9 | 702.5
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). |  | 5.825 | 32.14 | 42.22 | 50.22 | 50.22 | 50.22
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) |  | 2016-17: 40.29; 2017-18: 61.29; 2018-19: 61.29; 2019-20: 61.29
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). |  | 3.726 | 6.47 | 8.95 | 8.95 | 8.95 | 8.95
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). |  | 0.796 | 0.796 | 0.796 | 0.796 | 0.796 | 0.796
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) |  |  | 5.55 | 16.7 | 20.18 | 20.18 | 20.18
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) |  | 2017-18: 2.13; 2018-19: 2.13; 2019-20: 2.13
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  | 2017-18: 7.89; 2018-19: 9.49; 2019-20: 14.49
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) |  | 3.879 | 11.02 | 17.2 | 19.47 | 19.47 | 19.47
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) |  | 3.744 | 3.744 | 6.73 | 9.88 | 9.88 | 9.88
4112202 | A3 Combo Printer 2 nos ( PMO) |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) |  | 2.97 | 3.17 | 3.17 | 4.08 | 4.08 | 4.08
4112314 | Furnitures & Fixtures |  | 7.96 | 16.4 | 25.39 | 35.35 | 45.32 | 45.32
4112303 | Aircooler |  | 2016-17: 3.77; 2017-18: 5.77; 2018-19: 9.73; 2019-20: 13.73
4141101 | Land Acquisition ( 470 hectare) |  | 2016-17: 4649.65; 2017-18: 10443.7; 2018-19: 14323.6; 2019-20: 16373.02
4111306 | Construction of Irrigation Inlet (New Haors) |  | 2018-19: 116.72; 2019-20: 607.05
4111307 | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) |  | 2019-20: 0
4111307 | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) |  | 2016-17: 293.15; 2017-18: 3067.05; 2018-19: 6143.66; 2019-20: 14249.24
4111307 | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) |  | 2016-17: 349.16; 2017-18: 1189.16; 2018-19: 6011.48; 2019-20: 9967.56
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) |  | 2018-19: 455.04; 2019-20: 1355.77
4111201 | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) |  | 2018-19: 452.46; 2019-20: 1365.72
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) |  | 2018-19: 341.85; 2019-20: 999.4
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  | 2016-17: 336.91; 2017-18: 4246.91; 2018-19: 6127.06; 2019-20: 11041.37
4111201 | Rehabilitation of Regulator (New Haors) |  | 2018-19: 73.26; 2019-20: 73.26
4111201 | Embankment Slope Protection Work |  | 2019-20: 0
4111201 | Threshing Floor Construction |  | 2019-20: 0
4111201 | Construction of WMG Office |  | 2018-19: 42.09; 2019-20: 390.23
4111201 | O & M during Construction |  | 2019-20: 0
| (c) Physical Contingency ( Lump sum): | 71 | 2019-20: 0
| (d) Price Contingency (Lump sum): | 72 | 2019-20: 0

## Detail_9_input
Code | Description | rindex | Total-cum | GoB-cum | RPA-cum | DPA-cum | Total-19-20 | GoB-19-20 | RPA-19-20 | DPA-19-20 | Total-20-21 | GoB-20-21 | RPA-20-21 | DPA-20-21 | Total-21-22 | GoB-21-22 | RPA-21-22 | DPA-21-22
3111302 | Conveyance Allowance | 11 | 1.01 | 1.01 |  |  | 0.5 | 0.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3111327 | Overtime Allowance | 12 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3111338 | Other Allowance | 13 | 36.61 | 36.61 |  |  | 14 | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3241101 | Travel Expenses (TA & DA for PMO & PIU) | 15 | 58.54 | 58.54 |  |  | 14.98 | 14.98 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 16 | 116.67 | 116.67 |  |  | 34.21 | 34.21 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 17 | 1603.18 | 1603.18 |  |  | 177.18 | 177.18 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3211119 | Postage | 18 | 0.77 | 0.77 |  |  | 0.48 | 0.48 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3211120 | Telephones/Telegram/Teleprinter | 19 | 0.97 | 0.97 |  |  | 0.07 | 0.07 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3211117 | Telex/Fax/Internet | 20 | 0.44 | 0.44 |  |  | 0.1 | 0.1 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3221104 | Registration Fee (Vehicles) | 21 | 11.92 | 11.92 |  |  | 0.17 | 0.17 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3211115 | Water | 22 | 1.11 | 1.11 |  |  | 0.55 | 0.55 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3211113 | Electricity | 23 | 8.74 | 8.74 |  |  | 2.89 | 2.89 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3243102 | Gas & Fuel | 24 | 17.52 | 17.52 |  |  | 4.02 | 4.02 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3243101 | Petrol and Lubricant | 25 | 64.59 | 64.59 |  |  | 24.18 | 24.18 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3221108 | Insurance/Bank Charges (including Vehicles) | 26 | 1.16 | 1.16 |  |  | 0.91 | 0.91 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3255102 | Printing & Binding | 27 | 34.16 | 34.16 |  |  | 0.5 | 0.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3255104 | Stationery, Seals & Stamps | 28 | 49.91 | 49.91 |  |  | 19.95 | 19.95 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3211127 | Books & Periodicals | 29 | 0.28 | 0.28 |  |  | 0.2 | 0.2 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 31 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 32 | 301.5 | 22.54 | 278.96 |  | 22.22 | 2.72 | 19.5 |  | 0 | 0 | 0 | 0 | 0 | 0
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 33 | 1346.63 | 80.34 | 1266.29 |  | 338.11 | 34.46 | 303.65 |  | 0 | 0 | 0 | 0 | 0 | 0
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 34 | 578.2 | 35.47 | 542.73 |  | 82.97 | 7.97 | 75 |  | 0 | 0 | 0 | 0 | 0 | 0
3211109 | Casual labour/Job worker | 35 | 10.96 | 10.96 |  |  | 3.49 | 3.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3256103 | Consumable Stores | 36 | 3.74 | 3.74 |  |  | 3 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3257101 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | 37 | 5168.01 | 0 |  | 5168.01 | 450 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 38 | 12.73 | 12.73 |  |  | 3 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3111332 | b) Interim Evaluation | 39 | 1.29 | 1.29 |  |  | 0.41 | 0.41 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3111332 | c) Progress Monitoring | 40 | 1.3 | 1.3 |  |  | 0.41 | 0.41 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3257104 | Survey | 41 | 85.02 | 85.02 |  |  | 30 | 30 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3255101 | Computer Consumables | 42 | 20.47 | 20.47 |  |  | 10 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3256101 | Other Expenses: Salary of Manpower through Outsourcing | 43 | 875.46 | 875.46 |  |  | 299.96 | 299.96 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258101 | Motor Vehicles | 45 | 61.4 | 61.4 |  |  | 14.97 | 14.97 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258102 | Furnitures & Fixtures | 46 | 3.2 | 3.2 |  |  | 1.11 | 1.11 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258103 | Computers & office equipments | 47 | 5.34 | 5.34 |  |  | 3 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258105 | Machineries & Equipments | 48 | 1.22 | 1.22 |  |  | 1.99 | 1.99 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258107 | Office Building : Repair & Maintenance | 49 | 19.98 | 19.98 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258106 | Residential Building : Repair & Maintenance | 50 | 14.53 | 14.53 |  |  | 4.95 | 4.95 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258105 | Engineering Equipments | 51 | 1.39 | 1.39 |  |  | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 53 | 95.03 | 10.83 | 84.2 |  | 33.17 | 4.15 | 29.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3258128 | Water Transport : Repair of Speedboat(s) | 54 | 2.39 | 2.39 |  |  | 0.38 | 0.38 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3258107 | Others : Repair & Maintenance | 55 | 7.48 | 7.48 |  |  | 1.49 | 1.49 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 60 | 606.9 | 606.9 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 61 | 50.22 | 50.22 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 63 | 61.29 | 61.29 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 8.95 | 8.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 66 | 0.796 | 0.796 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 68 | 20.18 | 20.18 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 69 | 2.13 | 2.13 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 70 | 9.49 | 9.49 |  |  | 5 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 72 | 19.47 | 19.47 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 73 | 9.88 | 9.88 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112202 | A3 Combo Printer 2 nos ( PMO) | 74 | 0.2 | 0.2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 75 | 4.08 | 4.08 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112314 | Furnitures & Fixtures | 76 | 45.32 | 45.32 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
4112303 | Aircooler | 77 | 9.73 | 9.73 |  |  | 2.99 | 2.99 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4141101 | Land Acquisition ( 470 hectare) | 79 | 14323.6 | 14323.6 |  |  | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4111306 | Construction of Irrigation Inlet (New Haors) | 82 | 116.72 | 16.34 | 100.38 |  | 192.22 | 24.03 | 168.19 |  | 0 | 0 | 0 | 0 | 0 | 0
4111307 | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 84 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111307 | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 85 | 6143.66 | 889.49 | 5254.17 |  | 4075.22 | 509.4 | 3565.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111307 | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | 86 | 6011.48 | 791.08 | 5220.4 |  | 2673.22 | 334.15 | 2339.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | 88 | 455.04 | 64.36 | 390.68 |  | 726.54 | 90.82 | 635.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | 89 | 452.46 | 63.49 | 388.97 |  | 253.65 | 31.71 | 221.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | 90 | 341.85 | 48.84 | 293.01 |  | 179.68 | 22.46 | 157.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 91 | 6127.06 | 779.02 | 5348.04 |  | 2923.61 | 365.45 | 2558.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Rehabilitation of Regulator (New Haors) | 92 | 73.26 | 9.77 | 63.49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Embankment Slope Protection Work | 93 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Threshing Floor Construction | 94 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4111201 | Construction of WMG Office | 95 | 42.09 | 5.47 | 36.62 |  | 93.33 | 11.67 | 81.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111201 | O & M during Construction | 96 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (c) Physical Contingency ( Lump sum): | 99 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (d) Price Contingency (Lump sum): | 100 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet1
Yearly Cumulative Expenditure
| GOB | RPA | DPA | TOTAL
2014-15 | 606.65 | 0 | 849.68 | 1456.29
2015-16 | 1430.9 | 9.22 | 2699.1 |  | PA | GOB | DPA | RPA
2016-17 | 6989.43 | 1271 | 3792.25 | 12052.68 | 5063.25 |  | 3792.25
2017-18 | 14811.41 | 8624.49 | 4481.58 | 27917.48 | 13106.07 |  | 4481.58
2018-19 | 21124.75 | 19267.94 | 5168.01 | 45560.7 | 24435.95 |  | 5168.01
Yearly Expenditure
| GOB | RPA | DPA | TOTAL
2014-15 | 606.65 | 0 | 849.68 | 1456.29
2015-16
2016-17
2017-18
2018-19

## Sheet2
Civil Works | Total Cost | Gob | RPA
Construction of Irrigation Inlet (New Haors) | 192.22
Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 0
Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 4075.22
Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | 2673.22
Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | 726.54
Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | 253.65
Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | 179.68
Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 2923.61
Rehabilitation of Regulator (New Haors) | 0
Embankment Slope Protection Work | 0
Threshing Floor Construction | 0
Construction of WMG Office | 93.33
O & M during Construction | 0