## 9.Detil Phasing
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2019 (Year 1 to Year-5) † | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-21 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
(a) Revenue Component:
| 4700 | Allowances
| 4765 | Conveyance Allowance |  | Part | 1.01 | 1.01 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 4769 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 4795 | Other Allowance |  |  | 36.61 | 36.61 |  | 0 | 0 |  |  |  |  | Part | 14 | 14 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
| 4800 | Supplies and services:
| 4801 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 58.54 | 58.54 |  | 0 | 0 |  |  |  |  | Part | 15 | 15 |  | 0 | 0 |  |  |  |  | Part | 28.8052 | 28.8052 |  | 0 | 0 |  |  |  |  | Part | 17.6548 | 17.6548 |  | 0 | 0
| 4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 116.67 | 116.67 |  | 0 | 0 |  |  |  |  | Part | 34.25 | 34.25 |  | 0 | 0 |  |  |  |  | Part | 58.3296 | 58.3296 |  | 0 | 0 |  |  |  |  | Part | 35.7504 | 35.7504 |  | 0 | 0
| 4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1603.18 | 1603.18 |  | 0 | 0 |  |  |  |  | Part | 359.08 | 359.08 |  | 0 | 0 |  |  |  |  | Part | 367.7258 | 367.7258 |  | 0 | 0 |  |  |  |  | Part | 266.2842 | 266.2842 |  | 0 | 0
| 4815 | Postage |  | Part | 0.77 | 0.77 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.1634 | 2.1634 |  | 0 | 0 |  |  |  |  | Part | 1.5666 | 1.5666 |  | 0 | 0
| 4816 | Telephones/Telegram/Teleprinter |  | Part | 0.97 | 0.97 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 2.3363 | 2.3363 |  | 0 | 0 |  |  |  |  | Part | 1.4937 | 1.4937 |  | 0 | 0
| 4817 | Telex/Fax/Internet |  | Part | 0.44 | 0.44 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 2.4416 | 2.4416 |  | 0 | 0 |  |  |  |  | Part | 1.9184 | 1.9184 |  | 0 | 0
| 4818 | Registration Fee (Vehicles) |  | Part | 11.92 | 11.92 |  | 0 | 0 | [5 empty] | 1 | 1 |  | 0 | 0 | [5 empty] | 4.4604 | 4.4604 |  | 0 | 0 | [5 empty] | 2.6196 | 2.6196 |  | 0 | 0
| 4819 | Water |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 0.45 | 0.45 |  | 0 | 0 |  |  |  |  | Part | 2.0984 | 2.0984 |  | 0 | 0 |  |  |  |  | Part | 1.3416 | 1.3416 |  | 0 | 0
| 4821 | Electricity |  | Part | 8.74 | 8.74 |  | 0 | 0 |  |  |  |  | Part | 3.5 | 3.5 |  | 0 | 0 |  |  |  |  | Part | 4.268 | 4.268 |  | 0 | 0 |  |  |  |  | Part | 3.492 | 3.492 |  | 0 | 0
| 4822 | Gas & Fuel |  | Part | 17.52 | 17.52 |  | 0 | 0 |  |  |  |  | Part | 6 | 6 |  | 0 | 0 |  |  |  |  | Part | 46.6528 | 46.6528 |  | 0 | 0 |  |  |  |  | Part | 29.8272 | 29.8272 |  | 0 | 0
| 4823 | Petrol and Lubricant |  | Part | 64.59 | 64.59 |  | 0 | 0 |  |  |  |  | Part | 20 | 20 |  | 0 | 0 |  |  |  |  | Part | 65.7837 | 65.7837 |  | 0 | 0 |  |  |  |  | Part | 49.6263 | 49.6263 |  | 0 | 0
| 4824 | Insurance/Bank Charges (including Vehicles) |  | Part | 1.16 | 1.16 |  | 0 | 0 |  |  |  |  | Part | 0.15 | 0.15 |  | 0 | 0 |  |  |  |  | Part | 0.9295 | 0.9295 |  | 0 | 0 | [5 empty] | 0.7605 | 0.7605 |  | 0 | 0
| 4827 | Printing & Binding |  | Part | 34.16 | 34.16 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 9.3574 | 9.3574 |  | 0 | 0 |  |  |  |  | Part | 5.9826 | 5.9826 |  | 0 | 0
| 4828 | Stationery, Seals & Stamps |  | Part | 49.91 | 49.91 |  | 0 | 0 |  |  |  |  | Part | 20 | 20 |  | 0 | 0 |  |  |  |  | Part | 31.5567 | 31.5567 |  | 0 | 0 |  |  |  |  | Part | 18.5333 | 18.5333 |  | 0 | 0
| 4831 | Books & Periodicals |  | Part | 0.28 | 0.28 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
| 4840 | Training Expenditure
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 138.3532 | 0 |  | 138.3532 | 0 | [5 empty] | 100.1868 | 0 |  | 100.1868 | 0
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 301.5 | 22.54 |  | 278.96 | 0 |  |  |  |  | Part | 196.17 | 21.0294 |  | 175.1406 | 0 |  |  |  |  | Part | 23.346 | 2.5027 |  | 20.8433 | 0 |  |  |  |  | Part | 15.564 | 1.6685 |  | 13.8955 | 0
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1346.63 | 80.34 |  | 1266.29 | 0 |  |  |  |  | Part | 677.14 | 72.5894 |  | 604.5506 | 0 |  |  |  |  | Part | 703.0989 | 75.3722 |  | 627.7267 | 0 |  |  |  |  | Part | 412.9311 | 44.2662 |  | 368.6649 | 0
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 578.2 | 35.47 |  | 542.73 | 0 |  |  |  |  | Part | 246.66 | 26.442 |  | 220.218 | 0 |  |  |  |  | Part | 273.251 | 29.2925 |  | 243.9585 | 0 |  |  |  |  | Part | 223.569 | 23.9666 |  | 199.6024 | 0
| 4851 | Casual labour/Job worker |  | Part | 10.96 | 10.96 |  | 0 | 0 |  |  |  |  | Part | 3.5 | 3.5 |  | 0 | 0 |  |  |  |  | Part | 4.6748 | 4.6748 |  | 0 | 0 |  |  |  |  | Part | 2.8652 | 2.8652 |  | 0 | 0
| 4854 | Consumable Stores |  | Part | 3.74 | 3.74 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 4874 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5168.01 | 0 |  | 0 | 5168.01 |  |  |  | MM | Part | 500 | 0 |  | 0 | 500 |  |  |  | MM | Part | 1362.3679 | 0 |  | 0 | 1362.3679 |  |  |  | MM | Part | 871.0221 | 0 |  | 0 | 871.0221
| 4883 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 12.73 | 12.73 |  | 0 | 0 |  |  |  |  | Part | 5 | 5 |  | 0 | 0 |  |  |  |  | Part | 7.1166 | 7.1166 |  | 0 | 0 |  |  |  |  | Part | 5.1534 | 5.1534 |  | 0 | 0
|  | b) Interim Evaluation |  |  | 1.29 | 1.29 |  | 0 | 0 |  |  |  |  | Part | 1 | 1 |  | 0 | 0 | [5 empty] | 4.3176 | 4.3176 |  | 0 | 0 | [5 empty] | 3.3924 | 3.3924 |  | 0 | 0
|  | c) Progress Monitoring |  |  | 1.3 | 1.3 |  | 0 | 0 |  |  |  |  | Part | 1 | 1 |  | 0 | 0 |  |  |  |  | Part | 4.774 | 4.774 |  | 0 | 0 |  |  |  |  | Part | 2.926 | 2.926 |  | 0 | 0
| 4884 | Survey |  | Part | 85.02 | 85.02 |  | 0 | 0 |  |  |  |  | Part | 50 | 50 |  | 0 | 0 |  |  |  |  | Part | 37.0386 | 37.0386 |  | 0 | 0 |  |  |  |  | Part | 27.9414 | 27.9414 |  | 0 | 0
| 4888 | Computer Consumables |  | Part | 20.47 | 20.47 |  | 0 | 0 |  |  |  |  | Part | 10 | 10 |  | 0 | 0 |  |  |  |  | Part | 16.2415 | 16.2415 |  | 0 | 0 |  |  |  |  | Part | 13.2885 | 13.2885 |  | 0 | 0
| 4899 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 875.46 | 875.46 |  | 0 | 0 |  |  |  |  | Part | 300 | 300 |  | 0 | 0 |  |  |  |  | Part | 355.9878 | 355.9878 |  | 0 | 0 |  |  |  |  | Part | 268.5522 | 268.5522 |  | 0 | 0
| 4900 | Repair, Maintenance & Rehabilitation:
| 4901 | Motor Vehicles |  | Part | 61.4 | 61.4 |  | 0 | 0 |  |  |  |  | Part | 15 | 15 |  | 0 | 0 |  |  |  |  | Part | 26.73 | 26.73 |  | 0 | 0 |  |  |  |  | Part | 21.87 | 21.87 |  | 0 | 0
| 4906 | Furnitures & Fixtures |  | Part | 3.2 | 3.2 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 2.88 | 2.88 |  | 0 | 0 |  |  |  |  | Part | 1.92 | 1.92 |  | 0 | 0
| 4911 | Computers & office equipments |  | Part | 5.34 | 5.34 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 4916 | Machineries & Equipments |  | Part | 1.22 | 1.22 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 4921 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 4923 | Residential Building : Repair & Maintenance |  |  | 14.53 | 14.53 |  | 0 | 0 |  |  |  |  | Part | 5 | 5 |  | 0 | 0 |  |  |  |  | Part | 11.8726 | 11.8726 |  | 0 | 0 |  |  |  |  | Part | 8.5974 | 8.5974 |  | 0 | 0
| 4932 | Engineering Equipments |  | Part | 1.39 | 1.39 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
| 4947 | Drainage Structures :
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 95.03 | 10.83 |  | 84.2 | 0 |  |  |  | Nos. | Part | 58.25 | 8.5744 |  | 49.6756 | 0 |  |  |  | Nos. | Part | 131.8086 | 19.4022 |  | 112.4064 | 0 | [5 empty] | 77.4114 | 11.395 |  | 66.0164 | 0
| 4976 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.39 | 2.39 |  | 0 | 0 |  |  |  | Nos. | Part | 0.75 | 0.75 |  | 0 | 0 |  |  |  | Nos. | Part | 1.1346 | 1.1346 |  | 0 | 0 |  |  |  | Nos. | Part | 0.7254 | 0.7254 |  | 0 | 0
| 4991 | Others : Repair & Maintenance |  |  | 7.48 | 7.48 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 16.5312 | 16.5312 |  | 0 | 0 |  |  |  |  | Part | 12.9888 | 12.9888 |  | 0 | 0
(a) Sub-total Revenue Component:
(b) Capital Component:
| 6800 | Acquisition of Assets:
| 6807 | Motor Vehicle :
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
|  | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 10.0968 | 10.0968 |  | 0 | 0 | [5 empty] | 7.9332 | 7.9332 |  | 0 | 0
| 6809 | Water Transport :
|  | Speed Boat with Engine and all accessories (75 hp & 4 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 22.8389 | 22.8389 |  | 0 | 0 | [5 empty] | 15.8711 | 15.8711 |  | 0 | 0
| 6813 | Mechinary & Other Equipment
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.95 | 8.95 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0.0114 | 0.0114 |  | 0 | 0 | [5 empty] | 0.0086 | 0.0086 |  | 0 | 0
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 2 nos. | 0.796 | 0.796 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 2.4418 | 2.4418 |  | 0 | 0 | [5 empty] | 1.7682 | 1.7682 |  | 0 | 0
| 6814 | Engineering Equipments
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos,RTK GPS with Base and Rover Station 1 set) | Nos. | 11 nos. | 20.18 | 20.18 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.1824 | 0.1824 |  | 0 | 0 | [5 empty] | 0.1376 | 0.1376 |  | 0 | 0
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) |  |  | 2.13 | 2.13 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 2.4381 | 2.4381 |  | 0 | 0 | [5 empty] | 1.4319 | 1.4319 |  | 0 | 0
|  | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 9.49 | 9.49 |  | 0 | 0 | [5 empty] | 5 | 5 |  | 0 | 0 | [5 empty] | 19.5305 | 19.5305 |  | 0 | 0 | [5 empty] | 15.9795 | 15.9795 |  | 0 | 0
| 6815 | Computers & Accessories
|  | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.018 | 0.018 |  | 0 | 0 | [5 empty] | 0.012 | 0.012 |  | 0 | 0
|  | Laptop Computer -16 nos (PMO 7 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No,Chief Water Management 1 No) | Nos. | 7 nos. | 9.88 | 9.88 |  | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 2.3994 | 2.3994 |  | 0 | 0 | [5 empty] | 1.4706 | 1.4706 |  | 0 | 0
|  | A3 Combo Printer 5 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 |  | 0 | 0 |  |  |  | No. | 1 no. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.715 | 0.715 |  | 0 | 0 | [5 empty] | 0.585 | 0.585 |  | 0 | 0
|  | Laser Printer- 14 nos. (PMO 9 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 |  | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.6552 | 0.6552 |  | 0 | 0 | [5 empty] | 0.5148 | 0.5148 |  | 0 | 0
| 6821 | Furnitures & Fixtures |  | Part | 45.32 | 45.32 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9016 | 2.9016 |  | 0 | 0 |  |  |  |  | Part | 1.7784 | 1.7784 |  | 0 | 0
| 6869 | Aircooler | Nos. | 4 nos. | 9.73 | 9.73 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 4 | 4 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.7747 | 0.7747 |  | 0 | 0 | [5 empty] | 0.4953 | 0.4953 |  | 0 | 0
| 6900 | Acquisition/Purchase of lands and landed properties of Assets:
| 6901 | Land Acquisition ( 470 hectare) |  |  | 14323.6 | 14323.6 |  | 0 | 0 |  |  |  | ha. | Part | 2049.42 | 2049.42 |  | 0 | 0 |  |  |  | ha. | Part | 4499.9182 | 4499.9182 |  | 0 | 0 |  |  |  | ha. |  | 3127.0618 | 3127.0618 |  | 0 | 0
| 7000 | Construction and Works:
| 7036 | Irrigation Infrastructurs :
|  | Construction of Irrigation Inlet (New Haors) |  |  | 116.72 | 16.34 |  | 100.38 | 0 | [5 empty] | 490.33 | 68.6462 |  | 421.6838 | 0 |  |  |  | Nos. | 131 | 387.5245 | 54.2534 |  | 333.2711 | 0 | [5 empty] | 317.0655 | 44.3892 |  | 272.6763 | 0
| 7041 | Drainage Structures :
|  | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 281.5882 | 39.4223 |  | 242.1659 | 0 | [5 empty] | 180.0318 | 25.2045 |  | 154.8273 | 0
|  | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 6143.66 | 889.49 |  | 5254.17 | 0 |  |  |  | Nos. | Part | 8105.58 | 1134.7812 |  | 6970.7988 | 0 |  |  |  | Nos. | Part | 3756.7582 | 525.9461 |  | 3230.8121 | 0 |  |  |  | Nos. | Part | 2401.8618 | 336.2607 |  | 2065.6011 | 0
|  | Re-excavation of Khal/River (New Haors) (Earth Volume: 68.97 Lakh cum) |  |  | 6011.48 | 791.08 |  | 5220.4 | 0 |  |  |  | Km. | Part | 3936.68 | 551.1352 |  | 3385.5448 | 0 |  |  |  | Km. | Part | 0 | 0 |  | 0 | 0 |  |  |  | Km. | Part | 0 | 0 |  | 0 | 0
| 7081 | Others:
|  | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 28.01 Lakh cum) |  |  | 455.04 | 64.36 |  | 390.68 | 0 |  |  |  | Km. | Part | 900.73 | 126.1022 |  | 774.6278 | 0 |  |  |  | Km. | Part | 1021.9302 | 143.0702 |  | 878.86 | 0 | [5 empty] | 770.9298 | 107.9302 |  | 662.9996 | 0
|  | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) |  |  | 452.46 | 63.49 |  | 388.97 | 0 |  |  |  | Km. | Part | 913.26 | 127.8564 |  | 785.4036 | 0 |  |  |  | Km. | Part | 220.1853 | 30.8259 |  | 189.3594 | 0 | [5 empty] | 166.1047 | 23.2547 |  | 142.85 | 0
|  | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 7.43 lakh cum) |  |  | 341.85 | 48.84 |  | 293.01 | 0 |  |  |  | Km. | Part | 657.55 | 92.057 |  | 565.493 | 0 |  |  |  | Km. | Part | 320.8968 | 44.9256 |  | 275.9712 | 0 | [5 empty] | 188.4632 | 26.3848 |  | 162.0784 | 0
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 25.68 lakh cum) |  |  | 6127.06 | 779.02 |  | 5348.04 | 0 |  |  |  | Km. | Part | 4650.77 | 651.1078 |  | 3999.6622 | 0 |  |  |  | Km. | Part | 0 | 0 |  | 0 | 0 |  |  |  | Km. |  | 0 | 0 |  | 0 | 0
|  | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 |  | 63.49 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 |  |  |  | Nos. |  | 50.1332 | 7.0186 |  | 43.1146 | 0 |  |  |  | Nos. |  | 30.7268 | 4.3018 |  | 26.425 | 0
|  | Embankment Slope Protection Work |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 2924.5608 | 409.4385 |  | 2515.1223 | 0 | [5 empty] | 2297.8692 | 321.7017 |  | 1976.1675 | 0
|  | Threshing Floor Construction |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 549 | 76.86 |  | 472.14 | 0 | [5 empty] | 351 | 49.14 |  | 301.86 | 0
|  | Construction of WMG Office |  |  | 42.09 | 5.47 |  | 36.62 | 0 |  |  |  | Nos. | Part | 348.14 | 48.7396 |  | 299.4004 | 0 |  |  |  | Nos. |  | 1008.7643 | 141.227 |  | 867.5373 | 0 |  |  |  | Nos. |  | 701.0057 | 98.1408 |  | 602.8649 | 0
|  | O & M during Construction |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 114 | 114 |  | 0 | 0 | [5 empty] | 86 | 86 |  | 0 | 0
(b)Sub-total Capital Component:
Total Cost (a+b) :
(c) Physical Contingency ( Lump sum): |  |  |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 162.54 | 162.54 |  | 0 | 0 | [5 empty] | 95.46 | 95.46 |  | 0 | 0
(d) Price Contingency (Lump sum): |  |  |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 221.177 | 221.177 |  | 0 | 0 | [5 empty] | 180.963 | 180.963 |  | 0 | 0
Grand Total (a+b+c+d) : |  |  |  | 16%
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17

## Annex-II
Year wise Financial and Physical Target Plan | [16 empty] | Annexure-II | [11 empty] | Annexure-II
Name of the Project : Haor Flood Management and Livelihood Improvement Project.(BWDB Part)
Name of agency/Division/Ministry: Bangladesh Water Development Board / Ministry of Water Resources
Economic Code | Economic Sub-Code (In detail) | Sub Code Description (In detail) | Total Physical & Financial Target |  |  |  |  | FY: 2014-15 (Year-1) |  |  | FY: 2015-16 (Year-2) |  |  | FY: 2016-17 (Year-3) |  |  | FY: 2017-18 (Year-4) |  |  | FY: 2018-19 (Year-5) |  |  | FY: 2019-20 (Year-6) |  |  | FY: 2020-21 (Year-7) |  |  | FY: 2021-22 (Year-8)
|  |  | Unit | Unit Cost | Quantity | Total Cost (Taka in Lac) | Weight | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical
[9 empty] | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
(a) Revenue Component:
| 3111302 |  | Item | 5 | 0 | 5 |  | 0 |  |  | 0.3 |  |  | 0.13 |  |  | 0.28 |  |  | 0.3 |  |  | 0.5 |  |  | 2.0242 |  |  | 1.4658
| 3111327 |  | Item | 10 | 0 | 10 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6.3 |  |  | 3.7
| 3111338 |  | Item | 140 | 0 | 140 |  | 0 |  |  | 0 |  |  | 0 |  |  | 25 |  |  | 11.61 |  |  | 14 |  |  | 53.634 |  |  | 35.756
| 3241101 |  | Item | 120 | 0 | 120 |  | 0.991 |  |  | 11.909 |  |  | 14.98 |  |  | 17.96 |  |  | 12.7 |  |  | 15 |  |  | 28.8052 |  |  | 17.6548
| 3211129 |  | Months | 245 | 0 | 245 |  | 0 |  |  | 16.25 |  |  | 31.35 |  |  | 34.86 |  |  | 34.21 |  |  | 34.25 |  |  | 58.3296 |  |  | 35.7504
| 3821103 |  | Item | 2596.27 | 0 | 2596.27 |  | 223.746 |  |  | 464.654 |  |  | 327.7 |  |  | 337.33 |  |  | 249.75 |  |  | 359.08 |  |  | 367.7258 |  |  | 266.2842
| 3211119 |  | Item | 5 | 0 | 5 |  | 0 |  |  | 0.05 |  |  | 0.13 |  |  | 0.22 |  |  | 0.37 |  |  | 0.5 |  |  | 2.1634 |  |  | 1.5666
| 3211120 |  | Item | 5 | 0 | 5 |  | 0.21 |  |  | 0.24 |  |  | 0.29 |  |  | 0.15 |  |  | 0.08 |  |  | 0.2 |  |  | 2.3363 |  |  | 1.4937
| 3211117 |  | Item | 5 | 0 | 5 |  | 0.249 |  |  | 0.001 |  |  | 0.09 |  |  | 0.05 |  |  | 0.05 |  |  | 0.2 |  |  | 2.4416 |  |  | 1.9184
| 3221104 |  | Item | 20 | 0 | 20 |  | 1.1 |  |  | 8.37 |  |  | 0.08 |  |  | 0 |  |  | 2.37 |  |  | 1 |  |  | 4.4604 |  |  | 2.6196
| 3211115 |  | Item | 5 | 0 | 5 |  | 0 |  |  | 0.11 |  |  | 0.23 |  |  | 0.37 |  |  | 0.4 |  |  | 0.45 |  |  | 2.0984 |  |  | 1.3416
| 3211113 |  | Item | 20 | 0 | 20 |  | 0.187 |  |  | 1.683 |  |  | 1.78 |  |  | 2.31 |  |  | 2.78 |  |  | 3.5 |  |  | 4.268 |  |  | 3.492
| 3243102 |  | Item | 100 | 0 | 100 |  | 0.938 |  |  | 3.692 |  |  | 3 |  |  | 4 |  |  | 5.89 |  |  | 6 |  |  | 46.6528 |  |  | 29.8272
| 3243101 |  | Item | 200 | 0 | 200 |  | 0.625 |  |  | 6.995 |  |  | 18.97 |  |  | 18 |  |  | 20 |  |  | 20 |  |  | 65.7837 |  |  | 49.6263
| 3221108 |  | Item | 3 | 0 | 3 |  | 0.081 |  |  | 0.749 |  |  | 0.01 |  |  | 0.22 |  |  | 0.1 |  |  | 0.15 |  |  | 0.9295 |  |  | 0.7605
| 3255102 |  | Item | 50 | 0 | 50 |  | 0.196 |  |  | 6.994 |  |  | 16.99 |  |  | 6 |  |  | 3.98 |  |  | 0.5 |  |  | 9.3574 |  |  | 5.9826
| 3255104 |  | Item | 120 | 0 | 120 |  | 0.968 |  |  | 6.972 |  |  | 11.2 |  |  | 12.79 |  |  | 17.98 |  |  | 20 |  |  | 31.5567 |  |  | 18.5333
| 3211127 |  | Item | 2 | 0 | 2 |  | 0 |  |  | 0.1 |  |  | 0.03 |  |  | 0.05 |  |  | 0.1 |  |  | 0.2 |  |  | 0.8816 |  |  | 0.6384
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | Item | 238.54 | 0 | 238.54 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 138.3532 |  |  | 100.1868
| 3231201 |  |  | 536.58 | 0 | 536.58 |  | 0 |  |  | 9.22 |  |  | 29.86 |  |  | 86.55 |  |  | 175.87 |  |  | 196.17 |  |  | 23.346 |  |  | 15.564
| 3231201 |  |  | 3139.8 | 0 | 3139.8 |  | 0 |  |  | 0 |  |  | 199.49 |  |  | 524.89 |  |  | 622.25 |  |  | 677.14 |  |  | 703.0989 |  |  | 412.9311
| 3231201 |  |  | 1321.68 | 0 | 1321.68 |  | 0 |  |  | 0 |  |  | 119.7 |  |  | 224.29 |  |  | 234.21 |  |  | 246.66 |  |  | 273.251 |  |  | 223.569
| 3211109 |  | MM | 22 | 0 | 22 |  | 0.25 |  |  | 2.11 |  |  | 2.35 |  |  | 2 |  |  | 4.25 |  |  | 3.5 |  |  | 4.6748 |  |  | 2.8652
| 3256103 |  |  | 15 | 0 | 15 |  | 0 |  |  | 0.99 |  |  | 0.75 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 4.7908 |  |  | 3.4692
| 3257101 |  | MM | - | 71+234 | 7901.4 |  | 849.675 |  |  | 1819.425 |  |  | 1123.15 |  |  | 689.33 |  |  | 686.43 |  |  | 500 |  |  | 1362.3679 |  |  | 871.0221
| 3111332 |  | item | 30 | 0 | 30 |  | 0.4 |  |  | 1.33 |  |  | 1.5 |  |  | 4.5 |  |  | 5 |  |  | 5 |  |  | 7.1166 |  |  | 5.1534
| 3111332 |  | item | 10 | 0 | 10 |  | 0 |  |  | 0 |  |  | 0.27 |  |  | 0.25 |  |  | 0.77 |  |  | 1 |  |  | 4.3176 |  |  | 3.3924
| 3111332 |  | item | 10 | 0 | 10 |  | 0 |  |  | 0 |  |  | 0.3 |  |  | 0.25 |  |  | 0.75 |  |  | 1 |  |  | 4.774 |  |  | 2.926
| 3257104 |  | item | 200 | 0 | 200 |  | 0 |  |  | 7.62 |  |  | 17.47 |  |  | 30 |  |  | 29.93 |  |  | 50 |  |  | 37.0386 |  |  | 27.9414
| 3255101 |  | item | 60 | 0 | 60 |  | 0.491 |  |  | 1.499 |  |  | 4.5 |  |  | 6.48 |  |  | 7.5 |  |  | 10 |  |  | 16.2415 |  |  | 13.2885
| 3256101 |  | item | 1800 | 0 | 1800 |  | 0 |  |  | 84.32 |  |  | 227.97 |  |  | 263.24 |  |  | 299.93 |  |  | 300 |  |  | 355.9878 |  |  | 268.5522
| 3258101 |  |  | - | 0 | 125 |  | 0.983 |  |  | 5.967 |  |  | 12 |  |  | 21.99 |  |  | 20.46 |  |  | 15 |  |  | 26.73 |  |  | 21.87
| 3258102 |  |  | - | 0 | 10 |  | 0 |  |  | 0.49 |  |  | 0.74 |  |  | 0.98 |  |  | 0.99 |  |  | 2 |  |  | 2.88 |  |  | 1.92
| 3258103 |  |  | - | 0 | 15 |  | 0 |  |  | 0.5 |  |  | 0.85 |  |  | 2 |  |  | 1.99 |  |  | 3 |  |  | 3.9294 |  |  | 2.7306
| 3258105 |  |  | - | 0 | 10 |  | 0 |  |  | 0.21 |  |  | 0.01 |  |  | 0.5 |  |  | 0.5 |  |  | 2 |  |  | 4.1358 |  |  | 2.6442
| 3258107 | Office Building : Repair & Maintenance |  | 25 | 0 | 25 |  | 0 |  |  | 0 |  |  | 0 |  |  | 9.98 |  |  | 10 |  |  | 0 |  |  | 2.9618 |  |  | 2.0582
| 3258106 | Residential Building : Repair & Maintenance |  | - | 0 | 40 |  | 0 |  |  | 0 |  |  | 0 |  |  | 8.95 |  |  | 5.58 |  |  | 5 |  |  | 11.8726 |  |  | 8.5974
| 3258105 |  |  | - | 0 | 20 |  | 0 |  |  | 0.09 |  |  | 0.3 |  |  | 0.5 |  |  | 0.5 |  |  | 2 |  |  | 9.1355 |  |  | 7.4745
Drainage Structures :
| 3258114 |  | Nos. | - | 0 | 362.5 |  | 0 |  |  | 0 |  |  | 59.7 |  |  | 24.34 |  |  | 10.99 |  |  | 58.25 |  |  | 131.8086 |  |  | 77.4114
| 3258128 |  | Nos. | - | 0 | 5 |  | 0 |  |  | 0.9 |  |  | 0 |  |  | 0.75 |  |  | 0.74 |  |  | 0.75 |  |  | 1.1346 |  |  | 0.7254
| 3258107 |  |  | - | 0 | 40 |  | 0 |  |  | 0 |  |  | 0 |  |  | 2.5 |  |  | 4.98 |  |  | 3 |  |  | 16.5312 |  |  | 12.9888
(a)Sub-total Revenue Component:
(b) Capital Component:
| 4112101 |  | Nos. | 70.25 | 10 | 702.5 |  | 346.3 |  |  | 138.6 |  |  | 0 |  |  | 122 |  |  | 0 |  |  | 95.6 |  |  | 0 |  |  | 0
| 4112101 |  | Nos. | 1.36 | 50 | 68.25 |  | 5.825 |  |  | 26.315 |  |  | 10.08 |  |  | 8 |  |  | 0 |  |  | 0 |  |  | 10.0968 |  |  | 7.9332
| 4112102 |  | Nos. | 16.67 | 6 | 100 |  | 0 |  |  | 0 |  |  | 40.29 |  |  | 21 |  |  | 0 |  |  | 0 |  |  | 22.8389 |  |  | 15.8711
| 4112316 |  | Nos. | 1.28 | 7 | 8.97 |  | 3.726 |  |  | 2.744 |  |  | 2.48 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0.0114 |  |  | 0.0086
| 4112316 |  | Nos. | 0.71 | 7 | 5 |  | 0.796 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -0.006 |  |  | 0 |  |  | 2.4418 |  |  | 1.7682
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos,RTK GPS with Base and Rover Station 1 set) | Sets | 1.21 | 17 | 20.5 |  | 0 |  |  | 5.55 |  |  | 11.15 |  |  | 3.48 |  |  | 0 |  |  | 0 |  |  | 0.1824 |  |  | 0.1376
| 4112304 |  | Nos. | 1 | 6 | 6 |  | 0 |  |  | 0 |  |  | 0 |  |  | 2.13 |  |  | 0 |  |  | 0 |  |  | 2.4381 |  |  | 1.4319
| 4112304 |  | Nos. | 50 | L.S | 50 |  | 0 |  |  | 0 |  |  | 0 |  |  | 7.89 |  |  | 1.6 |  |  | 5 |  |  | 19.5305 |  |  | 15.9795
| 4112202 |  | Nos. | 0.65 | 30 | 19.5 |  | 3.879 |  |  | 7.141 |  |  | 6.18 |  |  | 2.27 |  |  | 0 |  |  | 0 |  |  | 0.018 |  |  | 0.012
| 4112202 |  | Nos. | 1.25 | 11 | 13.75 |  | 3.744 |  |  | 0 |  |  | 2.986 |  |  | 3.15 |  |  | 0 |  |  | 0 |  |  | 2.3994 |  |  | 1.4706
| 4112202 |  | No. | 0.75 | 2 | 1.5 |  | 0 |  |  | 0.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0.715 |  |  | 0.585
| 4112202 |  | Nos. | 0.48 | 11 | 5.25 |  | 2.97 |  |  | 0.2 |  |  | 0 |  |  | 0.91 |  |  | 0 |  |  | 0 |  |  | 0.6552 |  |  | 0.5148
| 4112314 |  | item | 50 | LS | 50 |  | 7.96 |  |  | 8.44 |  |  | 8.99 |  |  | 9.96 |  |  | 9.97 |  |  | 0 |  |  | 2.9016 |  |  | 1.7784
| 4112303 |  | Nos. | 1 | 15 | 15 |  | 0 |  |  | 0 |  |  | 3.77 |  |  | 2 |  |  | 3.96 |  |  | 4 |  |  | 0.7747 |  |  | 0.4953
| 4141101 |  | ha | 51.06 | 470 | 24000 |  | 0 |  |  | 0 |  |  | 4649.65 |  |  | 5794.05 |  |  | 3879.9 |  |  | 2049.42 |  |  | 4499.9182 |  |  | 3127.0618
| 4111306 |  | Nos. | 10.0895 | 130 | 1311.64 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 116.72 |  |  | 490.33 |  |  | 387.5245 |  |  | 317.0655
| 4111307 |  | Nos. | 153.8733 | 3 | 461.62 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 281.5882 |  |  | 180.0318
| 4111307 |  | Nos. | 170.0655 | 120 | 20407.86 |  | 0 |  |  | 0 |  |  | 293.15 |  |  | 2773.9 |  |  | 3076.61 |  |  | 8105.58 |  |  | 3756.7582 |  |  | 2401.8618
| 4111307 |  | km | 29.0793 | 342.105 | 9948.16 |  | 0 |  |  | 0 |  |  | 349.16 |  |  | 840.8 |  |  | 4821.52 |  |  | 3936.68 |  |  | 0 |  |  | 0
| 4111201 |  | km | 28.8947 | 108.969 | 3148.63 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 455.04 |  |  | 900.73 |  |  | 1021.9302 |  |  | 770.9298
| 4111201 |  | km | 26.1065 | 67.11 | 1752.01 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 452.46 |  |  | 913.26 |  |  | 220.1853 |  |  | 166.1047
| 4111201 |  | km | 25.8917 | 58.272 | 1508.76 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 341.85 |  |  | 657.55 |  |  | 320.8968 |  |  | 188.4632
| 4111201 |  | km | 44.8195 | 240.472 | 10777.83 |  | 0 |  |  | 0 |  |  | 336.91 |  |  | 3910 |  |  | 1880.15 |  |  | 4650.77 |  |  | 0 |  |  | 0
| 4111201 |  | Nos. | 22.0171 | 7 | 154.12 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 73.26 |  |  | 0 |  |  | 50.1332 |  |  | 30.7268
| 4111201 | Embankment Slope Protection Work | Km | 45 | 20 | 900 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 549 |  |  | 351
| 4111201 | Threshing Floor Construction | Nos. | 35 | 60 | 2100 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 42.09 |  |  | 348.14 |  |  | 1008.7643 |  |  | 701.0057
| 4111201 |  | Nos. | 200 | L.S | 200 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 114 |  |  | 86
| 4111201 |  | item | 200 | L.S | 200 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 114 |  |  | 86
(b) Sub-total Capital Component:
|  | Total Cost (a+b) : |  | 258 | 0 | 258 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 162.54 |  |  | 95.46
|  | (c) Physical Contingency ( Lump sum): | item | 402.14 | 0 | 402.14 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 221.177 |  |  | 180.963
|  | (d) Price Contingency (Lump sum): | item | 402.14 | 0 | 402.14 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 221.177 |  |  | 180.963
Grand Total (a+b+c+d) :
# Weight of each item = |  | (Est. cost of each respective item)
(Total cost of all Physical items)
# Physical Percentage of item = |  | Quantity/number targeted in each year |  |  |  |  | x 100
Total quantity/number of respective item for whole project period
# Physical % of total Project = |  | Weight of each item x % of item

## Inves._Cost
Investment Cost
Name of the Project : |  |  | Haor Flood Management and Livelihood Improvement Project.(BWDB Part)(Revised)
Name of agency/Division/Ministry : |  |  | Bangladesh Water Development Board / Ministry of Water Resources
(In Lakh Taka)
Budget Head | Economic Code/ Sub Code | Code/Sub Code Description | Total Project Cost | Financial | [7 empty] | CF | Economic
|  |  |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8 |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8
(a) Revenue Component:
0.902
0.902
0.902
0.902
0.812
0.812
0.812
0.812
0.812
0.812
0.812
0.812
0.812
0.72
0.902
0.812
0.812
0.812
0.902
0.902
0.902
0.902
0.902
0.812
0.902
0.902
0.902
0.902
| 4884 | [10 empty] | 0.902
0.902
0.86
0.86
0.86
0.86
0.86
| 4921 | Office Building : Repair & Maintenance | [9 empty] | 0.765
| 4923 | Residential Building : Repair & Maintenance | [9 empty] | 0.765
0.86
0.812
| 4976 | Water Transport : Repair of Speedboat(s) | [9 empty] | 0.812
| 4991 | Others : Repair & Maintenance | [9 empty] | 0.902
0.68
0.68
0.68
0.812
0.812
0.68
0.68
0.68
0.812
0.812
0.812
0.812
| 6821 | [10 empty] | 0.812
| 6869 | [10 empty] | 0.812
0.902
|  | Construction of Irrigation Inlet (New Haors) | [9 empty] | 0.902 | [8 empty] | 1310 | 996.91 | 0.761 | 996.91
0.765
0.765
0.761
0.761
0.761
0.761
0.761
0.761
1.761
2.761
0.765
0.761
(b) Sub-total Capital Component:
Total Cost (a+b) :
0.765
0
Grand Total (a+b+c+d) :

## Crop. Pattern
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
PRE - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic | ML | Seed | Urea | TSP | MP
1. | Boro (L) | 47000 | 3.5 |  | 10000
2. | Boro (HYV) | 125000 | 4 |  | 11000
| Total : |  | - | - | - | -
Cropping Intensity =
|  | Total Paddy Production = |  |  |  | mt.
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
POST - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic
1. | Boro (HYV) | 280500 | 5.5 |  | 10000
| Total : |  | - | - | - | -
|  | Cropping Intensity = |  |  | %
|  | Total Paddy Production = |  |  |  | mt.
|  | Incremental Paddy Production = |  |  |  | mt.
Variable Cost of Cultivation
PRE - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day |  | 100 | 75
2. | Power Tiller | - | - | - | -
3. | Seed/Seedlings
a) | Paddy | mt. |  | 30000
b) | Wheat | mt. | 0 | 30000
d) | Mustard | mt. | 0 | 50000
4. | Fertilizers
a) | Urea | mt. |  | 8000
b) | T.S.P. | mt. |  | 22000
c) | M.P. | mt. |  | 18000
5. | Insecticide | - | - | - | - | 200
6. | Irrigation Cost | - | - | - | - | 500
| Total | - | - | - | -
POST - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day |  | 100 | 75
2. | Power Tiller | - | - | - | -
3. | Seed/Seedlings
a) | Paddy | mt. |  | 30000
b) | Wheat | mt. | 0 | 30000
c) | Onion | mt. | 0 | 50000
d) | Jute | mt. | 0 | 50000
e) | Vegetables | mt. | 0 | 20000
4. | Fertilizers
a) | Urea | mt. |  | 8000
|  | mt. | 34.61 | 22000
b) | T.S.P. | mt. |  | 22000
|  | mt. | 34.61 | 200
c) | M.P. | mt. |  | 18000
|  |  | 0 | - | -
0
5. | Insecticide | - | - | - | - | 500
6. | Irrigation Cost | - | - | - | - | 1000
| Total | - | - | -
| Incremental Farm Labour = |  |  | mandays
FIXED COST
A. | PRE - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka)
Total for the project (Lakh Taka)
(Net Area= 240578 ha.)
B. | POST - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka)
Total for the project (Lakh Taka)
(Net Area= 240578 ha.)
SUMMARY OF BENEFIT
A. | POST - PROJECT CONDITION
|  |  |  | Financial |  |  | Economic
1. | Gross Production Value
2. | Cost of cultivation
i) Variable Cost
ii) Fixed Cost
3. | Net Benefit (A1-A2)
B. | PRE - PROJECT CONDITION
1. | Gross Production Value
2. | Cost of cultivation
i) Variable Cost
ii) Fixed Cost
3. | Net Benefit (B1-B2)
C. | Net Incremental Benefit from Agriculture (A3-B3)

## FIRR
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 |  | 0 |  |  | 0
|  | 0 |  | 0 | 0
|  | 0 |  | 0 | 0
|  | 0 |  | 0 | 0
|  | 0 |  | 0
0
0
0
670
NPV @12%
All calculations are based on project period of 30 years
FIRR base case
Benefit Cost Ratio
NPV @12%

## EIRR
Computation of Internal Rate of Return
(Economic)
(In Lakh Taka)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 |  | 0 |  | 0 | 0
|  | 0 |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  | 0 |  | 0 | 0
0
0
0
|  | 604.34 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
NPV @12%
All calculations are based on project period of 30 years
EIRR base case
Benefit Cost Ratio
NPV @12%

## Revised 1st
8.0 Economic code wise comparison of cost summary between the Original DPP and proposed Revised DPP | [27 empty] | (BDT in Lakh)
Economic Code | Economic Sub-Code | Sub-Code wise component description | Original approved DPP | [8 empty] | Proposed 1st Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(a) Revenue Component:
4700 | Allowances
| 4765 | Conveyance Allowance |  | 1 Item |  | 10 | [6 empty] | 1 Item |  | 10
| 4769 | Overtime Allowance |  | 1 Item |  | 50 | [6 empty] | 1 Item |  | 10
| 4795 | Other Allowance |  | 1 Item | [8 empty] | 1 Item |  | 140
4800 | Supplies and Services
| 4801 | Travel Expenses (TA & DA for PMO & PIU) |  | 1 Item |  | 100 | [6 empty] | 1 Item |  | 100
| 4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | 1 Item |  | 378 | [6 empty] | 1 Item |  | 245
| 4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 1 Item |  | 2396.27 | [6 empty] | 1 Item |  | 2596.27
| 4815 | Postage |  | 1 Item |  | 25 | [6 empty] | 1 Item |  | 25
| 4816 | Telephones/Telegram/Teleprinter |  | 1 Item |  | 25 | [6 empty] | 1 Item |  | 25
| 4817 | Telex/Fax/Internet |  | 1 Item |  | 25 | [6 empty] | 1 Item |  | 25
| 4818 | Registration Fee (Vehicles) |  | 1 Item |  | 10 | [6 empty] | 1 Item |  | 15
| 4819 | Water |  | 1 Item |  | 10 | [6 empty] | 1 Item |  | 10
| 4821 | Electricity |  | 1 Item |  | 15 | [6 empty] | 1 Item |  | 15
| 4822 | Gas & Fuel |  | 1 Item |  | 200 | [6 empty] | 1 Item |  | 200
| 4823 | Petrol and Lubricant |  | 1 Item |  | 150 | [6 empty] | 1 Item |  | 150
| 4824 | Insurance/Bank Charges (including Vehicles) |  | 1 Item |  | 3 | [6 empty] | 1 Item |  | 3
| 4827 | Printing & Binding |  | 1 Item |  | 25 | [6 empty] | 1 Item |  | 35
| 4828 | Stationery, Seals & Stamps |  | 1 Item |  | 150 | [6 empty] | 1 Item |  | 150
| 4831 | Books & Periodicals |  | 1 Item |  | 2 | [6 empty] | 1 Item |  | 2
| 4840 | Training Expenditure
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 1 Item |  |  |  | 238.54 |  |  |  |  | 1 Item |  |  |  | 238.54
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | [5 empty] | 78 | [6 empty] | 47.81 |  | 350.6
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | [5 empty] | 1815.8 | [6 empty] | 304 |  | 2229.34
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | [5 empty] | 298 | [6 empty] | 158.6 |  | 1163.08
| 4851 | Casual labour/Job worker |  |  |  | 10 | [6 empty] | 1 Item |  | 15
| 4854 | Consumable Stores |  |  |  | 25 | [6 empty] | 1 Item |  | 25
| 4874 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | MM | 71+324 |  |  |  | 5904.6 | 1996.8 |  |  | MM | 71+324 |  |  |  |  | 7901.4
| 4883 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 1 Item |  | 25 | [6 empty] | 1 Item |  | 25
|  | b) Interim Evaluation |  | 1 Item |  | 10 | [6 empty] | 1 Item |  | 10
|  | c) Progress Monitoring |  | 1 Item |  | 10 | [6 empty] | 1 Item |  | 10
| 4886 | Survey |  | 1 Item |  | 162 | [6 empty] | 1 Item |  | 162
| 4888 | Computer Consumables |  | 1 Item |  | 50 | [6 empty] | 1 Item |  | 50
| 4899 | Other Expenses: Salary of Manpower through Outsourcing |  | 1 Item |  | 912.29 | [6 empty] | 1 Item |  | 1700
4900 | Repair, Maintenance & Rehabilitation
| 4901 | Motor Vehicles |  | L.S. |  | 100 | [6 empty] | L.S. |  | 100
| 4906 | Furnitures & Fixtures |  | L.S. |  | 15 | [6 empty] | L.S. |  | 15
| 4911 | Computers & office equipments |  | L.S. |  | 25 | [6 empty] | L.S. |  | 25
| 4916 | Machineries & Equipments |  | L.S. |  | 25 | [6 empty] | L.S. |  | 25
| 4921 | Office Building : Repair & Maintenance |  | L.S. | [8 empty] | L.S. |  | 20
| 4923 | Residential Building : Repair & Maintenance |  | L.S. | [8 empty] | L.S. |  | 20
| 4932 | Engineering Equipments |  | L.S. |  | 25 | [6 empty] | L.S. |  | 25
| 4947 | Drainage Structures :
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | 98 |  | 14.75 |  | 281 |  |  |  | Nos. | 104 |  | 43.5 |  | 319
| 4976 | Water Transport : Repair of Speedboat(s) | Nos. | 5 |  | 10 | [5 empty] | Nos. | 5 |  | 10
| 4991 | Others : Repair & Maintenance | [10 empty] | L.S. |  | 25
Sub-total : (a) Revenue Component:
Economic Code | Economic Sub-Code | Sub-Code wise component description | Original approved DPP | [8 empty] | Proposed 1st Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(b) Capital Component:
6800 | Acquisition of Assets:
| 6807 | Motor Vehicle :
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 |  | 702.5 | [5 empty] | Nos. | 10 |  | 702.5
|  | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 35 |  | 68.25 | [5 empty] | Nos. | 35 |  | 68.25
| 6809 | Water Transport :
|  | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | Nos. | 5 |  | 100 | [5 empty] | Nos. | 6 |  | 100
| 6813 | Mechinary & Other Equipment
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 |  | 8.97 | [5 empty] | Nos. | 7 |  | 8.97
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 |  | 5 | [5 empty] | Nos. | 7 |  | 5
| 6814 | Engineering Equipments
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 17 |  | 20.5 | [5 empty] | Nos. | 17 |  | 20.5
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 6 |  | 6 | [5 empty] | Nos. | 6 |  | 6
|  | Engineering Laboratory Equipments for Kishoregonj WD Division | [10 empty] | L.S. |  | 50
| 6815 | Computers & Accessories
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos. | 30 |  | 19.5 | [5 empty] | Nos. | 30 |  | 19.5
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 11 |  | 13.75 | [5 empty] | Nos. | 11 |  | 13.75
|  | A3 Combo Printer 2 no ( PMO) | Nos. | 1 |  | 1.5 | [5 empty] | Nos. | 2 |  | 1.5
|  | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 |  | 5.25 | [5 empty] | Nos. | 11 |  | 5.25
| 6821 | Furnitures & Fixtures |  | L.S. |  | 50 | [6 empty] | L.S. |  | 50
| 6869 | Aircooler |  |  |  | 15 | [5 empty] | Nos. | 15 |  | 15 | [15 empty] | Ori |  | Pro | Diff
6900 |  | Acquisition/Purchase of lands and landed properties of Assets:
| 6901 | Land Acquisition ( 408 hectare) | ha. | 408 ha. |  | 30334.2 | [5 empty] | ha. | 470 |  | 24000 | [16 empty] | 50 | 371
7000 |  | Construction and Works:
| 7036 | Irrigation Infrastructures : | [27 empty] | 46.5 | 895.5 | 161 | 1182
|  | Construction of Irrigation Inlet (New Haors) | Nos. | [8 empty] | Nos. | 131 |  | 151.32 |  | 1109.68
| 7041 | Drainage Structures : | [27 empty] | 46.5 | 895.5 | 161 | 1182
|  | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | Nos. | 5 |  | 46.5 |  | 895.5 |  |  |  | Nos. | 7 (2+5) |  | 181.8 |  | 1333.2 | [12 empty] | 978.5 | 18871.5 | 3398 | 24917
|  | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 42 |  | 978.5 |  | 18871.5 |  |  |  | Nos. | 137 (57+35+ 1+44) |  | 2437.32 |  | 17873.68 | [12 empty] | 131 | 2528 | 455 | 3337
|  | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | Km. | 266 |  | 131 |  | 2528 |  |  |  | Km | 318.2 |  | 1167.48 |  | 8561.52
| 7081 | Others | [27 empty] | 18 | 360 | 65 | 475.36
|  | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | Km. | 75.4 |  | 18 |  | 360 |  |  |  | Km | 143 |  | 301.8 |  | 2213.2 | [12 empty] | 3 | 60 | 11 | 80
|  | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | Km. | 1.55 |  | 3 |  | 60 |  |  |  | Km | 84.31 |  | 306 |  | 2244 | [12 empty] | 8.25 | 170.25 | 31 | 225
|  | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | Km. | 8.09 |  | 8.25 |  | 170.25 |  |  |  | Km | 87.03 |  | 214.2 |  | 1570.8
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km. | 342.3 |  | 726.6 |  | 14031.95 |  |  |  | Km | 263.24 |  | 1434.3 |  | 10518.2
|  | Rehabilitation of Regulator (New Haors) | Nos. | [8 empty] | Nos. | 8 |  | 19.92 |  | 146.08 | [12 empty] | 8.25 | 170.25 | 31 | 225
|  | Construction of WMG Office | Nos. | [8 empty] | Nos. | 60 |  | 165.6 |  | 1214.4 | [12 empty] | 726.6 | 14031.95 | 2526 | 18527
|  | O & M during Construction |  | L.S. | [8 empty] | L.S. |  | 200
Sub-total : (b) Capital Component:
Total Cost (a+b) :
(c) Physical Contingency ( Lump sum): |  |  |  | L.S. |  | 393.04 |  | 2464.8 | [6 empty] | 100 |  | 158
(d) Price Contingency (Lump sum): |  |  |  | L.S. |  | 1243 |  | 9451.36 | [6 empty] | 100.76 |  | 301.38
Grand Total : (a)+(b)+(c)+(d):
* DOSA, CONTASA, SAFE, IMPREST etc.
c+d
|  |  |  | Phy.Works | [8 empty] | Phy.Works | [8 empty] | Phy.Works
c+d+works
other
[9 empty] | Reh | [7 empty] | Reh
[9 empty] | New | [7 empty] | New

## Annex-IV
Annexure-IV
Revised Amortization Schedule
Name of Project |  | : Haor Flood Management & Livelihood Improvement Project (BWDB Part)
Total Investment |  | : BDT 97865.00 Lakh
Loan Portion |  | : BDT 59529.60 Lakh
Loan Period |  | : 40 Years Including 10 Uears grace Period
Trate of Investment |  | : 0.01% per annum
(Taka in Lac)
Year | Beginning Principal Amount | Yearly Fixed Amount to be Paid (Principal) | Yearly Interes to be Paid | Total Payment (Principal + Interest) | Ending Principal Balance |  | 2014-15
1 | 2 | 3 | 4 | 5= (3+4) | 6=(2-3) |  | GoB | RPA | DPA | Total
11 | 59529.6 |  |  |  |  | Rev | 231.42 |  | 849.67
12 | [5 empty] | Cap | 375.2
13 | [5 empty] | Total
14
15 | [6 empty] | 2015-16
16 | [6 empty] | GoB | RPA | DPA | Total
17 | [5 empty] | Rev | 635.09 | 9.22 | 1849.43
18 | [5 empty] | Cap | 189.19
19 | [5 empty] | Total
20 | [5 empty] | Cum
21
22
23 | [6 empty] | 2016-17
24 | [6 empty] | GoB | RPA | DPA | Total
25 | [5 empty] | Rev | 703.95 | 401.59 | 1093.15
26 | [5 empty] | Cap | 4854.6 | 860.19
27 | [5 empty] | Total
28 | [5 empty] | Cum
29
30 | [5 empty] | ADP | 2017-18
31 | [6 empty] | GoB | RPA | DPA | Total
32 | [5 empty] | Rev | 700 | 800 | 800
33 | [5 empty] | Cap | 10300 | 7400
34 | [5 empty] | Total
35
36 | [6 empty] | July2016-Mar17
37 | [6 empty] | GoB | RPA | DPA | Total
38 | [5 empty] | Rev
39 | [5 empty] | Cap
40 | [5 empty] | Total
Total
Apr2017-June17
[7 empty] | GoB | RPA | DPA | Total
Rev
Cap
Total

## 9.0 Det Ph-Fak
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 15, 2017(Year 1 + Year 2 +Part of Year 3) † | [9 empty] | FY: June 16 to 30, 2017 of 2016-2017 (Remaining Part of Year-3) | [9 empty] | FY: 2017-2018 (Year-4) | [9 empty] | FY: 2018-2019 (Year-5) | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-2021 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8) | [9 empty] | Total
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others | Cost
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA |  |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP |  |  |  |  | RPA |  | DPA
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 15 | 16 | 17 | 18 | 19 | 20 | 21
(a) Revenue Component:
| 4700 | Allowances
| 4765 | Conveyance Allowance |  | Part |  | 0.43 | [7 empty] | Part |  | 0.02 | [7 empty] | Part |  | 2.4 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 1.15 | [7 empty] | Part | [9 empty] | 10
| 4769 | Overtime Allowance | [21 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part | [9 empty] | 10
| 4795 | Other Allowance | [21 empty] | Part |  | 64 | [7 empty] | Part |  | 32 | [7 empty] | Part |  | 20 | [7 empty] | Part |  | 14 | [7 empty] | Part |  | 10 | [7 empty] | Part | [9 empty] | 150
| 4800 | Supplies and services:
| 4801 | Travel Expenses (TA & DA for PMO & PIU) |  | Part |  | 27.88 | [7 empty] | Part | 0.02 | 1.09 | [7 empty] | Part |  | 17 | [7 empty] | Part |  | 17 | [7 empty] | Part |  | 15 | [7 empty] | Part |  | 13 | [7 empty] | Part |  | 10.1 | [7 empty] | Part | [9 empty] | 100
| 4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part |  | 44.76 | [7 empty] | Part |  | 2.84 | [7 empty] | Part |  | 39.4 | [7 empty] | Part |  | 39.4 | [7 empty] | Part |  | 39.4 | [7 empty] | Part |  | 39.6 | [7 empty] | Part |  | 39.6 | [7 empty] | Part | [9 empty] | 245
| 4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part |  | 997.69 | [7 empty] | Part | 18.41 | 30.46 | [7 empty] | Part |  | 375 | [7 empty] | Part |  | 375 | [7 empty] | Part |  | 325 | [7 empty] | Part |  | 275 | [7 empty] | Part |  | 230.17 | [7 empty] | Part | [9 empty] | 2496.27
| 4815 | Postage |  | Part |  | 0.18 | [7 empty] | Part | 0.02 | 0.04 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 4.8 | [7 empty] | Part | [9 empty] | 25
| 4816 | Telephones/Telegram/Teleprinter |  | Part |  | 0.59 | [7 empty] | Part | 0.16 | 0.18 | [7 empty] | Part |  | 6 | [7 empty] | Part |  | 6 | [7 empty] | Part |  | 4.35 | [7 empty] | Part |  | 4 | [7 empty] | Part |  | 3.9 | [7 empty] | Part | [9 empty] | 25
| 4817 | Telex/Fax/Internet |  | Part |  | 0.25 | [7 empty] | Part |  | 0.1 | [7 empty] | Part |  | 6 | [7 empty] | Part |  | 6 | [7 empty] | Part |  | 4.25 | [7 empty] | Part |  | 4.2 | [7 empty] | Part |  | 4.2 | [7 empty] | Part | [9 empty] | 25
| 4818 | Registration Fee (Vehicles) |  | Part |  | 9.55 | [7 empty] | Part |  | 0.52 | [9 empty] | 2.93 | [57 empty] | 13
| 4819 | Water |  | Part |  | 0.3 | [7 empty] | Part |  | 0.06 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 1.64 | [7 empty] | Part | [9 empty] | 10
| 4821 | Electricity |  | Part |  | 3.09 | [7 empty] | Part |  | 0.88 | [7 empty] | Part |  | 3.13 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 1.9 | [7 empty] | Part | [9 empty] | 15
| 4822 | Gas & Fuel |  | Part |  | 7.63 | [9 empty] | 0.3 | [7 empty] | Part |  | 40 | [7 empty] | Part |  | 40 | [7 empty] | Part |  | 40 | [7 empty] | Part |  | 36.37 | [7 empty] | Part |  | 36 | [7 empty] | Part | [9 empty] | 200
| 4823 | Petrol and Lubricant |  | Part |  | 25.42 | [7 empty] | Part | 1.2 | 2.77 | [7 empty] | Part |  | 27 | [7 empty] | Part |  | 25 | [7 empty] | Part |  | 23.38 | [7 empty] | Part |  | 23 | [7 empty] | Part |  | 25 | [7 empty] | Part | [9 empty] | 150
| 4824 | Insurance/Bank Charges (including Vehicles) |  | Part |  | 0.83 | [7 empty] | Part |  | 0.75 | [7 empty] | Part |  | 1 | [7 empty] | Part |  | 0.42 | [47 empty] | 3
| 4827 | Printing & Binding |  | Part |  | 18.3 | [7 empty] | Part | 5.89 | 6.01 | [7 empty] | Part |  | 4 | [7 empty] | Part |  | 2.5 | [7 empty] | Part |  | 2.31 | [7 empty] | Part |  | 2 | [17 empty] | Part | [9 empty] | 35
| 4828 | Stationery, Seals & Stamps |  | Part |  | 17.43 | [7 empty] | Part | 2.51 | 2.9 | [7 empty] | Part |  | 30 | [7 empty] | Part |  | 30 | [7 empty] | Part |  | 25 | [7 empty] | Part |  | 25 | [7 empty] | Part |  | 20.06 | [7 empty] | Part | [9 empty] | 150
| 4831 | Books & Periodicals |  | Part |  | 0.11 | [7 empty] | Part | 0.02 | 0.03 | [7 empty] | Part |  | 0.35 | [7 empty] | Part |  | 0.35 | [7 empty] | Part |  | 0.35 | [7 empty] | Part |  | 0.5 | [7 empty] | Part |  | 0.32 | [7 empty] | Part | [9 empty] | 2
| 4840 | Training Expenditure
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | [25 empty] | 238.54 | [57 empty] | 238.54
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part |  |  |  | 34.72 | [5 empty] | Part |  |  |  | 4.5 | [5 empty] | Part |  | 14.45 |  | 164 | [5 empty] | Part |  | 10.85 |  | 124 | [5 empty] | Part |  | 10.85 |  | 115.4 | [5 empty] | Part |  | 21.22 |  | 207.4 | [5 empty] | Part |  | 7.85 |  | 100 | [5 empty] | Part | [9 empty] | 65.22 |  | 750.02
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme. |  | Part |  |  |  | 196.5 | [5 empty] | Part |  |  |  | 3 | [5 empty] | Part |  | 34.3 |  | 425 | [5 empty] | Part |  | 29.34 |  | 375 | [5 empty] | Part |  | 29.34 |  | 375 | [5 empty] | Part |  | 42.27 |  | 334.33 | [5 empty] | Part |  | 39.25 |  | 297.81 | [5 empty] | Part | [9 empty] | 174.5 |  | 2006.64
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme. |  | Part |  |  |  | 118 | [5 empty] | Part |  |  |  | 1.7 | [5 empty] | Part |  | 15.5 |  | 178.46 | [5 empty] | Part |  | 14.86 |  | 171 | [5 empty] | Part |  | 14.26 |  | 163.97 | [5 empty] | Part |  | 21.05 |  | 164.12 | [5 empty] | Part |  | 20.1 |  | 189.11 | [5 empty] | Part | [9 empty] | 85.77 |  | 986.36
| 4849 | Compensation (Crop etc.) | [21 empty] | Part |  | 400 | [7 empty] | Part |  | 50 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [17 empty] | 450
| 4851 | Casual labour/Job worker |  | Part |  | 3.97 | [7 empty] | Part |  | 0.74 | [7 empty] | Part |  | 1.25 | [7 empty] | Part |  | 1.25 | [7 empty] | Part |  | 1.25 | [7 empty] | Part |  | 1.05 |  | 0 | [5 empty] | Part |  | 0.49 | [7 empty] | Part | [9 empty] | 10
| 4854 | Consumable Stores |  | Part |  | 1.21 | [7 empty] | Part |  | 0.53 | [7 empty] | Part |  | 8 | [7 empty] | Part |  | 8 | [7 empty] | Part |  | 6 | [7 empty] | Part |  | 1.26 |  | 0 | [7 empty] | 0 |  | 0 | [15 empty] | 25
| 4874 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | MM | Part |  |  |  |  | 3793.31 |  |  |  | MM | Part |  |  |  |  | 5.79 |  |  |  | MM | Part |  | 0 |  |  | 900 |  |  |  | MM | Part |  |  |  |  | 1000 |  |  |  | MM | Part |  | 0 |  |  | 1000 |  |  |  | MM | Part |  | 0 |  | 0 | 1000 |  |  |  | MM | Part |  | 0 |  | 0 | 202.3 |  |  |  |  | Part | [12 empty] | 7901.4
| 4883 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part |  | 3.23 | [17 empty] | Part |  | 4.77 | [7 empty] | Part |  | 4 | [7 empty] | Part |  | 4 | [7 empty] | Part |  | 4 |  | 0 | [5 empty] | Part |  | 5 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 25
|  | b) Interim Evaluation | [11 empty] | Part |  | 0.5 | [7 empty] | Part |  | 5 | [9 empty] | 2.5 | [9 empty] | 2 | [9 empty] | 0 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 10
|  | c) Progress Monitoring | [11 empty] | Part |  | 0.5 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 | [7 empty] | Part |  | 2 |  | 0 | [5 empty] | Part |  | 1.5 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 10
| 4884 | Survey |  | Part |  | 13.86 | [7 empty] | Part |  | 13.76 | [7 empty] | Part |  | 45 | [7 empty] | Part |  | 45 | [7 empty] | Part |  | 44.38 | [9 empty] | 0 |  | 0 | [7 empty] | 0 |  | 0 | [9 empty] | 0 | [5 empty] | 162
| 4888 | Computer Consumables |  | Part |  | 6.37 | [7 empty] | Part |  | 0.12 | [7 empty] | Part |  | 10 | [7 empty] | Part |  | 10 | [7 empty] | Part |  | 10 | [7 empty] | Part |  | 8 |  | 0 | [5 empty] | Part |  | 5.51 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 50
| 4899 | Other Expenses: Salary of Manpower through Outsourcing |  | Part |  | 310.68 | [7 empty] | Part |  | 1.61 | [7 empty] | Part |  | 290 | [7 empty] | Part |  | 290 | [7 empty] | Part |  | 290 | [7 empty] | Part |  | 290 |  | 0 | [5 empty] | Part |  | 227.71 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 1700
| 4900 | Repair, Maintenance & Rehabilitation:
| 4901 | Motor Vehicles |  | Part |  | 18.84 | [7 empty] | Part |  | 0.11 | [7 empty] | Part |  | 15 | [7 empty] | Part |  | 17 | [7 empty] | Part |  | 18 | [7 empty] | Part |  | 18 |  | 0 | [5 empty] | Part |  | 13.05 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 100
| 4906 | Furnitures & Fixtures |  | Part |  | 1.11 | [7 empty] | Part |  | 0.13 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 3.76 | [9 empty] | 0 |  | 0 | [7 empty] | 0 |  | 0 | [9 empty] | 0 | [5 empty] | 15
| 4911 | Computers & office equipments |  | Part |  | 1.35 | [17 empty] | Part |  | 3 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 |  | 0 | [5 empty] | Part |  | 5.65 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 25
| 4916 | Machineries & Equipments |  | Part |  | 0.28 | [7 empty] | Part |  | 0.53 | [7 empty] | Part |  | 3 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 |  | 0 | [5 empty] | Part |  | 6.19 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 25
| 4921 | Office Building : Repair & Maintenance | [21 empty] | Part |  | 10 | [7 empty] | Part |  | 3 | [7 empty] | Part |  | 3 | [7 empty] | Part |  | 2 |  | 0 | [5 empty] | Part |  | 2 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 20
| 4923 | Residential Building : Repair & Maintenance | [21 empty] | Part |  | 10 | [7 empty] | Part |  | 3 | [7 empty] | Part |  | 3 | [7 empty] | Part |  | 2 |  | 0 | [5 empty] | Part |  | 2 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 20
| 4932 | Engineering Equipments |  | Part |  | 0.37 | [7 empty] | Part |  | 0.02 | [7 empty] | Part |  | 3 | [7 empty] | Part |  | 6 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 |  | 0 | [5 empty] | Part |  | 5.61 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | 25
| 4947 | Drainage Structures :
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part |  | 3.6 |  | 26.4 |  |  |  |  | Nos. |  |  | 3.6 |  | 26.4 |  |  |  |  | Nos. | Part |  | 32 |  | 230 |  |  |  |  | Nos. | Part |  | 7 |  | 56 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [20 empty] | 46.2 |  | 338.8
| 4976 | Water Transport : Repair of Speedboat(s) | Nos. | Part |  | 0.9 | [6 empty] | Nos. | Part |  | 0.75 | [6 empty] | Nos. | Part |  | 2 | [6 empty] | Nos. | Part |  | 2 | [6 empty] | Nos. | Part |  | 2 | [6 empty] | Nos. | Part |  | 2 |  | 0 |  |  |  |  | Nos. | Part |  | 0.35 |  | 0 | [5 empty] | Part | [9 empty] | 10
| 4991 | Others : Repair & Maintenance |  | Part | [9 empty] | Part | [9 empty] | Part |  | 10 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 5 | [7 empty] | Part |  | 3 |  | 0 | [5 empty] | Part |  | 2 |  | 0 | 0 |  |  |  |  | Part |  |  |  | 0 | 0 |  |  |  |  | 25
(a) Sub-total Revenue Component:
(b) Capital Component:
| 6800 | Acquisition of Assets:
| 6807 | Motor Vehicle :
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO and Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. (PMO 2 Nos., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No.& Deputy Chief(Extension Officer) 1 No.) | Nos. | 7 nos. |  | 484.9 | [6 empty] | Nos. | [9 empty] | Nos. | 2 nos |  | 165.1 | [57 empty] | 46.2 |  | 338.8
|  | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 26 nos |  | 35.46 | [6 empty] | Nos. | 9 nos. |  | 15.68 | [6 empty] | Nos. | - |  | 17.11 | [57 empty] | 46.2 |  | 338.8
| 6809 | Water Transport :
|  | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 2 nos. |  | 27.9 | [6 empty] | Nos. | 1 no. |  | 17.1 | [6 empty] | Nos. | 2 nos |  | 30 | [57 empty] | 46.2 |  | 338.8
| 6813 | Mechinary & Other Equipment
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. |  | 8.97 | [16 empty] | Nos. |  |  | 0 | [57 empty] | 46.2 |  | 338.8
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 2 nos. |  | 0.79 | [6 empty] | Nos. | 1 no. |  | 0.5 | [6 empty] | Nos. | 4 nos. |  | 3.71 | [57 empty] | 46.2 |  | 338.8
| 6814 | Engineering Equipments
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 9 nos. |  | 11.7 | [6 empty] | Nos. | 2 nos. |  | 5 | [6 empty] | Nos. | 6 nos. |  | 3.8 | [57 empty] | 46.2 |  | 338.8
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | [20 empty] | Nos. | 6 nos. |  | 6 | [57 empty] | 46.2 |  | 338.8
|  | Engineering Laboratory Equipment 33 Nos. | [20 empty] | Nos. | 33 nos. |  | 36 | [57 empty] | 46.2 |  | 338.8
| 6815 | Computers & Accessories
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos. | 27 nos. |  | 17.2 | [9 empty] | 0.02 | [6 empty] | Nos. | 3 nos. |  | 2.28 | [57 empty] | 46.2 |  | 338.8
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. |  | 6.75 | [16 empty] | Nos. | 4 nos. |  | 7 | [57 empty] | 46.2 |  | 338.8
|  | A3 Combo Printer 1 no ( PMO) | No. | 1 no. |  | 0.2 | [16 empty] | No. | - |  | 1.3 | [57 empty] | 46.2 |  | 338.8
|  | Laser Printer- 7 nos. (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. |  | 3.17 | [16 empty] | Nos. | - |  | 2.08 | [57 empty] | 46.2 |  | 338.8
| 6821 | Furnitures & Fixtures |  | Part |  | 21.44 | [7 empty] | Part |  | 3.96 | [7 empty] | Part |  | 10 | [7 empty] | Part |  | 4.6 | [7 empty] | Part |  | 10 | [37 empty] | 46.2 |  | 338.8
| 6869 | Aircooler |  |  |  | 0 | [7 empty] | Part |  | 4 | [7 empty] | Part |  | 6 | [7 empty] | Part |  | 5 | [47 empty] | 46.2 |  | 338.8
| 6900 | Acquisition/Purchase of lands and landed properties of Assets:
| 6901 | Land Acquisition ( 470 hectare) | ha. | Part |  | 4649 | [6 empty] | ha. | Part |  | 0.65 | [6 empty] | ha. | Part |  | 10841.26 | [6 empty] | ha. | Part |  | 4577.87 | [6 empty] | ha. |  |  | 3931.22 | [37 empty] | 46.2 |  | 338.8
| 7000 | Construction and Works:
| 7041 | Drainage Structures :
|  | Re-installation/Construction of Regulator (Rehabilitation Haors) | [20 empty] | No. | Part |  | 45 |  | 330 |  |  |  |  | No. | Part |  | 22.8 |  | 167.2 | [45 empty] | 45 |  | 330
|  | Installation/Construction of New Regulators/Causeway/Bridge (New Haors) | Nos. | Part |  | 19.69 |  | 147.93 |  |  |  |  | Nos. | Part |  | 160.31 |  | 852.07 |  |  |  |  | Nos. | Part |  | 340.88 |  | 2500 |  |  |  |  | Nos. | Part |  | 1348 |  | 9885 |  |  |  |  | Nos. | Part |  | 144.84 |  | 1382.28 | [35 empty] | 46.2 |  | 338.8
|  | Re-excavation of Khal/River (New Haors) | Km. | Part |  | 57.86 |  | 424.22 |  |  |  |  | Km. | Part |  | 72.14 |  | 425.78 |  |  |  |  | Km. | Part |  | 340 |  | 2500 |  |  |  |  | Km. | Part |  | 109.7 |  | 811.36 |  |  |  |  | Km. | Part |  | 368.54 |  | 3119.51 |  |  |  |  | Km. | Part |  | 427.32 |  | 2806.57 | [25 empty] | 46.2 |  | 338.8
|  | Construction of Pipe Sluice/Culvert (New Haors) | [30 empty] | Nos. | 45 |  | 162 |  | 1188 | [45 empty] | 46.2 |  | 338.8
|  | Construction of Irrigation Inlet (New Haors) | [30 empty] | Nos. | 131 |  | 157.2 |  | 1152.8 | [45 empty] | 46.2 |  | 338.8
| 7081 | Others: | [81 empty] | 46.2 |  | 338.8
|  | Re-excavation of Khal/River (Rehabilitation Haors) | [20 empty] | Km. | Part |  | 110 |  | 800 |  |  |  |  | Km. | Part |  | 128.32 |  | 947.68 | [45 empty] | 46.2 |  | 338.8
|  | Rehabilitation of Full Embankment (Rehabilitation Haors) | [20 empty] | Km. | Part |  | 110 |  | 800 |  |  |  |  | Km. | Part |  | 124 |  | 916 | [45 empty] | 46.2 |  | 338.8
|  | Rehabilitation of Submergible Embankment (Rehabilitation Haors) | [20 empty] | Km. | Part |  | 68 |  | 500 |  |  |  |  | Km. | Part |  | 56.56 |  | 413.44 | [45 empty] | 46.2 |  | 338.8
|  | Construction of Submersible Embankment (New Haors) | Km. | Part |  | 34.09 |  | 249.95 |  |  |  |  | Km. | Part |  | 195.91 |  | 1198.05 |  |  |  |  | Km. | Part |  | 68 |  | 700 |  |  |  |  | Km. | Part |  | 588.12 |  | 4352.88 |  |  |  |  | Km. |  |  | 379.52 |  | 3449.84 |  |  |  |  | Km. |  |  | 246.5 |  | 1417.58 |  |  |  |  | Km. |  |  | 207.7 |  | 1243.86 | [15 empty] | 46.2 |  | 338.8
|  | Rehab./Construction of Closure (New Haors) | [20 empty] | Nos. | [9 empty] | Nos. |  |  | 10.56 |  | 77.44 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [20 empty] | 46.2 |  | 338.8
|  | Rehabilitation of Regulator (New Haors) | [20 empty] | Nos. | [9 empty] | Nos. |  |  | 22.8 |  | 167.2 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [20 empty] | 46.2 |  | 338.8
|  | Construction of WMG Office | [20 empty] | Nos. | Part |  | 236 |  | 1734 |  |  |  |  | Nos. |  |  | 16 |  | 114 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [20 empty] | 46.2 |  | 338.8
|  | O & M during Construction | L.S. | [30 empty] | Part |  | 400 | [9 empty] | 400 | [9 empty] | 100 | [9 empty] | 100 | [17 empty] | 46.2 |  | 338.8
(b)Sub-total Capital Component:
Total Cost (a+b) : | [83 empty] | 175 |  | 190
(c) Physical Contingency ( Lump sum): | [35 empty] | 10 |  | 45 | [7 empty] | 15 |  | 30 | [7 empty] | 16 |  | 20 | [7 empty] | 100 |  | 15 | [15 empty] | 553.3 |  | 624.9
(d) Price Contingency (Lump sum): | [35 empty] | 44 |  | 136 | [7 empty] | 75 |  | 64 | [7 empty] | 75 |  | 50 | [7 empty] | 370.58 |  | 89.7
Grand Total (a+b+c+d) :