## Abstract
Abstract of cost of estimate for the construction of Sub mergible embankment in between km.0.00 to km. 33.520 = 19.843 km in Dakshiner Haor Sub -Project in C/W Haor flood Management and Livelihood Improvement project Under Kishoreganj W.D Division,BWDB, Kishoreganj During the Financial year 2017-18 & 2018-19 . Package No. BWDB/Kish/HFMLIP/PW-24
Sl. No: | Item no & Code | Item Description | Qnty | Unit | Unit Rate (Tk) | Amount (Tk)
(A) Submergible Embankment Dakshiner Haor in between km 0.00 to 33.520 =19843.00 km
1 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cmx38cm x75cm on cement concrete (1:2:4) base of size 50cmx50cmx7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement mortar on top (1:2), with inscription of "BWDB" with 25cm of the pillar below ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | 41 | each | 1203.77 | 49354.57
2 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | 1591 | each | 290.48 | 462153.68
3 | 16-650 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-650-10 : Embankment by Mech. Equipment; ht: 0 to 4m; 85% comp | 127830.98 | Cum | 126.32 | 16147609.394
4 | 16-410 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) direction of Engineer in charge.Earth work bymanual labour in all kinds of soil for excavation/ re-excavation of pond/ tank in layers of 150mm includingbreaking clods, dressing, profiling etc. complete with all leads and lifts as per direction of Engineer in charge. 16-410-10 : 300m to 1.00 km.(85% compaction) | 70267.335 | Cum | 346.28 | 24332172.764
5 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference ..., (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 : 0 m to 3 m height with 85% compaction. | 57563.645 | Cum | 182.93 | 10530117.58
6 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3 m neglected) for all kinds of earth work. a) 1 no lead | 35133.6675 | Pld Cum | 14.57 | 511897.535
|  | b) 2 nos lead | 35133.6675 | Two lead/ Cum | 29.14 | 1023795.071
7 | 40-650-30 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. FM : 1.0 to 1.5 | 434.42 | cum | 1070.29 | 464955.382
8 | 40-600-20 | Supplying and placing non-woven needle punched type geotextile fabric (100% polypropylene fabric, unit weight 855kg/m3 tp946 kg/m3) as filter materials of elongation at maximum force machine direction (MD) =>60% and <=100%, elongatio at maqximum force (CMD) =>40% and <=100% horizontal and vertical permeability (under 2 kn/m2 pressure) =>2 x 10E-3 m/sec.for efective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labors, equipment's etc. complete as per direction of Engineer in charge.(Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric) Mass => 300 gm/m2, thickness (Under 2 kpa pressure) =>2.00mm, EoS<=0.11mm, strip tensile strength =>15kn/m, grab strength =>850N, CBR Puncture resistance =>2200 N | 4758.4 | sqm | 190.47 | 906332.448
9 | 40-610-20 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. Well graded between 40mm to 20mm size. | 217.21 | cum | 3730.47 | 810295.389
| 40-610-30 | Well graded between 20mm to 5mm size. | 217.21 | cum | 4076.09 | 885367.509
10 | 40-140-40 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>=1.5) and Stone Chips (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm² including grading,washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. block size 40cm x 40cm x 20cm | 26412 | Nos | 381.46 | 10075121.52
| 40-140-35 | block size 40cm x 40cm x 40cm | 1300 | Nos | 740.03 | 962039
11 | 40-220-10 | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. Within 200m | 464.19 | cum | 1145.88 | 531906.037
| 40-220-20 | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. Beyond 200m | 464.19 | cum | 2027.04 | 940931.698
12 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turfgrows properly, maintaining etc. complete (measurement will be given onwell grown grass only). as per direction of Engineer in charge. | 355563.4 | Sqm | 26.17 | 9305094.178
13 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge. | 238116 | m | 4.47 | 1064378.52
14 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | 172690.935 | cum | 14.27 | 2464299.642
| Sub-Total Sub-mergiable Embankment |  |  |  |  | 81467821.917
15 | 36-150 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | 25.3838 | sqm | 909.69 | 23091.386
16 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia | 120.1807 | kg | 77.34 | 9294.778
17 | 76-115-10 | M.S Work for reinforcement with Standard deformed bar fy=276 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-115-10: 6mm dia . | 25.2384 | kg | 74.37 | 1876.978
18 | 28-200-10 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: with stone chips . | 25.3838 | cum | 11674.49 | 296342.878
19 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge | 41 | each | 47.91 | 1964.31
20 | 40-540 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >= 8.0 cm in position etc. complete as per direction of Engineer in charge. 40-450-20 : Length: >= 2.0 m to < 4.5 m. | 12403 | Nos | 131.55 | 1631614.65
21 | 40-550 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. 40-550-10 : >= 1.50 m to <= 2.0 m drive, on dry land. | 14883.6 | m | 132.94 | 1978625.784
22 | 40-560 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge. 40-560-10 : Double Walling | 39686 | m | 64.53 | 2560937.58
23 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah doubly woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. | 14882.25 | Sqm | 162.45 | 2417621.513
24 | Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge. | 1 | LS | 967050.85 | 967050.85
25 | Approved Analysis Rate | Peovide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | 120 | Day | 2497.86 | 299743.2
26 | Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | LS | 112344.1 | 112344.1
27 | Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 4 nos. of tube well and sanitation facilities by installing 6 nos. of sanitary latrines for usage of labours, Officials and others for prevailing the hygenic and healthy environment at allover the working sithe as per direction of the engineer in charge. | 1 | LS | 111148.95 | 111148.95
28 | Approved Analysis Rate | Mobilize, strengthen required land based consatruction equipment such as excavator, dump truck, chain dozer, vibro-compactor and plants such as gemetor for site electrification, digital camera for taking photographs and digital vedio camera for recording/Taking Photograph as sequences of works etc. for keeping records of the works by providing following information including transfer to site, complete for the purposes stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | LS | 92026.55 | 92026.55
29 | Approved Analysis Rate | Operate, maintain of plant and equipment such as generator for site electrification for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | LS | 110909.92 | 110909.92
30 | NSI | Environmental Monitoring through Sample Collection and analysis such as Air quality test, Surface water test, Sound Level monitoring, Traffic signs and road navigation, safety provisions with first aid and medical Assistant as per direction of engineer in charge. | 1 | LS | 250000 | 250000
| Sub-Total |  |  |  |  | 10864593.427 | 92332415.344
|  |  |  | Grand Total |  | 92332415.344
(Taka Nine crore Twenty three lakh Thirty two thousand Four hundred Fifteen point three four four only)
(Md. Shahjahan)
SAE/SO
Bhairab O&M Section
BWDB, Kishoreganj.
Certificate
Certified that The Estimate has been prepared on the basis of preliminary draft design supplied by Consultant Nippon koei Co;ltd(NK) Joint Venture with BETS-CNRS and physical condition and examined on the basis of Standard schedule of rates of Mymensingh O&M Circle, BWDB, Mymensingh effective for the year 2016-17. The items provided are fully appropriate and essentially required. The estimated amount of Tk 9,23,32,415.344 (Taka Nine crore Twenty three lakh Thirty two thousand Four hundred Fifteen point three four four ) only is recommended for sanctioned.
(Mohammad Aktaruzzaman)
Sub- Divisional Engineer
Kishoregonj O&M Sub-Division
BWDB. Kishoregonj
Certificate
Certified that The Estimate has been prepared on the basis of preliminary draft design supplied by Consultant Nippon koei Co;ltd(NK) Joint Venture with BETS-CNRS and physical condition and examined on the basis of Standard schedule of rates of Mymensingh O&M Circle, BWDB, Mymensingh effective for the year 2016-17. The items provided are fully appropriate and essentially required. The estimated amount of Tk 9,23,32,415.344 (Taka Nine crore Twenty three lakh Thirty two thousand Four hundred Fifteen point three four four ) only is recommended for sanctioned.
(Md. Shafiqul Islam)
Executive Engineer
Kishoreganj WD Division
BWDB, Kishoreganj.

## Detailed
Detailed estimate for the construction of Sub mergible embankment in between from km 0.00 to km. 33.520 = 19.843 km in Dakshiner Haor Sub -Project in C/W Haor flood Management and Livelihood Improvement project Under Kishoreganj W.D Division,BWDB, Kishoreganj During the Financial year 2017-18 & 2018-19 . Package No. BWDB/Kish/HFMLIP/PW-24
Sl. No: | Item no & Code | Item Description | Measurement | [9 empty] | Quantity | Unit
(A) Submergible Embankment Dakshiner Haor in between km 0.00 to 33.520 =19843.00 km
1 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cmx38cm x75cm on cement concrete (1:2:4) base of size 50cmx50cmx7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement mortar on top (1:2), with inscription of "BWDB" with 25cm of the pillar below ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | = | 19843 |  |  | / | 500 | + | 1 | = | 41 | 41 | Nos
2 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. |  | 50 m interval & Four (4)
Nos Each Section
|  |  | = | 19843 |  |  | / | 50 | + | 1 | = | 397.86
|  |  | = | 397.86 |  |  | x | 4 | = | 1591 |  | Nos | 1591 | Nos
3 | 16-650 | Earth work by Mechanical Excavator (Long Boom) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-650-10 : Embankment by Mech. Equipment; ht: 0 to 4m; 85% comp
Total Calculated Earth
|  |  | = | 214238.23 |  |  | cum
(Attached Calculation)
Resectioning Km 0.240 to km 2.242
[9 empty] | = | 2002 |  | m
|  |  | = | 16016.35 |  |  | cum
At km 10.475 & 10.85
|  |  | = | 25407.38 |  |  | cum
(Attached Calculation)
Total Earth Volume
[5 empty] | = | 255661.96 |  |  |  | cum
Earth work by Mechanical Excavator
|  |  | = | 50 | % | of Total Earth
[5 empty] | = | 0.5 | x | 255661.96 |  |  | cum
[5 empty] | = | 127830.98 |  |  |  | cum |  |  | 127830.98 | cum
4 | 16-410 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) direction of Engineer in charge.Earth work bymanual labour in all kinds of soil for excavation/ re-excavation of pond/ tank in layers of 150mm includingbreaking clods, dressing, profiling etc. complete with all leads and lifts as per direction of Engineer in charge. 16-410-10 : 300m to 1.00 km.(85% compaction)
Total Calculated Earth
|  |  | = | 230254.58 |  |  |  | cum
(Attached Calculation)
Earth work by carried earth
|  |  | = | 25 | % | of Total Earth
|  |  |  | = | 0.25 |  | x | 230254.58 |  |  | cum
[5 empty] | = | 57563.645 |  |  |  | cum |  |  | 70267.335 | cum
At km 10.475 & 10.85
|  |  | = | 25407.38 |  |  | cum
(Attached Calculation)
|  |  | = | 50 | % | of Total Earth
|  |  |  | = | 0.5 |  | x | 25407.38 |  |  | cum
[5 empty] | = | 12703.69 |  |  |  | cum
|  |  | Total Earth Volume= | [6 empty] | 70267.335
5 | 16-120-20 | Earth work by manual labour in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference ..., (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 : 0 m to 3 m height with 85% compaction.
Total Calculated Earth
|  |  | = | 230254.58 |  |  | cum
(Attached Calculation)
Earth work by manual labour
|  |  | = | 25 | % | of Total Earth
|  |  |  | = | 0.25 |  | x | 230254.58 |  |  | cum
[5 empty] | = | 57563.645 |  |  |  | cum |  |  | 57563.645 | cum
6 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3 m neglected) for all kinds of earth work. | Lead Calculation for carried earth
for 50% of carried earth
|  |  | = | (0.5 |  | * top of borrow pit +0.50
filling +dead lead-15 )/30.0
|  |  | = | 1.9167 | ~ | 2 |  | Nos |  |  |  |  | 35133.6675 | Two lead/ Cum
|  |  | 1 no lead for 50% of carried earth | [9 empty] | 35133.6675 | Pld Cum
12 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turfgrows properly, maintaining etc. complete (measurement will be given onwell grown grass only). as per direction of Engineer in charge.
Length of Embankment
|  |  | = | 19843 |  |  | m
Total Turf
|  |  | Slope |  | = | 19843 |  |  | x | 8.9 | x | 2
[5 empty] | = | 353205.4 |  |  |  | sqm |  |  | 355563.4 | sqm
[5 empty] | = | 131 |  |  | x | 9 | x | 2
[5 empty] | = | 2358 |  |  |  | sqm
|  |  | Total |  | = | 355563.4 |  |  |  | sqm
13 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge. (6 Rows Each Side)
6 Rows Each Side
|  |  | = | 6 | x | 2 | x | 19843
[7 empty] | = | 238116 |  |  | m |  | 238116 | m
14 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. |  | 75% of total earth volume
[5 empty] | = | 75 | % | 230254.58 |  |  | cum |  | 172690.935 | cum
[5 empty] | = | 172690.935 |  |  | cum
15 | 36-150 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props
Nos of post,
[5 empty] | = | 19843 |  |  | + | 1 | = | 20.843
1000
Suttering
[5 empty] | = | 22 | x | 0.25 | = | 0.78571 |  | m
7
|  |  | Area Of Suttering | [5 empty] | H=(m) |  | 1.55
[5 empty] | = | 20.843 | x | 0.78571 | x | 1.55
[5 empty] | = | 25.3838 |  | sqm |  |  |  |  | 25.3838 | sqm
16 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia
D-10- 6Nos (Vertical)
|  |  |  | = |  | 20.843 | x | 6 | x | 1.55
|  |  |  | = | 193.8399 |  |  | m
|  |  |  | = | 193.8399 |  | x | 0.62
|  |  |  | = | 120.1807 |  |  | kg |  |  |  |  | 120.1807 | kg
17 | 76-115-10 | M.S Work for reinforcement with Standard deformed bar fy=276 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-115-10: 6mm dia .
D-6- 8Nos (Stirrups)
Each ring length=0.688 m
[5 empty] | = | 20.843 | x | 8 | x | 0.688
[5 empty] | = | 114.7199 |  | m
[5 empty] | = | 114.7199 | x | 0.22
[5 empty] | = | 25.2384 |  | kg |  |  |  |  | 25.2384 | kg
18 | 28-200-10 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: with stone chips .
Volume of RCC
[5 empty] | = | 20.843 | X | 22 | X | 0.25 | X | 1.55
7
[5 empty] | = | 25.3838 |  | cum |  |  |  |  | 25.3838 | cum
19 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge |  |  | 500 M C/C
Nos OF Pillar,
[5 empty] | = | 19843 |  |  | + | 1
500
[5 empty] | = | 40.686 | Nos | [5 empty] | 40.686 | Nos
20 | 40-540 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >= 8.0 cm in position etc. complete as per direction of Engineer in charge. 40-450-20 : Length: >= 2.0 m to < 4.5 m. | 50 % of total Length,
[5 empty] | = | 19843 |  |  | x | 0.5
[5 empty] | = | 9921.5 |  |  | m
|  |  |  | Spacing, |  |  | = | 0.8 | m |  |  |  | 12403 | Nos
Nos of Bamboo pin,
[5 empty] | = | 9921.5 |  |  | + | 1 | = | 12403
[6 empty] | 0.8 | [5 empty] | Nos
21 | 40-550 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. 40-550-10 : >= 1.50 m to <= 2.0 m drive, on dry land. |  | driving barrack bamboo pins
|  |  |  | H | = | 1.5 |  | m
[5 empty] | = | 12403 |  |  | x | 1.2 |  |  | 14883.6 | m
[5 empty] | = | 14883.6 |  |  | m
22 | 40-560 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge. 40-560-10 : Double Walling |  | Two Line Both side of pins,
half split walling pieces
[5 empty] | = | 9921.5 |  |  | x | 2 | x | 2 | 39686 | m
[5 empty] | = | 39686 |  |  | m
23 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah doubly woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. |  | fixing single layer tarjah
|  |  |  | doubly woven |  |  |  |  | Width=(m) |  |  | 1.5
[5 empty] | = | 9921.5 |  |  | x | 1.5
[5 empty] | = | 14882.25 |  |  | sqm |  |  |  | 14882.25 | sqm
24 | Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
25 | Approved Analysis Rate | Peovide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge.
[5 empty] | = | 120 |  | days |  |  |  |  | 120 | days
26 | Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
27 | Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 4 nos. of tube well and sanitation facilities by installing 6 nos. of sanitary latrines for usage of labours, Officials and others for prevailing the hygenic and healthy environment at allover the working sithe as per direction of the engineer in charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
28 | Approved Analysis Rate | Mobilize, strengthen required land based consatruction equipment such as excavator, dump truck, chain dozer, vibro-compactor and plants such as gemetor for site electrification, digital camera for taking photographs and digital vedio camera for recording/Taking Photograph as sequences of works etc. for keeping records of the works by providing following information including transfer to site, complete for the purposes stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
29 | Approved Analysis Rate | Operate, maintain of plant and equipment such as generator for site electrification for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
30 | NSI | Environmental Monitoring through Sample Collection and analysis such as Air quality test, Surface water test, Sound Level monitoring, Traffic signs and road navigation, safety provisions with first aid and medical Assistant as per direction of engineer in charge. |  |  |  | 1 |  | item |  |  |  |  | 1 | item

## Closure Details
Sl. No: | Item no & Code | Item Description | Measurement | [11 empty] | Quantity | Unit
Closure
7 | 40-650-30 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. FM : 1.0 to 1.5
[5 empty] | At km 10.475 | [8 empty] | cum
Average Slope Length
[7 empty] | = | 14.3 |  |  |  | m
Working length
[6 empty] | = | 14.3 | + | 0.8 |  |  | m
[6 empty] | = | 15.1 |  | m
|  |  | Filter thickness= |  |  |  |  | 0.1
Volume of filter
|  |  | = | 15.1 |  | x | 45 | x | 0.1 |  |  | x
[8 empty] | x | 2 |  |  | = | 135.9
[5 empty] | At km 10.85 | [8 empty] | cum
Average Slope Length
[7 empty] | = | 16.76 |  |  |  | m
Working length
[6 empty] | = | 16.76 | + | 0.8 |  |  | m
[6 empty] | = | 17.56 |  | m
|  |  | Filter thickness= |  |  |  |  | 0.1
Volume of filter
|  |  | = | 17.56 |  | x | 85 | x | 0.1 |  |  | x
[8 empty] | x | 2 |  |  | = | 298.52
[8 empty] | Total = |  |  |  |  | 434.42 | cum | 434.42 | cum
8 | 40-600-20 | Supplying and placing non-woven needle punched type geotextile fabric as filter materials of elongation >=40%, horizontal and vertical permeability (under 2 kn/m2 pressure) =2x10E-3m/sec. For effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropeline or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geo-textile material from UV ray and from any other damages including supply of all materials, labours, equipments etc. complete as per direction of Engineer in charge. (Geo-textile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals accross the body of the fabric). Mass => 250gm/m2, thickness (Under 2kpa pressure) =>2.00mm, EoS<=0.11mm, strip tensile strength=>15kn/m, grab strength => 850N, CBR puncture resistance => 2200N.
At km 10.475
Average Slope Length
[7 empty] | = | 14.28 |  |  |  | m
Working slope length
|  |  |  | = | 14.28 | + | 1.4 | + | 1 |  |  | m
[6 empty] | = | 16.68 |  | m
Filter area,
|  |  | = | 16.68 |  | x | 45 | x | 2 |  |  | = | 1501.2 | sqm
At km 10.85
Average Slope Length
[7 empty] | = | 16.76 |  |  |  | m
Working slope length
|  |  |  | = | 16.76 | + | 1.4 | + | 1 |  |  | m
[6 empty] | = | 19.16 |  | m
Filter area,
|  |  | = | 19.16 |  | x | 85 | x | 2 |  |  | = | 3257.2 | sqm
[8 empty] | Total = |  |  |  |  | 4758.4 | sqm | 4758.4 | sqm
9 (A) | 40-610-20 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. Well graded between 40mm to 20mm size. | Quantity same as item No 05
At km 10.475
[8 empty] | Quantity |  |  |  | = | 135.9 | cum
At km 10.85
[8 empty] | Quantity |  |  |  | = | 298.52 | cum
[7 empty] | Total |  |  |  | cum | = | 434.42 | cum
|  |  | = | 434.42 |  | x | 0.5 | = | 217.21
[9 empty] | cum | [5 empty] | 217.21 | cum
9 (B) | 40-610-30 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. Well graded between 20mm to 5mm size. (Combination of sub-item 10 and 30 or 20 and 30 shall be used) | Quantity same as item No 05
[7 empty] | Total |  |  |  | cum | = | 434.42 | cum
|  |  | 50% of total quantity | [6 empty] | m
|  |  | = | 434.42 |  | x | 0.5 | = | 217.21
[15 empty] | 217.21 | cum
10 (A) | 40-140-40 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>= 1.5) and stone chips (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. block size 40cm x 40cm x 20cm
At km 10.475
Average Slope Length
[7 empty] | = | 14.3 |  |  |  | m
Working slope length
[6 empty] | = | 14.3 | + | 1.2 |  |  | m
[6 empty] | = | 15.5 |  | m
area,
|  |  | = | 15.5 |  | x | 45 | x | 2
[6 empty] | = | 1395 |  | sqm
Block = 40cm x40 cm x20 cm
Nos of Block
[6 empty] | = | 1395
[7 empty] | 0.4 | x | 0.4
[6 empty] | = | 8718.75 |  | Nos |  |  |  | 8719 | Nos
At km 10.850
Average Slope Length
[7 empty] | = | 16.76 |  |  |  | m
Working slope length
[6 empty] | = | 16.76 | + | 1.2 |  |  | m
[6 empty] | = | 17.96 |  | m
area,
|  |  | = | 17.96 |  | x | 85 | x | 2
[6 empty] | = | 3053.2 |  | sqm
Block = 40cm x40 cm x20 cm
Nos of Block
[6 empty] | = | 3053.2
[7 empty] | 0.4 | x | 0.4
[6 empty] | = | 19082.5 |  | Nos |  |  |  | 19083 | Nos
[7 empty] | Total |  |  |  |  | = | 27802 | Nos
|  |  | 5% deduct for gap, | [8 empty] | - | 1390.1
[7 empty] | Net Quantity = | [5 empty] | 26412 | Nos | 26412 | Nos
10 (b) | 40-140-35 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>= 1.5) and stone chips (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. block size 40cm x 40cm x 40cm
At km 10.475
|  |  | Length |  |  | = | 45 | x | 2
[7 empty] | = | 90 |  |  |  | m
Nos of Block
[6 empty] | = | 90 |  | x |  |  | 2
0.4
[6 empty] | = | 450 |  | Nos |  |  |  | 450 | Nos
At km 10.85
|  |  | Length |  |  | = | 85 | x | 2
[7 empty] | = | 170 |  |  |  | m
Nos of Block
[6 empty] | = | 170 |  | x |  |  | 2
0.4
[6 empty] | = | 850 |  | Nos |  |  |  | 850 | Nos
[7 empty] | Total |  |  |  |  | = | 1300 | Nos | 1300 | Nos
11 (a) | 40-220-10 | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. Within 200m
Block 40 cm x40 cm x 20 cm
Nos of block
[5 empty] | = | 26412 |  |  | Nos
50% of Total Block
[5 empty] | = | 13206 |  |  | Nos
Volume
|  |  | = | 13206 |  | x | 0.4 | x | 0.4
[6 empty] | x | 0.2 | = | 422.592 |  |  |  | 422.592 | cum
Block 40 cm x40 cm x 40 cm
Nos of block
[5 empty] | = | 1300 |  |  | Nos
50% of Total Block
[5 empty] | = | 650 |  |  | Nos
Volume
|  |  | = | 650 |  | x | 0.4 | x | 0.4
[6 empty] | x | 0.4 | = | 41.6 |  |  |  | 41.6 | cum
[7 empty] | Total |  |  |  |  | = | 464.192 | cum | 464.192 | cum
11 (b) | 40-220-20 | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. Beyond 200m
Block 40 cm x40 cm x 20 cm
Nos of block
[5 empty] | = | 26412 |  |  | Nos
50% of Total Block
[5 empty] | = | 13206 |  |  | Nos
Volume
|  |  | = | 13206 |  | x | 0.4 | x | 0.4
[6 empty] | x | 0.2 | = | 422.592 |  |  |  | 422.592 | cum
Block 40 cm x40 cm x 40 cm
Nos of block
[5 empty] | = | 1300 |  |  | Nos
50% of Total Block
[5 empty] | = | 650 |  |  | Nos
Volume
|  |  | = | 650 |  | x | 0.4 | x | 0.4
[6 empty] | x | 0.4 | = | 41.6 |  |  |  | 41.6 | cum
[7 empty] | Total |  |  |  |  | = | 464.192 | cum | 464.192 | cum