## Sudhi Causeway
Details Estimate for construction Sudhi khal Causeway (4.00m) at km 33.30 of Boro haor in C/W Haor Flood Management & Livlihood Improvement Project under Kishoregonj WD Division during the financial year 2017-18 & 2018-19
Sl No | Code No | Item Description |  |  | Detail measurement | [8 empty] | Quantity | Unit
106 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cm x 38cm x 75cm on cement concrete (1:2:4) base of size 50cm x 50cm x 7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement morter on top (1:2), with inscription of "BWDB" with 25cm of the pillar balow ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. |  |  | 2 | x | 2 | + | 1 | = | 5 |  |  | 5 | Nos. | 1203.77 | 6018.85
107 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials form entire site and removing soil upto 15cm depth including uprooting stumps, jungle clearing, levelling dressing etc. complete as per direction of Engineer in charge. |  |  |  |  | 100 | x | 90 | = | 9000 |  | Sqm | 9000 | Sqm. | 27.72 | 249480
108 | 12-120 | Installation of pizeometer including supply of 40mm G.I. pipe, brass strainer, socket, labour, by wash boring, lowering, fixing the elevation and providing cover on the top of the well etc. complete as per direction of Engineer in charge. | [11 empty] | 6 | Nos.
[5 empty] | C/S = |  | 3 | x | 1 | = | 3 | nos.
[5 empty] | R/S |  | 3 | x | 1 | = | 3 | nos. |  |  |  | 2584.22 | 15505.32
[5 empty] | Total |  |  |  |  | = | 6 | nos.
109 | 16-310 | Earth work in excavation of foundation trenches in all kinds of soils as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. 16-310-10: For moving spoil earth upto a distance of 100m from the centre of the pit. |  |  | Barrel Portion | [9 empty] | Cum
[5 empty] | 1 | x | 4.3 | x | 10.6 | + | 20.6 | x | 2.5 | 167.7
2
C/S. & R/S Apron slope portion
|  |  | 2 | x | 10.8 | x{( | 10.6 | + | 20.6 | )+
2
[6 empty] | ( | 14.3 | + | 24.9 | x | 2.5 | = | 950.4 | 950.4
2
|  |  | R/W |  | 4 | x | 5.6 | x | 8.25 | + | 18.25 | x | 2.5 | 742
2
|  |  | Sheet pile key |  | 2 | x | 19.5 | x | 0.9 | + | 1.2 | x | 0.375 | 15.3563
2
C/S & R/S Loose Apron:
[5 empty] | 2 | x | 10.3 | x | 9.6 | + | 19.6 | x | 2 | 601.52
2
[11 empty] | Total |  |  | 2476.9763 |  | 246.71 | 611094.8106
110 | 16-560 | Shoring for slope protection of foundation trench, canal, embankment, road, pond etc. as per design slopes, grades including removal of spoils to a safe distance as per direction of Engineer in charge. 16-560-20: By bamboo post of 6.0m length, 60mm to 80mm dia, 20cm c/c driven 2.0m below ground, with drum sheet walling and average 70mm dia half split bamboo batten @ 2.0m c/c fixed with nails. |  |  | Shoring for local Bullah post | [8 empty] | 290.8 | Sqm.
|  |  | R/S. &C/S | = | 2 | x | 25.5 | x | 2 |  |  | = | 102
|  |  |  | = | 2 | x | 36 | x | 2 |  |  | = | 144
|  |  | R/W side | = | 4 | x | 5.6 | x | 2 |  |  | = | 44.8 |  |  | 837.15 | 243443.22
[11 empty] | Total = |  | 290.8
111 | 12-310 | Bailing out of water with all leads and lifts by manual labour or pump, with all arrengements for protection of ring bund and side slopes of foundation pit against erosion or washout etc. complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge. 12-310-20 :by pump. |  |  | 1 cusec pump 2 nos. 50 days 5 hrs. per day. | [8 empty] | 50971.2862 | cum | 6.13 | 312453.9843
[5 empty] | 50 | x | 5 | x | 2 | x | 60 | x | 60
[6 empty] | ÷ | 35.314 |  |  |  |  | = | 50971.2862
112 | 44-240 | Supplying at site U-shape hot rolled steel sheet piles of different sections of Phosphorus=0.04%(Max), Sulphur = 0.04% (Max), Copper = 0.5% (Min), Tensile strength=> 490 N/mm2, Yield strength => 296 N/mm2, Ellongation = 15% (Min) including all taxes, freights, incidental charges etc. complete as per direction of Engineer in charge. 44-240-30 : U-shape, hot- rolled steel sheet pile width= 400 mm to 600 mm: height=> 100mm, Th.=> 10.5: wt. p;er sqm of pile wall of pile wall =>120 kg/m2: sectional modulus per one meter of pile wall width => 874 cm3/m | [11 empty] | 14.112 | MT. | 145120.53 | 2047940.9194
Total Sheet pile
|  |  | R/S | = | 19.5 | ÷ | 0.4 | = | 48.75 | = | 48.75 | nos
|  |  | C/S | = | 19.5 | ÷ | 0.4 | = | 48.75 | = | 48.75 | nos
[9 empty] | Total | = | 97.5 | nos.
|  |  | Weight= |  | 98 | x | 3 | x | 0.4 | x | 120 | = | 14.112
MT
113 | 44-320 | Cutting of steel sheet piles to design and length and shape as per requirement in design and drawing and as per direction of Engineer in charge. 44-320-10: Upto 10mm thick. |  |  | Total Sheet pile | [8 empty] | 66.64
|  |  | R/S | = | 19.5 | ÷ | 0.4 | = | 48.75 | = | 48.75 | nos
|  |  | C/S | = | 19.5 | ÷ | 0.4 | = | 48.75 | = | 48.75 | nos
[9 empty] | Total | = | 97.5 | nos.
[7 empty] | 98 | x | 0.68 | = |  |  | 66.64 |  | M | 39.16 | 2609.6224
114 | 12-300 | Construction of sump well with dug holes of size 1.80m x 2.0m, laying in position the perforated empty diesel/petrol drum sheet of 1.00m dia to a depth 1.5m having slot area of 1000 sq.cm/sqm, slot dia being 30mm each with supply of necessary shrouding materials comprising of 60% 40mm down graded khoa and 40% coarse sand of FM>=2.50 and placing those around and beneath the drum sheet having thickness of 40cm and 50cm respectively including necessary welding, fitting etc. complete as per direction of Engineer in charge. |  |  | C/S | = | 5 |  | nos. |  |  |  |  | 10 | Nos. | 17211.17 | 172111.7
[5 empty] | R/S | = | 5 |  | nos.
[6 empty] | = | 10 |  | nos.
115 | 44-270 | Driving steel sheet piles of various sections and weights of any type of soil, by monkey hammer including handling and placing in position, staging and supplying of all equipments like monkey hammer, pully, rope, bamboo, bullah etc. including correcting leaning beyond tolerance & other defects and any other incidental cost etc. complete (measurement will be taken on projected width x height) as per direction of Engineer in charge. 44-270-20 : Flat type : Upto 4.50m depth. |  |  | Total Sheet pile |  |  |  | 98 |  | nos.
[7 empty] | 98 | x | 2.625 | x | 0.4 | = | 102.9 | 102.9 | Sqm. | 1250.75 | 128702.175
116 | 72-180 | Painting of steel sheet piles, 2 coats of bitumen paint, including preparation of surface with sand paper, iron brush etc. including the cost of all materials and labour etc. complete as per direction of Engineer in charge.
[14 empty] | 399.84 | Sqm. | 293.33 | 117285.0672
[5 empty] | Total Sheet pile |  |  | = |  |  | 98 |  | Nos
[5 empty] | 2 | x | 98 | x | 3 | x | 0.68 |  | 399.84
117 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge.
[5 empty] | 2 | x | 98 | x | 0.68 | x | 0.375 | = | 49.98 | 49.98 | Sqm. | 461.8 | 23080.764
118 | 44-220 | Supplying and laying single layer pholythene sheet in floor below cement concrete, RCC slab, on walls etc. complete in all respect as per direction of Engineer in charge. 44-220-10: Weighing minimum 1.0 kg. per 6.50 sqm. |  |  | Barrel base: | = | 1 | x | 4.3 | x | 4.6 | = | 19.78 | 249.964 | Sqm | 31.22 | 7803.8761
|  |  | R/S & C/S Apron |  | 2 | x | 10.8 | x | 4.6 | + | 8.9 | = | 145.8
2
|  |  | R/S & C/S R/W |  |  |  | 4 | x | 5.6 | x | 2.25 | = | 50.4
Guide Wall bed
|  |  | R/S & C/S bed |  | 1 | x | 2 | x | 8.3 | x | 0.4 | = | 6.64
[5 empty] | 2 | x | 2 | x | 10.3 | x | 0.4 | = | 16.48
|  |  | R/S & C/s slope |  | 2 | x | 2 | x | 6.79 | x | 0.4 | = | 10.864
[11 empty] | Total | = | 249.964
119 | 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-120-20: With 25mm down graded stone chips. | R/W base R/S & C/S |  | 4 | x | 5.6 | x | 2.25 | x | 0.075 | = | 3.78 | 33.8066 | Cum | 10954.48 | 370333.5045
R/S & C/S. Appron
|  |  | 2 | x | 10.8 | x | 4.6 | + | 8.9 | x | 0.075 | = | 10.935
2
|  |  | Barrel |  | 1 | x | 4.3 | x | 4.6 | x | 0.075 | = | 1.4835
Guide Wall
|  |  | R/S. & C/S bed |  | 2 | x | 8.3 | x | 0.3 | x | 0.65 | = | 3.237
|  |  | 2 | x | 2 | x | 12.3 | x | 0.3 | x | 0.38 | = | 2.8044
|  |  | 4 | x | 12.3 | x | 0.3 | + | 0.165 | x | 0.27 | = | 3.0885
2
|  |  | R/S. bed |  | 2 | x | 9 | x | 0.3 | x | 0.38 | = | 2.052
|  |  | 2 | x | 9 | x | 0.3 | + | 0.165 | x | 0.27 | = | 1.13
2
|  |  | slope |  | 4 | x | 6.79 | x | 0.3 | x | 0.65 | = | 5.2962
[11 empty] | Total= |  | 33.8066
120 | 28-100 | Cement concrete work in leanest mix. 1:4:8, with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-100-20 : With 25mm down graded stone chips. | Guide Wall | [10 empty] | 1.8592 | cum | 10601.19 | 19709.7324
|  |  | R/S. & C/S bed |  | 2 | x | 8.3 | x | 0.4 | x | 0.05 | = | 0.332
|  |  | C/S |  | 4 | x | 12.3 | x | 0.4 | x | 0.05 | = | 0.984
|  |  | Slope |  | 4 | x | 6.79 | x | 0.4 | x | 0.05 | = | 0.5432
[11 empty] | Total= |  | 1.8592
121 | 28-200 | Reinforced Cement Concrete Work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>= 2.0 to FM >= 2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: With stone chips. | Key of sheet pile R/S. & C/S
|  |  | 2 | x | 19.5 | x | 0.9 | + | 1.2 | x | 0.3 | = | 12.285 | 166.2642 | Cum | 11674.49 | 1941049.2149
2
|  |  | R/W base | = | 4 | x | 5.6 | x | 2.25 | x | 0.4 | = | 20.16
Wall Ver. R/W
[5 empty] | 4 | x | 5.6 | x | 0.3 | x | 2.5 | = | 16.8
Felet R/W
|  |  | 4 | x | 2 | x | 0.15 | x | 0.15 | x | 5.6 | = | 0.504
2
Felet W/W.
|  |  | 2 | x | 2 | x | 0.15 | x | 0.15 | x | 10.05 | = | 0.45225
2
Felet Barrel
|  |  | 1 | x | 2 | x | 0.15 | x | 0.15 | x | 4.3 | = | 0.09675
2
C/S & R/s Apron end
[5 empty] | 2 | x | 8.9 | x | 0.75 | x | 0.4 | = | 5.34
|  |  | C/S & R/s Apron flat |  | 2 | x | 8.25 | x | 8.9 | + | 5.32
|  |  |  | = |  |  |  |  | 2
[6 empty] | x | 0.4 | + | 0.45 |  |  | = | 49.8589
|  |  | Slope Portion | = |  |  | 2
|  |  | 2 | x | 1.8 | x | 4.6 | + | 5.32 | x | 0.45 | = | 8.0352
2
C/S & R/S Wing Wall (Ver.)
[5 empty] | 4 | x | 8.25 | x | 0.3 | x | 2.5 | = | 24.75
|  |  | Slope = |  | 4 | x | 1.8 | x | 0.3 | x | 2.5 | = | 5.4
Barrel
|  |  | Base |  | 1 | x | 4.3 | x | 4.6 | x | 0.45 | = | 8.901
Abutment Wall Ver.
|  |  |  | = | 2 | x | 4.3 | x | 0.3 | x | 2.4 | = | 6.192
|  |  | Block Protector C/S. & R/S |  | 4 | x | 0.75 | x | 0.3 | x | 0.3 | = | 0.27
Felet Ver.
[5 empty] | 4 | x | 0.3 | x | 0.3 | x | 2.5 | = | 0.45
2
C/S & R/S End Sill high
|  |  | 2 | x | 13 | x | 0.3 | x | 0.15 | x | 0.3 | = | 0.351
|  |  | 2 | x | 13 | x | 0.6 | x | 0.3 | x | 0.3 | = | 0.702
|  |  | Low |  |  |  |  | 2
|  |  | 4 | x | 12 | x | 0.375 | x | 0.1875 | x | 0.3 | = | 0.50625
2
C/S & R/S Baffle block
|  |  | 2 | x | 8 | x | 0.3 | x | 0.15 | x | 0.45 | = | 0.324
|  |  | 2 | x | 8 | x | 0.45 | x | 0.45 | x | 0.3 | = | 0.486
2
C/S & R/S Chute Block
|  |  | 2 | x | 6 | x | 1.35 | x | 0.45 | x | 0.3 | = | 1.0935
2
|  |  | Fin Barrel | =
|  |  | 2 | x | 7 | x | 2.5 | x | 0.3 | x | 0.3 | = | 3.15
|  |  | Name Plate | = | 2 | x | 0.75 | x | 0.45 | x | 0.15 | = | 0.10125
|  |  |  | = | 4 | x | 0.612 | x | 0.15 | x | 0.15 | = | 0.05508
[11 empty] | Total= |  | 166.2642
122 | 76-120 | M.S. Work for reinforcement with twisted M.S. bar, fy = 414 N/mm2, (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of twisted M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10 : 8mm dia to 30mm dia.
R/W base
12 mm dia rod
C/S & R/S out side key ring @ 150 mmc/c
|  |  | Ring |  |  | = | 2 | x | 130 | x | 2.02 | = | 525.2
|  |  | Binder |  |  | = | 2 | x | 5 | x | 20.1 | = | 201
|  |  | Inside V- Shape |  |  | = | 2 | x | 130 | x | 1.8 | = | 468
|  |  | Binder |  |  | = | 2 | x | 5 | x | 20.1 | = | 201
Top & bottom main bar @ 150 mmc/c
[6 empty] | = | 4 | x | 39 | x | 2.69 | = | 419.64
|  |  | Bottom binder @ 150 mmc/c |  |  | = | 4 | x | 16 | x | 6.48 | = | 414.72
|  |  | Top binder @ 150 mmc/c |  |  | = | 4 | x | 16 | x | 6.48 | = | 414.72
R/W Ver. @ 150 mm c/c both face
[5 empty] | 4 | x | 2 | x | 39 | x | 3.7 | = | 1154.4
Binder Both face @ 150 mm c/c
[5 empty] | 4 | x | 2 | x | 18 | x | 6.38 | = | 918.72
Felet bar @ 150 mm C/C
[5 empty] | 4 | x | 2 | x | 39 | x | 1.46 | = | 455.52
C/S & R/S Apron base
Bottom jali U- bar @ 150 mmc/c
|  |  |  | = | 2 | x | 67 | x | 14.8 | + | 10.4 | = | 1688.4
2
|  |  | Barrel U- Rod |  |  | = | 1 | x | 30 | x | 10.4 | = | 312
|  |  | Appron end |  |  | = | 2 | x | 5 | x | 9.86 | = | 98.6
|  |  | Bottom binder @ 150 mmc/c |  |  |  | 1 | x | 32 | x | 26.7 | = | 854.4
|  |  | 2 | x | 2 | x | 16 | x | 11 | + | 3 | = | 448
2
Ver. W/F @ 150 mm c/c.
[6 empty] | = | 2 | x | 164 | x | 3.7 | = | 1213.6
Wall Binder Both face @ 150 mm c/c
[5 empty] | 2 | x | 2 | x | 18 | x | 25.36 | = | 1825.92
Felet bar @ 150 mm C/C
[7 empty] | 2 | x | 164 | x | 1.55 | = | 508.4
[11 empty] | Total | = | 12122.24
[6 empty] | @ | 0.89 | Kg. per/m |  |  |  | = | 10788.7936 | 10788.7936 | Kg
16 mm dia rod
Apron & barrel Top main @200 mm c/c
|  |  | Apron | = | 2 | x | 55 | x | 5.5 | + | 10.18 | = | 862.4
2
binder @ 200 mmc/c
[6 empty] | = | 2 | x | 28 | x | 10 | = | 560
[5 empty] | 4 | x | 9 | x | 9 | + | 3 | = | 216
2
|  |  | Barrel Portion |  |  | = | 1 | x | 24 | x | 16.68 | = | 400.32
[5 empty] | 4 | x | 2 | x | 4 | + | 3 | = | 28
2
|  |  | Ver. Felet |  |  | = | 4 | x | 2 | x | 3.7 | = | 29.6
[11 empty] | Total | = | 2096.32
[6 empty] | @ | 1.58 | Kg. per/m |  |  |  | = | 3312.1856 | 3312.1856 | Kg
12 mm dia rod
End sill
|  |  | End sill High | = | 2 | x | 13 | x | 3 | x | 1.9 | = | 148.2
Binder Ver.
|  |  | 2 | x | 13 | x | 2 | x | 1.7 | + | 1.2 | = | 37.7
2
Binder Hor.
|  |  | 2 | x | 13 | x | 2 | x | 1.8 | + | 1.5 | = | 42.9
2
|  |  | End sill low | = | 2 | x | 12 | x | 3 | x | 1.6 | = | 115.2
|  |  | Binder | = |  |  | 2 | x | 5 | x | 9.86 | = | 98.6
|  |  | Baffelo block |  | 2 | x | 8 | x | 3 | x | 2.2 | = | 105.6
|  |  | Binder Ver. | =
|  |  | 2 | x | 8 | x | 2 | x | 2 | + | 1.5 | = | 56
2
Binder Hor.
|  |  | 2 | x | 8 | x | 2 | x | 1.5 | + | 1 | = | 40
2
|  |  | Chute block |  | 2 | x | 6 | x | 3 | x | 2.5 | = | 90
|  |  | Binder Ver. | =
|  |  | 2 | x | 6 | x | 9 | x | 2.2 | + | 1.2 | = | 183.6
2
Binder Hor.
|  |  | 2 | x | 6 | x | 2 | x | 3 | + | 2.5 | = | 66
2
Block Protector
|  |  | Ver |  |  | = | 4 | x | 5 | x | 1.5 | = | 30
|  |  | Binder |  |  | = | 4 | x | 4 | x | 1 | = | 16
|  |  | Fin ver. | = | 2 | x | 7 | x | 2 | x | 3.7 | = | 103.6
Fin binder @ 200 mm c/c
|  |  |  | = | 2 | x | 7 | x | 13 | x | 1.8 | = | 327.6
|  |  | Ver. Felet binder |  |  | = | 4 | x | 17 | x | 1.98 | = | 134.64
[11 empty] | Total | = | 1595.64
[6 empty] | @ | 0.89 | Kg. per/m |  |  |  | = | 1420.1196 | 1420.1196 | Kg
[13 empty] | Total = | 15521.0988
Add 5% for laping, Chair & Seperator etc
[6 empty] | = | 15521.0988 | x | 0.05 |  |  |  | = | 776.0549
[9 empty] | Grand total = |  |  |  |  | 16297.1537 | Kg | 77.34 | 1260421.8703
123 | 36-150 | Form work for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mm x 40mm x 6mm M.S. Angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per designed shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge.
(A) | 36-150-60 | A) 36-150-60: Footing, footing beams, girder beams, foundation slab with 60-80mm diabarrack bamboo props. | Key outside
[5 empty] | 1 | x | 2 | x | 19.5 | x | 0.775 | = | 30.225 | 201.339 | Sqm. | 735.35 | 148054.6337
R/W key
|  |  | 1 | x | 4 | x | 0.9 | + | 1.2 | x | 0.3 | = | 1.26
2
C/S.& R/S R/W Base
[5 empty] | 1 | x | 4 | x | 2.25 | x | 0.475 | = | 4.275
[5 empty] | 1 | x | 4 | x | 5.6 | x | 0.475 | = | 10.64
C/S & R/S. Apron
|  |  | Side |  | 4 | x | 8.25 | x | 0.475 | + | 0.525 | = | 16.5
2
|  |  | Slope = |  |  |  | 4 | x | 1.8 | x | 0.525 | = | 3.78
|  |  | Barrel |  |  |  | 2 | x | 4.3 | x | 0.525 | = | 4.515
Guide Wall C/S & R/S
|  |  | Bed |  | 2 | x | 2 | x | 8.3 | x | 0.7 | = | 23.24
|  |  | ,, |  | 4 | x | 2 | x | 12.3 | x | 0.7 | = | 68.88
Slope
|  |  | 2 | x | 2 | x | 2 | x | 6.79 | x | 0.7 | = | 38.024
[11 empty] | Total = |  | 201.339
(B) | 36-150-10 | B) 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | R/W. | = | 4 | x | 2 | x | 5.6 | x | 2.5 | = | 112 | 424.3 | Sqm. | 909.69 | 385981.467
|  |  | Side | = | 4 | x | 1 | x | 0.3 | x | 2.5 | = | 3
|  |  | C/S & R/s Wing Wall | = | 4 | x | 2 | x | 10.8 | x | 2.5 | = | 216
|  |  | Side | = |  |  | 4 | x | 0.3 | x | 2.5 | = | 3
|  |  | Barrel | = | 2 | x | 2 | x | 4.3 | x | 2.4 | = | 41.28
Fin
|  |  | 2 | x | 7 | x | 2 | x | 0.3 | x | 2.4 | = | 20.16
|  |  | Block protector |  | 4 | x | 2 | x | 0.75 | x | 0.3 | = | 1.8
[5 empty] | 4 | x | 1 | x | 0.3 | x | 0.3 | = | 0.36
|  |  | End Sill high |  | 2 | x | 13 | x | 0.3 | x | 0.3 | = | 2.34
|  |  | 4 | x | 13 | x | 0.15 | + | 0.375 | x | 0.4 | = | 5.46
2
Baffelo block R/S & C/S
[5 empty] | 8 | x | 2 | x | 0.3 | x | 0.45 | = | 2.16
|  |  | 8 | x | 4 | x | 0.15 | + | 0.45 | x | 0.45 | = | 4.32
2
|  |  | Chute block |  | 2 | x | 6 | x | 0.3 | x | 0.45 | = | 1.62
|  |  | 2 | x | 6 | x | 2 | x | 1.35 | + | 0.45 | = | 10.8
2
[11 empty] | Total= |  | 424.3
124 | 16-520 | Supplying and filling sand in foundation of hydraulic structures, buildings and in protective works with selected sand, in 150mm thick layer, including levelling, dressing, ramming, watering etc. complete (compacted to 50% relative density by manual laqbour using mallet/vibro compactor) as per direction of Engineer in charge. 16-520-20 : sand of FM>= 1.50 | R/W base | = | 4 | x | 5.6 | x | 3.45 | x | 0.625 | = | 48.3
|  |  | apron | [10 empty] | 226.9813 | Cum | 1420.06 | 322327.0826
|  |  | 2 | x | 9 | x | 6.4 | + | 10.1 | x | 0.625 | = | 92.8125
2
|  |  | Barrel = | =
|  |  | 4.3 | + | 7.9 | x | 5.8 | + | 8.15 | x | 1.175 | = | 49.9933
|  |  |  | 2 |  |  |  | 2
Below CC Block
|  |  | C/S & R/S Bed | = | 2 | x | 8.3 | x | 5 | x | 0.15 | = | 12.45
|  |  | Slope C/S &R/S | = | 4 | x | 6.79 | x | 5.75 | x | 0.15 | = | 23.4255
[11 empty] | Total | = | 226.9813
125 | 40-610 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. | Below CC Block
|  |  | C/S & R/S Bed | = | 2 | x | 8.3 | x | 5 | x | 0.15 | = | 12.45
|  |  | Slope C/S &R/S | = | 4 | x | 6.79 | x | 5.75 | x | 0.15 | = | 23.4255
[11 empty] | Total | = | 35.8755
(A) | 40-610-20 | A) Well graded between 40mm to 20mm size.
Total quantity = 35.88cum
50 % of total quantity =
[7 empty] | 35.8755 | x | 0.5 |  |  | = | 17.9377 | 17.9377 | Cum | 3730.47 | 66916.2382
Cum
(B) | 40-610-30 | B) Well graded between 20mm to 5mm size. (Combination of sub-item 10 and 30 or 20 and 30 shall be used) | Total quantity =35.876 cum
50 % of total quantity =
[5 empty] | 35.8755 |  | Cum | x | 0.5 |  |  | = | 17.9377 | 17.9377 | Cum | 4076.09 | 73115.8834
126 | 40-140-50 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>= 1.5) and shingles (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. A) 40-140-50: Block size 30cm x 30cm x 30cm | Block size 30cm x 30cm x 30cm
C/S & R/S loose apron
|  |  | Single layer bed |  |  | = | 2 | x | 5 | x | 8.3 | = | 83 | 5710.2389 | Nos. | 317.01 | 1810202.8302
|  |  | Double Layer |  |  | = | 4 | x | 5 | x | 8.3 | = | 166
|  |  | Slope single layer |  |  | = | 4 | x | 10.75 | x | 6.79 | = | 291.97
[11 empty] | Total | = | 540.97
|  |  | Area of each Block |  |  | = | 0.3 | x | 0.3 | = | 0.09 |  | sqm.
|  |  | Total nos. of block |  |  | = | 540.97 | ÷ | 0.09 | = | 6010.7778 |  | Nos.
|  |  | Deduction 5% gap |  |  | = | 6010.7778 | x | 0.05 | = | 300.5389 |  | Nos.
[9 empty] | Total | = | 5710.2389 |  | Nos.
|  | B) 40-140-40: Block size 40cm x 40cm x 20cm | On aproach road
Single layer
|  |  | Top | = | 4 | x | 5.6 | + | 7.75 | x | 10.85 | = | 289.695
2
[9 empty] | Total |  |  |  | 289.695
|  |  | Area of each Block |  |  | = | 0.4 | x | 0.4 | = | 0.16 |  | sqm.
|  |  | Total nos. of block |  |  | = | 289.695 | ÷ | 0.16 | = | 1810.5937 |  | Nos.
|  |  | Deduction 5% gap |  |  | = | 1810.5937 | x | 0.05 | = | 90.5297 |  | Nos.
[9 empty] | Total | = | 1720.0641 |  | Nos. | 1720.0641 | Nos | 381.46 | 656135.6373
127 |  | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. 40-220-10 : Within 200m | Block size 30cm x 30cm x 30cm
| 40-220 |  | Total nos. of block = |  |  |  | 5710.2389 | Nos
|  |  | Volume | = | 5710.2389 | x | 0.3 | x | 0.3 | x | 0.3 | = | 154.1764 | 209.2185 | cum | 1145.88 | 239739.2948
Block size 40cm x 40cm x 40cm
|  |  | Total nos. of block = |  |  |  | 1720.0641 | Nos
|  |  | Volume | = | 1720.0641 | x | 0.4 | x | 0.4 | x | 0.2 | = | 55.0421
[11 empty] | Total | = | 209.2185
128 | 40-600 | Supplying and placing non-woven needle punched type geotextile fabric as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropeline or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipments etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals accross the body of the fabric). 40-600-20 . Mass =>300 gm/m², thickness(Under 2 kpa pressure) =>2.00 mm, EoS<=0.11mm, strip tensile strength =>15 kn/m, grab strength =>850 N, CBR puncture resistance =>2200 N.
|  |  | Aproach road |  | 4 | x | 8.15 | + | 6 | x | 11.25 | = | 318.375 | 318.375 | Sqm | 158.66 | 50513.3775
2
129 | 16-140 | Earth work by manual labour in resectioning of embankment/ canal bank/ river slopes/road/compound etc. manually compacted by 7.0 kg iron rammer to avoid any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceding 150mm thickness with clod breaking to a maximum size of 100mm, removing roots & stumps of trees of girth upto 200mm from the ground, benching the side slopes, stripping/ploughing the base of embankment and borrowpit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of the crest (where necessary) etc. complete as per direction of Engineer in charge. 16-140-10: 0 m to 3.00m height.
For construction of Approach road / Dirversion Road
|  |  | 2 | x | 50 | x | 4.3 | + | 13.3 | x | 1.5 | = | 1320 | 4320 | cum | 187.79 | 811252.8
2
Earth filling for site depelopment of Saudi khal
|  |  |  | = | 1 | x | 50 | x | 10 | x | 2.4 | = | 1200
|  |  |  | = | 1 | x | 50 | x | 15 | x | 2.4 | = | 1800
[11 empty] | Total = |  | 4320
130 | 16-130 | Earth work by manual labour in all kinds of soil in excavation or reexcavation of channels with the initial lead of 30m and lift of 1.5m including levelling, dressing and throwing the spoils to profile with breaking clods, rough dressing, clearing jungles including cutting trees upto 200mm girth, dug bailing etc. complete as per direction of Engineer in charge. | Diversion Channel
C/S & R/S
|  |  | 2 | x | 100 | x | 9.6 | + | 14.1 | x | 1.5 | = | 3555 | 3555 | cum | 142.47 | 506480.85
2
[11 empty] | Total = |  | 3555
131 | 16-200 | Extra rate for every additional lift of 1.00 meter part thereof beyond the initial lift of 1.5m ( 30 cm neglected) for all kinds of earth work. 1 no. lift
Lift calculation =
[{(1.5÷2)+(3.60-2.60)+(2.6-2.10)/2}-1.5]÷1 =0.50 say 1 no lift
[5 empty] | Quantity same as item no. |  |  |  | 130 | = |  |  | 3555 | 3555 | Cum | 10.99 | 39069.45
132 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | Construction of Ring bundh
|  |  | 4 | x | 90 | x | 3.04 | + | 11.04 | x | 2 | = | 5068.8 | 2591.8237 | cum | 142.42 | 369127.5385
2
5068.8
|  |  | Deduction foundation excavation earth = | [7 empty] | (-) |  | 2476.9763
[11 empty] | Total | = | 2591.8237
133 | 16-190 | Extra rate for every additional lead of 15 m or part thereof beyond the initial lead of 30m up to a maximum of 19 leads (3m neglected) for all kinds of earth work 1 no lead
|  |  | Quantity same as item no |  |  | 132 |  |  |  | = |  |  | 2591.8237
[11 empty] | Total= |  | 2591.8237 | 2591.8237 |  | 14.57 | 37762.872
134 | 04-280 | Constructing at site, cement mortar gauge on masonry wall, including engraving in meter, decimeter & centimeter, painting and figuring with black and red water proof paint, etc. complete as per direction of Engineer in charge. 04-280-10 : 150mm x 25mm |  |  | 2 | x | 1 | x | 2.5 | = |  |  | 5 | 5 | m | 77.73 | 388.65
m
135 | 16-240 | Earth work by manual labour in all kinds of soil in removing the cross bundh/ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimum 15m apart from the bank) as per direction of Engineer in charge. | Removing Ring Bundh
|  |  | Total Ring Bundth Construction | [8 empty] | = | 5068.8 | 82.4796 | cum | 142.47 | 11750.8686
|  |  | Deduction back filling by earth | [6 empty] | = | 630.972
|  |  | Approach Road & Site filling earth | [6 empty] | = | 4320
[9 empty] | Total | = | 4950.972 | (-) | 4950.972
117.828
|  |  | 70% remove | = | 117.828 | x | 70% |  |  |  |  | = | 82.4796
cum
136 | 16-540 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. 16-540-20 : Sand of FM>= 0.80 | R/W side R/S & C/S.
|  |  | 4 | x | 2.25 | x | 0.6 | + | 3.725 | x | 3.125 | = | 60.8203
2
|  |  | 4 | x | 5.6 | x | 0.6 | + | 3.725 | x | 3.125 | = | 151.375
2
R/S. & C/S wing wall Side
|  |  | 4 | x | 8.25 | x | 0.6 | + | 3.725 | x | 3.125 | = | 223.0078
2
Barrel side
|  |  | 2 | x | 7.9 | x | 0.6 | + | 4.7 | x | 4.1 | = | 171.667
2
[11 empty] | Total |  | 606.8701 | 606.8701 | Cum | 757.75 | 459855.8372
137 | 16-530 | Back filling in hydraulic structures and slope building in protective works including all leads and lifts with selected local soil in layer of 150mm including watering, ramming etc. complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in charge.
|  |  | Barrel side | = | 2 | x | 7.9 | x | 2.4 | x | 4.1 | = | 155.472
|  |  | Wing wall side | = | 4 | x | 8.25 | x | 2.4 | x | 3.125 | = | 247.5
|  |  | R/W side | = | 4 | x | 5.6 | x | 2.4 | x | 3.125 | = | 168
|  |  |  | = | 4 | x | 2 | x | 2.4 | x | 3.125 | = | 60
[11 empty] | Total |  | 630.972 | 630.972 | Cum | 159.49 | 100633.7243
138 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurment will be given on well grown grass only), as per direction of Engineer in charge.
|  |  | Approach Road |  |  | = | 2 | x | 50 | x | 14.5 | = | 1450 | 1450 | sqm | 26.17 | 37946.5
13656300.1663
4

## Abstract Link With Details
Details Estimate for 2 vent (1.80 m x1.50 m) regulator at km 1.012 in markhali khal under Noagaon haor under Haor Flood Management & Livlihood Improvement Project during the financial year 2017-18.
Sl No | Code No | Item Description | Quantity | Unit | unit Rate (Tk) | Amount (Tk)
1 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cm x 38cm x 75cm on cement concrete (1:2:4) base of size 50cm x 50cm x 7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement morter on top (1:2), with inscription of "BWDB" with 25cm of the pillar balow ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | 5 | each | 1203.77 | 6018.85
2 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials form entire site and removing soil upto 15cm depth including uprooting stumps, jungle clearing, levelling dressing etc. complete as per direction of Engineer in charge. | 9000 | sqm | 27.72 | 249480
3 | 04-620-20 | Filling of expansion joints upto a depth of 40mm with bitumen mixed with coarse sand (FM>=2.5) in concrete works including supply of all materials etc. complete as per specification and direction of Engineer in charge. 20mm wide. |  | m | 69.54
4 | 12-120 | Installation of well point dewatering set including supply of all accessories, materials and labours for one 5 cusec vacuum pump for minimum 100 well points in controlling subsurface water during construction, providing shrouding materials, conducting test operation and subsequent removal of the complete dewatering set in accordance with standard specification and field requirement as per direction of Engineer in charge.
5 | 16-310 | Earth work in excavation of foundation trenches in all kinds of soils as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. For moving spoil earth upto a distance of 100m from the centre of the pit. | 2476.9763 | cum | 246.71
6 | 16-560-20 | Shoring for slope protection of foundation trench, canal, embankment, road, pond etc. as per design slopes, grades including removal of spoils to a safe distance as per direction of Engineer in charge. By bamboo post of 6.0m length, 60mm to 80mm dia, 20cm c/c driven 2.0m below ground, with drum sheet walling and average 70mm dia half split bamboo batten @ 2.0m c/c fixed with nails. |  | sqm | 837.15
7 | 12-310-20 | Bailing out of water with all leads and lifts by manual labour or pump, with all arrengements for protection of ring bund and side slopes of foundation pit against erosion or washout etc. complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge. by pump. |  | cum | 6.13
8 | 44-240 | Supplying at site steel sheet piles of different sections including all taxes, freights, incidental charges etc. complete as per direction of Engineer in charge. |  | M ton | 145120.53
9 | 44-320 | Cutting of steel sheet piles to design and length and shape as per requirement in design and drawing and as per direction of Engineer in charge. Upto 10mm thick. |  | m | 39.16
10 | 12-300 | Construction of sump well with dug holes of size 1.80m x 2.0m, laying in position the perforated empty diesel/petrol drum sheet of 1.00m dia to a depth 1.5m having slot area of 1000 sq.cm/sqm, slot dia being 30mm each with supply of necessary shrouding materials comprising of 60% 40mm down graded khoa and 40% coarse sand of FM>=2.50 and placing those around and beneath the drum sheet having thickness of 40cm and 50cm respectively including necessary welding, fitting etc. complete as per direction of Engineer in charge. |  | each | 17211.17
11 | 44-270 | Driving steel sheet piles of various sections and weights of any type of soil, by monkey hammer including handling and placing in position, staging and supplying of all equipments like monkey hammer, pully, rope, bamboo, bullah etc. including correcting leaning beyond tolerance & other defects and any other incidental cost etc. complete (measurement will be taken on projected width x height) as per direction of Engineer in charge. Flat type : Upto 4.50m depth.
12 | 72-180 | Painting of steel sheet piles, 2 coats of bitumen paint, including preparation of surface with sand paper, iron brush etc. including the cost of all materials and labour etc. complete as per direction of Engineer in charge.
13 | 72-540 | Epoxy paint 2 coats of approved colour and specification over a priming coat to gate, hoisting device and embedded metal parts includingscraping out rust and old paint with chisel, scraper, steel wire brush & emery paper etc. complete in all respects including the cost of all materials as per direction of Engineer in charge.
14 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge.
15 | 44-220 | Construction of pile yard for casting RCC pile with 50mm thick cement concrete (1:3:6) with cement, sand (FM>= 1.5) and 20mm down graded picked jhama or 1st class brick chips including breaking, screening, grading and washing chips, mixing, laying and compacting to levels, over a brick flat soling with 1st class bricks including preparation of base, sand filling to make a level base, ramming and sand blinding with sand of FM>= 0.8 etc. complete with neat cement finishing over the concrete surface including the cost for supply of all materials and as per direction of Engineer in charge.
16 | 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. With 25mm down graded picked jhama or 1st class brick chips.
17 | 28-100 | Cement concrete work in leanest mix. 1:4:8, with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. With 25mm down graded picked jhama or 1st class brick chips.
18 | 28-200 | Reinforced Cement Concrete Work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>= 2.0 to FM >= 2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. With stone chips.
19 | 76-120 | M.S. Work for reinforcement with twisted M.S. bar, fy = 414 N/mm2, (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of twisted M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 8mm dia to 30mm dia.
20 | 76-115 | M.S. Work for reinforcement with deformed M.S. bar, fy = 276 N/mm2, (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 6mm dia.
21 | 36-150 | Form work for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mm x 40mm x 6mm M.S. Angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per designed shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props.
22 | 36-150-60 | Form work for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mm x 40mm x 6mm M.S. Angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per designed shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. Footing, footing beams, girder beams, foundation slab with 60-80mm diabarrack bamboo props.
23 | 36-150-10 | Form work for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mm x 40mm x 6mm M.S. Angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per designed shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props.
24 | 36-150-20 | Form work for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mm x 40mm x 6mm M.S. Angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per designed shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. Deck slab, operating deck slab, top slab of barrel upto 3.5m of height with 60-80mm dia barrack bamboo props.
25 | 76-630 | Supply and fitting and fixing 23cm wide P.V.C water stops having minimum strength of 13.80N/mm2 at 225% elongation and of approved quality in antraction and expansion joints with necessary arrangements for modification in shuttering and keeping the water stop in position etc. complete as per design, specification anddirection of Engineer in charge. 3 bulb type.
26 | 16-520 | Supplying and filling sand in foundation of hydraulic structures, buildings and in protective works with selected sand, in 150mm thick layer, including levelling, dressing, ramming, watering etc. complete (compacted to 50% relative density by manual laqbour using mallet/vibro compactor) as per direction of Engineer in charge. sand of FM>= 1.50
27 | 40-610 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. Well graded between 50mm to 20mm size.
28 | 40-610-20 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. Well graded between 40mm to 20mm size.
29 | 40-610-30 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. Well graded between 20mm to 5mm size. (Combination of sub-item 10 and 30 or 20 and 30 shall be used)
30 | 40-650 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. FM : 2.0 to 2.5
31 | 40-190-50 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>= 1.5) and shingles (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. block size 30cm x 30cm x 30cm
32 | 40-220 | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. Within 200m
33 | 76-170 | M.S. Work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cutting, bending, welding, forging, drilling, revetting, embedding anchor bars, staging and fitting, fixing, local handling etc. complete with energy consumption and supply of labours including the cost of materials as per design, specification and direction of Engineer in charge.
34 | 80-230 | Supplying, laying, fitting and fixing of different dia G.I. pipes with all special fittings, such as bends, elbows, sockets, tees, unions, jam nuts etc. including cutting foundation trenches upto required depth where necessary and filling the same with earth duly compacted, making holes in floors and walls and clips, including cutting threads, making necessary connection etc. all complete including the cost of all materials as per direction of Engineer in charge. 40mm dia G.I. pipe line.
35 | 76-240 | Manufacturing, supplying, Installation and fitting, fixing the vertical steel lift gate/flap gate as per design and specification, including fabricating, rivetting, welding, fixing rubber seal, providing required nuts and bolts including the cost of all materials etc. complete with a prime coat of redoxide where necessary as per direction of Engineer in charge. (Applicable only for size not specified and smaller than size mentioned in Item code 76-240 & 76-250)
36 | 76-260 | Labour charge for fitting and fixing of M.S. vertical lift gate/flap gate shutters of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/sluice and mending the damages with CC (1:2:4), removing the spoils etc.complete including the cost of all materials as per direction of Engineer in charge. Size 1.00m x 1.00m or 1.35m x 1.35m
37 | 76-190 | Manufacturing, supplying and Installation of Padestal type lifting device for slide gate with 63mm dia threaded steel shaft, 146mm outer dia bronze nut, thrust bearing, steel bevel gear etc. as per approved design including supply of all components, labours with a prime coat of redoxide where necessary etc. complete including the cost of all materials as per specification and direction of Engineer in charge.
38 | 16-140 | Earth work by manual labour in resectioning of embankment/ canal bank/ river slopes/road/compound etc. manually compacted by 7.0 kg iron rammer to avoid any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceding 150mm thickness with clod breaking to a maximum size of 100mm, removing roots & stumps of trees of girth upto 200mm from the ground, benching the side slopes, stripping/ploughing the base of embankment and borrowpit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of the crest (where necessary) etc. complete as per direction of Engineer in charge. 0.00m to 3.00m height.
39 | 16-130 | Earth work by manual labour in all kinds of soil in excavation or reexcavation of channels with the initial lead of 30m and lift of 1.5m including levelling, dressing and throwing the spoils to profile with breaking clods, rough dressing, clearing jungles including cutting trees upto 200mm girth, dug bailing etc. complete as per direction of Engineer in charge.
40 | 16-200 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm negleted) for all kinds of earth work.
41 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3m negleted) for all kinds of earth work.
42 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge.
43 | 04-280 | Constructing at site, cement mortar gauge on masonry wall, including engraving in meter, decimeter & centimeter, painting and figuring with black and red water proof paint, etc. complete as per direction of Engineer in charge.
44 | 16-240 | Earth work by manual labour in all kinds of soil in removing the cross bundh/ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimum 15m apart from the bank) as per direction of Engineer in charge.
45 | 16-540 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. Sand of FM>= 0.50
46 | 16-530 | Back filling in hydraulic structures and slope building in protective works including all leads and lifts with selected local soil in layer of 150mm including watering, ramming etc. complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in charge.
47 | 68-130 | Supplying pressure treated wooden fall boards/stop logs of different size (not less than 15cm in depth) of Sal, Sundari, Garjan, Shishu or equivalant for regulator/sluices, including fixing in position with eye hook etc. complete as per direction of Engineer in charge.
48 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurment will be given on well grown grass only), as per direction of Engineer in charge.
49 | 80-260 | Supplying, fitting and fixing of the different dia G.I. water distribution pipe line, with all special fittings such as bends, elbows, sockets, reducing sockets, tees, unions etc. including cutting trench up to an average depth of 0.90m, maintaining proper level, cutting pipes where necessary, making threads etc. all complete, as per direction of Engineer in charge. 50mm dia G.I. pipe line.
50 | NSI | Part TimE Employment of environmental inspector for implementation and reporting .
255498.85

## Abstract
Abstruct cost of estimate for construction of Chhitra khal causeway (4.00 m)at km 21.77 of Nunnir haor
under Haor Flood Management & Livlihood Improvement Project during the financial year 2017-18
Sl No | Code No | Item Description | Quantity | Unit | unit Rate (Tk) | Amount (Tk)
1 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cm x 38cm x 75cm on cement concrete (1:2:4) base of size 50cm x 50cm x 7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement morter on top (1:2), with inscription of "BWDB" with 25cm of the pillar balow ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | 5 | each | 1203.77 | 6018.85
2 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials form entire site and removing soil upto 15cm depth including uprooting stumps, jungle clearing, levelling dressing etc. complete as per direction of Engineer in charge. | 9000 | sqm | 27.72 | 249480
3 | 12-120 | Installation of pizeometer including supply of 40mm G.I. pipe, brass strainer, socket, labour, by wash boring, lowering, fixing the elevation and providing cover on the top of the well etc. complete as per direction of Engineer in charge. | 6 |  |  | 0
4 | 16-310 | Earth work in excavation of foundation trenches in all kinds of soils as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. For moving spoil earth upto a distance of 100m from the centre of the pit. | 2476.9763 | cum | 246.71 | 611094.8106
5 | 16-560-20 | Shoring for slope protection of foundation trench, canal, embankment, road, pond etc. as per design slopes, grades including removal of spoils to a safe distance as per direction of Engineer in charge. 16-560-20 : By bamboo post of 6.0m length, 60mm to 80mm dia, 20cm c/c driven 2.0m below ground, with drum sheet walling and average 70mm dia half split bamboo batten @ 2.0m c/c fixed with nails. | 290.8 | sqm | 837.15 | 243443.22
6 | 12-310-20 | Bailing out of water with all leads and lifts by manual labour or pump, with all arrengements for protection of ring bund and side slopes of foundation pit against erosion or washout etc. complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge. by pump. | 50971.2862 | cum | 6.13 | 312453.9843
7 | 44-240 | Supplying at site steel sheet piles of different sections including all taxes, freights, incidental charges etc. complete as per direction of Engineer in charge. | 14.112 | M ton | 145120.53 | 2047940.9194
8 | 44-320 | Cutting of steel sheet piles to design and length and shape as per requirement in design and drawing and as per direction of Engineer in charge. Upto 10mm thick. | 66.64 | m | 39.16 | 2609.6224
9 | 12-300 | Construction of sump well with dug holes of size 1.80m x 2.0m, laying in position the perforated empty diesel/petrol drum sheet of 1.00m dia to a depth 1.5m having slot area of 1000 sq.cm/sqm, slot dia being 30mm each with supply of necessary shrouding materials comprising of 60% 40mm down graded khoa and 40% coarse sand of FM>=2.50 and placing those around and beneath the drum sheet having thickness of 40cm and 50cm respectively including necessary welding, fitting etc. complete as per direction of Engineer in charge. | 10 | each | 17211.17 | 172111.7
10 | 44-270 | Driving steel sheet piles of various sections and weights of any type of soil, by monkey hammer including handling and placing in position, staging and supplying of all equipments like monkey hammer, pully, rope, bamboo, bullah etc. including correcting leaning beyond tolerance & other defects and any other incidental cost etc. complete (measurement will be taken on projected width x height) as per direction of Engineer in charge. Flat type : Upto 4.50m depth. | 102.9 | sqm | 1250.75 | 128702.175
11 | 72-180 | Painting of steel sheet piles, 2 coats of bitumen paint, including preparation of surface with sand paper, iron brush etc. including the cost of all materials and labour etc. complete as per direction of Engineer in charge. | 399.84 | sqm | 293.33 | 117285.0672
12 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge. | 49.98 | sqm | 461.8 | 23080.764
13 | 44-220 | Supplying and laying single layer pholythene sheet in floor below cement concrete, RCC slab, on walls etc. complete in all respect as per direction of Engineer in charge. 44-220-10: Weighing minimum 1.0 kg. per 6.50 sqm. | 249.964 | Sqm | 31.22 | 7803.8761
16 | 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. With 25mm down graded picked jhama or 1st class brick chips. | 33.8066 | cum | 10954.48 | 370333.5045
17 | 28-100 | Cement concrete work in leanest mix. 1:4:8, with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. With 25mm down graded picked jhama or 1st class brick chips. | 1.8592 | cum | 10601.19 | 19709.7324
18 | 28-200 | Reinforced Cement Concrete Work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>= 2.0 to FM >= 2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. With stone chips. | 166.2642 | cum | 11674.49 | 1941049.2149
19 | 76-120 | M.S. Work for reinforcement with twisted M.S. bar, fy = 414 N/mm2, (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of twisted M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 8mm dia to 30mm dia. | 16297.1537 | kg | 77.34 | 1260421.8703
21 | 36-150 | Form work for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mm x 40mm x 6mm M.S. Angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per designed shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge.
22 | 36-150-60 | 36-150-60 : Footing, footing beams, girder beams, foundation slab with 60-80mm dia barrack bamboo props. | 201.339 | sqm | 735.35 | 148054.6337
23 | 36-150-10 | 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | 424.3 | sqm | 909.69 | 385981.467
26 | 16-520 | Supplying and filling sand in foundation of hydraulic structures, buildings and in protective works with selected sand, in 150mm thick layer, including levelling, dressing, ramming, watering etc. complete (compacted to 50% relative density by manual laqbour using mallet/vibro compactor) as per direction of Engineer in charge. 16-520-10 : Sand of FM>= 1.50 | 226.9813 | cum | 1420.06 | 322327.0826
27 | 40-610 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge.
(A) | 40-610-20 | A) Well graded between 40mm to 20mm size. | 17.9377 | cum | 3730.47 | 66916.2382
(B) | 40-610-30 | B) Well graded between 20mm to 5mm size. (Combination of sub-item 10 and 30 or 20 and 30 shall be used) | 17.9377 | cum | 4076.09 | 73115.8834
31 | 40-140 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>= 1.5) and shingles (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge.
(A) | 40-140-50 | A) 40-140-50: Block size 30cm x 30cm x 30cm | 5710.2389 | Each | 317.01 | 1810202.8302
|  | B) 40-140-40: Block size 40cm x 40cm x 20cm | 1720.0641 | Each | 381.46 | 656135.6373
32 | 40-220 | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. Within 200m | 209.2185 | cum | 1145.88 | 239739.2948
| 40-600 | Supplying and placing non-woven needle punched type geotextile fabric as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. foreffective erosion protection in hydraulic structures /river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropeline or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damagesincluding supply of all materials, labours, equipments etc. complete as per direction of Engineer in charge.(Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals accross the body of the fabric). 40-600-20 . Mass =>300 gm/m², thickness(Under 2 kpa pressure) =>2.00 mm, EoS<=0.11mm, strip tensile strength =>15 kn/m, grab strength =>850 N, CBR puncture resistance =>2200 N. | 318.375 | Sqm | 158.66
|  |  | 318.375 | Sqm | 158.66 | 50513.3775
38 | 16-140 | Earth work by manual labour in resectioning of embankment/ canal bank/ river slopes/road /compound etc. manually compacted by 7.0 kg iron rammer to avoid any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceding 150mm thickness with clod breaking to a maximum size of 100mm, removing roots & stumps of trees of girth upto 200mm from the ground, benching the side slopes, stripping/ploughing the base of embankment and borrowpit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of the crest (where necessary) etc. complete as per direction of Engineer in charge. 16-140-10: 0.00m to 3.00m height. | 4320 | cum | 187.79 | 811252.8
39 | 16-130 | Earth work by manual labour in all kinds of soil in excavation or reexcavation of channels with the initial lead of 30m and lift of 1.5m including levelling, dressing and throwing the spoils to profile with breaking clods, rough dressing, clearing jungles including cutting trees upto 200mm girth, dug bailing etc. complete as per direction of Engineer in charge. | 3555 | each | 142.47 | 506480.85
40 | 16-200 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm negleted) for all kinds of earth work. | 3555 | pldcum | 10.99 | 39069.45
42 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | 2591.8237 | cum | 142.42 | 369127.5385
41 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3m negleted) for all kinds of earth work. | 2591.8237 | pldcum | 29.14 | 75525.7441
43 | 04-280 | Constructing at site, cement mortar gauge on masonry wall, including engraving in meter, decimeter & centimeter, painting and figuring with black and red water proof paint, etc. complete as per direction of Engineer in charge. | 5 | m | 77.73 | 388.65
44 | 16-240 | Earth work by manual labour in all kinds of soil in removing the cross bundh/ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimum 15m apart from the bank) as per direction of Engineer in charge. | 82.4796 | cum | 142.47 | 11750.8686
45 | 16-540 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. Sand of FM>= 0.50 | 606.8701 | cum | 757.75 | 459855.8372
46 | 16-530 | Back filling in hydraulic structures and slope building in protective works including all leads and lifts with selected local soil in layer of 150mm including watering, ramming etc. complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in charge. | 630.972 | cum | 159.49 | 100633.7243
48 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurment will be given on well grown grass only), as per direction of Engineer in charge. | 1450 | sqm | 26.17 | 37946.5
50 | NSI | Part TimE Employment of environmental inspector for implementation and reporting . |  |  |  | 0
|  |  |  | Total |  | 13678557.7183