## Kishoregnj
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 | OG |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 | OG |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 | P | Not Started |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 | P | Not Started |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 | P | Not Started |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 | P | Not Started |  | Munshi Zahirul Islam
7 | KISH/PW-02 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 | C |  |  | Md. Amirul Islam
8 | KISH/PW-02 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 | C |  |  | Md. Amirul Islam
9 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 | C |  |  | Md. Amirul Islam
10 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 | C |  |  | Md. Amirul Islam
11 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 | C |  |  | Md. Amirul Islam
12 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 | C |  |  | Md. Amirul Islam
13 | KISH/PW-02 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 | C |  |  | Md. Amirul Islam
14 | KISH/PW-03 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 | C | Sign Board Remaining |  | Md.Abudl Latif
15 | KISH/PW-03 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 | OG | C:9.18R:1.2 |  | Md.Abudl Latif
16 | KISH/PW-03 | Block Road | Km |  | C |  |  | Md.Abudl Latif
17 | KISH/PW-04 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 | C |  |  | Md. Amirul Islam
18 | KISH/PW-04 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 | C |  |  | Md. Amirul Islam
19 | KISH/PW-04 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 | C |  |  | Md. Amirul Islam
20 | KISH/PW-04 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 | C |  |  | Md. Amirul Islam
21 | KISH/PW-05 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 | C | Gate Problem |  | Md.Abudl Latif
22 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 |  |  |  | Md.Abudl Latif
23 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0 |  |  |  | Md.Abudl Latif
24 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0 |  |  |  | Md.Abudl Latif
25 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 0 |  |  |  | Md.Abudl Latif
26 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 0 |  |  |  | Md.Abudl Latif
27 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 12.214 | OG | C:4ROG:5R:3 | 3 | Md.Abudl Latif
28 | KISH/PW-05 | Block Road | Km | 12.214 |  | CC Block Manufacture Complete |  | Md.Abudl Latif
29 | KISH/PW-06 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 | C |  |  | Md.Abudl Latif
30 | KISH/PW-06 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 | C |  |  | Md.Abudl Latif
31 | KISH/PW-06 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 | C |  |  | Md.Abudl Latif
32 | KISH/PW-06 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 | C |  |  | Md.Abudl Latif
33 | KISH/PW-06 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 | C |  |  | Md.Abudl Latif
34 | KISH/PW-06 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 | OG | C:7R:1.4 |  | Md.Abudl Latif
35 | KISH/PW-06 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 | OG | C:3.0R:0.56 | 1 | Md.Abudl Latif
36 | KISH/PW-07 | Hazir Khal | Km | 1.73 | C | 0.200 C D:1.53 |  | Md. Amirul Islam
37 | KISH/PW-07 | Karpasha Khal | Km | 1.615 | C | 3.4 KM Complete |  | Md. Amirul Islam
38 | KISH/PW-07 | Dampara Khal | Km | 3.6 |  | 1.2 C R:2.4 Can Not Done LP |  | Md. Amirul Islam
39 | KISH/PW-07 | Baniajan | Km | 6.854 | C |  |  | Md. Amirul Islam
40 | KISH/PW-07 | Suti Khal | Km | 6.1 | C |  |  | Md. Amirul Islam
41 | KISH/PW-07 | Digha Nadi | Km | 5.7 |  | 4.5 C 1.2 R |  | Md. Amirul Islam
42 | KISH/PW-07 | Old Singua | Km | 10.86 | P | Dropped |  | Md. Amirul Islam
43 | KISH/PW-07 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 | OG | 3 KM Dropped |  | Md. Amirul Islam
44 | KISH/PW-07 | Block Road | Km |  | P | Dropped |  | Md. Amirul Islam
45 | KISH/PW-09 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 | OG | P:0.9 |  | Md.Abudl Latif
46 | KISH/PW-09 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 | OG | Will be strated Soon |  | Md.Abudl Latif
47 | KISH/PW-09 | Causeway 6.0m wide-1 at Dampara | Nos | 1 | C |  |  | Md.Abudl Latif
48 | KISH/PW-09 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 | C |  |  | Md.Abudl Latif
49 | KISH/PW-10 | Causeway 6.0m wide-1 | Nos | 1 | P | NS |  | Md. Amirul Islam
50 | KISH/PW-10 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 | OG | Return Wall |  | Md. Amirul Islam
51 | KISH/PW-10 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 | OG | OG:5.5 | 1 | Md. Amirul Islam
52 | KISH/PW-10 | Block Road | Km |  | P | CC Block Not Manufatured |  | Md. Amirul Islam
53 | KISH/PW-11 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 | OG | Loose Apron Block Placing Going o.Gate Fitting is not completed |  | Md. Amirul Islam
54 | KISH/PW-11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 | P | C:10.36R:1.5 |  | Md. Amirul Islam
55 | KISH/PW-12 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 | C |  |  | Md. Amirul Islam
56 | KISH/PW-12 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 | OG | R/S Approach Channel not done |  | Md. Amirul Islam
57 | KISH/PW-12 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 | OG |  |  | Md. Amirul Islam
58 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 | C |  |  | Md. Amirul Islam
59 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 | C | C:2D:1 |  | Md. Amirul Islam
60 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 | C |  |  | Md. Amirul Islam
61 | KISH/PW-12 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 | C |  |  | Md. Amirul Islam
62 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
63 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
64 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 | OG | C:2OG:4P:4 |  | Munshi Zahirul Islam
65 | KISH/PW-14 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
66 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 | OG | C:13G:3.9 |  | Munshi Zahirul Islam
67 | KISH/PW-15 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 | P | Not Started/May Be Flood Fuse |  | Md.Khalilur Rahman
68 | KISH/PW-15 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 | C | Not Started |  | Md.Khalilur Rahman
69 | KISH/PW-16 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 | C | Loose Appron,Diversion Channel remainig P0.80 |  | Md.Khalilur Rahman
70 | KISH/PW-16 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 14.12 | OG | C:7.5OG:6.62 | 2 | Md.Khalilur Rahman
71 | KISH/PW-16 | Block Road | Km |  |  | CC Block Complete |  | Md.Khalilur Rahman
72 | KISH/PW-17 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 | P | Dameged Reaparing Going On |  | Md.Khalilur Rahman
73 | KISH/PW-17 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 | P | Structure:up to deck slab complete.0.70 |  | Md.Khalilur Rahman
74 | KISH/PW-17 | Box Drainage Outlet-1 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
75 | KISH/PW-17 | Box Drainage Outlet-2 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
76 | KISH/PW-17 | Box Drainage Outlet-3 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
77 | KISH/PW-17 | Box Drainage Outlet-4 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
78 | KISH/PW-17 | Box Drainage Outlet-5 | Nos | 1 | P |  |  | Md.Khalilur Rahman
79 | KISH/PW-17 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 | C | Dameged Reaparing Needed |  | Md.Khalilur Rahman
80 | KISH/PW-17 | Block Road | Km |  |  | CC Block Complete |  | Md.Khalilur Rahman
81 | KISH/PW-17 | Irrigation Pipe Inlet-1 | Nos | 25 | OG | C:23 Gate Installation remaining |  | Md.Khalilur Rahman
82 | KISH/PW-18 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 | P |  |  | Md.Khalilur Rahman
83 | KISH/PW-18 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 | P |  |  | Md.Khalilur Rahman
84 | KISH/PW-18 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 | P |  |  | Md.Khalilur Rahman
85 | KISH/PW-18 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 | C | Divesion Channel Remaining |  | Md.Khalilur Rahman
86 | KISH/PW-18 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 | OG | C:0.7 | 1 | Md.Khalilur Rahman
87 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 | C |  |  | Md.Khalilur Rahman
88 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 | C |  |  | Md.Khalilur Rahman
89 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 | C |  |  | Md.Khalilur Rahman
90 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 | P |  |  | Md.Khalilur Rahman
91 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 | C |  |  | Md.Khalilur Rahman
92 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 | P | Not Started |  | Munshi Zahirul Islam
93 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 | OG |  |  | Munshi Zahirul Islam
94 | KISH/PW-20 | Chitra Khal 4m wide | Nos | 1 | OG | 0.95 |  | Md.Abudl Latif
95 | KISH/PW-20 | Nabinpur Khal 4m Wide | Nos | 1 | OG | 0.95 |  | Md.Abudl Latif
96 | KISH/PW-20 | Dipjuri Khal 4m CW | Nos | 1 | P | 0.9 |  | Md.Abudl Latif
97 | KISH/PW-20 | Sudhikhal 4m wide CW | Nos | 1 | OG | 0.8 |  | Md.Abudl Latif
98 | KISH/PW-20 | Chhagalia khal sluice | Nos | 1 | OG | 0.9 |  | Md.Abudl Latif
99 | KISH/PW-20 | Near nasir sluice | Nos | 1 | OG | 0.9 |  | Md.Abudl Latif
100 | KISH/PW-20 | Shingpur khal sluice | Nos | 1 | C |  |  | Md.Abudl Latif
101 | KISH/PW-20 | Gharu khal sluice | Nos | 1 | P |  |  | Md.Abudl Latif
102 | KISH/PW-20 | Irrigation Pipe Inlet 600mm dia | Nos | 36 | OG | 5 Nos 0.90 |  | Md.Abudl Latif
103 | KISH/PW-21 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 | OG | Sheet Pile Drive Complete.CC going on |  | Md.Khalilur Rahman
104 | KISH/PW-21 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 | OG | Sheet Pile Drive Complete.CC Complete |  | Md.Khalilur Rahman
105 | KISH/PW-21 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 | P |  |  | Md.Khalilur Rahman
106 | KISH/PW-21 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 | P |  |  | Md.Khalilur Rahman
107 | KISH/PW-22 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 | OG | 10 KM 2 layer | 4 | Md.Khalilur Rahman
108 | KISH/PW-22 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 | P |  |  | Md.Khalilur Rahman
109 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 | C | C:0.65R:0.05 |  | Md.Khalilur Rahman
110 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 | P |  |  | Md.Khalilur Rahman
111 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 | P |  |  | Md.Khalilur Rahman
112 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 | OG |  | 1 | Md.Khalilur Rahman
113 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 | P |  |  | Md.Khalilur Rahman
114 | KISH/PW-22 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 | OG |  | 1 | Md.Khalilur Rahman
115 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 | OG |  | 1 | Md.Khalilur Rahman
116 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 | P |  |  | Md.Khalilur Rahman
117 | KISH/PW-22 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 | OG | CC Block:10000 out 20000 |  | Md.Khalilur Rahman
118 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 | P |  |  | Md.Khalilur Rahman
119 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 | P |  |  | Md.Khalilur Rahman
120 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 | P |  |  | Md.Khalilur Rahman
121 | KISH/PW-23 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 | OG | 0.6 | 1 | Anil Chandra Roy
122 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 | OG | Bsae Dhali River Side(max0.70) |  | Anil Chandra Roy
123 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 | OG | c0.50 proj 0.75 |  | Anil Chandra Roy
124 | KISH/PW-23 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 | P |  |  | Anil Chandra Roy
125 | KISH/PW-23 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 | P |  |  | Anil Chandra Roy
126 | KISH/PW-23 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 | OG | 0.7 Will Be complete |  | Anil Chandra Roy
127 | KISH/PW-23 | Irrigation Pipe Inlet 600mm dia | Nos | 4 | OG | 2OG |  | Anil Chandra Roy
128 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 | C | Diversion Channel Incomplete |  | Munshi Zahirul Islam
129 | KISH/PW-25 | Regulator 5-Vent-1 | Nos | 1 | OG | 0.75.Structure Complete |  | Md.Khalilur Rahman
130 | KISH/PW-25 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 | C | C:7R:1.5 Not As Per Design |  | Md.Khalilur Rahman
131 | KISH/PW-25 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Nos | 1 | OG | C:0.350R:1.30 |  | Md.Khalilur Rahman
132 | KISH/PW-25 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 | P | Not Started.Design Change Required |  | Md.Khalilur Rahman
133 | KISH/PW-25 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 | P | Not Started.Design Change Required |  | Md.Khalilur Rahman
134 | KISH/PW-25 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 | OG | 0.75.Structure Complete |  | Md.Khalilur Rahman
135 | KISH/PW-25 | Box Sluice-1 | Nos | 1 | P | Not Started |  | Md.Khalilur Rahman
136 | KISH/PW-25 | Irrigation Pipe Inlet 600mm dia | Nos | 15 | OG | 5C |  | Md.Khalilur Rahman
137 | KISH/PW-26 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 | P | Dropped |  | Anil Chandra Roy
138 | KISH/PW-26 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 | P | 0.3 LFY NS |  | Anil Chandra Roy
139 | KISH/PW-26 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 | P | Dropped |  | Anil Chandra Roy
140 | KISH/PW-26 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 | P | 0.3 LFY NS |  | Anil Chandra Roy
141 | KISH/PW-26 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 | OG | C:10.5OG:5 Siltation Check | 6 | Anil Chandra Roy
142 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | Nos | 1 | P | Not Started |  | Anil Chandra Roy
143 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | Nos | 1 | P | Not Started |  | Anil Chandra Roy
144 | KISH/PW-27 | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | Nos | 1 | P | Not Started |  | Anil Chandra Roy
145 | KISH/PW-27 | D 4.0 m width Chonati Causeway | Nos | 1 | OG | Layout |  | Anil Chandra Roy
146 | KISH/PW-27 | R.C.C Box Drainage Outlet 900mm x 900mm | Nos | 1 | P | Not Started |  | Anil Chandra Roy
Munshi Zahirul Islam
Md. Amirul Islam
Md.Abudl Latif
Anil Chandra Roy
Md.Khalilur Rahman

## Munshi
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 | OG |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 | OG |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 | P | Not Started |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 | P | Not Started |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 | P | Not Started |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 | P | Not Started |  | Munshi Zahirul Islam
7 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
8 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
9 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 | OG | C:2OG:4P:4 |  | Munshi Zahirul Islam
10 | KISH/PW-14 | Gokhra KhalRegulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
11 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 | OG | C:13G:3.9 |  | Munshi Zahirul Islam
12 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 | P | Not Started |  | Munshi Zahirul Islam
13 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 | OG |  |  | Munshi Zahirul Islam
14 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 | C | Diversion Channel Incomplete |  | Munshi Zahirul Islam

## Amirul
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-02 | Bata Khal Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 | C |  |  | Md. Amirul Islam
2 | KISH/PW-02 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 | C |  |  | Md. Amirul Islam
3 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 | C |  |  | Md. Amirul Islam
4 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 | C |  |  | Md. Amirul Islam
5 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 | C |  |  | Md. Amirul Islam
6 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 | C |  |  | Md. Amirul Islam
7 | KISH/PW-02 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 | C |  |  | Md. Amirul Islam
8 | KISH/PW-04 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 | C |  |  | Md. Amirul Islam
9 | KISH/PW-04 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 | C |  |  | Md. Amirul Islam
10 | KISH/PW-04 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 | C |  |  | Md. Amirul Islam
11 | KISH/PW-04 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 | C |  |  | Md. Amirul Islam
12 | KISH/PW-07 | Hazir Khal | Km | 1.73 | C | 0.200 C D:1.53 |  | Md. Amirul Islam
13 | KISH/PW-07 | Karpasha Khal | Km | 1.615 | C | 3.4 KM Complete |  | Md. Amirul Islam
14 | KISH/PW-07 | Dampara Khal | Km | 3.6 |  | 1.2 C R:2.4 Can Not Done LP |  | Md. Amirul Islam
15 | KISH/PW-07 | Baniajan | Km | 6.854 | C |  |  | Md. Amirul Islam
16 | KISH/PW-07 | Suti Khal | Km | 6.1 | C |  |  | Md. Amirul Islam
17 | KISH/PW-07 | Digha Nadi | Km | 5.7 |  | 4.5 C 1.2 R |  | Md. Amirul Islam
18 | KISH/PW-07 | Old Singua | Km | 10.86 | P | Dropped |  | Md. Amirul Islam
19 | KISH/PW-07 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 | OG | 3 KM Dropped |  | Md. Amirul Islam
20 | KISH/PW-07 | Block Road | Km |  | P | Dropped |  | Md. Amirul Islam
21 | KISH/PW-10 | Causeway 6.0m wide-1 | Nos | 1 | P | NS |  | Md. Amirul Islam
22 | KISH/PW-10 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 | OG | Return Wall |  | Md. Amirul Islam
23 | KISH/PW-10 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 | OG | OG:5.5 | 1 | Md. Amirul Islam
24 | KISH/PW-10 | Block Road | Km |  | P | CC Block Not Manufatured |  | Md. Amirul Islam
25 | KISH/PW-11 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 | OG | Loose Apron Block Placing Going o.Gate Fitting is not completed |  | Md. Amirul Islam
26 | KISH/PW-11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 | P | C:10.36R:1.5 |  | Md. Amirul Islam
27 | KISH/PW-12 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 | C |  |  | Md. Amirul Islam
28 | KISH/PW-12 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 | OG | R/S Approach Channel not done |  | Md. Amirul Islam
29 | KISH/PW-12 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 | OG |  |  | Md. Amirul Islam
30 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 | C |  |  | Md. Amirul Islam
31 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 | C | C:2D:1 |  | Md. Amirul Islam
32 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 | C |  |  | Md. Amirul Islam
33 | KISH/PW-12 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 | C |  |  | Md. Amirul Islam

## Latif
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-03 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 | C | Sign Board Remaining |  | Md.Abudl Latif
2 | KISH/PW-03 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 | OG | C:9.18R:1.2 |  | Md.Abudl Latif
3 | KISH/PW-03 | Block Road | Km |  | C |  |  | Md.Abudl Latif
4 | KISH/PW-05 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 | C | Gate Problem |  | Md.Abudl Latif
5 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 |  |  |  | Md.Abudl Latif
6 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 |  |  |  | Md.Abudl Latif
7 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 |  |  |  | Md.Abudl Latif
8 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 |  |  |  | Md.Abudl Latif
9 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 |  |  |  | Md.Abudl Latif
10 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 |  | C:4ROG:5R:3 | 3 | Md.Abudl Latif
11 | KISH/PW-05 | Block Road | Km | 12.214 |  | CC Block Manufacture Complete |  | Md.Abudl Latif
12 | KISH/PW-06 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 | C |  |  | Md.Abudl Latif
13 | KISH/PW-06 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 | C |  |  | Md.Abudl Latif
14 | KISH/PW-06 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 | C |  |  | Md.Abudl Latif
15 | KISH/PW-06 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 | C |  |  | Md.Abudl Latif
16 | KISH/PW-06 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 | C |  |  | Md.Abudl Latif
17 | KISH/PW-06 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 | OG | C:7R:1.4 |  | Md.Abudl Latif
18 | KISH/PW-06 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 | OG | C:3.0R:0.56 | 1 | Md.Abudl Latif
19 | KISH/PW-09 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali/Samer Bari CW 6.0 | Nos | 1 | OG | P:0.9 |  | Md.Abudl Latif
20 | KISH/PW-09 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj/Box Sluice | Nos | 1 | OG | Will be strated Soon |  | Md.Abudl Latif
21 | KISH/PW-09 | Causeway 6.0m wide-1 at Dampara | Nos | 1 | C |  |  | Md.Abudl Latif
22 | KISH/PW-09 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 | C |  |  | Md.Abudl Latif
23 | KISH/PW-20 | Chitra Khal 4m wide | Nos | 1 | OG | 0.95 |  | Md.Abudl Latif
24 | KISH/PW-20 | Nabinpur Khal 4m Wide | Nos | 1 | OG | 0.95 |  | Md.Abudl Latif
25 | KISH/PW-20 | Dipjuri Khal 4m CW | Nos | 1 | P | 0.9 |  | Md.Abudl Latif
26 | KISH/PW-20 | Sudhikhal 4m wide CW | Nos | 1 | OG | 0.8 |  | Md.Abudl Latif
27 | KISH/PW-20 | Chhagalia khal sluice | Nos | 1 | OG | 0.9 |  | Md.Abudl Latif
28 | KISH/PW-20 | Near nasir sluice | Nos | 1 | OG | 0.9 |  | Md.Abudl Latif
29 | KISH/PW-20 | Shingpur khal sluice | Nos | 1 | C |  |  | Md.Abudl Latif
30 | KISH/PW-20 | Gharu khal sluice | Nos | 1 | P |  |  | Md.Abudl Latif
31 | KISH/PW-20 | Irrigation Pipe Inlet 600mm dia | Nos | 36 | OG | 5 Nos 0.90 |  | Md.Abudl Latif

## Anil
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-23 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 | OG | 0.6 | 1 | Anil Chandra Roy
2 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 | OG | Bsae Dhali River Side(max0.70) |  | Anil Chandra Roy
3 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 | OG | c0.50 proj 0.75 |  | Anil Chandra Roy
4 | KISH/PW-23 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 | P |  |  | Anil Chandra Roy
5 | KISH/PW-23 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 | P |  |  | Anil Chandra Roy
6 | KISH/PW-23 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 | OG | 0.7 Will Be complete |  | Anil Chandra Roy
7 | KISH/PW-23 | Irrigation Pipe Inlet 600mm dia | Nos | 4 | OG | 2OG |  | Anil Chandra Roy
8 | KISH/PW-26 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 | P | Dropped |  | Anil Chandra Roy
9 | KISH/PW-26 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 | P | 0.3 LFY NS |  | Anil Chandra Roy
10 | KISH/PW-26 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 | P | Dropped |  | Anil Chandra Roy
11 | KISH/PW-26 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 | P | 0.3 LFY NS |  | Anil Chandra Roy
12 | KISH/PW-26 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 | OG | C:10.5OG:5 Siltation Check | 6 | Anil Chandra Roy
13 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | Nos | 1 | P | Not Started |  | Anil Chandra Roy
14 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | Nos | 1 | P | Not Started |  | Anil Chandra Roy
15 | KISH/PW-27 | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | Nos | 1 | P | Not Started |  | Anil Chandra Roy
16 | KISH/PW-27 | D 4.0 m width Chonati Causeway | Nos | 1 | OG | Layout |  | Anil Chandra Roy
17 | KISH/PW-27 | R.C.C Box Drainage Outlet 900mm x 900mm | Nos | 1 | P | Not Started |  | Anil Chandra Roy

## Khalil
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-15 | Khyerkhal RegRegulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 | P | Not Started/May Be Flood Fuse |  | Md.Khalilur Rahman
2 | KISH/PW-15 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 | C | Not Started |  | Md.Khalilur Rahman
3 | KISH/PW-16 | Markhali Khal Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 | C | Loose Appron,Diversion Channel remainig P0.80 |  | Md.Khalilur Rahman
4 | KISH/PW-16 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 14.12 | OG | C:7.5OG:6.62 | 2 | Md.Khalilur Rahman
5 | KISH/PW-16 | Block Road | Km |  |  | CC Block Complete |  | Md.Khalilur Rahman
6 | KISH/PW-17 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 | P | Dameged Reaparing Going On |  | Md.Khalilur Rahman
7 | KISH/PW-17 | Bogadia Regulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 | P | Structure:up to deck slab complete.0.70 |  | Md.Khalilur Rahman
8 | KISH/PW-17 | Box Drainage Outlet-1 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
9 | KISH/PW-17 | Box Drainage Outlet-2 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
10 | KISH/PW-17 | Box Drainage Outlet-3 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
11 | KISH/PW-17 | Box Drainage Outlet-4 | Nos | 1 | C | Gate Installation Not Done |  | Md.Khalilur Rahman
12 | KISH/PW-17 | Box Drainage Outlet-5 | Nos | 1 | P |  |  | Md.Khalilur Rahman
13 | KISH/PW-17 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 13.17 | C | Dameged Reaparing Needed |  | Md.Khalilur Rahman
14 | KISH/PW-17 | Block Road | Km |  |  | CC Block Complete |  | Md.Khalilur Rahman
15 | KISH/PW-17 | Irrigation Pipe Inlet-1 | Nos | 25 | OG | C:23 Gate Installation remaining |  | Md.Khalilur Rahman
16 | KISH/PW-18 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 | P |  |  | Md.Khalilur Rahman
17 | KISH/PW-18 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 | P |  |  | Md.Khalilur Rahman
18 | KISH/PW-18 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 | P |  |  | Md.Khalilur Rahman
19 | KISH/PW-18 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 | C | Divesion Channel Remaining |  | Md.Khalilur Rahman
20 | KISH/PW-18 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 | OG | C:0.7 | 1 | Md.Khalilur Rahman
21 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 | C |  |  | Md.Khalilur Rahman
22 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 | C |  |  | Md.Khalilur Rahman
23 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 | C |  |  | Md.Khalilur Rahman
24 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 | P |  |  | Md.Khalilur Rahman
25 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 | C |  |  | Md.Khalilur Rahman
26 | KISH/PW-21 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 | OG | Sheet Pile Drive Complete.CC going on |  | Md.Khalilur Rahman
27 | KISH/PW-21 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 | OG | Sheet Pile Drive Complete.CC Complete |  | Md.Khalilur Rahman
28 | KISH/PW-21 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 | P |  |  | Md.Khalilur Rahman
29 | KISH/PW-21 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 | P |  |  | Md.Khalilur Rahman
30 | KISH/PW-22 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 | OG | 10 KM 2 layer | 4 | Md.Khalilur Rahman
31 | KISH/PW-22 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 | P |  |  | Md.Khalilur Rahman
32 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 | C | C:0.65R:0.05 |  | Md.Khalilur Rahman
33 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 | P |  |  | Md.Khalilur Rahman
34 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 | P |  |  | Md.Khalilur Rahman
35 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 | OG |  | 1 | Md.Khalilur Rahman
36 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 | P |  |  | Md.Khalilur Rahman
37 | KISH/PW-22 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 | OG |  | 1 | Md.Khalilur Rahman
38 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 | OG |  | 1 | Md.Khalilur Rahman
39 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 | P |  |  | Md.Khalilur Rahman
40 | KISH/PW-22 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 | OG | CC Block:10000 out 20000 |  | Md.Khalilur Rahman
41 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 | P |  |  | Md.Khalilur Rahman
42 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 | P |  |  | Md.Khalilur Rahman
43 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 | P |  |  | Md.Khalilur Rahman
44 | KISH/PW-25 | Regulator 5-Vent-1 | Nos | 1 | OG | 0.75.Structure Complete |  | Md.Khalilur Rahman
45 | KISH/PW-25 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 | C | C:7R:1.5 Not As Per Design |  | Md.Khalilur Rahman
46 | KISH/PW-25 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Nos | 1 | OG | C:0.350R:1.30 |  | Md.Khalilur Rahman
47 | KISH/PW-25 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 | P | Not Started.Design Change Required |  | Md.Khalilur Rahman
48 | KISH/PW-25 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 | P | Not Started.Design Change Required |  | Md.Khalilur Rahman
49 | KISH/PW-25 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 | OG | 0.75.Structure Complete |  | Md.Khalilur Rahman
50 | KISH/PW-25 | Box Sluice-1 | Nos | 1 | P | Not Started |  | Md.Khalilur Rahman
51 | KISH/PW-25 | Irrigation Pipe Inlet 600mm dia | Nos | 15 | OG | 5C |  | Md.Khalilur Rahman

## Cost
Package Name | Component | Package2 | Unit | Qnty | Contract Value | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | Value of Work Done as on 15/3/2020 | Projection | Remarks | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature
BWDB/Kish/HFMLIP/ PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | KISH/PW-01 | Km | 2.151 | 40.94 | OG |  |  | 0 | 40.94 |  | KISH/PW-01 | Rehab | 8 | 1 | R-2 | KISH | OG |  |  | Munshi Zahirul Islam
BWDB/Kish/HFMLIP/ PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | KISH/PW-01 | Km | 1.22 | 35.88 | OG |  |  | 0 | 35.88 |  | KISH/PW-01 | Rehab | 8 | 1 | R-1 | KISH | OG |  |  | Munshi Zahirul Islam
BWDB/Kish/HFMLIP/ PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | KISH/PW-01 | Km | 1.55 | 19.18 | P | Not Started |  | 0 | 0 |  | KISH/PW-01 | Rehab | 8 | 1 | R-3 | KISH | P | Not Started |  | Munshi Zahirul Islam
BWDB/Kish/HFMLIP/ PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | KISH/PW-01 | Km | 5.625 | 309.8 | P | Not Started |  | 0 | 0 |  | KISH/PW-01 | Rehab | 8 | 1 | R-3 | KISH | P | Not Started |  | Munshi Zahirul Islam
BWDB/Kish/HFMLIP/ PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | KISH/PW-01 | Km | 1 | 45.95 | P | Not Started |  | 0 | 0 |  | KISH/PW-01 | Rehab | 8 | 1 | R-3 | KISH | P | Not Started |  | Munshi Zahirul Islam
BWDB/Kish/HFMLIP/ PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | KISH/PW-01 | Km | 1 | 44.79 | P | Not Started |  | 0 | 0 |  | KISH/PW-01 | Rehab | 2 | 1 | R-1 | KISH | P | Not Started |  | Munshi Zahirul Islam
Package No-02 /ChandpurHaor | Regulator 2 vent (1.50m X 1.80m)-1 | KISH/PW-02 | Nos | 1 | 155.5114 | C |  |  | 155.51 | 155.51 |  | KISH/PW-02 | New | 3 | 1 | N-1 | KISH | C |  |  | Md. Amirul Islam
Package No-02 /ChandpurHaor | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | KISH/PW-02 | Km | 2.98 | 31.9576 | C |  |  | 31.96 | 31.96 |  | KISH/PW-02 | New | 7 | 1 | N-2 | KISH | C |  |  | Md. Amirul Islam
Package No-02 /ChandpurHaor | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | KISH/PW-02 | Km | 4.475 | 93.4351 | C |  |  | 93.44 | 93.44 |  | KISH/PW-02 | New | 7 | 1 | N-3 | KISH | C |  |  | Md. Amirul Islam
Package No-02 /ChandpurHaor | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | KISH/PW-02 | Km | 2.225 | 52.1722 | C |  |  | 52.17 | 52.17 |  | KISH/PW-02 | New | 7 | 1 | N-4 | KISH | C |  |  | Md. Amirul Islam
Package No-02 /ChandpurHaor | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | KISH/PW-02 | Km | 0.46 | 16.201 | C |  |  | 16.2 | 16.2 |  | KISH/PW-02 | New | 7 | 1 | N-5 | KISH | C |  |  | Md. Amirul Islam
Package No-02 /ChandpurHaor | Bata khal from km, 0.000 to km. 2.790 km | KISH/PW-02 | Km | 2.79 | 68.8599 | C |  |  | 68.86 | 68.86 |  | KISH/PW-02 | New | 7 | 1 | N-6 | KISH | C |  |  | Md. Amirul Islam
Package No-02 /ChandpurHaor | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | KISH/PW-02 | Km | 0.315 | 14.8109 | C |  |  | 14.81 | 14.81 |  | KISH/PW-02 | New | 11 | 1 | N-7 | KISH | C |  |  | Md. Amirul Islam
Package No.-03/ Nunnir Haor (Part-A) | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | KISH/PW-03 | Nos | 1 | 155.5114 | C | Sign Board Remaining |  | 155.51 | 155.51 |  | KISH/PW-03 | New | 3 | 1 | N-2 | KISH | C | Sign Board Remaining |  | Md.Abudl Latif
Package No.-03/ Nunnir Haor (Part-A) | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | KISH/PW-03 | Km | 10.383 | 247.1255 | OG | C:9.18R:1.2 |  | 216.6514 | 247.1255 |  | KISH/PW-03 | New | 11 | 1 | N-2 | KISH | OG | C:9.18R:1.2 |  | Md.Abudl Latif
Package No.-03/ Nunnir Haor (Part-A) | Block Road | KISH/PW-03 | Km |  | 286.8206 | C |  |  | 286.8206 | 286.8206 |  | KISH/PW-03 | New | 11 | 1 | N-2 | KISH | C |  |  | Md.Abudl Latif
Package No.-04/ Nunnir Haor (Part B+C) | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | KISH/PW-04 | Nos | 1 | 97.9579 | C |  |  | 97.9579 | 97.9579 |  | KISH/PW-04 | New | 3 | 1 | N-2 | KISH | C |  |  | Md. Amirul Islam
Package No.-04/ Nunnir Haor (Part B+C) | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | KISH/PW-04 | Nos | 1 | 97.9579 | C |  |  | 97.9579 | 97.9579 |  | KISH/PW-04 | New | 3 | 1 | N-2 | KISH | C |  |  | Md. Amirul Islam
Package No.-04/ Nunnir Haor (Part B+C) | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | KISH/PW-04 | Nos | 1 | 257.73 | C |  |  | 257.73 | 257.73 |  | KISH/PW-04 | New | 3 | 1 | N-2 | KISH | C |  |  | Md. Amirul Islam
Package No.-04/ Nunnir Haor (Part B+C) | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | KISH/PW-04 | Km | 6.471 | 256.8713 | C |  |  | 256.8713 | 256.8713 |  | KISH/PW-04 | New | 11 | 1 | N-2 | KISH | C |  |  | Md. Amirul Islam
Package No.-05/ NunnirHaor (Part-A& C) | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | KISH/PW-05 | Nos | 1 | 190.22 | C | Gate Problem |  | 184.77 | 190.22 |  | KISH/PW-05 | New | 3 | 1 | N-2 | KISH | C | Gate Problem |  | Md.Abudl Latif
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | KISH/PW-05 | Km | 1.697 | 35.282 | P |  |  | 0 | 0 |  | KISH/PW-05 | New | 11 | 1 | N-2 | KISH | P |  |  | Md.Abudl Latif
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | KISH/PW-05 | Km | 0.083 | 4.0969 | p |  |  | 0 | 0 |  | KISH/PW-05 | New | 11 | 1 | N-2 | KISH | p |  |  | Md.Abudl Latif
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | KISH/PW-05 | Km | 0.59 | 8.7693 | p |  |  | 0 | 0 |  | KISH/PW-05 | New | 11 | 1 | N-2 | KISH | p |  |  | Md.Abudl Latif
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | KISH/PW-05 | Km | 7.494 | 156.8227 | p |  |  | 0 | 0 |  | KISH/PW-05 | New | 11 | 1 | N-2 | KISH | p |  |  | Md.Abudl Latif
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | KISH/PW-05 | Km | 1.499 | 28.9482 | p |  |  | 0 | 0 |  | KISH/PW-05 | New | 11 | 1 | N-2 | KISH | p |  |  | Md.Abudl Latif
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | KISH/PW-05 | Km | 0.851 | 17.8983 | OG | C:4ROG:5R:3 | 3 | 91.443 | 189.9855 |  | KISH/PW-05 | New | 11 | 1 | N-2 | KISH | OG | C:4ROG:5R:3 | 3 | Md.Abudl Latif
Package No.-05/ NunnirHaor (Part-A& C) | Block Road | KISH/PW-05 | Km | 12.214 | 325.54 | P | CC Block Manufacture Complete |  | 253.85 | 253.85 |  | KISH/PW-05 | New | 11 | 1 | N-2 | KISH | P | CC Block Manufacture Complete |  | Md.Abudl Latif
Package No.-06/ NunnirHaor (Part-A) | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | KISH/PW-06 | Nos | 1 | 227.8819 | C |  |  | 227.8819 | 227.8819 |  | KISH/PW-06 | New | 3 | 1 | N-2 | KISH | C |  |  | Md.Abudl Latif
Package No.-06/ NunnirHaor (Part-A) | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | KISH/PW-06 | Km | 4.5 | 67.5613 | C |  |  | 67.5613 | 67.5613 |  | KISH/PW-06 | New | 7 | 1 | N-2 | KISH | C |  |  | Md.Abudl Latif
Package No.-06/ NunnirHaor (Part-A) | Samar bari khal-2 form km. 0.20 to km 3.99 | KISH/PW-06 | Km | 3.99 | 99.5765 | C |  |  | 99.5765 | 99.5765 |  | KISH/PW-06 | New | 7 | 1 | N-2 | KISH | C |  |  | Md.Abudl Latif
Package No.-06/ NunnirHaor (Part-A) | Mahinhandra khal-3 from km 1.00 to km 1.90 | KISH/PW-06 | Km | 1.9 | 28.0877 | C |  |  | 28.0877 | 28.0877 |  | KISH/PW-06 | New | 7 | 1 | N-2 | KISH | C |  |  | Md.Abudl Latif
Package No.-06/ NunnirHaor (Part-A) | Kata khal-4 from km 0.100 to km 0.600 | KISH/PW-06 | Km | 0.6 | 16.0154 | C |  |  | 16.0154 | 16.0154 |  | KISH/PW-06 | New | 7 | 1 | N-2 | KISH | C |  |  | Md.Abudl Latif
Package No.-06/ NunnirHaor (Part-A) | Kurigai Gang-5 from km 0.00 to km 8.400 | KISH/PW-06 | Km | 8.4 | 225.9517 | OG | C:7R:1.4 |  | 188.2931 | 225.9517 |  | KISH/PW-06 | New | 7 | 1 | N-2 | KISH | OG | C:7R:1.4 |  | Md.Abudl Latif
Package No.-06/ NunnirHaor (Part-A) | Beri Gang-6 from km 0.00 to km 3.56 | KISH/PW-06 | Km | 3.56 | 109.6136 | OG | C:3.0R:0.56 | 1 | 92.371 | 109.6136 |  | KISH/PW-06 | New | 7 | 1 | N-2 | KISH | OG | C:3.0R:0.56 | 1 | Md.Abudl Latif
Package No.-07/ Boro Haor | Hazir Khal | KISH/PW-07 | Km | 1.73 | 20.5494 | C | 0.200 C D:1.53 |  | 2.6862 | 2.69 |  | KISH/PW-07 | New | 7 | 1 | N-3 | KISH | C | 0.200 C D:1.53 |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Karpasha Khal | KISH/PW-07 | Km | 1.615 | 26.0781 | C | 3.4 KM Complete |  | 26.0781 | 54.7318 |  | KISH/PW-07 | New | 7 | 1 | N-3 | KISH | C | 3.4 KM Complete |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Dampara Khal | KISH/PW-07 | Km | 3.6 | 46.8873 | p | 1.2 C R:2.4 Can Not Done LP |  | 15.6291 | 15.63 |  | KISH/PW-07 | New | 7 | 1 | N-3 | KISH | p | 1.2 C R:2.4 Can Not Done LP |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Baniajan | KISH/PW-07 | Km | 6.854 | 130.1184 | C |  |  | 130.1184 | 130.1184 |  | KISH/PW-07 | New | 7 | 1 | N-3 | KISH | C |  |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Suti Khal | KISH/PW-07 | Km | 6.1 | 120.3313 | C |  |  | 120.3313 | 120.3313 |  | KISH/PW-07 | New | 7 | 1 | N-3 | KISH | C |  |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Digha Nadi | KISH/PW-07 | Km | 5.7 | 424.0032 | p | 4.5 C 1.2 R |  | 334.7394 | 334.74 |  | KISH/PW-07 | New | 7 | 1 | N-3 | KISH | p | 4.5 C 1.2 R |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Old Singua | KISH/PW-07 | Km | 10.86 | 197.6384 | P | Dropped |  | 0 | 0 |  | KISH/PW-07 | New | 7 | 1 | N-3 | KISH | P | Dropped |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | KISH/PW-07 | Km | 3.879 | 35.33 | OG | 3 KM Dropped |  | 8.013 | 8.01 |  | KISH/PW-07 | New | 11 | 1 | N-3 | KISH | OG | 3 KM Dropped |  | Md. Amirul Islam
Package No.-07/ Boro Haor | Block Road | KISH/PW-07 | Km |  | 55.74 | P | Dropped |  | 0 | 0 |  | KISH/PW-07 | New | 11 | 1 | N-3 | KISH | P | Dropped |  | Md. Amirul Islam
Package No.PW-09/Kish/ Boro Haor | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | KISH/PW-09 | Nos | 1 | 185.76 | OG | P:0.9 |  | 167.184 | 185.76 |  | KISH/PW-09 | New | 3 | 1 | N-3 | KISH | OG | P:0.9 |  | Md.Abudl Latif
Package No.PW-09/Kish/ Boro Haor | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | KISH/PW-09 | Nos | 1 | 211.88 | OG | Will be strated Soon |  | 0 | 105.94 |  | KISH/PW-09 | New | 3 | 1 | N-3 | KISH | OG | Will be strated Soon |  | Md.Abudl Latif
Package No.PW-09/Kish/ Boro Haor | Causeway 6.0m wide-1 at Dampara | KISH/PW-09 | Nos | 1 | 174.59 | C |  |  | 174.59 | 174.59 |  | KISH/PW-09 | New | 5 | 1 | N-3 | KISH | C |  |  | Md.Abudl Latif
Package No.PW-09/Kish/ Boro Haor | Causeway 4.0m wide-1 at Karpasha | KISH/PW-09 | Nos | 1 | 143.6138 | C |  |  | 143.6138 | 143.6138 |  | KISH/PW-09 | New | 5 | 1 | N-3 | KISH | C |  |  | Md.Abudl Latif
Package No.: PW-10/ Noapara Haor | Causeway 6.0m wide-1 | KISH/PW-10 | Nos | 1 | 137.35 | P | NS |  | 0 | 0 |  | KISH/PW-10 | New | 3 | 1 | N-4 | KISH | P | NS |  | Md. Amirul Islam
Package No.: PW-10/ Noapara Haor | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | KISH/PW-10 | Nos | 1 | 128.67 | OG | Return Wall |  | 77.202 | 109.3695 |  | KISH/PW-10 | New | 3 | 1 | N-4 | KISH | OG | Return Wall |  | Md. Amirul Islam
Package No.: PW-10/ Noapara Haor | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | KISH/PW-10 | Km | 11.75 | 274.06 | OG | OG:5.5 | 1 | 128.2834 | 274.06 |  | KISH/PW-10 | New | 11 | 1 | N-4 | KISH | OG | OG:5.5 | 1 | Md. Amirul Islam
Package No.: PW-10/ Noapara Haor | Block Road | KISH/PW-10 | Km |  | 343.88 | P | CC Block Not Manufatured |  | 0 | 0 | Scope of Block Manufacture | KISH/PW-10 | New | 11 | 1 | N-4 | KISH | P | CC Block Not Manufatured |  | Md. Amirul Islam
Package No.-11/ Noapara Haor | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | KISH/PW-11 | Nos | 1 | 274.49 | OG | Loose Apron Block Placing Going o.Gate Fitting is not completed |  | 223.04 | 274.49 |  | KISH/PW-11 | New | 3 | 1 | N-4 | KISH | OG | Loose Apron Block Placing Going o.Gate Fitting is not completed |  | Md. Amirul Islam
Package No.-11/ Noapara Haor | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | KISH/PW-11 | Km | 10.86 | 245.37 | P | C:10.36R:1.5 |  | 211.4791 | 211.48 |  | KISH/PW-11 | New | 11 | 1 | N-4 | KISH | P | C:10.36R:1.5 |  | Md. Amirul Islam
Package No.-11/ Noapara Haor | Block Road | KISH/PW-11 | Km |  | 294.89 | P | CC Block Manufactured |  | 198.45 | 198.45 |  | KISH/PW-11 | [8 empty] | Md. Amirul Islam
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | KISH/PW-12 | Nos | 1 | 253.8935 | C |  |  | 253.89 | 253.89 |  | KISH/PW-12 | New | 3 | 1 | N-4 | KISH | C |  |  | Md. Amirul Islam
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | KISH/PW-12 | Nos | 1 | 277.0365 | OG | R/S Approach Channel not done |  | 269.98 | 269.98 |  | KISH/PW-12 | New | 3 | 1 | N-4 | KISH | OG | R/S Approach Channel not done |  | Md. Amirul Islam
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | KISH/PW-12 | Km | 3.9 | 18.397 | OG |  |  | 0 | 18.4 |  | KISH/PW-12 | New | 7 | 1 | N-4 | KISH | OG |  |  | Md. Amirul Islam
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NaluarKhal km 0.200 to km 0.800 = 0.600 km | KISH/PW-12 | Km | 0.6 | 4.398 | C |  |  | 4.4 | 4.4 |  | KISH/PW-12 | New | 7 | 1 | N-4 | KISH | C |  |  | Md. Amirul Islam
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | KISH/PW-12 | Km | 3 | 99.257 | C | C:2D:1 |  | 66.17 | 66.17 |  | KISH/PW-12 | New | 7 | 1 | N-4 | KISH | C | C:2D:1 |  | Md. Amirul Islam
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NabinpurKhal km 4.000 to km 6.800= 2.800 km | KISH/PW-12 | Km | 2.8 | 110.6945 | C |  |  | 110.69 | 110.69 |  | KISH/PW-12 | New | 7 | 1 | N-4 | KISH | C |  |  | Md. Amirul Islam
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | KISH/PW-12 | Km | 0.367 | 167.984 | C |  |  | 167.98 | 167.98 |  | KISH/PW-12 | New | 7 | 1 | N-4 | KISH | C |  |  | Md. Amirul Islam
Package No.-13/ Naogaon Haor (Part-A) | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | KISH/PW-13 | Nos | 1 | 232.96 | P | Diversion Channel Incomplete |  | 228.44 | 228.44 |  | KISH/PW-13 | New | 3 | 1 | N-5 | KISH | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
Package No.-13/ Naogaon Haor (Part-A) | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | KISH/PW-13 | Nos | 1 | 193 | P | Diversion Channel Incomplete |  | 180.8 | 180.8 |  | KISH/PW-13 | New | 3 | 1 | N-5 | KISH | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
Package No.-13/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | KISH/PW-13 | Km | 10 | 489.18 | OG | C:2OG:4P:4 |  | 195.672 | 293.508 |  | KISH/PW-13 | New | 11 | 1 | N-5 | KISH | OG | C:2OG:4P:4 |  | Munshi Zahirul Islam
Package No.-13/ Naogaon Haor (Part-A) | Block Road | KISH/PW-13 | Km |  | 70.99 | p | CC Block Complete |  | 58.34 | 58.34 |  | KISH/PW-13 | [8 empty] | Munshi Zahirul Islam
Package No.-14/ Naogaon Haor (Part-A) | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | KISH/PW-14 | Nos | 1 | 176.58 | P | Diversion Channel Incomplete |  | 168.13 | 168.13 |  | KISH/PW-14 | New | 3 | 1 | N-5 | KISH | P | Diversion Channel Incomplete |  | Munshi Zahirul Islam
Package No.-14/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | KISH/PW-14 | Km | 16.9 | 500.08 | OG | C:13G:3.9 |  | 442.38 | 500.08 |  | KISH/PW-14 | New | 11 | 1 | N-5 | KISH | OG | C:13G:3.9 |  | Munshi Zahirul Islam
Package No.-14/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | KISH/PW-14 | Km |  | 162.75 | OG | Block Complete |  | 142.3339 | 142.3339 |  | KISH/PW-14 | [8 empty] | Munshi Zahirul Islam
Package No.-15/ Naogaon Haor- Part-B | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | KISH/PW-15 | Nos | 1 | 166.9 | P | Not Started/May Be Flood Fuse |  | 0 | 0 |  | KISH/PW-15 | New | 3 | 1 | N-5 | KISH | P | Not Started/May Be Flood Fuse |  | Md.Khalilur Rahman
Package No.-15/ Naogaon Haor- Part-B | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | KISH/PW-15 | Km | 9 | 437.59 | C | Not Started Repair |  | 437.59 | 437.59 |  | KISH/PW-15 | New | 11 | 1 | N-5 | KISH | C | Not Started |  | Md.Khalilur Rahman
Package No.-15/ Naogaon Haor- Part-B | Block Road | KISH/PW-15 | Km |  | 96.35 | P | CC Block Complete |  | 0 | 82.09 |  | KISH/PW-15 | New | 11 | [6 empty] | Md.Khalilur Rahman
Package No.-16/ NaogaonHaor-Part-B | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | KISH/PW-16 | Nos | 1 | 267.88 | P | Loose Appron,Diversion Channel remainig P0.80 |  | 382.84 | 382.84 |  | KISH/PW-16 | New | 3 | 1 | N-5 | KISH | C | Loose Appron,Diversion Channel remainig P0.80 |  | Md.Khalilur Rahman
Package No.-16/ NaogaonHaor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | KISH/PW-16 | km | 14.12 | 343.32 | OG | C:7.5OG:6.62 | 2 | 262.8392 | 343.32 |  | KISH/PW-16 | New | 11 | 1 | N-5 | KISH | OG | C:7.5OG:6.62 | 2 | Md.Khalilur Rahman
Package No.-16/ NaogaonHaor-Part-B | Block Road | KISH/PW-16 | Km |  | 167.97 | P | CC Block Complete |  | 146.01 | 167.97 |  | KISH/PW-16 | New | 11 | 1 | N-5 | KISH | P | CC Block Complete |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | KISH/PW-17 | Nos | 1 | 348.66 | P | Dameged Reaparing Going On |  | 418.02 | 418.02 |  | KISH/PW-17 | New | 3 | 1 | N-5 | KISH | P | Dameged Reaparing Going On |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | KISH/PW-17 | Nos | 1 | 217.5324 | P | Structure:up to deck slab complete.0.70 |  | 152.27 | 152.27 |  | KISH/PW-17 | New | 3 | 1 | N-5 | KISH | P | Structure:up to deck slab complete.0.70 |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-1 | KISH/PW-17 | Nos | 1 | 35.4887 | C | Gate Installation Not Done |  | 34.25 | 35.4887 |  | KISH/PW-17 | New | 4 | 1 | N-5 | KISH | C | Gate Installation Not Done |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-2 | KISH/PW-17 | Nos | 1 | 35.4887 | C | Gate Installation Not Done |  | 34.25 | 35.4887 |  | KISH/PW-17 | New | 4 | 1 | N-5 | KISH | C | Gate Installation Not Done |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-3 | KISH/PW-17 | Nos | 1 | 35.4887 | C | Gate Installation Not Done |  | 34.25 | 35.4887 |  | KISH/PW-17 | New | 4 | 1 | N-5 | KISH | C | Gate Installation Not Done |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-4 | KISH/PW-17 | Nos | 1 | 35.4887 | C | Gate Installation Not Done |  | 34.25 | 35.4887 |  | KISH/PW-17 | New | 4 | 1 | N-5 | KISH | C | Gate Installation Not Done |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-5 | KISH/PW-17 | Nos | 1 | 35.4887 | P |  |  | 0 | 0 |  | KISH/PW-17 | New | 4 | 1 | N-5 | KISH | P |  |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | KISH/PW-17 | Km | 1 | 460.54 | C | Dameged Reaparing Needed |  | 460.54 | 460.54 |  | KISH/PW-17 | New | 11 | 1 | N-5 | KISH | C | Dameged Reaparing Needed |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Block Road | KISH/PW-17 | Km |  | 89.5 | P | CC Block Complete |  | 72.59 | 89.5 |  | KISH/PW-17 | New | 11 | 1 | N-5 |  | P | CC Block Complete |  | Md.Khalilur Rahman
Package No.-17/ Naogaon Haor-Part-B | Irrigation Pipe Inlet-1 | KISH/PW-17 | Nos | 25 | 274.47 | OG | C:23 Gate Installation remaining |  | 246.56 | 274.47 |  | KISH/PW-17 | New | 1 | 1 | N-5 | KISH | OG | C:23 Gate Installation remaining |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-1 DheuhalKhal at km 12.44 | KISH/PW-18 | Nos | 1 | 159.8606 | P | Not started |  | 0 | 0 | May be Converted to Flood Fuse | KISH/PW-18 | New | 5 | 1 |  | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | KISH/PW-18 | Nos | 1 | 161.4295 | P | Not started |  | 0 | 0 | May be Converted to Flood Fuse | KISH/PW-18 | New | 5 | 1 |  | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-3 NeoraKhal at km 44.20 | KISH/PW-18 | Nos | 1 | 186.8205 | P | Washed Out |  | 182.82 | 182.82 |  | KISH/PW-18 | New | 5 | 1 |  | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | KISH/PW-18 | Nos | 1 | 265.5873 | P | Divesion Channel Remaining |  | 244.31 | 265.5873 |  | KISH/PW-18 | New | 5 | 1 |  | KISH | C | Divesion Channel Remaining |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | KISH/PW-18 | Km | 4.28 | 101.2011 | OG | C:0.7 | 1 | 70 | 101.2 |  | KISH/PW-18 | New | 7 | 1 |  | KISH | OG | C:0.7 | 1 | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | KISH/PW-18 | Km | 1.51 | 35.7041 | C |  |  | 35.7041 | 35.7041 |  | KISH/PW-18 | New | 7 | 1 |  | KISH | C |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | KISH/PW-18 | Km | 0.725 | 17.1427 | C |  |  | 17.1427 | 17.1427 |  | KISH/PW-18 | New | 7 | 1 |  | KISH | C |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | KISH/PW-18 | Km | 2.515 | 59.4674 | C |  |  | 59.4674 | 59.4674 |  | KISH/PW-18 | New | 7 | 1 |  | KISH | C |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | KISH/PW-18 | Km | 5.985 | 141.516 | P |  |  | 0 | 0 |  | KISH/PW-18 | New | 7 | 1 |  | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | KISH/PW-18 | Km | 7.91 | 187.0328 | C |  |  | 187.0328 | 187.0328 |  | KISH/PW-18 | New | 7 | 1 |  | KISH | C |  |  | Md.Khalilur Rahman
BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | KISH/PW-19 | Km | 15.82 | 472.9622 | OG | 3.5KM C |  | 104.6377 | 189.1849 |  | KISH/PW-19 | New | 7 | 1 | N-5 | KISH | P | Not Started |  | Munshi Zahirul Islam
BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | KISH/PW-19 | Km | 7.113 | 374.9638 | OG | 2KM C |  | 105.475 | 158.2126 |  | KISH/PW-19 | New | 7 | 1 | N-5 | KISH | OG |  |  | Munshi Zahirul Islam
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chitra Khal 4m wide | KISH/PW-20 | Nos | 1 | 136.31 | OG | 0.95 |  | 129.4945 | 136.31 |  | KISH/PW-20 | New | 5 | 1 |  | KISH | OG | 0.95 |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Nabinpur Khal 4m Wide | KISH/PW-20 | Nos | 1 | 193.69 | OG | 0.95 |  | 184.0055 | 193.69 |  | KISH/PW-20 | New | 5 | 1 |  | KISH | OG | 0.95 |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Dipjuri Khal 4m CW | KISH/PW-20 | Nos | 1 | 185.03 | P | 0.9 |  | 166.527 | 166.527 |  | KISH/PW-20 | New | 5 | 1 |  | KISH | P | 0.9 |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Sudhikhal 4m wide CW | KISH/PW-20 | Nos | 1 | 136.66 | OG | 0.8 |  | 109.328 | 109.328 |  | KISH/PW-20 | New | 5 | 1 |  | KISH | OG | 0.8 |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chhagalia khal sluice | KISH/PW-20 | Nos | 1 | 41.0186 | OG | 0.9 |  | 36.9167 | 41.0186 |  | KISH/PW-20 | New | 3 | 1 |  | KISH | OG | 0.9 |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Near nasir sluice | KISH/PW-20 | Nos | 1 | 42.7991 | OG | 0.9 |  | 38.5192 | 42.7991 |  | KISH/PW-20 | New | 3 | 1 |  | KISH | OG | 0.9 |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Shingpur khal sluice | KISH/PW-20 | Nos | 1 | 41.9704 | C |  |  | 41.9704 | 41.9704 |  | KISH/PW-20 | New | 3 | 1 |  | KISH | C |  |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Gharu khal sluice | KISH/PW-20 | Nos | 1 | 41.9704 | P |  |  | 0 | 0 |  | KISH/PW-20 | New | 3 | 1 |  | KISH | P |  |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Irrigation Pipe Inlet 600mm dia | KISH/PW-20 | Nos | 36 | 334.27 | OG | 5 Nos 0.90 |  | 41.7837 | 46.4264 | Speed up for Progress | KISH/PW-20 | New | 1 | 1 |  | KISH | OG | 5 Nos 0.90 |  | Md.Abudl Latif
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | KISH/PW-21 | Nos | 1 | 321.3991 | OG | Sheet Pile Drive Complete.CC going on |  | 64.2798 | 192.8394 |  | KISH/PW-21 | New | 3 | 1 | N-6 | KISH | OG | Sheet Pile Drive Complete.CC going on |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | KISH/PW-21 | Nos | 1 | 156.6821 | OG | Sheet Pile Drive Complete.CC Complete |  | 31.3364 | 94.0092 |  | KISH/PW-21 | New | 3 | 1 | N-6 | KISH | OG | Sheet Pile Drive Complete.CC Complete |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | KISH/PW-21 | Nos | 5 | 120.5564 | P | Not Started |  | 0 | 0 |  | KISH/PW-21 | New | 12 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | KISH/PW-21 | Km | 9.494 | 329.1074 | P | Not Started |  | 0 | 0 |  | KISH/PW-21 | New | 11 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | KISH/PW-22 | Km | 10.463 | 235.9924 | OG | 10 KM 2 layer |  | 94.397 | 212.3932 |  | KISH/PW-22 | New | 11 | 1 | N-6 | KISH | OG | 10 KM 2 layer | 4 | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | KISH/PW-22 | Km | 1 | 18.1492 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chandpur Khal from km. 0.000 to km. 0.700 | KISH/PW-22 | Km | 0.7 | 28.0679 | C | C:0.65R:0.05 |  | 26.063 | 26.063 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | C | C:0.65R:0.05 |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Baduti Khal from km. 0.000 to km. 1.000 | KISH/PW-22 | Km | 1 | 5.8814 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kanala Khal from km. 0.000 to km. 0.584 | KISH/PW-22 | Km | 0.584 | 8.1389 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kursi Khal from km. 0.000 to km. 2.900 | KISH/PW-22 | Km | 2.9 | 84.8797 | OG |  | 1 | 0 | 84.8797 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | OG |  | 1 | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Bamuna Khal from km. 0.000 to km. 1.400 | KISH/PW-22 | Km | 1.4 | 11.9047 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chouganga Khal from km. 1.700 to km. 1.900 | KISH/PW-22 | Km | 1.9 | 2.4463 | OG |  | 1 | 0 | 2.45 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | OG |  | 1 | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Maora Khal from km. 0.000 to km. 1.700 | KISH/PW-22 | Km | 1.7 | 14.6073 | OG |  | 1 | 0 | 14.61 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | OG |  | 1 | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Burimara Khal from km. 0.000 to km. 0.439 | KISH/PW-22 | Km | 0.439 | 4.4592 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 7 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | KISH/PW-22 | Nos | 1 | 195.2169 | OG | CC Block:10000 out 20000 |  | 25.9 | 31.4 |  | KISH/PW-22 | New | 5 | 1 | N-6 | KISH | OG | CC Block:10000 out 20000 |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-1 | KISH/PW-22 | Nos | 1 | 36.662 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 4 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-2 | KISH/PW-22 | Nos | 1 | 36.662 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 4 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-3 | KISH/PW-22 | Nos | 1 | 36.662 | P |  |  | 0 | 0 |  | KISH/PW-22 | New | 4 | 1 | N-6 | KISH | P |  |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | KISH/PW-23 | Km | 4.51 | 107.4208 | OG | 0.6 | 1 | 60 | 107.42 |  | KISH/PW-23 | New | 11 | 1 | N-7 | KISH | OG | 0.6 | 1 | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | KISH/PW-23 | Nos | 1 | 295.5262 | OG | Bsae Dhali River Side(max0.70) |  | 118.21 | 206.87 |  | KISH/PW-23 | New | 3 | 1 | N-7 | KISH | OG | Bsae Dhali River Side(max0.70) |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | KISH/PW-23 | Nos | 1 | 227.0604 | OG | c0.50 proj 0.75 |  | 113.53 | 170.3 |  | KISH/PW-23 | New | 3 | 1 | N-7 | KISH | OG | c0.50 proj 0.75 |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | KISH/PW-23 | Km | 1.775 | 28.5772 | P |  |  | 0 | 0 |  | KISH/PW-23 | New | 7 | 1 | N-7 | KISH | P |  |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | KISH/PW-23 | km | 0.15 | 3.8604 | P |  |  | 0 | 0 |  | KISH/PW-23 | New | 7 | 1 | N-7 | KISH | P |  |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | KISH/PW-23 | Nos | 1 | 38.9293 | OG | 0.7 Will Be complete |  | 27.25 | 27.25 |  | KISH/PW-23 | New | 4 | 1 | N-7 | KISH | OG | 0.7 Will Be complete |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Irrigation Pipe Inlet 600mm dia | KISH/PW-23 | Nos | 4 | 62.862 | OG | 2OG |  | 15.72 | 31.43 |  | KISH/PW-23 | New | 1 | 1 | N-7 | KISH | OG | 2OG |  | Anil Chandra Roy
Package No.-24/ Dakshiner Haor. | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | KISH/PW-24 | Nos | 19.843 | 1149.1962 | C |  |  | 1149.1962 | 1149.1962 |  | KISH/PW-24 | New | 11 | 1 | N-8 | KISH | C | Diversion Channel Incomplete |  | Munshi Zahirul Islam
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Regulator 5-Vent-1 | KISH/PW-25 | Nos | 1 | 405.9371 | OG | 0.75.Structure Complete |  | 304.4528 | 304.4528 |  | KISH/PW-25 | New | 3 | 1 | N-8 | KISH | OG | 0.75.Structure Complete |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | KISH/PW-25 | Km | 8.595 | 320.0346 | C | C:7R:1.5 Not As Per Design |  | 260.49 | 260.49 |  | KISH/PW-25 | New | 7 | 1 | N-8 | KISH | C | C:7R:1.5 Not As Per Design |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | KISH/PW-25 | Nos | 1.65 | 54.4035 | OG | C:0.350R:1.30 |  | 9.89 | 54.4 |  | KISH/PW-25 | New | 7 | 1 | N-8 | KISH | OG | C:0.350R:1.30 |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Joyshiddhi Causeway 6.0m wide-1 | KISH/PW-25 | Nos | 1 | 346.4138 | P | Not Started.Design Change Required |  | 0 | 0 |  | KISH/PW-25 | New | 5 | 1 | N-8 | KISH | P | Not Started.Design Change Required |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Khal Causeway 6.0m wide-2 | KISH/PW-25 | Nos | 1 | 288.0795 | P | Not Started.Design Change Required |  | 0 | 0 |  | KISH/PW-25 | New | 5 | 1 | N-8 | KISH | P | Not Started.Design Change Required |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Kha Causeway 4.0m wide-1 | KISH/PW-25 | Nos | 1 | 189.5297 | OG | 0.75.Structure Complete |  | 142.15 | 142.15 |  | KISH/PW-25 | New | 5 | 1 | N-8 | KISH | OG | 0.75.Structure Complete |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Box Sluice-1 | KISH/PW-25 | Nos | 1 | 41.8221 | P | Not Started |  | 0 | 0 |  | KISH/PW-25 | New | 4 | 1 | N-8 | KISH | P | Not Started |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Irrigation Pipe Inlet 600mm dia | KISH/PW-25 | Nos | 15 | 118.5673 | OG | 5C |  | 39.52 | 39.52 |  | KISH/PW-25 | New | 1 | 1 | N-8 | KISH | OG | 5C |  | Md.Khalilur Rahman
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | KISH/PW-26 | Km | 0.54 | 22.7161 | P | Dropped |  | 0 | 0 |  | KISH/PW-26 | New | 11 | 1 | N-9 | KISH | P | Dropped |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | KISH/PW-26 | Km | 3.96 | 71.5264 | P | 0.3 LFY NS |  | 5.42 | 5.42 |  | KISH/PW-26 | New | 7 | 1 | N-9 | KISH | P | 0.3 LFY NS |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | KISH/PW-26 | Km | 2.1 | 12.7224 | P | Dropped |  | 0 | 0 |  | KISH/PW-26 | New | 7 | 1 | N-9 | KISH | P | Dropped |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | KISH/PW-26 | Km | 1.14 | 16.3878 | P | 0.3 LFY NS |  | 4.31 | 4.31 |  | KISH/PW-26 | New | 7 | 1 | N-9 | KISH | P | 0.3 LFY NS |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | SutiNadi from km 2.200 to km 17.700= 15.500 km) | KISH/PW-26 | Km | 15.5 | 367.3183 | OG | C:10.5OG:5 Siltation Check | 6 | 248.83 | 248.83 |  | KISH/PW-26 | New | 7 | 1 | N-9 | KISH | OG | C:10.5OG:5 Siltation Check | 6 | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-27 Sonai Haor | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | KISH/PW-27 | Nos | 1 | 156.62 | P | Not Started |  | 0 | 0 |  | KISH/PW-27 | New | 3 | 1 | N-9 | KISH | P | Not Started |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-27 Sonai Haor | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | KISH/PW-27 | Nos | 1 | 148.01 | P | Not Started |  | 0 | 0 |  | KISH/PW-27 | New | 3 | 1 | N-9 | KISH | P | Not Started |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-27 Sonai Haor | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | KISH/PW-27 | Nos | 1 | 406.93 | P | Not Started |  | 0 | 0 |  | KISH/PW-27 | New | 5 | 1 | N-9 | KISH | P | Not Started |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-27 Sonai Haor | D 4.0 m width Chonati Causeway | KISH/PW-27 | Nos | 1 | 159.19 | OG | Layout |  | 0 | 119.37 |  | KISH/PW-27 | New | 5 | 1 | N-9 | KISH | OG | Layout |  | Anil Chandra Roy
BWDB/Kish/HFMLIP/ PW-27 Sonai Haor | R.C.C Box Drainage Outlet 900mm x 900mm | KISH/PW-27 | Nos | 1 | 41.87 | P | Not Started |  | 0 | 0 |  | KISH/PW-27 | New | 4 | 1 | N-9 | KISH | P | Not Started |  | Anil Chandra Roy
23194.7068
|  |  |  | Code | TS | [5 empty] | Completed | Ongoing | Problem
|  |  | Inlet | 1 | 4 | [5 empty] | 0 | 4 | 0 | C | OG | P
|  |  | Reg Rehb | 2 | 1 | [5 empty] | 0 | 0 | 1 | C | OG | P
|  |  | Reg Connst | 3 | 32 | [5 empty] | 10 | 12 | 10 | C | OG | P
|  |  | Box | 4 | 11 | [5 empty] | 4 | 1 | 6 | C | OG | P
|  |  | Causeway | 5 | 16 | [5 empty] | 3 | 6 | 7 | C | OG | P
|  |  | Bridge | 6 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  | Khal/Riv New | 7 | 48 | [5 empty] | 23 | 10 | 15 | C | OG | P
|  |  | Khal/Riv Rehab | 8 | 5 | [5 empty] | 0 | 2 | 3 | C | OG | P
|  |  |  | 9 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  |  | 10 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  | Emb | 11 | 28 | [5 empty] | 6 | 9 | 13 | C | OG | P
|  |  | Rehab Reg New | 12 | 1 | [5 empty] | 0 | 0 | 1 | C | OG | P
|  |  |  | 13 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  |  | 14 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  |  | 15 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  |  | 16 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  |  | 17 | 0 | [5 empty] | 0 | 0 | 0 | C | OG | P
|  |  | Total |  | 146 | [5 empty] | 46 | 44 | 56
146
[7 empty] | Package | Contract Value | Bill Paid | Remaining | Value of Work Done 16/03/2020 | Projection
[7 empty] | KISH/PW-01 | 496.54 | 0 | 496.54 | 0 | 76.82
[7 empty] | KISH/PW-02 | 432.95 | 311.23 | 121.72 | 432.95 | 432.95
[7 empty] | KISH/PW-03 | 689.46 | 581.99 | 107.47 | 658.98 | 689.46
[7 empty] | KISH/PW-04 | 710.52 | 657.81 | 52.71 | 710.52 | 710.52
[7 empty] | KISH/PW-05 | 767.58 | 491.28 | 276.3 | 530.06 | 634.06
[7 empty] | KISH/PW-06 | 774.69 | 719.83 | 54.86 | 719.79 | 774.69
[7 empty] | KISH/PW-07 | 1056.68 | 514.22 | 542.46 | 637.6 | 666.25
[7 empty] | KISH/PW-09 | 715.84 | 473.31 | 242.53 | 485.39 | 609.9
[7 empty] | KISH/PW-10 | 883.96 | 335.7 | 548.26 | 205.49 | 383.43
[7 empty] | KISH/PW-11 | 814.75 | 487.04 | 327.71 | 632.97 | 684.42
[7 empty] | KISH/PW-12 | 931.66 | 527.99 | 403.67 | 873.11 | 891.51
[7 empty] | KISH/PW-13 | 986.13 | 533.22 | 452.91 | 663.25 | 761.09
[7 empty] | KISH/PW-14 | 839.41 | 680.94 | 158.47 | 752.84 | 810.54
[7 empty] | KISH/PW-15 | 700.84 | 333.94 | 366.9 | 437.59 | 519.68
[7 empty] | KISH/PW-16 | 779.17 | 613.21 | 165.96 | 791.69 | 894.13
[7 empty] | KISH/PW-17 | 1568.15 | 1209.62 | 358.53 | 1486.98 | 1536.75
[7 empty] | KISH/PW-18 | 1315.76 | 711.02 | 604.74 | 796.48 | 848.95
[7 empty] | KISH/PW-19 | 847.93 | 296.36 | 551.57 | 210.11 | 347.4
[7 empty] | KISH/PW-20 | 1153.72 | 657.37 | 496.35 | 748.55 | 778.07
[7 empty] | KISH/PW-21 | 927.74 | 0 | 927.74 | 95.62 | 286.85
[7 empty] | KISH/PW-22 | 719.73 | 120.78 | 598.95 | 146.36 | 371.8
[7 empty] | KISH/PW-23 | 764.24 | 115.92 | 648.32 | 334.71 | 543.27
[7 empty] | KISH/PW-24 | 1149.2 | 787.65 | 361.55 | 1149.2 | 1149.2
[7 empty] | KISH/PW-25 | 1764.79 | 638.19 | 1126.6 | 756.5 | 801.01
[7 empty] | KISH/PW-26 | 490.67 | 216.63 | 274.04 | 258.56 | 258.56
[7 empty] | KISH/PW-27 | 912.62 | 0 | 912.62 | 0 | 119.37
[7 empty] | Total | 23194.73 | 12015.25 | 11179.48 | 14515.3 | 16580.68
4565.43

## Sheet2
Package | Contract Value | Bill Paid | Remaining | VWD | Projection
KISH/PW-01 | 496.54 | 0 | 496.54 | 0 | 76.82
KISH/PW-02 | 432.95 | 311.23 | 121.72 | 432.95 | 432.95
KISH/PW-03 | 689.46 | 581.99 | 107.47 | 658.98 | 689.46
KISH/PW-04 | 710.52 | 657.81 | 52.71 | 710.52 | 710.52
KISH/PW-05 | 767.58 | 491.28 | 276.3 | 530.06 | 634.06
KISH/PW-06 | 774.69 | 719.83 | 54.86 | 719.79 | 774.69
KISH/PW-07 | 1056.68 | 514.22 | 542.46 | 637.6 | 666.25
KISH/PW-09 | 715.84 | 473.31 | 242.53 | 485.39 | 609.9
KISH/PW-10 | 883.96 | 335.7 | 548.26 | 205.49 | 383.43
KISH/PW-11 | 814.75 | 487.04 | 327.71 | 632.97 | 684.42
KISH/PW-12 | 931.66 | 527.99 | 931.66 | 873.11 | 891.51
KISH/PW-13 | 986.13 | 533.22 | 452.91 | 663.25 | 761.09
KISH/PW-14 | 839.41 | 680.94 | 158.47 | 752.84 | 810.54
KISH/PW-15 | 700.84 | 333.94 | 366.9 | 437.59 | 519.68
KISH/PW-16 | 779.17 | 613.21 | 165.96 | 791.69 | 894.13
KISH/PW-17 | 1568.15 | 1209.62 | 358.53 | 1486.98 | 1536.75
KISH/PW-18 | 1315.76 | 711.02 | 604.74 | 796.48 | 848.95
KISH/PW-19 | 847.93 | 296.36 | 551.57 | 210.11 | 347.4
KISH/PW-20 | 1153.72 | 657.37 | 496.35 | 748.55 | 778.07
KISH/PW-21 | 927.74 | 0 | 927.74 | 95.62 | 286.85
KISH/PW-22 | 719.73 | 120.78 | 598.95 | 146.36 | 371.8
KISH/PW-23 | 764.24 | 115.92 | 648.32 | 334.71 | 543.27
KISH/PW-24 | 1149.2 | 787.65 | 361.55 | 1149.2 | 1149.2
KISH/PW-25 | 1764.79 | 638.19 | 1126.6 | 756.5 | 801.01
KISH/PW-26 | 490.67 | 216.63 | 274.04 | 258.56 | 258.56
KISH/PW-27 | 912.62 | 0 | 912.62 | 0 | 119.37