## Embankment
Sl No | Item Code | Description | Unit | Rate | Noapara Haor
1 | 01-120 |  | each |  | 23
2 | 16-100 |  | each |  | 881
3 | 16-650-10 |  | cum |  | 65493.18
4 | 16-410-10 |  | cum |  | 21831.06
5 | 16-120-10 |  | cum |  | 21831.06
6 | 16-190 |  | 2 Lead Cum |  | 10915.53
7 | 16-190 |  | pld Cum |  | 10915.53
8 | 48-100 |  | sqm |  | 80364
9 | 16-300 |  | cum |  | 87324.24
10 | 48-130 |  | m |  | 130320

## Regulator
Sl No | Item Code | Description | Unit | Rate | Lalpur Khal
1 | 04-120 | BM pilar | each |  | 5
2 | 04-180 | Site preparation | Sqm |  | 9600
3 | 04-620-20 | Filing Expansion joint | m |  | 23
4 | 12-100 | Pizeometer | each |  | 4
5 | 16-310 | Foundation Excavation | cum |  | 7241.83
6 | 16-560 | Shoring for slope protection | Sqm |  | 243
7 | 12-310-20 | Bailing out | cum |  | 91748.32
8 | 44-240-30 | Sheet pile Supply | M ton |  | 26.88
9 | 44-320-10 | Cutting of sheet Pile | m |  | 91
10 | 12-300 | Construction of sump well | each |  | 4
11 | 44-270-20 | Sheet pile Drive | Sqm |  | 336
12 | 72-180 | Painting of steel sheet pile | Sqm |  | 336
13 | 72-540 |  | Sqm |  | 95.1
14 | 44-310 | Supplying and placing of hesian cloth | Sqm |  | 81.9
15 | 44-220-10 | Supplying and laying of polythene | Sqm |  | 377.77
16 | 28-120 | CC 1:3:6 | cum |  | 46.4
17 | 28-100-20 | CC 1:4:8 | cum |  | 1.75
18 | 28-200-10 | RCC 1:1.5:3 | cum |  | 371.6
19 | 76-120-10 | Reinforcement: 8 mm to 22mm | kg |  | 29475
20 | 76-115-10 | Reinforcement: 6 mm | kg |  | 33.26
21 | 36-150-60 | Shuttering : Footing beams,beams, grade beams | Sqm |  | 301.52
22 | 36-150-10 | Shuttering : Vertical and inclined walls | Sqm |  | 790.26
23 | 36-150-20 | Shuttering : Deck slab operating deck slab | Sqm |  | 106.01
24 | 76-630-10 | P.V.C water stops | m |  | 23
25 | 16-520-20 | Back filling sand:FM>1.50 | cum |  | 261.41
26 | 40-610-20 | Khoa filter: 40mm to 20mm | cum |  | 64.72
27 | 40-610-30 | Khoa filter: 20mm to 5mm | cum |  | 67.4
28 | 40-650-20 | Sand filter: FM 1.50 to 2.0 | cum |  | 8.79
29 | 40-140-50 | CC Block 30x30x30 | each |  | 10932
30 | 40-220-10 | Labour charge | each |  | 295.18
31 | 76-170 | M.S Work in plats, angles, channels | kg |  | 971.67
32 | 80-230-20 | G.I water distribution pipe: 20mm dia G.I pipe line | m |  | 9.2
33 | 76-240-40 | Sulpply of lift gate: 1.95mx1.65m | each |  | 2
33 | 76-260-20 | Labour charge for fitting lift gate | each |  | 2
34 | 76-190 | Supply and instalation of padestal type lifting device | each |  | 2
35 | 16-140-10 | Earth Work in embankment construction | cum |  | 1732.5
36 | 16-130 | Earth Work in Channel excavation | cum |  | 23009.21
37 | 16-200 | Extra rate for additoinal lift | cum |  | 23009.21
38 | 16-190 | Extra rate for additoinal lead | cum |  | 13987.39
39 | 16-220 | Ring bundh Constructiuon | cum |  | 4092
40 | 04-280 | Cement mortar gauge | m |  | 6
41 | 16-240 | Ring bundh remover | cum |  | 2455.2
42 | 16-540-20 | Back filling sand:FM>.80 | cum |  | 1361.58
43 | 16-530 | Back file by earth | cum |  | 1584.19
44 | 68-130 | Fall boards | cum |  | 1.33
45 | 48-100 | Fine dreasing and close turfing | Sqm |  | 1320
46 | 80-260-20 | G.I water distribution pipe: 50mm dia G.I pipe line | m |  | 14
47 | NSI | Name plate | each |  | 1

## Block Road
Sl No | Item Code | Description | Unit | Rate | Noapara Haor
1 | 56-100 |  | cum |  | 2199.15
2 | 56-110 |  | cum |  | 733.05
3 | Approved Analysis Rate |  | sqm |  | 4887
4 | Approved Analysis Rate |  | No |  | 49006
5 | Approved Analysis Rate |  | No |  | 3258
6 | 24-310-10 |  | sqm |  | 4887
7 | 40-220-10 |  | cum |  | 1587.87
8 | 36-150-10 |  | sqm |  | 14.44
9 | 76-120-10 |  | kg |  | 68.38
10 | 76-115-10 |  | kg |  | 14.36
11 | 28-200-10 |  | cum |  | 14.44
12 | 04-110 |  | each |  | 12
13 | 40-540 |  | No |  | 5431
14 | 40-550 |  | m |  | 8146.5
15 | 40-560-10 |  | m |  | 21720
16 | 40-580 |  | sqm |  | 8145
17 | Approved Analysis Rate |  | sum |  | 1
18 | Approved Analysis Rate |  | Day |  | 150
19 | Approved Analysis Rate |  | sum |  | 1
20 | Approved Analysis Rate |  | sum |  | 1
21 | Approved Analysis Rate |  | sum |  | 1
22 | Approved Analysis Rate |  | sum |  | 1

## Sheet2
1 | 04-120 (Submersible Road) | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cmx38cm x75cm on cement concrete (1:2:4) base of size 50cmx50cmx7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement mortar on top (1:2), with inscription of "BWDB" with 25cm of the pillar below ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | each | 23 | 1203.771 | One Thousand Two Hundred and Three point Seven Seven One | 27686.733
2 | 16-100 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | each | 881 | 290.481 | Two Hundred and Ninety point Four Eight One | 255913.761
3 | 16-650 | 16-650-10 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. Embankment by Mech. Equipment; ht: 0 to 4m; 85% comp | cum | 65493.18 | 126.321 | One Hundred and Twenty-Six point Three Two One | 8273163.991
4 | 16-410 | 16-410-10 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) direction of Engineer in charge.Earth work bymanual labour in all kinds of soil for excavation/ re-excavation of pond/ tank in layers of 150mm includingbreaking clods, dressing, profiling etc. complete with all leads and lifts as per direction of Engineer in charge. | cum | 21831.06 | 346.281 | Three Hundred and Forty-Six point Two Eight One | 7559681.288
5 | 16-120 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference ..., (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. | cum | 21831.06 | 182.931 | One Hundred and Eighty-Two point Nine Three One | 3993577.637
6(a) | 16-190 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3 m neglected) for all kinds of earth work. | two lead/cum | 10915.53 | 29.141 | Twenty-Nine point One Four One | 318089.46
6(b) | 16-190 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3 m neglected) for all kinds of earth work. | pld/cum | 10915.53 | 14.571 | Fourteen point Five Seven One | 159050.188
7 | 48-100 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turfgrows properly, maintaining etc. complete (measurement will be given onwell grown grass only). as per direction of Engineer in charge | sqm | 80364 | 26.171 | Twenty-Six point One Seven One | 2103206.244
8 | 16-300 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | cum | 87324.24 | 14.471 | Fourteen point Four Seven One | 1263669.077
9 | 48-130 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge.(6 rows each side) | m | 130320 | 4.471 | Four point Four Seven One | 582660.72 | 24536699.099
10 | 56-100 (Block Road) | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge. | cum | 2199.15 | 135.005 | One Hundred and Thirty-Five point Zero Zero Five | 296896.246
11 | 56-110 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by..drawing and direction of Engineer in charge (payment shall be made on compacted volume). | cum | 733.05 | 733.121 | Seven Hundred and Thirty-Three point One Two One | 537414.349
12 | Approved Analysis Rate | Approved Analysis Rate | Preparetion of Bed by cutting and filling including watering to bring moisture+-2% of OMC & compaction by appropiate machanical meands etc to attain minimum compaction 98% oc MDD (standard) to obtain a minimum soaked CBR 4& etc all complete as per direction of the Engineer in charge. | sqm | 4887 | 11.309 | Eleven point Three Zero Nine | 55267.083
13 | Approved Analysis Rate | Approved Analysis Rate | Manufacturing and supplying of 30cm x 30cm x 30cm C.C Block inleanest mix. 1:2:4, with cement , sand(Fm>=1.5) and stone chips (40mm down graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing stone chips, mixing laying in forms, consolidation, curing for at lest 21 days, including preparation of platform, shuttering and stackiing in measureable stacks etc complete including supply of all materials (steel shutter to be used) as per direction of Engineer in Charge. Block size 30cm x 30cm x 30 cm | each | 49006 | 340.001 | Three Hundred and Forty point Zero Zero One | 16662089.006
14 | Approved Analysis Rate | Approved Analysis Rate | Manufacturing and supplying of trapezoidal size 100cm x 65cm x(10-15)cm C.C. blocks in leanest mix. 1:2:4 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a minimum 28 days cylinder strength of 15.0 N/mm² including grading, washing stonechips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. Block size 100 cm x 65 cm x 12.5 cm | each | 3258 | 977.181 | Nine Hundred and Seventy-Seven point One Eight One | 3183655.698
15 | 24-310 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge. | sqm | 4887 | 162.471 | One Hundred and Sixty-Two point Four Seven One | 793995.777
16 | 40-220 | 40-220-10 | Labour charge for protective work in laying sand cement blocks of different sizes including preparation of base, ramming of base etc. complete as per direction of the Engineer in charge: | cum | 1587.87 | 2027.041 | Two Thousand AND Twenty-Seven point Zero Four One | 3218677.593
17 | 36-150 | 36-150-10 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. | sqm | 14.44 | 909.691 | Nine Hundred and Nine point Six Nine One | 13135.938
18 | 76-120 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia | kg | 68.38 | 77.341 | Seventy-Seven point Three Four One | 5288.578
19 | 76-115 | 76-115-10 | M.S Work for reinforcement with Standard deformed bar fy=276 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. | kg | 14.36 | 74.371 | Seventy-Four point Three Seven One | 1067.968
20 | 28-200 | 28-200-10 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. | cum | 14.44 | 11674.491 | Eleven Thousand Six Hundred and Seventy-Four point Four Nine One | 168579.65
21 | 04-110 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge | each | 12 | 47.911 | Forty-Seven point Nine One One | 574.932
22 | 40-540 | 40-450-20 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >= 8.0 cm in position etc. complete as per direction of Engineer in charge. | nos | 5431 | 131.551 | One Hundred and Thirty-One point Five Five One | 714453.481
23 | 40-550 | 40-550-10 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. | m | 8146.5 | 132.941 | One Hundred and Thirty-Two point Nine Four One | 1083003.857
24 | 40-560 | 40-560-10 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge. | m | 21720 | 64.531 | Sixty-Four point Five Three One | 1401613.32
25 | 40-580 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah doubly woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. | sqm | 8145 | 162.451 | One Hundred and Sixty-Two point Four Five One | 1323163.395
26 | Approved Analysis Rate | Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge. | LS | 1 | 967050.851 | Nine Lakh Sixty-Seven Thousand AND Fifty point Eight Five One | 967050.851
27 | Approved Analysis Rate | Approved Analysis Rate | Peovide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | DAY | 150 | 2497.861 | Two Thousand Four Hundred and Ninety-Seven point Eight Six One | 374679.15
28 | Approved Analysis Rate | Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | LS | 1 | 112344.101 | One Lakh Twelve Thousand Three Hundred and Forty-Four point One Zero One | 112344.101
29 | Approved Analysis Rate | Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 4 nos. of tube well and sanitation facilities by installing 6 nos. of sanitary latrines for usage of labours, Officials and others for prevailing the hygenic and healthy environment at allover the working sithe as per direction of the engineer in charge. | LS | 1 | 111148.951 | One Lakh Eleven Thousand One Hundred and Forty-Eight point Nine Five One | 111148.951
30 | Approved Analysis Rate | Approved Analysis Rate | Mobilize, strengthen required land based consatruction equipment such as excavator, dump truck, chain dozer, vibro-compactor and plants such as gemetor for site electrification, digital camera for taking photographs and digital vedio camera for recording/Taking Photograph as sequences of works etc. for keeping records of the works by providing following information including transfer to site, complete for the purposes stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | LS | 1 | 92026.551 | Ninety-Two Thousand AND Twenty-Six point Five Five One | 92026.551
31 | Approved Analysis Rate | Approved Analysis Rate | Operate, maintain of plant and equipment such as generator for site electrification for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | LS | 1 | 110909.921 | One Lakh Ten Thousand Nine Hundred and Nine point Nine Two One | 110909.921
[7 empty] | EMB | 24536699.099
[7 empty] | Block Road | 29458876.871
[7 empty] | CC Block | 19845744.704

## Sheet1
1 | 76-240 | 76-240-40 | Manufacturing & Supplying of M.S. Vertical Lift Gate shutter of 8mm thick M.S. skin plate and stiffener with minimum 75mmx75mmx10mm M.S. angle as frame, horizontal & vertical beam, 75mmx25mmx12mm P-type rubber seal, fixed with 10mm dia x 63.5mm M.S. counter shank bolts with nuts and 40mmx10mm M.S. strip as clamp drilled spaces @ 150mm c/c, stem attachment with proper thread, nut, cotter pin and washer as per approved design including the cost of all materials of proper grade & brand new with a prime coat of redoxide where necessary as per specification and direction of Engineer in charge. | each | 2 | 96799.631 | Ninety-Six Thousand Seven Hundred and Ninety-Nine point Six Three One | 193599.262
62 | 76-260 | 76-260-20 | Labour charge for fitting and fixing of M.S. vertical lift gate/ flap gate shutters of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/sluice and mending the damages with CC (1:2:4), removing the spoils etc. complete including the cost of all materials as per direction of Engineer in charge. | each | 2 | 9991.911 | Nine Thousand Nine Hundred and Ninety-One point Nine One One | 19983.822
63 | 76-190 | 76-190 | Manufacturing, supplying and Installation of Padestal type lifting device for slide gate with 63mm dia threaded steel shaft, 146mm outer dia bronze nut, thrust bearing, steel bevel gear etc. as per approved design including supply of all components, labours with a prime coat of redoxide where necessary etc. complete including the cost of all materials as per specification and direction of Engineer in charge. | each | 2 | 84135.851 | Eighty-Four Thousand One Hundred and Thirty-Five point Eight Five One | 168271.702
64 | 16-140 | 16-140-10 | Earth work by manual labour in resectioning of embankment/ canal bank/ river slopes/ road/ compound etc. manually compacted by 7.0 kg iron rammer to avoid any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceeding 150mm thickness with clod breaking to a maximum size of 100mm, removing roots & stumps of trees of girth upto 200mm from the ground, benching the side slopes, stripping/ ploughing the base of embankment and borrowpit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of the crest (where necessary) etc. complete as per direction of Engineer in charge. | cum | 1732.5 | 187.791 | One Hundred and Eighty-Seven point Seven Nine One | 325347.908
65 | 16-130 | 16-130 | Earth work by manual labour in all kinds of soil in excavation or reexcavation of channels with the initial lead of 30m and lift of 1.5m including levelling, dressing and throwing the spoils to profile with breaking clods, rough dressing, clearing jungles including cutting trees upto 200mm girth, dug bailing etc. complete as per direction of Engineer in charge. | cum | 23009.21 | 142.471 | One Hundred and Forty-Two point Four Seven One | 3278145.158
66 | 16-200 | 16-200 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm neglected) for all kinds of earth work. | plt/cum | 23009.21 | 10.991 | Ten point Nine Nine One | 252894.227
67 | 16-190 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3m negleted) for all kinds of earth work | pld/cum | 13987.39 | 14.571 | Fourteen point Five Seven One | 203810.26
68 | 16-220 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | cum | 4092 | 142.421 | One Hundred and Forty-Two point Four Two One | 582786.732
69 | 04-280 | 04-280 | Constructing at site, cement mortar gauge on masonry wall, including engraving in meter, decimeter & centimeter, painting and figuring with | m | 6 | 77.931
70 | 16-240 | 16-240 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge. | cum | 2455.2 | 142.471
71 | 16-540 | 16-540-20 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming, compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. | cum | 1361.58 | 757.751
72 | 16-530 | 16-530 | Back filling in hydraulic structures and slope building in protective works including all leads and lifts with selected local soil in layer of 150mm including watering, ramming etc. complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in charge. | cum | 1584.19 | 159.491
73 | 68-130 | 68-130 | Supplying pressure treated wooden fall boards/stop logs of different sizes (not less than 15cm in depth) of sal, sundari, garjan, shishu or equivalent for regulator/ sluices, including fixing in position with eye hook etc. complete as per direction of Engineer in charge. | cum | 1.33 | 60966.401 | Sixty Thousand Nine Hundred and Sixty-Six point Four Zero One | 81085.313
74 | 48-100 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only). as per direction of Engineer in charge. | sqm | 1320 | 26.171 | Twenty-Six point One Seven One | 34545.72
75 | 80-260 | 80-260-20 | Supplying, fitting and fixing of the different dia G.I. water distribution pipe line, with all special fittings such as bends, elbows, sockets, reducing sockets, tees, unions etc. including cutting trench up to an average depth of 0.90m, maintaining proper level, cutting pipes where necessary, making threads etc. all complete, as per direction of Engineer in charge. 50mm dia G.I. pipe line. 80-260-20: 50mm dia G.I. pipe line. | m | 14 | 339.021 | Three Hundred and Thirty-Nine point Zero Two One | 4746.294
76 | NSI | NSI | Environmental Monitoring through Sample Collection and analysis such as Air quality test, Surface water test, Sound Level monitoring, Traffic signs and road navigation, safety provisions with first aid and medical Assistant as per direction of engineer in charge. | LS | 1 | 200000.001
5145216.398