## Embankment
Sl No | Item Code | Description | Unit | Rate | Noapara Haor
7 | 04-150 |  | nos | 493.069 | 18
8 | 04-160 |  | nos | 38.654 | 18
9 | 48-130 |  | m | 3.471 | 202800
10 | 16-100 |  | each | 185.381 | 339
11 | 40-540-10 |  | nos | 123.002 | 1501
12 | 40-550-20 |  | m | 54.671 | 2251.5
13 | 40-580 |  | sqm | 281.157 | 1200
14 | 16-410-10 |  | cum | 332.451 | 77941.09
15 | 16-120-10 |  | cum | 150.188 | 58455.82
16 | 16-190 |  | 2 Lead Cum | 34.886 | 23382.33
17 | 16-650-10 |  | cum | 119.899 | 58455.82
18 | 16-300 |  | cum | 9.561 | 116911.64
19 | 48-100 |  | sqm | 19.266 | 257077.5
50007553.7689
500.0755

## Block Road
Sl No | Item Code | Description | Unit | Rate | Noapara Haor
21 | 56-100 |  | cum | 107.757 | 1249.5
22 | Analysis Rate/LGED |  | Sqm | 143.418 | 2380
23 | 56-110 |  | cum | 512.069 | 357
24 | Analysis Rate |  | nos | 442.206 | 26444
25 | Analysis Rate |  | nos | 1493.938 | 1700
26 | 24-310-10 |  | Sqm | 126.901 | 2380
27 | 40-220-10 |  | cum | 917.146 | 426.06
| 40-220-20 |  | cum | 1620.357 | 426.06
16275328.8167
162.7533
|  |  |  | CC Block | 142.3339

## Regulator
Sl No | Item Code | Description | Unit | Rate | Gokhra Khal
1 | 04-180 | Site preparation | Sqm | 21.898 | 3213.6 | 70371.4128
2 | 04-100 | BM Pillar | nos | 1014.741 | 4 | 4058.964
3 | 04-160 | BM Installation | nos | 37.287 | 4 | 149.148
4 | 04-320 |  | nos | 12.016 | 160 | 1922.56
5 | 04-330 |  | nos | 2.259 | 160 | 361.44
6 | 16-220 | Ring bundh Constructiuon | cum | 113.717 | 796.31 | 90553.9843
7 | 16-560-30 | Shoring for slope protection | Sqm | 1008.603 | 262.5 | 264758.2875
8 | 16-310-10 | Foundation Excavation | cum | 194.233 | 5208.25 | 1011614.0223
9 | 40-440-20 |  | cum | 54.006 | 12100 | 653472.6
10 | 16-520-20 | Back filling sand:FM>1.50 | cum | 750.501 | 340.67 | 255673.1757
11 | 16-540-20 | Back filling sand:FM>.80 | cum | 551.241 | 750.94 | 413948.9165
12 | 44-240-30 | Supplying and laying of polythene | Sqm | 125491.945 | 17.43 | 2187324.6014
13 | 44-320-20 | Cutting of sheet Pile | m | 64.758 | 61.88 | 4007.225
14 | 72-540 |  | Sqm | 204.844 | 495.04 | 101405.9738
15 | 44-270-20 | Sheet pile Drive | Sqm | 1029.837 | 134.68 | 138698.4472
16 | 44-310 | Supplying and placing of hesian cloth | Sqm | 374.883 | 21.84 | 8187.4447
17 | 44-220-10 | Supplying and laying of polythene | Sqm | 7.529 | 351.4 | 2645.6906
18 | 40-610-20 | Khoa filter: 40mm to 20mm | cum | 3042.905 | 50.61 | 154001.4221
19 | 40-610-30 | Khoa filter: 20mm to 5mm | cum | 3302.305 | 50.61 | 167129.656
20 | 40-650-30 |  | cum | 620.411 | 160.08 | 99315.3929
21 | 40-650-20 | Sand filter: FM 1.50 to 2.0 | cum | 978.956 | 9.05 | 8859.5518
22 | 12-310-20 | Bailing out | cum | 6.827 | 28547.15 | 194891.3931
23 | 28-120-20 | CC 1:3:6 | cum | 7834.122 | 43.91 | 343996.297
24 | 28-100-30 | CC 1:4:8 | cum | 7497.508 | 1.37 | 10271.586
25 | 36-150-10 | Shuttering : Vertical and inclined walls | Sqm | 651.726 | 562.84 | 366817.4618
26 | 36-150-20 | Shuttering : Deck slab operating deck slab | Sqm | 657.846 | 90.2 | 59337.7092
27 | 36-150-60 | Shuttering : Footing beams,beams, grade beams | Sqm | 536.163 | 164.42 | 88155.9205
28 | 76-120-10 | Reinforcement: 8 mm to 22mm | kg | 84.908 | 25887.52 | 2198057.5482
29 | 76-115-10 | Reinforcement: 6 mm | kg | 70.566 | 34.78 | 2454.2855
30 | 80-230-40 | G.I water distribution pipe: 20mm dia G.I pipe line | m | 492.066 | 14.29 | 7031.6231
31 | 76-170 | M.S Work in plats, angles, channels | kg | 128.309 | 2512 | 322312.208
32 | 28-200-10 | RCC 1:1.5:3 | cum | 10008.221 | 274.68 | 2749058.1443
33 | 4-600-10 |  | Sqm | 254.136 | 11.66 | 2963.2258
34 | 04-280-10 | Cement mortar gauge | m | 64.219 | 9.1 | 584.3929
35 | 56-430 |  | m | 119.781 | 28.2 | 3377.8242
36 | 40-140-50 | CC Block 30x30x30 | each | 248.701 | 8712.29 | 2166755.2353
37 | 40-140-40 |  | each | 299.176 | 4631.25 | 1385558.85
38 | 40-220-10 | Labour charge | each | 917.146 | 191.73 | 175844.4026
39 | 40-220-20 |  | each | 1620.357 | 191.73 | 310671.0476
40 | 76-630-10 | P.V.C water stops | m | 645.979 | 28.2 | 18216.6078
41 | 16-240 | Ring bundh remover | cum | 113.751 | 3526.88 | 401186.1269
42 | 76-240-40 | Sulpply of lift gate: 1.95mx1.65m | each | 91129.043 | 2 | 182258.086
43 | 76-260-20 | Labour charge for fitting lift gate | each | 8977.697 | 2 | 17955.394
44 | 76-190 | Supply and instalation of padestal type lifting device | each | 83530.181 | 2 | 167060.362
45 | 16-600-10 | Channel Excavation | cum | 76.653 | 11022.13 | 844879.3309
17658154.9789
176.5815
|  |  | without DV Channel |  |  | 168.1328
168.13

## Rate_Embankment
7 | 04-150 | 04-150 | Manufacturing and supplying R.C.C. (1:2:4) BM Pillars of size 15cmx 15cmx75cm, with 40cmx40cmx10cm base having 3 nos.10mm dia MS.bar each way at base,4nos.10mm dia vertical bar and 8nos 6mm dia ring,excluding cost of M.S.works for reinforcement but including cost of form works, concreting, plastering at top, finishing surface, curing etc. complete, with inscription of "BWDB", on exposed surface etc. complete as per direction of Engineer in charge. | nos | 18 | 493.069 | Four Hundred and Ninety-Three point Zero Six Nine | 8875.242
8 | 04-160 | 04-160 | Fixing in position B.M. pillars and kilometer posts of size 15cmx15cmx75cm with 40cmx40cmx10cm base, embedding 45cm below G.L. including carriage, earth cutting, backfilling, ramming, etc. complete as per direction of Engineer in charge. | nos | 18 | 38.654 | Thirty-Eight point Six Five Four | 695.772
9 | 48-130 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge. | m | 202800 | 3.471 | Three point Four Seven One | 703918.8
10 | 16-100 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | nos | 339 | 185.381 | One Hundred and Eighty-Five point Three Eight One | 62844.159
11 | 40-540 | 40-540-10 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >=8.0 cm in position etc. complete as per direction of Engineer in charge. Length : >=4.5 m to <=6.0m | nos | 1501 | 123.002 | One Hundred and Twenty-Three point Zero Zero Two | 184626.002
12 | 40-550 | 40-550-20 | Labour charge for driving barrack bamboo pins of diameter >=8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge.>=1.50 m to <=2.0 m drive, in water including necessary staging etc. as required | m | 2251.5 | 54.671 | Fifty-Four point Six Seven One | 123091.757
13 | 40-580 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah double woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. | sqm | 1200 | 281.157 | Two Hundred and Eighty-One point One Five Seven | 337388.4
14 | 16-410 | 16-410-10 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge.300m to 1.00 km.(85% compaction) | cum | 77941.09 | 332.451 | Three Hundred and Thirty-Two point Four Five One | 25911593.312
15 | 16-120 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/ canalbank/road etccompacted to 85%/90% maximum drydensity at optimum moisture content,with referenceto laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay,0-40% silt, 0-30% sand) within the initial lead of 30m & all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots & stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc.complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 m to 3 m height with 85% compaction. | Cum | 58455.82 | 150.188 | One Hundred and Fifty point One Eight Eight | 8779362.694
16 | 16-190 | 16-190 | Extra rate for every additional lead of 15 m or part thereof beyond the initial lead of 30m up to a maximum of 19 leads (3m neglected) for all kinds of earth work. 3 nos Lead (Quoted rate will be applicable for 3 nos lead) | cum | 23382.33 | 34.886 | Thirty-Four point Eight Eight Six | 815715.964
17 | 16-650 | 16-650-10 | "Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 to 4 m height with 85% compaction. | cum | 58455.82 | 119.899 | One Hundred and Nineteen point Eight Nine Nine | 7008794.362
18 | 16-300 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | cum | 116911.64 | 9.561 | Nine point Five Six One | 1117792.19
19 | 48-100 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75 mm thick good quality durba or charkanta sods of size 200 mm x 200 mm with all leads and lifts including ramming watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only) as per direction of Engineer in charge. | Sqm | 257077.5 | 19.266 | Nineteen point Two Six Six | 4952855.115
20 | 56-100 | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge. | cum | 1249.5 | 107.757 | One Hundred and Seven point Seven Five Seven | 134642.372
21 | Analysis Rate/LGED | Analysis Rate/LGED | BP: Preperation of bed by cutting and filling including watering to bring moisture content ±2% of OMC & compacting by appropiate mechanical means etc to attain minimum compaction 98% of MDD (standard) to obtain a minimum soaked CBR 4% etc all complete as per direction of the E-I-C. | Sqm | 2380 | 143.418 | One Hundred and Forty-Three point Four One Eight | 341334.84
22 | 56-110 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by manual labour using mallet/ vibro compactor including cost of all materials etc. complete as per design, drawing and direction of Engineer in charge (payment shall be made on compacted volume). | cum | 357 | 512.069 | Five Hundred and Twelve point Zero Six Nine | 182808.633
23(a) | Analysis Rate | Analysis Rate | Manufacturing and supplying of CC blocks in leanest mix (1:2:4) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. Block size: 30cm x 30cm x 30cm | nos | 26444 | 442.206 | Four Hundred and Forty-Two point Two Zero Six | 11693695.464
23(b) | Analysis Rate | Analysis Rate | Manufacturing and supplying of CC blocks in leanest mix (1:2:4) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. Block size: 100cm x 65cm x (10-15)cm | nos | 1700 | 1493.938 | One Thousand Four Hundred and Ninety-Three point Nine Three Eight | 2539694.6
24 | 24-310 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge. | Sqm | 2380 | 126.901 | One Hundred and Twenty-Six point Nine Zero One | 302024.38
25(a) | 40-220 | 40-220-10 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.Within 200m | cum | 426.06 | 917.146 | Nine Hundred and Seventeen point One Four Six | 390759.225
25(b) | 40-220 | 40-220-20 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.Beyond 200m | cum | 426.06 | 1620.357 | One Thousand Six Hundred and Twenty point Three Five Seven | 690369.303

## Rate_Reg
26(gokhra khal regulator) | 04-180 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials from entire site and removing soil upto 15cm depth including uprooting stumps, jungle, cleaning, levelling, dressing etc. complete as per direction of Engineer in charge | sqm | 3213.6 | 21.898 | Twenty-One point Eight Nine Eight | 70371.413
27 | 04-100 | 04-100 | Manufacturing and supplying R.C.C boundary pillar, bench mark pillar and kilometer post in proportion 1:2:4, as per approved drawing and specifications, 110cm height, bottom dia 25cm and top dia 20cm, of which 15cm slanting and 50 level; with 6 nos. 10mm dia vertical rod and 8 nos. 6mm dia binder excluding the cost of M.S work or reinforcement but including the cost of form works, plastering top, finishing surface, curing with inscription of "BWDB, R.L./K.M." mark, as per approved size and shape in exposed surface etc. complete, as per direction of Engineer in charge. | nos | 4 | 1014.741 | One Thousand AND Fourteen point Seven Four One | 4058.964
28 | 04-110 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge. | nos | 4 | 37.287 | Thirty-Seven point Two Eight Seven | 149.148
29 | 04-320 | 04-320 | Supply of bamboo pegs 0.45m to 0.75m long and average dia. 6 cm, with saw cut top as per direction of Engineer in charge. | nos | 160 | 12.016 | Twelve point Zero One Six | 1922.56
30 | 04-330 | 04-330 | Labour charge for fixing of bamboo pegs 0.45m to 0.75m long and average dia 6cm, as per direction of Engineer in charge. | nos | 160 | 2.259 | Two point Two Five Nine | 361.44
31 | 16-220 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | cum | 796.31 | 113.717 | One Hundred and Thirteen point Seven One Seven | 90553.984
32 | 16-560 | 16-560-30 | Shoring for slope protection of foundation trench, canal, embankment, road, pond etc. as per design slopes, grades including removal of spoils to a safe distance as per direction of Engineer in charge. By local hard wood ballah post of 6.0m length, 125mm dia, 1.0m c/c, and 2.0m drive with 6.0m long bamboo of average 75mm dia, @1.0m c/c and 2.0m drive with drum sheet walling and average 70mm dia half split bamboo batten @ 2.0m c/c fixed with nails. | sqm | 262.5 | 1008.603 | One Thousand AND Eight point Six Zero Three | 264758.287
33 | 16-310 | 16-310-10 | Earth work in excavation of foundation trenches in all kinds of soil as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. | cum | 5208.25 | 194.233 | One Hundred and Ninety-Four point Two Three Three | 1011614.022
34 | 40-440 | 40-440-20 | "Supplying and filling empty gunny/synthetic bags as approved in design & drawing with sand/ earth available at site sewing the end with sutly, including carrying and placing in position within the site with supply of all materials as per direction of Engineer in charge. | cum | 12100 | 54.006 | Fifty-Four point Zero Zero Six | 653472.6
35 | 16-520 | 16-520-20 | Supplying and filling sand in foundation of hydraulic structures, buildings and in protective works with selected sand, in 150mm thick layer, including levelling, dressing, ramming, watering etc. complete (compacted to 50% relative density by manual labour using mallet/ vibro compactor) as per direction of Engineer in charge. | cum | 340.67 | 750.501 | Seven Hundred and Fifty point Five Zero One | 255673.176
36 | 16-540 | 16-540-20 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. | cum | 750.94 | 551.241 | Five Hundred and Fifty-One point Two Four One | 413948.917
37 | 44-240 | 44-240-30 | Supplying at site U-shape hot rolled steel sheet piles of different sections as mentioned in the material specification of this manual as tabular form of Phosphorus = 00.04% (Maximum), Sulphur = 0.04% (Maximum), Copper = 0.25% (Minimum), Tensile strength => 490 N/mm2, Yield strength => 296 N/mm2, Elongation = 15% (Minimum) including all taxes, freights, incidental charges etc. complete as per direction of Engineer in charge. | M.ton | 17.43 | 125491.945 | One Lakh Twenty-Five Thousand Four Hundred and Ninety-One point Nine Four Five | 2187324.601
38 | 44-320 | 44-320-20 | Cutting of steel sheet piles to design length and shape as per requirement in design and drawing and as per direction of Engineer in charge. | m | 61.88 | 64.758 | Sixty-Four point Seven Five Eight | 4007.225
39 | 72-540 | 72-540 | Epoxy paint 2 coats of approved colour and specification over a priming coat to gate, hoisting device and embedded metal parts including scraping out rust and old paint with chisel, scraper, steel wire brush & emery paper etc. complete in all respect including the cost of all materials as per direction of Engineer in charge. | m | 495.04 | 204.844 | Two Hundred and Four point Eight Four Four | 101405.974
40 | 44-270 | 44-270-20 | Driving steel sheet piles of various sections and weights of any type of soil, by monkey hammer including handling and placing in position, staging and supplying of all equipments like monkey hammer, pully, rope, bamboo, bullah etc. including correcting leaning beyond tolerance & other defects and any other incidental cost etc. complete (measurement will be taken on projected width x height) as per direction of Engineer in charge. | sqm | 134.68 | 1029.837 | One Thousand AND Twenty-Nine point Eight Three Seven | 138698.447
41 | 44-310 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge. | sqm | 21.84 | 374.883 | Three Hundred and Seventy-Four point Eight Eight Three | 8187.445
42 | 44-220 | 44-220-10 | Supplying and laying single layer polythene sheet in floor below cement concrete, RCC slab, on walls etc. complete in all respect as per direction of Engineer in charge. | sqm | 351.4 | 7.529 | Seven point Five Two Nine | 2645.691
43(a) | 40-610 | 40-610-20 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: | cum | 50.61 | 3042.905 | Three Thousand AND Forty-Two point Nine Zero Five | 154001.422
43(b) | 40-610 | 40-610-30 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: | cum | 50.61 | 3302.305 | Three Thousand Three Hundred and Two point Three Zero Five | 167129.656
44 | 40-650 | 40-650-30 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. | cum | 160.08 | 620.411 | Six Hundred and Twenty point Four One One | 99315.393
45 | 40-650 | 40-650-20 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. | cum | 9.05 | 978.956 | Nine Hundred and Seventy-Eight point Nine Five Six | 8859.552
46 | 12-310 | 12-310-20 | Bailing out of water with all leads and lifts by manual labour or pump, with all arrangements for protection of ring bund and side slopes of foundation pit against erosion or washout etc. complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge. | cum | 28547.15 | 6.827 | Six point Eight Two Seven | 194891.393
47 | 28-120 | 28-120-20 | Cement concrete in leanest mix 1:3:6 with sand of F.M.>=1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of form works etc complete as per direction of Engineer in charge | cum | 43.91 | 7834.122 | Seven Thousand Eight Hundred and Thirty-Four point One Two Two | 343996.297
48 | 28-100 | 28-100-30 | Cement concrete in leanest mix 1:4:8 with sand of F.M.>=1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials excluding the cost of form works etc complete as per direction of Engineer in charge. | cum | 1.37 | 7497.508 | Seven Thousand Four Hundred and Ninety-Seven point Five Zero Eight | 10271.586
49(a) | 36-150 | 36-150-10 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M .S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. | sqm | 562.84 | 651.726 | Six Hundred and Fifty-One point Seven Two Six | 366817.462
49(b) | 36-150 | 36-150-20 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M .S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. | sqm | 90.2 | 657.846 | Six Hundred and Fifty-Seven point Eight Four Six | 59337.709
49(c) | 36-150 | 36-150-60 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M .S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. | sqm | 164.42 | 536.163 | Five Hundred and Thirty-Six point One Six Three | 88155.92
50(a) | 76-120 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm² (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. | Kg | 25887.52 | 84.908 | Eighty-Four point Nine Zero Eight | 2198057.548
50(b) | 76-115 | 76-115-10 | b) 6mm dia | Kg | 34.78 | 70.566 | Seventy point Five Six Six | 2454.285
51 | 80-230 | 80-230-40 | Supplying, laying, fitting and fixing of different dia G.I. pipes with all special fittings, such as bends, elbows, sockets, tees, unions, jam nuts etc. including cutting foundation trenches upto required depth where necessary and filling the same with earth duly compacted, making holes in floors and walls and mending the damages, fixing in walls with holders and clips, including cutting threads, making necessary connection etc. all complete, and as per direction of Engineer in charge. | m | 14.29 | 492.066 | Four Hundred and Ninety-Two point Zero Six Six | 7031.623
52 | 76-170 | 76-170 | M.S. Work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cutting, bending, welding, forging, drilling, revetting, embedding anchor bars, staging and fitting, fixing, local handling etc. comlpete with energy consumption and supply of labours including the cost of materials as per design, specification and direction of Engineer in charge. | kg | 2512 | 128.309 | One Hundred and Twenty-Eight point Three Zero Nine | 322312.208
53 | 28-200 | 28-200-10 | Reinforced Cement Concrete Work in leanest mix. 1:1.5:3 with 25mm down graded coarse aggregates and sand of FM>= 2.0 to FM >= 2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. | cum | 274.68 | 10008.221 | Ten Thousand AND Eight point Two Two One | 2749058.144
54 | 4-600 | 4-600-10 | Providing cork sheet/polysterene sheet in expansion joints of concrete works including supply of all materials etc. complete as per direction of Engineer in charge. 25mm thick sheet. | sqm | 11.66 | 254.136 | Two Hundred and Fifty-Four point One Three Six | 2963.226
55 | 04-280 | 04-280-10 | Constructing at site, cement mortar gauge on masonry wall, including engraving in meter, decimeter & centimeter, painting and figuring with black and red water proof paint, etc. complete as per direction of Engineer in charge. | m | 9.1 | 64.219 | Sixty-Four point Two One Nine | 584.393
56 | 56-430 | 56-430 | Filling up the expansion joints by asphalt, sand and jute waste etc. complete including supply of all materials and as per direction of Engineer in charge. | m | 28.2 | 119.781 | One Hundred and Nineteen point Seven Eight One | 3377.824
57(a) | 40-140 | 40-140-50 | Manufacturing and supplying of CC blocks in leanest mix (1:3:6) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. | nos | 8713.29 | 248.701 | Two Hundred and Forty-Eight point Seven Zero One | 2167003.936
57(b) | 40-140 | 40-140-40 | Manufacturing and supplying of CC blocks in leanest mix (1:3:6) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. | nos | 4631.25 | 299.176 | Two Hundred and Ninety-Nine point One Seven Six | 1385558.85
58(a) | 40-220 | 40-220-10 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in chargeWithin 200m | cum | 191.73 | 917.146 | Nine Hundred and Seventeen point One Four Six | 175844.403
58(b) | 40-220 | 40-220-20 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge | cum | 191.73 | 1620.357 | One Thousand Six Hundred and Twenty point Three Five Seven | 310671.048
59 | 76-630 | 76-630-10 | Supply and fitting fixing 23cm PVC water stops having minimum strength of 13.80 N/mm2 at 225% elongation and of approved quality in contraction and expansion joints with necessary arrangement for modification of shuttering and keeping the water stop in position etc as per design, specification and direction of Engineer in charge | m | 28.2 | 645.979 | Six Hundred and Forty-Five point Nine Seven Nine | 18216.608
60 | 16-240 | 16-240 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge. | cum | 3526.88 | 113.751 | One Hundred and Thirteen point Seven Five One | 401186.127
61 | 76-240 | 76-240-40 | Manufacturing & Supplying of M.S. Vertical Lift Gate shutter of 8mm thick M.S. skin plate and stiffener with minimum 75mmx75mmx10mm M.S. angle as frame, horizontal & vertical beam 75mmx25mmx12mm P-type rubber seal, fixed with 10mm dia x 63 .5mm M.S. counter shank bolts with nuts and 40mmx10mm M.S. strip as clamp drilled spaces @ 150mm c/c, stem attachment with proper thread, nut, cotter pin and washer as per approved design including the cost of all materials of proper grade & brand new with a prime coat of redoxide where necessary as per specification and direction of Engineer in charge. | nos | 2 | 91129.043 | Ninety-One Thousand One Hundred and Twenty-Nine point Zero Four Three | 182258.086
62 | 76-260 | 76-260-20 | Labour charge for fitting and fixing of M.S. vertical lift gate/flap gate shutters of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/sluice and mending the damages with CC (1:2:4), removing the spoils etc.complete including the cost of all materials as per direction of Engineer in charge.Size 1.95m x 1.65m. | nos | 2 | 8977.697 | Eight Thousand Nine Hundred and Seventy-Seven point Six Nine Seven | 17955.394
63 | 76-190 | 76-190 | Manufacturing, supplying and Installation of Padestal type lifting device for slide gate with 63mm dia threaded steel shaft, 146mm outer dia bronze nut, thrust bearing, steel bevel gear etc. as per approved design including supply of all components, labours with a prime coat of redoxide where necessary etc. complete including the cost of all materials as per specification and direction of Engineer in charge. | nos | 2 | 83530.181 | Eighty-Three Thousand Five Hundred and Thirty point One Eight One | 167060.362
64 | 16-600 | 16-600-10 | Earth work by Mechanical Excavator ( Long Boom ) in all kinds of soil in excavation/re-excavation of Channel/Canal/khal etc. Including disposal of spoil-soil upto 30m away from the point of excavation with rough dressing and leveling etc. Complete as per direction of Engineer in charge. | cum | 11022.13 | 76.653 | Seventy-Six point Six Five Three | 844879.331