## Estimate
Detail estimate for
#REF! | [33 empty] | 153
Item No | Item Code | Description of Item | [21 empty] | Measurement
1 | 04-150 | Manufacturing and supplying R.C.C. (1:2:4) BM Pillars of size 15cmx 15cmx75cm, with 40cmx40cmx10cm base having 3 nos.10mm dia MS.bar each way at base,4nos.10mm dia vertical bar and 8nos 6mm dia ring,excluding cost of M.S.works for reinforcement but including cost of form works, concreting, plastering at top, finishing surface, curing etc. complete, with inscription of "BWDB", on exposed surface etc. complete as per direction of Engineer in charge.
|  | Total Length |  |  |  |  | = | 13.17 |  | KM |  | = | @ | 0.5 | KM C/C |  |  | = | 26 |  | + | 1 | nos |  |  |  |  | = | 27 | nos
[24 empty] | Total |  |  |  | = | 27 | nos
2 | 04-160 | Fixing in position B.M. pillars and kilometer posts of size 15cmx15cmx75cm with 40cmx40cmx10cm base, embedding 45cm below G.L. including carriage, earth cutting, backfilling, ramming, etc. complete as per direction of Engineer in charge.
|  | Total Length |  |  |  |  | = | 13.17 |  | KM |  | = | @ | 0.5 | KM C/C |  |  | = | 26 |  | + | 1 | nos |  |  |  |  | = | 27 | nos
[8 empty] | Kilometer post |  |  |  | = | 14 | [14 empty] | = | 14
[24 empty] | Total |  |  |  | = | 41 | nos
3 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge.
|  | Total Length |  |  |  |  | = | 13.17 |  | KM |  | = | 13170 |  |  | m
|  | Considering 6 row at toe | [9 empty] | = | 13170 |  |  | x | 6 |  | x | 2 | m | [6 empty] | = | 158040 | m
[24 empty] | Total |  |  |  | = | 158040 | m
4 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge.
|  | Total Length |  |  |  |  | = | 13.17 |  | KM |  | = | @ | 50 |  | m c/c |  |  |  | = | 263 |  | + | 1 | nos |  |  | = | 264 | nos
[24 empty] | Total |  |  |  | = | 264 | nos
5 | 40-540-20 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >=8.0 cm in position etc. complete as per direction of Engineer in charge. Length : >=2.0 m to <=4.5m
|  | Total Length |  |  |  | = | 5000 |  |  | M |  | = | @ | 0.8 |  | m c/c |  |  |  | = | 6250 |  | x | 2 | nos |  |  | = | 12500 | nos
[24 empty] | Total |  |  |  | = | 12500 | nos
6 | 40-560-10 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge.Double Walling.
|  | Total Length |  |  |  | = | 5000 |  |  | M |  | x | 1 | x |  | 1 |  | line |  | = | 5000 |  |  | Measurement |  |  |  | = | 5000 | m
[24 empty] | Total |  |  |  | = | 5000 | m
7 | 40-550-30 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. >= 0.75 m to < 1.50 m, on dry land.
|  | Total Length |  |  |  | = | 5000 |  |  | M |  | = | @ | 0.8 |  | m c/c |  |  | = | 6250 |  | x | 2 | nos x |  | 0.6 | m | = | 3751.2 | m
[24 empty] | Total |  |  |  | = | 3751.2 | m
8 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah double woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge.
|  | Total Length |  |  |  | = | 5000 |  |  | m |  | x | 1.5 |  | x | 2 | Layer |  | = | 15000 |  |  | sqm |  |  |  |  | = | 15000 | sqm
[24 empty] | Total |  |  |  | = | 15000 | sqm
9 | 16-410-10 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge.300m to 1.00 km.(85% compaction)
|  | As per calculation sheet attached total Earth volume= | [16 empty] | 202851.032 | [5 empty] | cum
|  | Earth work by carried earth quantity 25% of total earth= | [16 empty] | 50712.758 | [5 empty] | cum
[24 empty] | Total |  |  |  | = | 50712.76 | cum | 50712.76
10 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/ canalbank/road etccompacted to 85%/90% maximum drydensity at optimum moisture content,with referenceto laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay,0-40% silt, 0-30% sand) within the initial lead of 30m & all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots & stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc.complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 m to 3 m height with 85% compaction.
|  | As per calculation sheet attached total Earth volume= | [17 empty] | 202851.032 | [5 empty] | cum
|  | Earth work by manual labour, quantity 25% of total earth= | [17 empty] | 50712.758 | [5 empty] | cum
[24 empty] | Total |  |  |  | = | 50712.76 | cum | 50712.76
11 | 16-190 | Extra rate for every additional lead of 15 m or part thereof beyond the initial lead of 30m up to a maximum of 19 leads (3m neglected) for all kinds of earth work. 2 nos Lead (Quoted rate will be applicable for 2 nos lead)
Extra Lead 2 nos
|  | As per calculation sheet attached total Earth volume= | [17 empty] | 202851.032 | [5 empty] | cum
|  | Earth work by manual labour, quantity 25% of total earth= | [17 empty] | 50712.758 | [5 empty] | cum
|  | Lead quantity of earth work by manual labour= | [17 empty] | 50712.758 | [5 empty] | cum
[24 empty] | Total |  |  |  | = | 50712.76 | cum
12 | 16-650-10 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 to 4 m height with 85% compaction.
|  | As per calculation sheet attached total Earth volume= | [17 empty] | 202851.032 | [5 empty] | cum
|  | Earth work by mechanical excavator, quantity 50% of remaining earth= | [17 empty] | 101425.516 | [5 empty] | cum
[24 empty] | Total |  |  |  | = | 101425.52 | cum | 101425.52 | 0.008
13 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement.
|  | As per calculation sheet attached total Earth volume= | [17 empty] | 202851.032 | [5 empty] | cum
|  | Remaining Earth work quantity 75% of total earth= | [17 empty] | 152138.274 | [5 empty] | cum
|  | Royalty Earth = | [17 empty] | 152138.274 | [5 empty] | cum
[24 empty] | Total |  |  |  | = | 152138.27 | cum
14 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75 mm thick good quality durba or charkanta sods of size 200 mm x 200 mm with all leads and lifts including ramming watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only) as per direction of Engineer in charge.
|  | Embankment Length | [11 empty] | = | 13170
|  | Slope protection length | [11 empty] | = | 25
|  | Turfing area | [11 empty] | = | 13170 |  |  |  | x | 18.5 |  |  | = | 243645 |  |  | sqm
|  | Closure | [11 empty] | = | 80 |  |  |  | x | 18 |  |  | = | 1440 |  |  | sqm
|  | Deduction | [11 empty] | = | 25 |  |  |  | x | 18.5 |  |  | = | -462.5 |  |  | sqm
|  | Top Protection | [11 empty] | = | 650 |  |  |  | x | 3 |  |  | = | -1950 |  |  | sqm
[19 empty] | Total |  |  |  | = | 242672.5 |  |  | sqm
[24 empty] | Total |  |  |  | = | 242672.5 | sqm
15 | 36-150 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props
|  | Total Length |  |  |  |  | = | 13.17 |  | KM |  | = | @ | 1 | KM C/C |  |  | = | 13 |  | + | 1 | nos |  |  |  |  | = | 14 | nos
[6 empty] | Suttering |  |  |  | = | 22 |  | x | 0.25 | = | 0.78571 |  |  | m
7
[7 empty] | Area of Shattering |  |  |  |  | = | 14 |  | x | 0.78571 |  | x | 1.55 | = | 17.05 |  |  | sqm
[24 empty] | Total |  |  |  | = | 17.05 | sqm
16 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia
|  |  |  | D-10- 6Nos (Vertical) | [13 empty] | D-6- 8Nos (Stirrups)
|  |  |  | = | 14 |  | x |  | 6 |  | x | 1.55 |  |  |  | = | 14 |  | x | 8 | x | 0.688
|  |  |  | = | 130.2 |  |  |  |  | m | [5 empty] | = | 77.056 |  |  | m
|  |  |  | = | 130.2 |  |  |  |  | x | 0.62 |  |  |  |  | = | 77.056 |  | x | 0.22
|  |  |  | = | 80.724 |  |  |  |  | kg | [5 empty] | = | 16.9523 |  | kg | [12 empty] | = | 18.841 | x | 8 | x | 0.688
[24 empty] | Total |  |  |  | = | 97.68 | Kg |  | = | 103.7009 | x | 0.22
17 | 76-115-10 | M.S Work for reinforcement with Standard deformed bar fy=276 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 6mm dia
|  |  | 14 |  | × | 8 | × | 0.688 |  |  | = | 77.056 |  | × | 0.22 |  | = | 16.95
[32 empty] | = | 18.841 | x | 8 | x | 0.688
[24 empty] | Total |  |  |  | = | 16.95 | Kg |  | = | 103.7009 | x | 0.22
18 | 28-200-10 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: with stone chips . | [29 empty] | = | 22.8142 |  | kg
Volume of RCC
[8 empty] | = | 14 |  | X | 22 |  | X | 0.25 |  | X | 1.55
7
[9 empty] | = | 17.05 |  | cum
[24 empty] | Total |  |  |  | = | 17.05 | cum
19 | Approved Rate | Preparation and mobilization of the Site for Construction of Submersible Embankment or other Structural Components in c/w "Haor Flood Management and Livelihood Improved Improvement Project(BWDB Part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office(40sqm), CI Sheet labour sheds(200sqm), CI Sheet Stores(200sqm), supply of wooden & cane seated furniture etc. as specified and as per Contractor's Method Statement and as per direction of Engineer in charge. | [25 empty] | = | 1 | LS
20 | Approved Rate | Provide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor’s Method Statement and as per direction of Engineer in charge. | [25 empty] | = | 60 | Days
21 | Approved Rate | Demobilization and clean-up of the site upon completion of the works, as per Specifications and Contractor's Method Statement and as per direction of Engineer in Charge | [25 empty] | = | 1 | LS
22 | Approved Rate | Providing and maintaining adequate portable water supply by installing 6 Nos. of tube well and sanitation facilities by installing 6 Nos. of sanitary latrines for usage of labours,officials and others for prevailing the hygenic and healthy environment at allover the working site As per direction of the Engineer in charge. | [25 empty] | = | 1 | LS
23 | Approved Rate | Mobilize, strengthen required land based construction equipment such as excavator, dump truck, chain dozer, vibro-compactor, and plants such as generator for site electrification, digital camera for taking photographs and digital video camera for recording/Taking photograph all sequences of works etc for keeping records of the Works by providing following information including transfer to site, complete for the purposes stated in the Technical Specification and Contractor’s Method Statement and as per direction of Engineer in charge. | [25 empty] | = | 1 | LS
24 | Approved Rate | Operate , maintain of plant and equipment such as generator for site electrification, for the purpose stated in the Technical Specification and in the Contractor’s Method Statement and as per direction of Engineer in charge. | [25 empty] | = | 1 | LS
25 | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge.
|  |  | Length= |  |  | 650 |  |  |  |  | width |  | = | 3 |  |  |  | h | = | 0.45
[11 empty] | Volume= |  |  |  | 877.5 |  |  | cum
|  |  | Block edge |  |  |  |  | = |  |  | 2 |  | x | 650 |  | x | 0.3 |  | x | 0.2 |  | = | 78 |  |  | cum
[22 empty] | = | 955.5 |  |  | cum
[24 empty] | Total |  |  |  | = | 955.5 | cum
26 | Approved Rate/LGED | BP: Preperation of bed by cutting and filling including watering to bring moisture content ±2% of OMC & compacting by appropiate mechanical means etc to attain minimum compaction 98% of MDD (standard) to obtain a minimum soaked CBR 4% etc all complete as per direction of the E-I-C.
|  |  | Length= |  |  | 550 |  |  |  |  | width |  | = | 2.8
[11 empty] | Volume= |  |  |  | 1540 |  |  | sqm
[24 empty] | Total |  |  |  | = | 1540 | sqm
27 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by manual labour using mallet/ vibro compactor including cost of all materials etc. complete as per design, drawing and direction of Engineer in charge (payment shall be made on compacted volume).
|  |  | Length= |  |  | 550 |  |  |  |  | width |  | = | 2.8 |  |  |  | h | = | 0.15
[11 empty] | Volume= |  |  |  | 231 |  |  | cum
[24 empty] | Total |  |  |  | = | 231 | cum
28 | Approved Rate | Manufacturing and supplying of CC blocks in leanest mix (1:2:4) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge.
Block size: 30cm x 30cm x 30cm
|  |  | Length= |  |  | 550 |  |  |  |  | width |  | = | 2.8 |  |  |  | Area |  | = | 1540 |  |  | sqm
|  |  |  | No of blocks | [15 empty] | = | 17111 |  |  | nos
[24 empty] | Total |  |  |  | = | 17111 | nos
| Approved Rate | Block size: 100cm x 65cm x (10-15)cm
|  |  | Length= |  |  | 550
|  |  |  | No of blocks(Edging) | [9 empty] | 2 |  | X | 550 |  |  | = | 1100 |  |  | nos
[24 empty] | Total |  |  |  | = | 1100 | nos
29 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge.
|  |  | Length= |  |  | 550 |  |  |  |  | width |  | = | 2.8
[11 empty] | Area= |  |  |  | 1540 |  |  | sqm
[24 empty] | Total |  |  |  | = | 1540 | sqm
30 | 40-220-10 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.Within 200m
Within 200m
|  | Block nos |  |  |  | = | 17111 |  |  |  | nos | + | 1100 |  | Volume= |  |  |  | 551.372 |  | cum
[20 empty] | 50% of total quantity | [7 empty] | = | 275.69 | cum
| 40-220-20 | Beyond 200m
[20 empty] | 50% of total quantity | [7 empty] | = | 275.69 | cum
31 | NSI | Environmental Monitoring through Sample Collection and analysis such as Air quality test, Surface water test, Sound Level monitoring, Traffic signs and road navigation, safety provisions with first aid and medical Assistant as per direction of engineer in charge. | [25 empty] | = | 1 | LS
|  | (Md. Shafiqul Islam) | [11 empty] | (Md. Zahurul Islam) | [12 empty] | (Md. Shahjahan)
|  | Executive Engineer | [11 empty] | Sub- Divisional Engineer | [12 empty] | SAE/SO
|  | Kishoreganj WD Division | [11 empty] | Kishoregonj O&M Sub-Division | [12 empty] | Bhairab O&M Section
|  | BWDB, Kishoreganj. | [11 empty] | BWDB. Kishoregonj | [12 empty] | BWDB, Kishoreganj.

## Embankment
Item No | Item Code | Description of Item | Unit | Quantity | Unit Rate
1 | 04-150 | Manufacturing and supplying R.C.C. (1:2:4) BM Pillars of size 15cmx 15cmx75cm, with 40cmx40cmx10cm base having 3 nos.10mm dia MS.bar each way at base,4nos.10mm dia vertical bar and 8nos 6mm dia ring,excluding cost of M.S.works for reinforcement but including cost of form works, concreting, plastering at top, finishing surface, curing etc. complete, with inscription of "BWDB", on exposed surface etc. complete as per direction of Engineer in charge. | nos | 27
2 | 04-160 | Fixing in position B.M. pillars and kilometer posts of size 15cmx15cmx75cm with 40cmx40cmx10cm base, embedding 45cm below G.L. including carriage, earth cutting, backfilling, ramming, etc. complete as per direction of Engineer in charge. | nos | 41
3 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge. | m | 158040
4 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | nos | 264
5 | 40-540-20 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >=8.0 cm in position etc. complete as per direction of Engineer in charge. Length : >=2.0 m to <=4.5m | nos | 12500
6 | 40-560-10 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge.Double Walling. | m | 5000
7 | 40-550-30 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. >= 0.75 m to < 1.50 m, on dry land. | m | 3751.2
8 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah double woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. | Sqm | 15000
9 | 16-410-10 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge.300m to 1.00 km.(85% compaction) | cum | 50712.76
10 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/ canalbank/road etccompacted to 85%/90% maximum drydensity at optimum moisture content,with referenceto laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay,0-40% silt, 0-30% sand) within the initial lead of 30m & all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots & stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc.complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 m to 3 m height with 85% compaction. | Cum | 50712.76
11 | 16-190 | Extra rate for every additional lead of 15 m or part thereof beyond the initial lead of 30m up to a maximum of 19 leads (3m neglected) for all kinds of earth work. 2 nos Lead (Quoted rate will be applicable for 2 nos lead) | 2 lead/Cum | 50712.76
12 | 16-650-10 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 to 4 m height with 85% compaction. | cum | 101425.52
13 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | cum | 152138.27
14 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75 mm thick good quality durba or charkanta sods of size 200 mm x 200 mm with all leads and lifts including ramming watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only) as per direction of Engineer in charge. | Sqm | 242672.5
15 | 36-150 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props | Sqm | 17.05
16 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia | kg | 97.68
17 | 76-115-10 | M.S Work for reinforcement with Standard deformed bar fy=276 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 6mm dia | kg | 16.95
18 | 28-200-10 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: with stone chips . | cum | 17.05
19 | Approved Rate | Preparation and mobilization of the Site for Construction of Submersible Embankment or other Structural Components in c/w "Haor Flood Management and Livelihood Improved Improvement Project(BWDB Part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office(40sqm), CI Sheet labour sheds(200sqm), CI Sheet Stores(200sqm), supply of wooden & cane seated furniture etc. as specified and as per Contractor's Method Statement and as per direction of Engineer in charge. | LS | 1
20 | Approved Rate | Provide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor’s Method Statement and as per direction of Engineer in charge. | Days | 60
21 | Approved Rate | Demobilization and clean-up of the site upon completion of the works, as per Specifications and Contractor's Method Statement and as per direction of Engineer in Charge | LS | 1
22 | Approved Rate | Providing and maintaining adequate portable water supply by installing 6 Nos. of tube well and sanitation facilities by installing 6 Nos. of sanitary latrines for usage of labours,officials and others for prevailing the hygenic and healthy environment at allover the working site As per direction of the Engineer in charge. | LS | 1
23 | Approved Rate | Mobilize, strengthen required land based construction equipment such as excavator, dump truck, chain dozer, vibro-compactor, and plants such as generator for site electrification, digital camera for taking photographs and digital video camera for recording/Taking photograph all sequences of works etc for keeping records of the Works by providing following information including transfer to site, complete for the purposes stated in the Technical Specification and Contractor’s Method Statement and as per direction of Engineer in charge. | LS | 1
24 | Approved Rate | Operate , maintain of plant and equipment such as generator for site electrification, for the purpose stated in the Technical Specification and in the Contractor’s Method Statement and as per direction of Engineer in charge. | LS | 1
(B)Block Road
25 | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge. | cum | 955.5
26 | Approved Rate/LGED | BP: Preperation of bed by cutting and filling including watering to bring moisture content ±2% of OMC & compacting by appropiate mechanical means etc to attain minimum compaction 98% of MDD (standard) to obtain a minimum soaked CBR 4% etc all complete as per direction of the E-I-C. | Sqm | 1540
27 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by manual labour using mallet/ vibro compactor including cost of all materials etc. complete as per design, drawing and direction of Engineer in charge (payment shall be made on compacted volume). | cum | 231
28 |  | Manufacturing and supplying of CC blocks in leanest mix (1:2:4) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge.
| Approved Rate | Block size: 30cm x 30cm x 30cm | nos | 17111
| Approved Rate | Block size: 100cm x 65cm x (10-15)cm | nos | 1100
29 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge. | Sqm | 1540
30 | 40-220-10 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.Within 200m | cum | 275.69
| 40-220-20 | Beyond 200m | cum | 275.69
31 | NSI |  | LS | 1

## Regulator
Item No | Item Code | Description of Item | Unit | Unit Rate | Bagadia Khal | Neora Khal
(C) Bagadia Khal Rehulator (1-Vent,1.50m×1.80m) at KM 14.52
1 | 01-120 | Construction of B.M. pillar at site first class bricks in cement mortar (1:4) of size 36cm x 38cm x 75cm of cement concrete (1:2:4) base size 50cm x 50cm x 75cm with 12mm thick cement plastering (1:2) in exposed surface of pillar and cement mortar on top (1:2) with in ascription of “BWDB” with 25cm of the pillar below ground level etc. complete including ramming the backfilling and the cost of all materials as per direction of Engineer in charge. | Nos |  | 4 | 7
2 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials from entire site and removing soil upto 15cm depth including uprooting stumps, jungle, cleaning, levelling, dressing etc. complete as per direction of Engineer in charge | Sqm |  | 8274.48 | 6750
3 | 04-620-20 | 20mm wide. | Sqm |  | 11 | 29.6
4 | 12-100 | Installation of pizeometer including supply of 40mm G.I, pipe, brass strainer, socket, labor, by wash boring, lowering, fixing the elevation and providing cover of the top of the well etc, complete as par direction of Engineer in charge. | each |  | 6 | 6
5 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0.40% silt and 0-30% sabd) in construction of cross/ring bundh as per design & specification with all lead and lifts throwing the earth in layer not exceeding 150mm. In thickness in/c clod’s breaking rough dressing, clearing the Jungles removing stumps dug baling and 75mm cambering etc. complete as per direction of Engineer in charge. | Cum |  | 2880 | 1250
6 | 40-440-20 | Capacity 50kg. (2nd hand bag) | Nos |  | 1125 | 8010.35
7 | 16-310-10 | For moving spoil earth upto a distance of 100m from the centre of the pit | Cum |  | 5026.69
8 | 16-560-10 | By bamboo post of 6.00 m length, 60mm to 80mm dia, 25 cm c/c and 2.00m drive with diagonally woven tarza walling and avarage 70mm dia half split bamboo batten @ 2.00m c/c fixed with nails. qbelow ground with | sqm |  | 300 | 447.2
9 | 16-560-30 | By Local hard wood ballah post 6.00 m length, 125mm dia, 1m c/c and 2.00m drive with 6.0m long bamboo of average 75mm @ 1.00m c/c and average 70mm dia half split bamboo batten @ 2.00m c/c fixed with nails. | sqm |  | 273.6 | 114188.62
10 | 12-310-20 | By pump. | cum |  | 51384.88 | 22.27
11 | 44-240-30 | U-shape, hot- rolled steel sheet pile width= 400mm to 600mm: height=>100mm, Th.=> 10.5: wt. per sqm of pile wall =>120 kg/m2: sectional modulus per one meter of pile wall width => 874 cm3/m. | Mt. |  | 18.05 | 126.21
12 | 44-320-20 | Above 10mm thick. | m |  | 102.27 | 6
13 | 12-300 | Construction of sump well with dug holes of size 1.80m x 2.00m, laying in position the perforated empty diesel/ petrol drum sheet of 1.00m dia to a depth 1.50m having slot area of 1000 sq.cm/sqm. slot dia being 30mm each with supply of necessary shrouding materials comprising of 60% 40mm down graded khoa and 40% coarse sand of FM>= 2.50 and placing those around and beneath the drum sheet having thickness of 40cm and 50cm respectively including necessary welding, fitting etc, complete as per direction of Engineer in charge. | each |  | 4 | 169.36
14 | 44-270-20 | U-type or any other type : Upto 4.50 m depth. | sqm |  | 137.24 | 144.87
15 | 72-540 | Epoxy paint 2 coats of approved colour and specification over a priming coat to gate, hoisting device and embedded metal parts including scraping out rust and old paint with chisel, scraper, steel wire brush & emery paper etc. complete in all respect including the cost of all materials as per direction of Engineer in charge. | Sqm |  | 441.11 | 59.16
16 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge. | Sqm |  | 29.68
17 | 44-220-10 | Weighing minimum 1.0 Kg. per 6.50 sqm. | Sqm |  | 182.95 | 447.69
18 | 28-100 | Cement concrete work in leanest mix 1:4:8, with sand of (FM >= 1.5) in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of form works etc. complete as per direction of Engineer in charge. | Cum |  | 0.73 | 2.556
19 | 28-120-20 | With 25mm down graded stone chips. | Cum |  | 25.25 | 59.64
20 | 04-320 | Supplying bamboo pegs 0.45m to 0.75m long and average dia 6cm, with saw cut top as per terms & condition of the Engineer in charge. | Nos |  | 120 | 160
21 | 04-330 | Labour charge for fixing the bamboo pegs 0.45 to 0.7i5 long and average dia 6cm complete as per direction of Engineer in charge. | Nos |  | 120 | 160
22 | 76-120-10 | 8mm dia to 30mm dia | kg |  | 18361.92 | 32245.47
23 | 76-115-10 | 6mm dia | kg |  | 33.83 | 105.3
24 | 28-200-10 | With stone chips | Cum |  | 225.56 | 354.81
25 | 36-150-60 | Footing , footing beams, girder beams, foundation slab with 60-80 mm dia barrack bamboo props. | Sqm |  | 269.36 | 356.88
26 | 36-150-10 | Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | Sqm |  | 696.97 | 777.53
27 | 36-150-20 | Deck slab, operating deck slab, top slab of barrel up to 3.50m of height with 60-80 dia barrack bamboo props. | Sqm |  | 32.98 | 116.73
28 | 76-630-10 | 3 Bulb type | M. |  | 17.6 | 29.9
29 | 40-650-30 | F.M. : 1.00 to 1.50. | Cum |  | 36.97 | 33.72
30 | 40-650-20 | F.M. : 1.50 to 2.00. | Cum |  | 6.59 | 10.07
31 | 16-520-20 | Sand of FM >= 1.50 | Cum |  | 47.91 | 147.35
32 | 40-640-20 | Well graded between 40mm to 20mm size. | Cum |  | 45.3 | 91.1403
33 | 40-610-30 | Well graded between 20mm to5mm size. (Combination of sub item 10 & 30 or 20 & 30 shall be used. | Cum |  | 45.3 | 91.14
34 | 40-140-50 | Block Size 30cm X 30cm X 30cm. | each |  | 6477 | 10878
35 | 40-140-40 | Block Size 40cm X 40cm X 20cm. | each |  | 1541 | 5276
36 | 40-220-10 | Within 200m. | cum |  | 101.49 | 231.26
37 | 40-220-20 | Beyond 200m | cum |  | 101.49 | 231.26
38 | 76-170 | M.S. work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cuttings, bending, welding, forging, drilling, riveting, embedding anchor bars, staging and fitting, fixing, local handling etc. complete with energy consumption and supply of labors including the cost of all materials as per design, specification and direction of Engineer in charge. | kg |  | 2158.79 | 7571.72
39 | 80-230-40 | 40mm dia G.I. pipe line. | M |  | 4.5 | 4.5
40 | 80-260-20 | 50mm dia G.I pipe. | M |  | 4.7 | 18.8
41 | 76-240-40 | Size 1.95m x 1.65m. | each |  | 2 | 8
42 | 76-260-20 | Size 1.95m X 1.35m or 1.95m X 1.65m. | each |  | 2 | 8
43 | 76-190 | Manufacturing and supplying and installation of pedestal type lifting devise for slide gate with 63mm dia, threaded steel shaft, 146mm outer dia bronze nut, thrust bring steel bevel gear etc, as per approved desing including supply of all components, labors with prime coat of red oxide where necessary etc. complete including the cost of all materials as per specification and direction of the Engineer in charge. | each |  | 2 | 8
44 | 68-130 | Supplying wooden flap gates with pressure treated fall boards/ stop logs of different sizes (not less than 15cm in depth) of Sal, Sundry, garjan Shishu of equivalent timber for regulator/ sluices, including fixing in position with eye hook etc. complete as per direction of Engineer in charge | Cum |  | 1.72 | 6.89
45 | 16-140-10 | 0 to 3m height. | Cum |  | 2640 | 7112
46 | 16-130 | Earth work by manual labour in all kinds of soil in excavation or reexcavation of channels with the initial lead of 30m and lift of 1.5m including levelling, dressing and throwing the spoils to profile with breaking clods, rough dressing, clearing jungles including cutting trees upto 200mm girth, dug bailing etc. complete as per direction of Engineer in charge. | Cum |  | 7558.5 | 10120.5
47 | 16-190 | Extra rate for every additional lead of 15m or part here of beyond the initial lead of 30m up to a maximum of 19 leads (3m neglected) for all kinds of earth work. (One No Lead) | pld Cum |  | 1320 | 4978.4
48 | 16-200 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.50m (30cm neglected for all kinds of earth work. (One No. Lift) | plt/ cum |  | 3779.25 | 5060.25
49 | 16-300 | Royalty of specified earth taken from private land (with permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | Cum |  | 2640 | 4934.26
50 | 04-280-10 | 150mm X 25mm | m |  | 6.4 | 6.4
51 | . 16-240 | Earth work by manual labour in all kinds of soil in removing the cross bundh/Ring bundh including all leads and lifts complete and placing the spoils to a safe distance-do-as per direction of Engineer in charge | Cum |  | 2016 | 2177.74
52 | 16-540-20 | Sand of Fm >0.80 | Cum |  | 982.58 | 625.76
53 | 16-530 | Back filling of hydraulic structure and slop building in protective work including all leads and lifts with selected local soil in layer if 150mm including, watering, ramming etc complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in char. | Cum |  | 2455.84 | 5784.57
54 | . 48-100 | Fine dressing and close turfing of the slope and the crest of embankment with 75mm thick good quality durba or charkanta sods of size 200mm x 200mm with all leads and lifts- do-do- etc. complete as per direction of Engineer in charge | Sqm |  | 2600 | 4220
55 | 40-600-20 | Thickness =>2.00mm, CBR puncture resistance => 2100 N Effective opening size <= 0.11mm, horizontal permeability => 4x10E-3m/sec, Vertical permeability => 6x10E-4m/sec, grab tensile strength => 760 N strip tensile strength => 13.00 KN/m. | Sqm |  | 369.2 | 1052.242

## Inlet
Item No | Item Code | Description of Item | Unit | Quantity | Unit Rate | Amount
127 | 04-180 | Site Preparation by manually removing all miscellaneous objectionable materials from entire site and including soil up to 15 cm depth including do – do etc. complete | Sqm | 5000 | 27.72 | 138600
128 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0.40% silt and 0-30% sabd) in construction of cross/ring bundh as per design & specification with all lead and lifts throwing the earth in layer not exceeding 150mm. In thickness in/c clod’s breaking rough dressing, clearing the Jungles removing stumps dug baling and 75mm cambering etc. complete as per direction of Engineer in charge. | Cum | 10080 | 142.42 | 1435593.6
129 | 04-120 | Construction of B.M. pillar at site first class bricks in cement mortar (1:4) of size 36cm x 38cm x 75cm of cement concrete (1:2:4) base size 50cm x 50cm x 75cm with 12mm thick cement plastering (1:2) in exposed surface of pillar and cement mortar on top (1:2) with in ascription of “BWDB” with 25cm of the pillar below ground level etc. complete including ramming the backfilling and the cost of all materials as per direction of Engineer in charge. | each | 100 | 1203.77 | 120377
130 | 2.16-150 | Earth work in excavation of foundation trenches in all kings of soils including leveling, dressing, placing, removal of spoils to a safe distance with initial lead of 30m and lift of 1.5m as per specification and direction of Engineer in charge | Cum | 15793.0363 | 172.85 | 2729826.316
131 | 16-520 | Supplying and filling sand in foundation of hydraulic structure, buildings and in protective works with selected sand in 150mm thick layer, including leveling, dressing, ramming, watering etc complete (compacted to 50% relative density by manual labour using mallet/ vibro compactor) as per direction of Engineer in charge. |  |  |  | 0
| 16-520-10 | Sand of FM >= 1.00 | Cum | 91.4 | 858.01 | 78422.114
132 | 44-220 | Supplying and laying single layer polythene sheet in floor below cement concrete, RCC slab, on walls etc. complete in all respect as per direction of Engineer in charge |  |  |  | 0
| 44-220-10 | Weighing minimum 1.0 Kg. per 6.50 sqm. | Sqm | 456 | 31.22 | 14236.32
133 | 28-120 | Cement concrete work in leanest mix 1:3:6 with sand of (FM >= 1.5) in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of form works etc. complete as per direction of Engineer in charge. |  |  |  | 0
| 28-120-20 | With 25mm down graded stone chips. | Cum | 34.2 | 10954.48 | 374643.216
134 | 76-120 | M.S. Work for reinforcement with twisted M.S. bar, fy=414 N/mm2, (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of twisted M.S. bar in different sizes and blinding with 22 to 18 gages G.I. wire etc complete including the cost of all materials as per direction of Engineer in charge |  |  |  | 0
A | 76-120-10 | 8mm dia to 30mm dia | Kg. | 41397.755 | 77.34 | 3201702.372
135 | 28-200 | Reinforced Cement concrete work in leanest mix 1:1.5:3 with 20mm down graded coarse aggregate and sand of FM >= 2.0 to FM<= 2.5, to attain a minimum 28 days cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding the cost of M.S. work for reinforcements and formworks etc. Complete as per direction of Engineer in charge. |  |  |  | 0
| 28-200-10 | With stone chips | Cum | 456.212 | 11674.49 | 5326042.015
136 | 36-150 | Form work for centering and water tight shuttering as per drawing with 24 BWG M.S sheet, fitted fixed with 40mm x 40mm x 6mm), M.S. angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens struts nuts and bolts, props etc. as per desired shape and size including leveling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge |  |  |  | 0
A | 36-150-60 | Footing , footing beams, girder beams, foundation slab with 60-80 mm dia barrack bamboo props. | Sqm | 971.25 | 735.35 | 714208.688
B | 36-150-10 | Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | Sqm | 935.9457 | 909.69 | 851420.457
137 | 40-610 | Supplying and laying dry 1st class tick jhama brick chips as jilter in two layers (top and bottom) as per specification size, range and gradation, including breaking chips, grading preparation of surface, compacting each layer etc, with supply of all materials and as per direction of Engineer in charge. |  |  |  | 0
| 40-610-30 | Well graded between 20mm to5mm size. (Combination of sub item 10 & 30 or 20 & 30 shall be used. | Cum | 23 | 4076.09 | 93750.07
138 | 12-310 | Bailing out of water with all leads and lifts by manual labour or pump. With all arrangements for protection of ring bund and side slopes of foundation pit against erosion or washout etc complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge |  |  |  | 0
| 12-310-20 | By pump. | Cum | 24978.7596 | 6.13 | 153119.796
139 | 76-170 | M.S. work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cuttings, bending, welding, forging, drilling, riveting, embedding anchor bars, staging and fitting, fixing, local handling etc. complete with energy consumption and supply of labors including the cost of all materials as per design, specification and direction of Engineer in charge. | Kg. | 3962.5575 | 144.42 | 572272.554
140 | 40-140 | Manufacturing and supplying C.C. blocks in leanest mix 1:3:6 with cement and sand (FM>=1.5) and 1st class or picked jhama brick chips (25mm down graded), to attain a minimum 28 day strength of 9.00 N/mm2 including breaking, screening, grading, washing chip, mixing, laying in forms, consolidation, curing for at least 21 days including preparation of platform, shuttering and stacking in measurable stacks etc, complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. |  |  |  | 0
| 40-140-50 | Block Size 30cm X 30cm X 30cm. | Each | 2400 | 317.01 | 760824
141 | 40-220 | Lobour charge for protective work in laying C.C blocks of different sizes including preparation of base, ramming of base etc. complete as per direction of the Engineer in charge |  |  |  | 0
| 40-220-10 | Within 200m. | Cum | 64.8 | 1145.88 | 74253.024
142 | 60-260 | Manufacturing and supplying Standard machine made RCC Pipe of different diameter, length and thickness in construction of Drain/ Sluice/ Culvert/ Out let and any other works in leanest mix 1:1.5:3 with 15mm down graded stone shingles and sand of FM>= 2.0 to attain a minimum 28 Days cylinder strength of 25 N/mm2 including breaking, screening, grading, laying in forms, consolidating, curing, including the cost of 6mm dia M.S. work for reinforcement and specification including tools. Plants, testing, stacking in measurable stack etc. complete as per design specification and direction of Engineer in charge. |  |  |  | 0
| 60-260-35 | RCC Pipe: 600mm dia, wall thickness not less than 60mm, circular reinforcement 100mm c/c and longitudinal reinforcement 210mmc/c. | m | 405 | 2636.65 | 1067843.25
143 | 60.3 | Lying in position standard machine made R.C.C. Pipe of different diameter in construction of drain/ sluice/ culvert/ outlet and any other work including fitting, fixing the socket where necessary, local handing, cutting, dressing, leveling, plumbing etc. complete as per design, specification and direction of Engineer in charge. |  |  |  | 0
| 60-300-35 | : 600mm dia | m | 405 | 66.31 | 26855.55
144 | 16-540 | Back filling of hydraulic structure including all leads and lifts in 150mm layer including watering, ramming, compaction to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. |  |  |  | 0
| 16-540-20 | Sand of Fm >0.80 | Cum | 1100.4761 | 757.75 | 833885.797
145 | 16-530 | Back filling of hydraulic structure and slop building in protective work including all leads and lifts with selected local soil in layer if 150mm including, watering, ramming etc complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in char. | Cum | 18483.1981 | 159.49 | 2947885.272
146 | . 16-240 | Earth work by manual labour in all kinds of soil in removing the cross bundh/Ring bundh including all leads and lifts complete and placing the spoils to a safe distance-do-as per direction of Engineer in charge | Cum | 7056 | 142.47 | 1005268.32
147 | 76-230 | Manufacturing, supplying, installation and fitting, fixing the vertical steel lift gate/ flap gate as per design and specification, including fabricating, reverting, welding, fixing rubber seal, providing required nuts and bolts including the cost of all materials etc. complete with a prime coat of red oxide where necessary as per direction of Engineer in charge, (Applicable only for size not specified in Item code 76-240 & 76-250) | Kg. | 5538 | 292.74 | 1621194.12
148 | 76-200 | Manufacturing supplying & installation of Hand Wheel type lifting device for slide gate with 63mm dia steel shaft, 108mm outer dia bronze nut taper roller bearing SKF-50216 etc. as per approved design in/c. supply of all components, labours with a prime coat of red oxide where necessary etc. comp. in/c. the cost of all materials as per specification & direction of ENGINEER IN CHARGE. | Each | 25 | 46820.84 | 1170521
149 | . 76-260 | Labour charge for fitting fixing of M.S. vertical lift/ flap gate shutter of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/ sluice and mending the damages with cc (1:2:4), removing the spoils etc. complete including the cost of all materials and as per direction of the Engineer in charge. | Each |  |  | 0
| 76-260-10 | Small size | Each | 50 | 8463.38 | 423169
25735913.851
(F) 5 Nos Box Drainage Outlet
150 | 01-120 | Construction of B.M. pillar at site first class bricks in cement mortar (1:4) of size 36cm x 38cm x 75cm of cement concrete (1:2:4) base size 50cm x 50cm x 75cm with 12mm thick cement plastering (1:2) in exposed surface of pillar and cement mortar on top (1:2) with in ascription of “BWDB” with 25cm of the pillar below ground level etc. complete including ramming the backfilling and the cost of all materials as per direction of Engineer in charge. | Nos | 20 | 1203.77 | 24075.4
151 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials from entire site and removing soil upto 15cm depth including uprooting stumps, jungle, cleaning, levelling, dressing etc. complete as per direction of Engineer in charge | Sqm | 6540 | 27.72 | 181288.8
152 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0.40% silt and 0-30% sabd) in construction of cross/ring bundh as per design & specification with all lead and lifts throwing the earth in layer not exceeding 150mm. In thickness in/c clod’s breaking rough dressing, clearing the Jungles removing stumps dug baling and 75mm cambering etc. complete as per direction of Engineer in charge. | Cum | 14000 | 142.42 | 1993880
153 | 16-150 | Earth work in excavation of foundation trenches in all kings of soils including leveling, dressing, placing, removal of spoils to a safe distance with initial lead of 30m and lift of 1.5m as per specification and direction of Engineer in charge | Cum | 8640.63 | 172.85 | 1493532.896
154 | 12-310 | Bailing out of water with all leads and lifts by manual labour or pump. With all arrangements for protection of ring bund and side slopes of foundation pit against erosion or washout etc complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge |  |  |  | 0
| 12-310-20 | By pump. | cum | 10705.1827 | 6.13 | 65622.77
155 | 44-220 | Supplying and laying single layer polythene sheet in floor below cement concrete, RCC slab, on walls etc. complete in all respect as per direction of Engineer in charge |  |  |  | 0
| 44-220-10 | Weighing minimum 1.0 Kg. per 6.50 sqm. | Sqm | 378.85 | 31.22 | 11827.697
156 | 28-100 | Cement concrete work in leanest mix 1:4:8, with sand of (FM >= 1.5) in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of form works etc. complete as per direction of Engineer in charge. |  |  |  | 0
| 28-100-50 | With 40mm down graded stone chips. | Cum | 1.9245 | 10601.19 | 20401.986
157 | 28-120 | Cement concrete work in leanest mix 1:3:6 with sand of (FM >= 1.5) in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of form works etc. complete as per direction of Engineer in charge. |  |  |  | 0
| 28-120-20 | With 25mm down graded stone chips. | Cum | 43.7189 | 10954.48 | 478918.048
158 | 76-120 | M.S. Work for reinforcement with twisted M.S. bar, fy=414 N/mm2, (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of twisted M.S. bar in different sizes and blinding with 22 to 18 gages G.I. wire etc complete including the cost of all materials as per direction of Engineer in charge |  |  |  | 0
| 76-120-10 | 8mm dia to 30mm dia | kg | 26201.0619 | 77.34 | 2026390.128
159 | 28-200 | Reinforced Cement concrete work in leanest mix 1:1.5:3 with 20mm down graded coarse aggregate and sand of FM >= 2.0 to FM<= 2.5, to attain a minimum 28 days cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding the cost of M.S. work for reinforcements and formworks etc. Complete as per direction of Engineer in charge. |  |  |  | 0
| 28-200-10 | With stone chips | Cum | 244.405 | 11674.49 | 2853303.728
160 | 36-150 | Form work for centering and water tight shuttering as per drawing with 24 BWG M.S sheet, fitted fixed with 40mm x 40mm x 6mm), M.S. angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens struts nuts and bolts, props etc. as per desired shape and size including leveling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge |  |  |  | 0
A | 36-150-60 | Footing , footing beams, girder beams, foundation slab with 60-80 mm dia barrack bamboo props. | Sqm | 964.2749 | 735.35 | 709079.567
B | 36-150-10 | Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | Sqm | 683.162 | 909.69 | 621465.64
C | 36-150-20 | Deck slab, operating deck slab, top slab of barrel up to 3.50m of height with 60-80 dia barrack bamboo props. | Sqm | 83.72 | 921.99 | 77189.003
161 | 16-520 | Supplying and filling sand in foundation of hydraulic structure, buildings and in protective works with selected sand in 150mm thick layer, including leveling, dressing, ramming, watering etc complete (compacted to 50% relative density by manual labour using mallet/ vibro compactor) as per direction of Engineer in charge. |  |  |  | 0
| 16-520-20 | Sand of FM >= 1.50 | Cum | 376.1276 | 1420.06 | 534123.727
162 | 40-610 | Supplying and laying dry 1st class tick jhama brick chips as jilter in two layers (top and bottom) as per specification size, range and gradation, including breaking chips, grading preparation of surface, compacting each layer etc, with supply of all materials and as per direction of Engineer in charge. |  |  |  | 0
A | 40-640-20 | Well graded between 40mm to 20mm size. | Cum | 77.549 | 3730.47 | 289294.218
B | 40-610-30 | Well graded between 20mm to5mm size. (Combination of sub item 10 & 30 or 20 & 30 shall be used. | Cum | 77.549 | 4076.09 | 316096.703
163 | 40-140 | Manufacturing and supplying C.C. blocks in leanest mix 1:3:6 with cement and sand (FM>=1.5) and 1st class or picked jhama brick chips (25mm down graded), to attain a minimum 28 day strength of 9.00 N/mm2 including breaking, screening, grading, washing chip, mixing, laying in forms, consolidation, curing for at least 21 days including preparation of platform, shuttering and stacking in measurable stacks etc, complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. |  |  |  | 0
| 40-140-50 | Block Size 30cm X 30cm X 30cm. | Nos | 4212 | 317.01 | 1335246.12
164 | 40-220 | Lobour charge for protective work in laying C.C blocks of different sizes including preparation of base, ramming of base etc. complete as per direction of the Engineer in charge |  |  |  | 0
| 40-220-10 | Within 200m. | Cum | 113.724 | 1145.88 | 130314.057
165 | 76-170 | M.S. work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cuttings, bending, welding, forging, drilling, riveting, embedding anchor bars, staging and fitting, fixing, local handling etc. complete with energy consumption and supply of labors including the cost of all materials as per design, specification and direction of Engineer in charge. | kg | 826.4745 | 144.42 | 119359.447
166 | 76-240 | Manufacturing and supplying of M.S. Vertical lift gate shutter of 8mm thick M.S. plate and stiffener with minimum 75mm x 10mm M.S. angle as frame, horizontal & vertical beam, 75mm x 25mm x 12mm p-type rubber seal, fixed with 10mm dia x 63.5mm M.S. counter shank bolts with nuts and 40mm x 10mm M.S. strip as clamp drilled spaces @ 150mm c/c, stem attachment with proper thread, nut cotter pin and washer as per approved design including the cost of all materials of proper grade & brand new prime coat of red oxide where necessary as specification and direction of the Engineer in charge. |  |  |  | 0
| 76-240-10 | Size 1.00m x 1.00m. | Nos | 5 | 47702.43 | 238512.15
167 | 76-250 | Manufacturing and supplying of M.S. Flap gate shutter of 8mm thick M.S. skin plate and stiffener with minimum 75mm x 75.00mm x 10mm M.S. angle as frame, horizontal & vertical beam, 100mm x 45mm x 16mm p-type rubber seal, fixed with 10mm dia x 63.5mm M.S. counter shank and hex nuts & bolts and 40mm x 10mm M.S. strip as clamp drilled spaces @ 150mm c/c, hinge assay with gate and wall bracket, link arm of 19mm thick M.S. Plate, 4 nos. 25mm dia x 150mm stainless steel hinge pin with proper thread, nut, cotter pin and washer as per approved design including the cost of all materials of proper grade &i brand new prime coat of red oxide where necessary as specification and direction of the Engineer in charge. . |  |  |  | 0
| 76-250-10 | Size 1.00m x 1.00m. | Nos | 5 | 59678.51 | 298392.55
168 | 76-260 | Labour charge for fitting fixing of M.S. vertical lift/ flap gate shutter of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/ sluice and mending the damages with cc (1:2:4), removing the spoils etc. complete including the cost of all materials and as per direction of the Engineer in charge. |  |  |  | 0
| 76-260-10 | Size 1.00m X 1.00m or 1.35m X 1.35m. | Nos | 10 | 8463.38 | 84633.8
169 | 76-200 | Manufacturing supplying & installation of Hand Wheel type lifting device for slide gate with 63mm dia steel shaft, 108mm outer dia bronze nut taper roller bearing SKF-50216 etc. as per approved design in/c. supply of all components, labours with a prime coat of red oxide where necessary etc. comp. in/c. the cost of all materials as per specification & direction of ENGINEER IN CHARGE. | Each | 5 | 46820.84 | 234104.2
170 | 16-140 | Earth work by manual labor in resection of embankment/ canal bank / river slopes/ road/ compound etc. manually compacted by 7.0 kg iron rammer to abode any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceeding 150mm 100mm, removing roots & stumps of trees of girth unto 200mm from the ground, benching the side slopes, stripping/ sloughing the bees of embankment and borrow pit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the center of the crest (where necessary) etc. complete as per direction of Engineer in charge. |  |  |  | 0
| 16-140-10 | 0 to 3m height. | Cum | 3090 | 187.79 | 580271.1
171 | 16-600-10 | Earth work by Mechanical Excavator ( Long Boom ) in all kinds of soil in excavation/re-excavation of Channel/Canal/khal etc. Including disposal of spoil-soil upto 30m away from the point of excavation with rough dressing and leveling etc. Complete as per direction of Engineer in charge. |  | 866.25 | 142.27 | 123241.388
172 | 16-190 | Extra rate for every additional lead of 15m or part here of beyond the initial lead of 30m up to a maximum of 19 leads (3m neglected) for all kinds of earth work. | pld Cum | 1545 | 14.57 | 22510.65
173 | 16-200 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.50m (30cm neglected for all kinds of earth work. | plt/ cum | 433.125 | 10.99 | 4760.044
174 | 16-300 | Royalty of specified earth taken from private land (with permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | Cum | 3090 | 14.27 | 44094.3
175 | . 16-240 | Earth work by manual labour in all kinds of soil in removing the cross bundh/Ring bundh including all leads and lifts complete and placing the spoils to a safe distance-do-as per direction of Engineer in charge | Cum | 7000 | 142.47 | 997290
176 | 16-540 | Back filling of hydraulic structure including all leads and lifts in 150mm layer including watering, ramming, compaction to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. |  |  |  | 0
| 16-540-20 | Sand of Fm >0.80 | Cum | 235.5665 | 757.75 | 178500.515
177 | 16-530 | Back filling of hydraulic structure and slop building in protective work including all leads and lifts with selected local soil in layer if 150mm including, watering, ramming etc complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in char. | Cum | 3699.629 | 159.49 | 590053.829
178 | . 48-100 | Fine dressing and close turfing of the slope and the crest of embankment with 75mm thick good quality durba or charkanta sods of size 200mm x 200mm with all leads and lifts- do-do- etc. complete as per direction of Engineer in charge | Sqm | 2475 | 26.17 | 64770.75
Sub total for 5 nhos. Box Drainage Outlet ( F ) | [5 empty] | 16742545.211
Grand Total ( A+B+C+D+E+F ) | [5 empty] | #REF!

## Box
Sl No | Item Code | Description | Unit | Rate | Box Drainage-1 | Box Drainage-2 | Box Drainage-3 | Box Drainage-4 | Box Drainage-5
[5 empty] | Quantity | Quantity | Quantity | Quantity | Quantity
1 | 04-120 | BM pilar | each |  | 4 | 0 | 4 | 4 | 4
2 | 04-180 | Site preparation | sqm |  | 1308 | 0 | 1308 | 1308 | 1308
3 | 16-220 |  | cum |  | 2800 | 0 | 2800 | 2800 | 2800
4 | 16-150 |  | cum |  | 1728.126 | 0 | 1728.126 | 1728.126 | 1728.126
5 | 12-310-20 | Bailing out | cum |  | 2141.036 | 0 | 2141.036 | 2141.036 | 2141.036
6 | 44-220-10 | Supply ing and laying of polythene | kg |  | 75.77 | 0 | 75.77 | 75.77 | 75.77
7 | 28-100-50 | CC 1:4:8 | cum |  | 0.384 | 0 | 0.384 | 0.384 | 0.384
8 | 28-120-20 | CC 1:3:6 | cum |  | 8.744 | 0 | 8.744 | 8.744 | 8.744
9 | 76-120-10 | Reinforcement 8mm to 30mm | kg |  | 5240.212 | 0 | 5240.212 | 5240.212 | 5240.212
10 | 28-200-10 | RCC 1:1.5:3 | cum |  | 48.882 | 0 | 48.882 | 48.882 | 48.882
11 | 36-150-60 | Shuttering : Footing beams,beams, grade beams | sqm |  | 192.854 | 0 | 192.854 | 192.854 | 192.854
12 | 36-150-10 | Shuttering : Vertical and inclined walls | sqm |  | 136.632 | 0 | 136.632 | 136.632 | 136.632
13 | 36-150-20 | Shuttering : Deck slab operating deck slab | Sqm |  | 16.744 | 0 | 16.744 | 16.744 | 16.744
14 | 16-520-20 | Back filling sand:FM>1.50 | cum |  | 75.226 | 0 | 75.226 | 75.226 | 75.226
15 | 40-610-20 | Khoa filter: 40mm to 20mm | cum |  | 15.51 | 0 | 15.51 | 15.51 | 15.51 | 21753240.973
16 | 40-610-30 | Khoa filter: 20mm to 5mm | cum |  | 15.51 | 0 | 15.51 | 15.51 | 15.51 | 217.5324
17 | 40-140-50 | CC Block 30x30x30 | each |  | 842.4 | 0 | 842.4 | 842.4 | 842.4
18 | 40-220-10 | Labour charge | each |  | 22.744 | 0 | 22.744 | 22.744 | 22.744
19 | 76-170 | M.S Work in plats, angles, channels | each |  | 165.294 | 0 | 165.294 | 165.294 | 165.294
20 | 76-240-10 | Supply ing of M.S vertical lift gate: 8mm | Nos |  | 1 | 0 | 1 | 1 | 1
21 | 76-250-10 | Supplying Flap gate | each |  | 1 | 0 | 1 | 1 | 1
22 | 76-260-10 | Labour charge for fitting Flap gate | each |  | 2 | 0 | 2 | 2 | 2
23 | 76-200 |  | each |  | 1 | 0 | 1 | 1 | 1 | 17744329.895
24 | 16-140-10 | Earth Work in embankment construction | cum |  | 618 | 0 | 618 | 618 | 618 | 3548865.979
25 | 16-600-10 | Channel excavation of excavator | cum |  | 173.25 | 0 | 173.25 | 173.25 | 173.25 | 35.4887
26 | 16-190 |  | pld cum |  | 309 | 0 | 309 | 309 | 309
27 | 16-200 |  | plt cum |  | 86.626 | 0 | 86.626 | 86.626 | 86.626
28 | 16-300 |  | cum |  | 618 | 0 | 618 | 618 | 618
29 | 16-240 | Ring Budh removal | cum |  | 1400 | 0 | 1400 | 1400 | 1400
30 | 16-540-20 | Back filling sand:FM>.80 | cum |  | 47.114 | 0 | 47.114 | 47.114 | 47.114
31 | 16-530 | Back filling soil | cum |  | 753.738 | 0 | 753.738 | 753.738 | 753.738
| 48-100 | Fine dreasing and close turfing | sqm |  | 495 | 0 | 495 | 495 | 495
Sum-total