## Regulatior.
Sl No | Item Code | Description | Unit | Rate | phuleshwari | Kalna
[7 empty] | code | rate
1 | 04-120 | BM pilar | each | 124.461 | 2 | 2 | 04-120 | 124.461
2 | 04-180 | Site preparation | Sqm | 38.131 | 9000 | 9000 | 04-180 | 38.131
3 | 04-620-20 |  | m | 92.201 | 21.4 | 24 | 04-620-20 | 92.201
4 | 12-100 | Pizeometer | each | 3382.871 | 4 | 4 | 12-100 | 3382.871
5 | 16-510 |  | cum | 341.371 | 5558.85 | 3393.44 | 16-510-10 | 341.371
6 | 16-620-20 |  | Sqm | 775.001 | 285.6 | 221.36 | 16-620-20 | 775.001
7 | 12-310-20 | Bailing out | cum | 6.001 | 50971.29 | 50971.29 | 12-310-20 | 6.001
8 | 44-240 | Sheet pile Supply | M ton | 116000.001 | 11.232 | 10.08 | 44-240-30 | 116000.001
9 | 44-320 | Cutting of sheet Pile | m | 45.611 | 50.07 | 45.5 | 44-320-10 | 45.611
10 | 12-300 | Construction of sump well | each | 20828.401 | 10 | 10 | 12-300 | 20828.401
11 | 44-270 | Sheet pile Drive | Sqm | 1709.051 | 81.9 | 73.5 | 44-270-20 | 1709.051
12 | 72-180 | Painting of steel sheet pile | Sqm | 249.101 | 311.22 | 279.3 | 72-180 | 249.101
13 | 72-540 |  | Sqm | 428.821 | 35.3 | 35.3 | 72-540 | 428.821
14 | 44-310 | Supplying and placing of hesian cloth | Sqm | 514.211 | 38.9 | 34.91 | 44-310 | 514.211
15 | 44-220 | Supplying and laying of polythene | Sqm | 31.821 | 143.22 | 149.19 | 44-220-10 | 31.821
16 | 28-120-20 | CC 1:3:6 | cum | 12907.661 | 17.86 | 13.91 | 28-120-20 | 12907.661
17 | 28-100-20 | CC 1:4:8 | cum | 12479.851 | 1.139 | 0.952 | 28-100-20 | 12479.851
18 | 28-200-20 | RCC 1:1.5:3 | cum | 14581.841 | 140.858 | 135.192 | 28-200-10 | 14581.841
19 | 76-120 | Reinforcement: 8 mm to 22mm | kg | 102.441 | 15026.92 | 15141.3 | 76-120-10 | 102.441
20 | 36-150-60 | Shuttering : Footing beams,beams, grade beams | Sqm | 924.951 | 147.839 | 133.535 | 36-150-60 | 924.951
21 | 36-150-10 | Shuttering : Vertical and inclined walls | Sqm | 970.001 | 396.12 | 350 | 36-150-10 | 970.001
22 | 36-150-20 |  | Sqm | 970.001 | 12.53 | 12.53 | 36-150-20 | 970.001
23 | 76-630-10 |  | m | 1174.191 | 13.4 | 15 | 76-630-10 | 1174.191
24 | 16-540-20 | Back filling sand:FM>.80 | cum | 1400.001 | 327.2 | 227.47 | 16-540-20 | 1400.001
25 | 40-520-20 |  | cum | 4000.001 | 36.405 | 30.837 | 40-520-20 | 4000.001
26 | 40-520-30 |  | cum | 4525.001 | 38.673 | 30.837 | 40-520-30 | 4525.001
27 | 40-500-20 |  | Sqm | 217.701 | 315.828 | 337.428 | 40-500-20 | 217.701
28 | 40-550-10 |  | cum | 2177.011 | 7.297 | 10.692 | 40-550-10 | 2177.011
29 | 40-150-50 |  | cum | 371.821 | 4988 | 3348 | 40-150-50 | 371.821
30 | 40-150-40 |  | cum | 446.541 | 1727 | 1917 | 40-150-40 | 446.541
31 | 40-270-10 |  | cum | 1395.003 | 189.95 | 151.76 | 40-270-10 | 1395.003
32 | 76-170 |  | kg | 161.491 | 938.77 | 938.77 | 76-170 | 161.491
33 | 80-230 |  | m | 356.081 | 21.35 | 22.26 | 80-230-40 | 356.081
34 | 76-240-40 |  | each | 109392.431 | 1 | 1 | 76-240-40 | 109392.431
35 | 76-260-20 |  | each | 12923.011 | 1 | 1 | 76-260-20 | 12923.011
36 | 76-190 |  | each | 93037.271 | 1 | 1 | 76-190 | 93037.271
37 | 16-130 | Earth Work in Channel excavation | cum | 228.001 | 2012 | 9370.24 | 76-250-20 | 79418.421
38 | 16-400 |  | cum | 180.001 | 3637.37 | 1358.3 | 76-260-10 | 10941.291
39 | 16-170 | 2 nos Lift | pltcum | 30.721 |  | 1358.3 | 16-130-10 | 228.001
40 | 16-170 | 3 nos lift | pltcum | 46.081 | 3637.37 |  | 16-400 | 180.001
41 | 16-450 |  | cum | 180.001 | 41.148 | 2206.559 | 16-170 | 30.721
42 | 04-280 |  | m | 98.481 | 2.8 | 3.4 | 16-170 | 46.081
43 | 16-560-20 |  | cum | 860.141 | 626.39 | 451.53 | 16-450 | 180.001
44 | 16-550 |  | cum | 190.001 | 1439.87 | 831.58 | 04-280 | 98.481
45 | 16-470 |  | cum | 180.001 | 1503.69 | 0 | 16-560-20 | 860.141
46 | 68-130 |  | cum | 92159.901 | 1.7213 | 1.7213 | 16-550 | 190.001
47 | 48-100 | Fine dreasing and close turfing | Sqm | 32.971 | 1872 | 2896 | 16-470 | 180.001
[5 empty] | 15662254.1902 | 14800543.6802 | 68-130 | 92159.901
[5 empty] | 156.6225 | 148.0054 | 48-100 | 32.971

## Causeway & Drainage
Sl No | Item Code | Description | Unit | Rate | Quantuty
[6 empty] | code | rate
1 | 04-120 | BM pilar | each | 124.461 | 2 |  |  | 1
2 | 04-180 | Site preparation | Sqm | 38.131 | 10000 |  |  | 2
3 | 12-100 | Pizeometer | each | 3382.871 | 4 |  |  | 3
4 | 16-510 |  | cum | 341.371 | 14222.44 |  |  | 4
5 | 16-620-20 |  | Sqm | 775.001 | 338.2 |  |  | 5
6 | 12-310-20 | Bailing out | cum | 6.001 | 50971.29 |  |  | 6
7 | 44-240 | Sheet pile Supply | M ton | 116000.001 | 22.752 |  |  | 7
8 | 44-320 | Cutting of sheet Pile | m | 45.611 | 102.7 |  |  | 8
9 | 12-300 | Construction of sump well | each | 20828.401 | 10 |  |  | 9
10 | 44-270 | Sheet pile Drive | Sqm | 1709.051 | 165.9 |  |  | 10
11 | 72-180 | Painting of steel sheet pile | Sqm | 249.101 | 630.42 |  |  | 11
12 | 72-540 |  | Sqm | 428.821 | 26.3 |  |  | 12
13 | 44-310 | Supplying and placing of hesian cloth | Sqm | 514.211 | 78.8 |  |  | 13
14 | 44-220 | Supplying and laying of polythene | Sqm | 31.821 | 556.92 |  |  | 14
15 | 28-120-20 | CC 1:3:6 | cum | 12907.661 | 63.71 |  |  | 15
16 | 28-100-20 | CC 1:4:8 | cum | 12479.851 | 2.329 |  |  | 16
17 | 28-200-20 | RCC 1:1.5:3 | cum | 14581.841 | 448.831 |  |  | 17
18 | 76-120 | Reinforcement: 8 mm to 22mm | kg | 102.441 | 45689.63 |  |  | 18
19 | 36-150-60 | Shuttering : Footing beams,beams, grade beams | Sqm | 924.951 | 247.457 |  |  | 19
20 | 36-150-10 | Shuttering : Vertical and inclined walls | Sqm | 970.001 | 958 |  |  | 20
21 | 36-150-20 |  | Sqm | 970.001 | 14.41 |  |  | 21
22 | 16-540-20 | Back filling sand:FM>.80 | cum | 1400.001 | 788.09 |  |  | 22
23 | 40-520-20 |  | cum | 4000.001 | 80.861 |  |  | 23
24 | 40-520-30 |  | cum | 4525.001 | 80.861 |  |  | 24
25 | 40-500-20 |  | Sqm | 217.701 | 1572.04 |  |  | 25
26 | 40-150-50 |  | cum | 371.821 | 8190 |  |  | 26
27 | 40-150-40 |  | cum | 446.541 | 5922 |  |  | 27
28 | 40-270-10 |  | cum | 1395.003 | 410.63 |  |  | 28
29 | 76-170 |  | kg | 161.491 | 1106.67 |  |  | 29
30 | 76-250-20 |  |  | 79418.421 | 3 |  |  | 30
31 | 76-260-10 |  | each | 10941.291 | 3 |  |  | 31
32 | 16-130 | Earth Work in Channel excavation | cum | 228.001 | 16788 |  |  | 32
33 | 16-400 |  | cum | 180.001 | 18893.33 |  |  | 33
34 | 16-170 | 2 nos Lift | pltcum | 30.721 | 1746.65 |  |  | 34
35 | 04-280 |  | m | 98.481 | 8 |  |  | 35
36 | 16-560-20 |  | cum | 860.141 | 1880.83 |  |  | 36
37 | 16-550 |  | cum | 190.001 | 1880.83 |  |  | 37
38 | 68-130 |  | cum | 92159.901 | 1.65 |  |  | 38
39 | 48-100 | Fine dreasing and close turfing | Sqm | 32.971 | 1190 |  |  | 39
40725844.8571
407.2584

## R.C.C Box Drainage
Sl No | Item Code | Description | Unit | Rate | Quantity
[6 empty] | code | rate
1 | 04-120 | BM pilar | each | 124.461 | 2 | 04-120 | 124.461 | 1
2 | 04-180 | Site preparation | Sqm | 38.131 | 2750 | 04-180 | 38.131 | 2
3 | 16-510-20 |  | cum | 341.371 | 783.95 | 16-510-10 | 341.371 | 3
4 | 04-620-20 |  | m | 92.201 | 71.1 | 04-620-20 | 92.201 | 4
5 | 12-310-20 | Bailing out | cum | 6.001 | 16310.81 | 12-310-20 | 6.001 | 5
6 | 12-300 | Construction of sump well | each | 20828.401 | 6 | 12-300 | 20828.401 | 6
7 | 44-220 | Supplying and laying of polythene | Sqm | 31.821 | 61.38 | 44-220-10 | 31.821 | 7
8 | 28-120-20 | CC 1:3:6 | cum | 12907.661 | 8.51 | 28-120-20 | 12907.661 | 8
9 | 28-100-20 | CC 1:4:8 | cum | 12479.851 | 0.4 | 28-100-20 | 12479.851 | 9
10 | 28-200-20 | RCC 1:1.5:3 | cum | 14581.841 | 48.879 | 28-200-10 | 14581.841 | 10
11 | 76-120 | Reinforcement: 8 mm to 22mm | kg | 102.441 | 5321.07 | 76-120-10 | 102.441 | 11
12 | 36-150-60 | Shuttering : Footing beams,beams, grade beams | Sqm | 924.951 | 144.1 | 36-150-60 | 924.951 | 12
13 | 36-150-10 | Shuttering : Vertical and inclined walls | Sqm | 970.001 | 318.1 | 36-150-10 | 970.001 | 13
14 | 36-150-20 |  | Sqm | 970.001 | 17.25 | 36-150-20 | 970.001 | 14
15 | 16-540-20 | Back filling sand:FM>.80 | cum | 1400.001 | 220.75 | 16-540-20 | 1400.001
16 | 40-520-20 |  | cum | 4000.001 | 4.3 | 40-520-20 | 4000.001
17 | 40-520-30 |  | cum | 4525.001 | 4.3 | 40-520-30 | 4525.001
18 | 40-150-50 |  | cum | 371.821 | 908 | 40-150-50 | 371.821
19 | 76-170 |  | kg | 161.491 | 246.95 | 76-170 | 161.491
20 | 72-540 |  | each |  | 3.166
21 | 40-270-10 |  | cum | 1395.003 | 24.52 | 40-270-10 | 1395.003
22 | 16-130 | Earth Work in Channel excavation | cum | 228.001 | 1442 | 16-130-10 | 228.001
23 | 16-400 |  | cum | 180.001 | 346.5 | 16-400 | 180.001
24 | 16-450 |  | cum | 180.001 | 1206.45 | 16-450 | 180.001
25 | 76-250-20 |  | each | 1174.191 | 1 | 76-630-10 | 1174.191
26 | 76-260-20 |  | each | 12923.011 | 1 | 76-260-20 | 12923.011
27 | 16-560-20 |  | cum | 860.141 | 141.85 | 16-560-20 | 860.141
28 | 16-550 |  | cum | 190.001 | 357.72 | 16-550 | 190.001
29 | 68-130 |  | cum | 92159.901 | 0.169 | 68-130 | 92159.901
30 | 48-100 | Fine dreasing and close turfing | Sqm | 32.971 | 1196 | 48-100 | 32.971
4060140.7246
[5 empty] | 40.6014 | 40-150-40 | 446.541
[6 empty] | 80-230-40 | 356.081
[6 empty] | 76-240-40 | 109392.431
[6 empty] | 76-190 | 93037.271
[6 empty] | 76-250-20 | 79418.421
[6 empty] | 76-260-10 | 10941.291
[6 empty] | 16-170 | 30.721
[6 empty] | 16-170 | 46.081
[6 empty] | 04-280 | 98.481
[6 empty] | 16-470 | 180.001
[6 empty] | 48-100 | 32.971

## Sheet1
1 | Approved Analysis Rate | Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200 sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge. | L.S | 1 | 967050.851 | Nine Lakh Sixty-Seven Thousand AND Fifty point Eight Five One | 967050.851 | Nine Lakh Sixty-Seven Thousand AND Fifty point Eight Five One
2 | Approved Analysis Rate | Approved Analysis Rate | Mobilize, strengthen required land based construction equipment such as excavator, dump truck, chain dozer, vibro-compactor, and plants such as generator for site electrification, digital camera for taking photographs and digital video camera for recording/Taking photograph all sequences of works etc for keeping records of the Works by providing following information including transfer to site, complete for the purposes stated in the Technical Specification and Contractor's Method Statement and as per direction of Engineer in charge. | L.S | 1 | 92026.551 | Ninety-Two Thousand AND Twenty-Six point Five Five One | 92026.551 | Ninety-Two Thousand AND Twenty-Six point Five Five One
3 | Approved Analysis Rate | Approved Analysis Rate | Provide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in charge. | Day | 120 | 2497.861 | Two Thousand Four Hundred and Ninety-Seven point Eight Six One | 299743.32 | Two Lakh Ninety-Nine Thousand Seven Hundred and Forty-Three point Three Two
4 | Approved Analysis Rate | Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 6 Nos. of tube well and sanitation facilities by installing 6 Nos. of sanitary latrines for usage of labours,officials and others for prevailing the hygenic and healthy environment at allover the working site As per direction of the Engineer in charge. | L.S | 1 | 111148.951 | One Lakh Eleven Thousand One Hundred and Forty-Eight point Nine Five One | 111148.951 | One Lakh Eleven Thousand One Hundred and Forty-Eight point Nine Five One
5 | Approved Analysis Rate | Approved Analysis Rate | Operate , maintain of plant and equipment such as generator for site electrification, for the purpose stated in the Technical Specification and in the Contractor's Method Statement and as per direction of Engineer in charge. | L.S | 1 | 110909.921 | One Lakh Ten Thousand Nine Hundred and Nine point Nine Two One | 110909.921 | One Lakh Ten Thousand Nine Hundred and Nine point Nine Two One
6 | Approved Analysis Rate | Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Specifications and Contractor's Method Statement and as per direction of Engineer in Charge | L.S | 1 | 112344.101 | One Lakh Twelve Thousand Three Hundred and Forty-Four point One Zero One | 112344.101 | One Lakh Twelve Thousand Three Hundred and Forty-Four point One Zero One
7 | Approved Analysis Rate | Approved Analysis Rate | Construction of Bill board at site with M.S. plates, flat bars, Tees etc of size 8'-0''x12'-0'' including fabricating, machining, cutting, bending, welding, forging, drilling, revetting, staging and fitting, fixing, local supply of labours including the cost of materials as specification and direction of Engineer in Charge. | L.S | 1 | 50000.001 | Fifty Thousand point Zero Zero One | 50000.001 | Fifty Thousand point Zero Zero One
8 | NSI | NSI | Part Time Employment of environmental inspector for Implementation and reporting on environmental management plan provision for first aid box and medical assistant as per specification and direction of engineer in charge. | L.S | 1 | 250000.001 | Two Lakh Fifty Thousand point Zero Zero One | 250000.001 | Two Lakh Fifty Thousand point Zero Zero One
9 | 04-120 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cm x 38cm x 75cm on cement concrete (1:2:4) base of size 50cm x 50cm x 7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement morter on top (1:2), with inscription of "BWDB" with 25cm of the pillar balow ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | each | 10 | 124.461 | One Hundred and Twenty-Four point Four Six One | 1244.61 | One Thousand Two Hundred and Forty-Four point Six One
10 | 04-180 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials form entire site and removing soil upto 15cm depth including uprooting stumps, jungle clearing, levelling dressing etc. complete as per direction of Engineer in charge. | sqm | 39750 | 38.131 | Thirty-Eight point One Three One | 1515707.25 | Fifteen Lakh Fifteen Thousand Seven Hundred and Seven point Two Five
11 | 04-620 | 04-620-20 | Filling of expansion joints upto a depth of 40mm with bitumen mixed with coarse sand (FM>=2.5) in concrete works including supply of all materials etc. complete as per specification and direction of Engineer in charge. 04-620-20: 20mm wid | m | 46 | 92.201 | Ninety-Two point Two Zero One | 4241.246 | Four Thousand Two Hundred and Forty-One point Two Four Six
12 | 12-100 | 12-100 | Installation of pizeometer including supply of 38mm G.I. pipe, brass strainer, socket, labour, by wash boring, lowering, fixing the elevation and providing cover on the top of the well etc. complete as per direction of Engineer in charge. | each | 16 | 3382.871 | Three Thousand Three Hundred and Eighty-Two point Eight Seven One | 54125.936 | Fifty-Four Thousand One Hundred and Twenty-Five point Nine Three Six
13 | 16-510 | 16-510-10 | Earth work in excavation of foundation trenches in all kinds of soils as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. 16-510-10: For moving spoil earth upto a distance of 100m from the centre of the pit. | Cum | 26490.65 | 341.371 | Three Hundred and Forty-One point Three Seven One | 9043139.681 | Ninety Lakh Forty-Three Thousand One Hundred and Thirty-Nine point Six Eight One
14 | 16-620 | 16-620-20 | Shoring for slope protection of foundation trench, canal, embankment, road, pond etc. as per design slopes, grades including removal of spoils to a safe distance as per direction of Engineer in charge. 16-620-20 : By bamboo post of 6.0m length, 60mm to 80mm dia, 20cm c/c driven 2.0m below ground, with drum sheet walling and average 70mm dia half split bamboo batten @ 2.0m c/c fixed with nails. | sqm | 1185.86 | 775.001 | Seven Hundred and Seventy-Five point Zero Zero One | 919042.686 | Nine Lakh Nineteen Thousand AND Forty-Two point Six Eight Six
15 | 12-310 | 12-310-20 | Bailing out of water with all leads and lifts by manual labour or pump, with all arrengements for protection of ring bund and side slopes of foundation pit against erosion or washout etc. complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge. by pump. | Cum | 220195.97 | 6.001 | Six point Zero Zero One | 1321396.016 | Thirteen Lakh Twenty-One Thousand Three Hundred and Ninety-Six point Zero One Six
16 | 44-240 | 44-240-30 | Supplying at site steel sheet piles of different sections including all taxes, freights, incidental charges etc. complete as per direction of Engineer in charge. 44-240-30 : U-shape, hot- rolled steel sheet pile width= 400 mm to 600 mm: height=> 100mm, Th.=> 10.5: wt. p;er sqm of pile wall of pile wall =>120 kg/m2: sectional modulus per one meter of pile wall width => 874 cm3/m | M. ton | 58.034 | 116000.001 | One Lakh Sixteen Thousand point Zero Zero One | 6731944.058 | Sixty-Seven Lakh Thirty-One Thousand Nine Hundred and Forty-Four point Zero Five Eight
17 | 44-320 | 44-320-10 | Cutting of steel sheet piles to design and length and shape as per requirement in design and drawing and as per direction of Engineer in charge. 44-320-10: Upto 10mm thick. | m | 261.95 | 45.611 | Forty-Five point Six One One | 11947.801 | Eleven Thousand Nine Hundred and Forty-Seven point Eight Zero One
18 | 12-300 | 12-300 | Construction of sump well with dug holes of size 1.80m x 2.0m, laying in position the perforated empty diesel/petrol drum sheet of 1.00m dia to a depth 1.5m having slot area of 1000 sq.cm/sqm, slot dia being 30mm each with supply of necessary shrouding materials comprising of 60% 40mm down graded khoa and 40% coarse sand of FM>=2.50 and placing those around and beneath the drum sheet having thickness of 40cm and 50cm respectively including necessary welding, fitting etc. complete as per direction of Engineer in charge. | each | 46 | 20828.401 | Twenty Thousand Eight Hundred and Twenty-Eight point Four Zero One | 958106.446 | Nine Lakh Fifty-Eight Thousand One Hundred and Six point Four Four Six
19 | 44-270 | 44-270-20 | Driving steel sheet piles of various sections and weights of any type of soil, by monkey hammer including handling and placing in position, staging and supplying of all equipments like monkey hammer, pully, rope, bamboo, bullah etc. including correcting leaning beyond tolerance & other defects and any other incidental cost etc. complete (measurement will be taken on projected width x height) as per direction of Engineer in charge. 44-270-20: U-type or any other type : Upto 4.50 m depth | Sqm | 423.15 | 1709.051 | One Thousand Seven Hundred and Nine point Zero Five One | 723184.931 | Seven Lakh Twenty-Three Thousand One Hundred and Eighty-Four point Nine Three One
20 | 72-180 | 72-180 | Provide 1 (one) coat of Zinc phosphate as primary coat and 2 (two) coat of coaltar epoxy coat over primary coat to steel surface with paint of approved colour etc. complete including the cost of all materials as per direction of Engineer in charge. | Sqm | 1607.97 | 249.101 | Two Hundred and Forty-Nine point One Zero One | 400546.935 | Four Lakh Five Hundred and Forty-Six point Nine Three Five
21 | 72-540 | 72-540 | Epoxy paint 2 coats of approved colour and specification over a priming coat to gate, hoisting device and embedded metal parts includingscraping out rust and old paint with chisel, scraper, steel wire brush & emery paper etc. complete in all respects including the cost of all materials as per direction of Engineer in charge. | Sqm | 100.066 | 428.821 | Four Hundred and Twenty-Eight point Eight Two One | 42910.402 | Forty-Two Thousand Nine Hundred and Ten point Four Zero Two
22 | 44-310 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge. | Sqm | 200.99 | 514.211 | Five Hundred and Fourteen point Two One One | 103351.269 | One Lakh Three Thousand Three Hundred and Fifty-One point Two Six Nine
23 | 44-220 | 44-220-10 | Supplying and laying single layer pholythene sheet in floor below cement concrete, RCC slab, on walls etc. complete in all respect as per direction of Engineer in charge. 44-220-10: Weighing minimum 1.0 kg. per 6.50 sqm. | Sqm | 1126.41 | 31.821 | Thirty-One point Eight Two One | 35843.493 | Thirty-Five Thousand Eight Hundred and Forty-Three point Four Nine Three
24 | 28-120 | 28-120-20 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-120-20: With 25mm down graded stone chips | Cum | 124.65 | 12907.661 | Twelve Thousand Nine Hundred and Seven point Six Six One | 1608939.944 | Sixteen Lakh Eight Thousand Nine Hundred and Thirty-Nine point Nine Four Four
25 | 28-100 | 28-100-20 | Cement concrete work in leanest mix. 1:4:8, with sand of FM>= 1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. 28-100-20: With 25mm down graded stone chips | Cum | 6.006 | 12479.851 | Twelve Thousand Four Hundred and Seventy-Nine point Eight Five One | 74953.985 | Seventy-Four Thousand Nine Hundred and Fifty-Three point Nine Eight Five
26 | 28-200 | 28-200-10 | Reinforced Cement Concrete Work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>= 2.0 to FM >= 2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: With stone chips. | Cum | 927.107 | 14581.841 | Fourteen Thousand Five Hundred and Eighty-One point Eight Four One | 13518926.864 | One Crore Thirty-Five Lakh Eighteen Thousand Nine Hundred and Twenty-Six point Eight Six Four
27 | 76-120 | 76-120-10 | M.S. Work for reinforcement with twisted M.S. bar, fy = 414 N/mm2, (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of twisted M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia. | Kg | 99169.67 | 102.441 | One Hundred and Two point Four Four One | 10159040.164 | One Crore One Lakh Fifty-Nine Thousand AND Forty point One Six Four
28(A) | 36-150 | 36-150-60 | Form work for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mm x 40mm x 6mm M.S. Angle frame and 25mm x 6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per designed shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. | Sqm | 819.929 | 924.951 | Nine Hundred and Twenty-Four point Nine Five One | 758394.148 | Seven Lakh Fifty-Eight Thousand Three Hundred and Ninety-Four point One Four Eight
A) 36-150-60: Footing, footing beams, girder beams, foundation slab with 60-80mm diabarrack bamboo props.
28(B) | 36-150 | 36-150-10 | B) 36-150-10 : Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | Sqm | 2404.25 | 970.001 | Nine Hundred and Seventy point Zero Zero One | 2332124.904 | Twenty-Three Lakh Thirty-Two Thousand One Hundred and Twenty-Four point Nine Zero Four
28(C) | 36-150 | 36-150-20 | C) 36-150-20 : Deck slab, operating deck slab, top slab of barrel upto 3.5m of height with 60-80mm dia barrack bamboo props. | Sqm | 56.72 | 970.001 | Nine Hundred and Seventy point Zero Zero One | 55018.457 | Fifty-Five Thousand AND Eighteen point Four Five Seven
29 | 76-630 | 76-630-10 | Supply and fitting and fixing 23cm wide P.V.C water stops having minimum strength of 13.80N/mm2 at 225% elongation and of approved quality in antraction and expansion joints with necessary arrangements for modification in shuttering and keeping the water stop in position etc. complete as per design, specification anddirection of Engineer in charge. 76-630-10: bulb type. | m | 28.4 | 1174.191 | One Thousand One Hundred and Seventy-Four point One Nine One | 33347.024 | Thirty-Three Thousand Three Hundred and Forty-Seven point Zero Two Four
30 | 16-540 | 16-540-20 | Supplying and filling sand in foundation of hydraulic structures, buildings and in protective works with selected sand, in 150mm thick layer, including levelling, dressing, ramming, watering etc. complete (compacted to 50% relative density by manual laqbour using mallet/vibro compactor) as per direction of Engineer in charge. 16-540-20: Sand of FM>= 1.50 | Cum | 2227.63 | 1400.001 | One Thousand Four Hundred point Zero Zero One | 3118684.228 | Thirty-One Lakh Eighteen Thousand Six Hundred and Eighty-Four point Two Two Eight
31(A) | 40-520 | 40-520-20 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge. A) 40-520-20: Well graded between 40mm to 20mm size. | Cum | 183.679 | 4000.001 | Four Thousand point Zero Zero One | 734716.184 | Seven Lakh Thirty-Four Thousand Seven Hundred and Sixteen point One Eight Four
31(B) | 40-520-30 | 40-520-30 | B) 40-520-30 : Well graded between 20mm to 5mm size. (Combination of sub-item 10 and 30 or 20 and 30 shall be used) | Cum | 185.947 | 4525.001 | Four Thousand Five Hundred and Twenty-Five point Zero Zero One | 841410.361 | Eight Lakh Forty-One Thousand Four Hundred and Ten point Three Six One
32 | 40-500 | 40-500-20 | "Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/ m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)= 2 x 10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment's etc. complete as per direction of Engineer in charge. | Sqm | 2443.296 | 217.701 | Two Hundred and Seventeen point Seven Zero One | 531907.982 | Five Lakh Thirty-One Thousand Nine Hundred and Seven point Nine Eight Two
33 | 40-550 | 40-550-10 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550-10 : FM : 2.0 to 2.5 | Cum | 17.989 | 2177.011 | Two Thousand One Hundred and Seventy-Seven point Zero One One | 39162.251 | Thirty-Nine Thousand One Hundred and Sixty-Two point Two Five One
34(A) | 40-150 | 40-150-50 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>= 1.5) and shingles (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. (A) 40-150-50 : block size 30cm x 30cm x 30cm | each | 22436 | 371.821 | Three Hundred and Seventy-One point Eight Two One | 8342175.956 | Eighty-Three Lakh Forty-Two Thousand One Hundred and Seventy-Five point Nine Five Six
34(B) | 40-150 | 40-150-40 | B) 40-150-40 : block size 40cm x 40cm x 40cm | each | 10469 | 446.541 | Four Hundred and Forty-Six point Five Four One | 4674837.729 | Forty-Six Lakh Seventy-Four Thousand Eight Hundred and Thirty-Seven point Seven Two Nine
35 | 40-270 | 40-270-10 | Labour charge for protective works in laying C.C. blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of the Engineer in charge. 40-270-10 : Within 200m | Cum | 940.8 | 1395.003 | One Thousand Three Hundred and Ninety-Five point Zero Zero Three | 1312418.822 | Thirteen Lakh Twelve Thousand Four Hundred and Eighteen point Eight Two Two
36 | 76-170 | 76-170 | M.S. Work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cutting, bending, welding, forging, drilling, revetting, embedding anchor bars, staging and fitting, fixing, local handling etc. complete with energy consumption and supply of labours including the cost of materials as per design, specification and direction of Engineer in charge. | Kg | 3231.16 | 161.491 | One Hundred and Sixty-One point Four Nine One | 521803.26 | Five Lakh Twenty-One Thousand Eight Hundred and Three point Two Six
37 | 80-230 | 80-230-40 | Supplying, laying, fitting and fixing of different dia G.I. pipes with all special fittings, such as bends, elbows, sockets, tees, unions, jam nuts etc. including cutting foundation trenches upto required depth where necessary and filling the same with earth duly compacted, making holes in floors and walls and clips, including cutting threads, making necessary connection etc. all complete including the cost of all materials as per direction of Engineer in charge. 80-230-40 : 40 mm dia G.I. pipe line. | m | 43.61 | 356.081 | Three Hundred and Fifty-Six point Zero Eight One | 15528.692 | Fifteen Thousand Five Hundred and Twenty-Eight point Six Nine Two
38 | 76-240 | 76-240-40 | Manufacturing, supplying, Installation and fitting, fixing the vertical steel lift gate/flap gate as per design and specification, including fabricating, rivetting, welding, fixing rubber seal, providing required nuts and bolts including the cost of all materials etc. complete with a prime coat of redoxide where necessary as per direction of Engineer in charge. 76-240-40 : Size 1.95m x 1.65m (Applicable only for size not specified and smaller than size mentioned in Item code 76-240 & 76-250) | each | 2 | 109392.431 | One Lakh Nine Thousand Three Hundred and Ninety-Two point Four Three One | 218784.862 | Two Lakh Eighteen Thousand Seven Hundred and Eighty-Four point Eight Six Two
39 | 76-260 | 76-260-20 | Labour charge for fitting and fixing of M.S. vertical lift gate/flap gate shutters of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/sluice and mending the damages with CC (1:2:4), removing the spoils etc.complete including the cost of all materials as per direction of Engineer in charge. 76-260-20 : Size 1.95m x 1.35m or 1.95m x 1.65m | each | 2 | 12923.011 | Twelve Thousand Nine Hundred and Twenty-Three point Zero One One | 25846.022 | Twenty-Five Thousand Eight Hundred and Forty-Six point Zero Two Two
40 | 76-190 | 76-190 | Manufacturing, supplying and Installation of Padestal type lifting device for slide gate with 63mm dia threaded steel shaft, 146mm outer dia bronze nut, thrust bearing, steel bevel gear etc. as per approved design including supply of all components, labours with a prime coat of redoxide where necessary etc. complete including the cost of all materials as per specification and direction of Engineer in charge. | each | 2 | 93037.271 | Ninety-Three Thousand AND Thirty-Seven point Two Seven One | 186074.542 | One Lakh Eighty-Six Thousand AND Seventy-Four point Five Four Two
41 | 76-250 | 76-250-20 | "Manufacturing & Supplying of M.S. Flap Gate shutter of 8mm thick M.S. skin plate and stiffener with minimum 75mmx75mm x10mmM.S. angle as frame, horizontal & vertical beams, 100mmx 45mmx16mm P-type rubber seal, fixed with 10mm dia x 63.5mm M.S. counter sink and hax. nuts & bolts and 40mm x10mm M.S. strip as clamp drilled spaces @ 150mm c/c hinge assy with gateand wall bracket, link arm of 19mm thick M.S. plate, 4 nos 25mm dia x 150mm stainless steel hinge pin with proper thread, nut, cotter pin and washer as per approved design including the cost of all materials of proper grade & brand new with a prime coat of redoxide wherenecessary as per specification and direction of Engineer in charge. | each | 4 | 79418.421 | Seventy-Nine Thousand Four Hundred and Eighteen point Four Two One | 317673.684 | Three Lakh Seventeen Thousand Six Hundred and Seventy-Three point Six Eight Four
42 | 76-260 | 76-260-10 | "Labour charge for fitting and fixing of M.S. vertical lift gate/ flap gate shutters of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/sluice andmending the damages with CC (1:2:4), removing the spoils etc. complete including the cost of all materials as per direction of Engineer in charge. | each | 4 | 10941.291 | Ten Thousand Nine Hundred and Forty-One point Two Nine One | 43765.164 | Forty-Three Thousand Seven Hundred and Sixty-Five point One Six Four
43 | 16-130 | 16-130-10 | Earth work by manual labour in resectioning of embankment/ canal bank/ river slopes/road/compound etc. manually compacted by 7.0 kg iron rammer to avoid any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceding 150mm thickness with clod breaking to a maximum size of 100mm, removing roots & stumps of trees of girth upto 200mm from the ground, benching the side slopes, stripping/ploughing the base of embankment and borrowpit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of the crest (where necessary) etc. complete as per direction of Engineer in charge. 16-130-10 : .00m to 3.00m height. | Cum | 31597.52 | 228.001 | Two Hundred and Twenty-Eight point Zero Zero One | 7204266.158 | Seventy-Two Lakh Four Thousand Two Hundred and Sixty-Six point One Five Eight
44 | 16-400 | 16-400 | Earth work by manual labour in all kinds of soil in excavation or reexcavation of channels with the initial lead of 30m and lift of 1.5m including levelling, dressing and throwing the spoils to profile with breaking clods, rough dressing, clearing jungles including cutting trees upto 200mm girth, dug bailing etc. complete as per direction of Engineer in charge. | Cum | 26163.3 | 180.001 | One Hundred and Eighty point Zero Zero One | 4709420.163 | Forty-Seven Lakh Nine Thousand Four Hundred and Twenty point One Six Three
45(A) | 16-170 | 16-170 | Extra rate for every additional lift of 1.0m or part thereof beyond the initial lift of 1.5m (30cm negleted) for all kinds of earth work. A) 2 nos. lifts = 2x15.36 = 30.72 | Pltcum | 5032.75 | 30.721 | Thirty point Seven Two One | 154611.113 | One Lakh Fifty-Four Thousand Six Hundred and Eleven point One One Three
45(B) | 16-170 | 16-170 | B) 3 nos. lifts = 3x15.36 = 46.08 | Pltcum | 3637.37 | 46.081 | Forty-Six point Zero Eight One | 167613.647 | One Lakh Sixty-Seven Thousand Six Hundred and Thirteen point Six Four Seven
46 | 16-450 | 16-450 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | Cum | 6522.189 | 180.001 | One Hundred and Eighty point Zero Zero One | 1174000.542 | Eleven Lakh Seventy-Four Thousand point Five Four Two
47 | 04-280 | 04-280 | Constructing at site, cement mortar gauge on masonry wall, including engraving in meter, decimeter & centimeter, painting and figuring with black and red water proof paint, etc. complete as per direction of Engineer in charge. | m | 20 | 98.481 | Ninety-Eight point Four Eight One | 1969.62 | One Thousand Nine Hundred and Sixty-Nine point Six Two
48 | 16-560 | 16-560-20 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. 16-560-20: Sand of FM>= 0.80 | Cum | 4502.31 | 860.141 | Eight Hundred and Sixty point One Four One | 3872621.426 | Thirty-Eight Lakh Seventy-Two Thousand Six Hundred and Twenty-One point Four Two Six
49 | 16-550 | 16-550 | Back filling in hydraulic structures and slope building in protective works including all leads and lifts with selected local soil in layer of 150mm including watering, ramming etc. complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in charge. | Cum | 4896.18 | 190.001 | One Hundred and Ninety point Zero Zero One | 930279.096 | Nine Lakh Thirty Thousand Two Hundred and Seventy-Nine point Zero Nine Six
50 | 16-470 | 16-470 | Earth work by manual labour in all kinds of soil in removing the cross bundh/ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimum 15m apart from the bank) as per direction of Engineer in charge. | Cum | 3763.67 | 180.001 | One Hundred and Eighty point Zero Zero One | 677464.364 | Six Lakh Seventy-Seven Thousand Four Hundred and Sixty-Four point Three Six Four
51 | 68-130 | 68-130 | Supplying pressure treated wooden fall boards/stop logs of different size (not less than 15cm in depth) of Sal, Sundari, Garjan, Shishu or equivalant for regulator/sluices, including fixing in position with eye hook etc. complete as per direction of Engineer in charge. | Cum | 5.262 | 92159.901 | Ninety-Two Thousand One Hundred and Fifty-Nine point Nine Zero One | 484945.399 | Four Lakh Eighty-Four Thousand Nine Hundred and Forty-Five point Three Nine Nine
52 | 48-100 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurment will be given on well grown grass only), as per direction of Engineer in charge. | Sqm | 8344 | 32.971 | Thirty-Two point Nine Seven One | 275110.024 | Two Lakh Seventy-Five Thousand One Hundred and Ten point Zero Two Four

## Sheet2
Construction of A 1- vent 1.80 m x1.50 m Phuleshwari Regulator at km 8.241 no B 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 1 no C 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 no. & D 4.0 m width Chonati Causeway 1 no. E R.C.C Box Drainage Outlet 900mm x 900mm 1 no of Sunair Haor in connection with Haor Flood Management & Livlihood Improvement Project under Kishoregonj WD. Division BWDB Kishoregonj during the financial year 2019-20.Contract Package no.BWDB/Kish/HFMLIP/ PW-27