## Projected_Cost_OF_OnHold_Work
Projected Cost of Stopped Works At Kishoregonj WD Division
Package Name | Component | Unit | Qnty | Tendered Cost | Remarks | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code | Billed Amount | Current Status | Remaining Bill
PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 1 | 45 |  | KISH/PW-01 | Rehab | 2 |  | R-1 | KISH | 0 | P | 45
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 1.22 | 48.08 |  | KISH/PW-01 | Rehab | 8 | 304227.48 | R-1 | KISH | 0 | P | 48.08
PW-01 4 Nos. Rehabilitation Haor | Re-sectioning of Full Embankment | Km | 0 | 0 |  | KISH/PW-01 | Rehab | 9 |  | R-1 | KISH | 0 | P | 0
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 2.151 | 84.76 |  | KISH/PW-01 | Rehab | 8 | 304227.48 | R-2 | KISH | 0 | P | 84.76
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 8.175 | 322.16 |  | KISH/PW-01 | Rehab | 8 | 304227.48 | R-3 | KISH | 0 | P | 322.16
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 |  | KISH/PW-02 | New | 3 |  | N-1 | KISH | 103.45 | P | 20
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | Km | 11.095 | 211.74 |  | KISH/PW-02 | New | 7 | 211770.02 | N-1 | KISH | 196.26 | P | 15.48
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | Km | 0.315 | 14.81 |  | KISH/PW-02 | New | 11 | 2953 | N-1 | KISH | 11.01 | P | 3.8
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 |  | KISH/PW-03 | New | 3 |  | N-2 | KISH | 149.3 | P | 6.21
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | Km | 6.471 | 256.87 |  | KISH/PW-04 | New | 11 | 50421.04 | N-2 | KISH | 246.65 | P | 10.22
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 |  | KISH/PW-05 | New | 3 |  | N-2 | KISH | 141.59 | P | 51.9
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 232.99 |  | KISH/PW-06 | New | 3 |  | N-2 | KISH | 206.98 | P | 26.01
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | Km | 25.7 | 854.17 |  | KISH/PW-07 | New | 7 | 945139.04 | N-3 | KISH | 514.22 | P | 339.95
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | Km | 0.8 | 91 |  | KISH/PW-07 | New | 11 | 12696 | N-3 | KISH | 0 | P | 91
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | Km | 10.86 | 557.63 |  | KISH/PW-11 | New | 11 | 109155.3 | N-4 | KISH | 320.79 | P | 236.84
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 |  | KISH/PW-12 | New | 3 |  | N-4 | KISH | 181.28 | P | 46.21
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 |  | KISH/PW-12 | New | 3 |  | N-4 | KISH | 241.72 | P | 61.61
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 246.15 |  | KISH/PW-13 | New | 3 |  | N-5 | KISH | 215.59 | P | 30.56
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 180.96 |  | KISH/PW-13 | New | 3 |  | N-5 | KISH | 158.49 | P | 22.47
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 176.58 |  | KISH/PW-14 | New | 3 |  | N-5 | KISH | 164.5 | P | 12.08
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-14 | New | 3 |  | N-5 | KISH | 0 | P | 0
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 16.9 | 680.42 |  | KISH/PW-14 | New | 11 | 194853 | N-5 | KISH | 516.29 | P | 164.13
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of 6.00 m causeway | nos. | 1 | 166.9 | Regulator c onverted by 6.00 m causeway | KISH/PW-15 | New | 5 |  | N-5 | KISH | 0 | P | 166.9
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 9 | 616.92 |  | KISH/PW-15 | New | 11 | 133316.13 | N-5 | KISH | 333.94 | P | 282.98
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 |  | KISH/PW-16 | New | 3 |  | N-5 | KISH | 323.54 | P | 80.96
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 600 |  | KISH/PW-17 | New | 3 |  | N-5 | KISH | 403.5 | P | 196.5
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 |  | KISH/PW-17 | New | 3 |  | N-5 | KISH | 0 | P | 115.24
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 13.17 | 550.04 |  | KISH/PW-17 | New | 11 | 202851.03 | N-5 | KISH | 420.64 | P | 129.4
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 1 | 300 |  | KISH/PW-18 | New | 5 |  | N-5 | KISH | 182 | p | 118
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.m width Causeway | nos. | 1 | 274.54 |  | KISH/PW-18 | New | 5 |  | N-5 | KISH | 166.64 | p | 107.9
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 |  | KISH/PW-18 | New | 7 | 453822.6 | N-5 | KISH | 361.81 | P | 253.79
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 160 |  | KISH/PW-21 | New | 3 |  | N-7 | KISH | 0 | P | 160
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | nos. | 5 | 125 |  | KISH/PW-21 | New | 12 |  | N-9 | KISH | 0 | P | 125
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | nos. | 4 | 41.87 |  | KISH/PW-23 | New | 1 |  | N-7 | KISH | 0 | P | 41.87
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | nos. | 1 | 39.54 |  | KISH/PW-23 | New | 4 |  | N-7 | KISH | 0 | P | 39.54
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 |  | KISH/PW-23 | New | 7 | 23149.28 | N-7 | KISH | 0 | P | 32.63
BWDB/Kish/HFMLIP/PW-24 Dakshiner Haor | Const. of Submersible Embankment | Km | 19.843 | 918.58 |  | KISH/PW-24 | New | 11 | 214238.2 | N-8 | KISH | 787.65 | P | 130.93
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | nos. | 1 | 43.25 |  | KISH/PW-25 | New | 4 |  | N-8 | KISH | 0 | P | 43.25
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 |  | KISH/PW-25 | New | 5 |  | N-8 | KISH | 0 | P | 450.435
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Re-excavation of Khal (New) | Km | 22.7 | 486.56 |  | KISH/PW-26 | New | 7 | 468821.04 | N-9 | KISH | 216.24 | P | 270.32
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Const. of Submersible Embankment | Km | 0.54 | 22.72 |  | KISH/PW-26 | New | 11 | 11787.77 | N-9 | KISH | 0 | P | 22.72
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 314 |  | KISH/PW-27 | New | 3 |  | N-9 | KISH | 0 | P | 314
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-27 | New | 3 |  | N-9 | KISH | 0 | P | 0
BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | nos. | 4 | 195 |  | KISH/PW-27 | New | 4 |  | N-9 | KISH | 0 | P | 195
BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | nos. | 1 | 294 |  | KISH/PW-27 | New | 5 |  | N-9 | KISH | 0 | P | 294
BWDB/Kish/HFMLIP/PW-27 | Const. of 4.0 m width Causeway | nos. | 1 | 160 |  | KISH/PW-27 | New | 5 |  | N-9 | KISH | 0 | P | 160
BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 60 | 1298.8 |  | KISH/PW-28 | New | 15 |  | N-2 | KISH | 116.5 | P | 1182.3
Total |  |  |  | 13232.715 | [7 empty] | 6680.58 |  | 6552.135

## Projected_Cost_OF_Ongoing_Work
Projected Cost of Running Works At Kishoregonj WD Division
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | Remarks | Package | Haor Type | STC Code | Earth Volume | Hoar Code | District Code | Billed Amount | Current Status | Remaining Bill
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | Km | 10.383 | 533.94 |  | KISH/PW-03 | New | 11 | 109104.8 | N-2 | KISH | 432.69 | OG | 101.25
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 |  | KISH/PW-04 | New | 3 |  | N-2 | KISH | 179.54 | OG | 18.46
4 | 4b | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 |  | KISH/PW-04 | New | 3 |  | N-2 | KISH | 231.82 | OG | 23.83
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | Km | 12.214 | 577.36 |  | KISH/PW-05 | New | 11 | 98770 | N-2 | KISH | 349.59 | OG | 227.77
6 | 6a | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | Km | 20 | 557.44 |  | KISH/PW-06 | New | 7 | 577707.02 | N-2 | KISH | 512.85 | OG | 44.59
9 | 9a | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 193.13 | Regulators are converted to causeway. | KISH/PW-09 | New | 5 |  | N-3 | KISH | 56.15 | OG | 136.98
9 | 9b | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 2 | 463.51 |  | KISH/PW-09 | New | 5 |  | N-3 | KISH | 134.76 | OG | 328.75
9 | 9c | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 77.25 |  | KISH/PW-09 | New | 4 |  | N-3 | KISH | 22.46 | OG | 54.79
10 | 10a | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 114 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3 |  | N-4 | KISH | 14.22 | OG | 99.78
10 | 10b | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 1 | 152 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5 |  | N-4 | KISH | 18.96 | OG | 133.04
10 | 10c | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | Km | 11.98 | 617.94 | 0 | KISH/PW-10 | New | 11 | 121988 | N-4 | KISH | 211.56 | OG | 406.38
11 | 11a | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 |  | KISH/PW-11 | New | 3 |  | N-4 | KISH | 134.1 | OG | 140.4
12 | 12a | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | Km | 10.757 | 422.65 |  | KISH/PW-12 | New | 7 | 371757.99 | N-4 | KISH | 104.15 | OG | 318.5
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 10 | 576.67 |  | KISH/PW-13 | New | 11 | 215922 | N-5 | KISH | 86.55 | OG | 490.12
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | Km | 14.12 | 511.3 |  | KISH/PW-16 | New | 11 | 143610.85 | N-5 | KISH | 248.13 | OG | 263.17
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 25 | 274.46 |  | KISH/PW-17 | New | 1 |  | N-5 | KISH | 117.08 | OG | 157.38
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 5 | 177.44 |  | KISH/PW-17 | New | 4 |  | N-5 | KISH | 82.41 | OG | 95.03
19 | 19a | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 1065 |  | KISH/PW-19 | New | 7 | 577753.68 | N-5 | KISH | 296.36 | OG | 768.64
20 | 20a | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 15 | 118.56 |  | KISH/PW-20 | New | 1 |  | N-2 | KISH | 4.91 | OG | 113.65
20 | 20b | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 |  | KISH/PW-20 | New | 4 |  | N-2 | KISH | 32.21 | OG | 10.39
20 | 20c | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 |  | KISH/PW-20 | New | 5 |  | N-2 | KISH | 93.225 | OG | 84.775
20 | 20d | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 7 | 55.33 |  | KISH/PW-20 | New | 1 |  | N-3 | KISH |  | OG | 55.33
20 | 20e | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 |  | KISH/PW-20 | New | 4 |  | N-3 | KISH | 32.21 | OG | 10.39
20 | 20f | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 2 | 356 |  | KISH/PW-20 | New | 5 |  | N-3 | KISH | 186.46 | OG | 169.54
20 | 20g | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 14 | 110.66 |  | KISH/PW-20 | New | 1 |  | N-4 | KISH |  | OG | 110.66
20 | 20h | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 2 | 85.22 |  | KISH/PW-20 | New | 4 |  | N-4 | KISH | 64.22 | OG | 21
20 | 20i | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 |  | KISH/PW-20 | New | 5 |  | N-4 | KISH | 93.225 | OG | 84.775
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 |  | KISH/PW-21 | New | 3 |  | N-6 | KISH | 0 | OG | 225
21 | 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 10 | 478.31 |  | KISH/PW-21 | New | 11 | 121065.93 | N-8 | KISH | 0 | OG | 478.31
22 | 22a | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | nos. | 6 | 72.88 |  | KISH/PW-22 | New | 1 |  | N-10 | KISH | 0 | OG | 72.88
22 | 22b | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | nos. | 3 | 116.03 |  | KISH/PW-22 | New | 4 |  | N-11 | KISH | 0 | OG | 116.03
22 | 22c | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 |  | KISH/PW-22 | New | 5 |  | N-12 | KISH | 0 | OG | 194.91
22 | 22d | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 |  | KISH/PW-22 | New | 7 | 146641.43 | N-13 | KISH | 0 | OG | 209.47
22 | 22e | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 11 | 252.89 |  | KISH/PW-22 | New | 11 | 91984.7 | N-14 | KISH | 0 | OG | 252.89
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 298.3 |  |  |  | 3 |  |  |  | 0 | OG | 298.3
| 23b | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 230.33 |  | KISH/PW-23 | New | 3 |  | N-7 | KISH | 0 | OG | 230.33
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 4.51 | 105.29 |  | KISH/PW-23 | New | 11 | 51688.691 | N-7 | KISH | 0 | OG | 105.29
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | nos. | 15 | 124.68 |  | KISH/PW-25 | New | 1 |  | N-8 | KISH | 0 | OG | 124.68
25 | 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 |  | KISH/PW-25 | New | 3 |  | N-8 | KISH | 304.53 | OG | 92.43
25 | 25c | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 |  | KISH/PW-25 | New | 5 |  | N-8 | KISH | 23.35 | OG | 126.795
25 | 25d | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 |  | KISH/PW-25 | New | 7 | 342244.7 | N-8 | KISH | 190.84 | OG | 234.14
Sub-Total | [5 empty] | 11489.385 | [7 empty] | 4258.56 |  | 7230.825
1 | 1a | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 1 | 45 |  | KISH/PW-01 |  | 2 |  |  |  | 0 | P | 45
1 | 1b | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 1.22 | 48.08 |  | KISH/PW-01 |  | 8 |  |  |  | 0 | P | 48.08
1 | 1c | PW-01 4 Nos. Rehabilitation Haor | Re-sectioning of Full Embankment | Km | 0 | 0 |  | KISH/PW-01 |  | 9 |  |  |  | 0 | P | 0
1 | 1d | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 2.151 | 84.76 |  | KISH/PW-01 |  | 8 |  |  |  | 0 | P | 84.76
1 | 1e | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 8.175 | 322.16 |  | KISH/PW-01 |  | 8 |  |  |  | 0 | P | 322.16
2 | 2a | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 |  | KISH/PW-02 |  | 3 |  |  |  | 103.45 | P | 20
2 | 2b | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | Km | 11.095 | 211.74 |  | KISH/PW-02 |  | 7 |  |  |  | 196.26 | P | 15.48
2 | 2c | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | Km | 0.315 | 14.81 |  | KISH/PW-02 |  | 11 |  |  |  | 11.01 | P | 3.8
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 |  | KISH/PW-03 |  | 3 |  |  |  | 149.3 | P | 6.21
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | Km | 6.471 | 256.87 |  | KISH/PW-04 |  | 11 |  |  |  | 246.65 | P | 10.22
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 |  | KISH/PW-05 |  | 3 |  |  |  | 141.59 | P | 51.9
6 | 6a | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 232.99 |  | KISH/PW-06 |  | 3 |  |  |  | 206.98 | P | 26.01
7 | 7a | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | Km | 25.7 | 854.17 |  | KISH/PW-07 |  | 7 |  |  |  | 514.22 | P | 339.95
7 | 7b | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | Km | 0.8 | 91 |  | KISH/PW-07 |  | 11 |  |  |  | 0 | P | 91
11 | 7c | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | Km | 10.86 | 557.63 |  | KISH/PW-11 |  | 11 |  |  |  | 320.79 | P | 236.84
12 | 12a | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 |  | KISH/PW-12 |  | 3 |  |  |  | 181.28 | P | 46.21
12 | 12b | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 |  | KISH/PW-12 |  | 3 |  |  |  | 241.72 | P | 61.61
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 246.15 |  | KISH/PW-13 |  | 3 |  |  |  | 215.59 | P | 30.56
13 | 13b | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 180.96 |  | KISH/PW-13 |  | 3 |  |  |  | 158.49 | P | 22.47
14 | 14a | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 176.58 |  | KISH/PW-14 |  | 3 |  |  |  | 164.5 | P | 12.08
14 | 14b | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-14 |  | 3 |  |  |  | 0 | P | 0
14 | 14c | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 16.9 | 680.42 |  | KISH/PW-14 |  | 11 |  |  |  | 516.29 | P | 164.13
15 | 15a | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of 6.00 m causeway | nos. | 1 | 166.9 |  | KISH/PW-15 |  | 5 |  |  |  | 0 | P | 166.9
15 | 15b | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 9 | 616.92 |  | KISH/PW-15 |  | 11 |  |  |  | 333.94 | P | 282.98
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 |  | KISH/PW-16 |  | 3 |  |  |  | 323.54 | P | 80.96
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 600 |  | KISH/PW-17 |  | 3 |  |  |  | 403.5 | P | 196.5
17 | 17b | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 |  | KISH/PW-17 |  | 3 |  |  |  | 0 | P | 115.24
17 | 17c | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 13.17 | 550.04 |  | KISH/PW-17 |  | 11 |  |  |  | 420.64 | P | 129.4
18 | 18a | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 1 | 300 |  | KISH/PW-18 |  | 5 |  |  |  | 182 | p | 118
18 | 18b | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.m width Causeway | nos. | 1 | 274.54 |  | KISH/PW-18 |  | 5 |  |  |  | 166.64 | p | 107.9
18 | 18c | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 |  | KISH/PW-18 |  | 7 |  |  |  | 361.81 | P | 253.79
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 160 |  | KISH/PW-21 |  | 3 |  |  |  | 0 | P | 160
21 | 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | nos. | 5 | 125 |  | KISH/PW-21 |  | 12 |  |  |  | 0 | P | 125
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | nos. | 4 | 41.87 |  | KISH/PW-23 |  | 1 |  |  |  | 0 | P | 41.87
23 | 23b | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | nos. | 1 | 39.54 |  | KISH/PW-23 |  | 4 |  |  |  | 0 | P | 39.54
23 | 23c | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 |  | KISH/PW-23 |  | 7 |  |  |  | 0 | P | 32.63
24 | 24a | BWDB/Kish/HFMLIP/PW-24 Dakshiner Haor | Const. of Submersible Embankment | Km | 19.843 | 918.58 |  | KISH/PW-24 |  | 11 |  |  |  | 787.65 | P | 130.93
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | nos. | 1 | 43.25 |  | KISH/PW-25 |  | 4 |  |  |  | 0 | P | 43.25
25 | 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 |  | KISH/PW-25 |  | 5 |  |  |  | 0 | P | 450.435
26 | 26a | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Re-excavation of Khal (New) | Km | 22.7 | 486.56 |  | KISH/PW-26 |  | 7 |  |  |  | 216.24 | P | 270.32
26 | 26b | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Const. of Submersible Embankment | Km | 0.54 | 22.72 |  | KISH/PW-26 |  | 11 |  |  |  | 0 | P | 22.72
27 | 27a | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 314 |  | KISH/PW-27 |  | 3 |  |  |  | 0 | P | 314
27 | 27b | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-27 |  | 3 |  |  |  | 0 | P | 0
27 | 27c | BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | nos. | 4 | 195 |  | KISH/PW-27 |  | 4 |  |  |  | 0 | P | 195
27 | 27d | BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | nos. | 1 | 294 |  | KISH/PW-27 |  | 5 |  |  |  | 0 | P | 294
27 | 27e | BWDB/Kish/HFMLIP/PW-27 | Const. of 4.0 m width Causeway | nos. | 1 | 160 |  | KISH/PW-27 |  | 5 |  |  |  | 0 | P | 160
28 | 28a | BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 60 | 1298.8 |  | KISH/PW-28 |  | 15 |  |  |  | 116.5 | P | 1182.3
Sub-Total | [5 empty] | 13232.715 | [7 empty] | 6680.58 |  | 6552.135
Grand-Total | [5 empty] | 24722.1 | [7 empty] | 10939.14 |  | 13782.96

## Status
Projected Cost of Running Works At Kishoregonj WD Division
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | Remarks | Package | Haor Type | STC Code | Earth Volume | Hoar Code | District Code | Billed Amount | Current Status | Remaining Bill
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | Km | 10.383 | 533.94 |  | KISH/PW-03 | New | 11 | 109104.8 | N-2 | KISH | 432.69 | OG | 101.25
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 |  | KISH/PW-04 | New | 3 |  | N-2 | KISH | 179.54 | OG | 18.46
| 4b | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 |  | KISH/PW-04 | New | 3 |  | N-2 | KISH | 231.82 | OG | 23.83
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | Km | 12.214 | 577.36 |  | KISH/PW-05 | New | 11 | 98770 | N-2 | KISH | 349.59 | OG | 227.77
6 | 6a | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | Km | 20 | 557.44 |  | KISH/PW-06 | New | 7 | 577707.02 | N-2 | KISH | 512.85 | OG | 44.59
9 | 9a | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 193.13 | Regulators are converted to causeway. | KISH/PW-09 | New | 5 |  | N-3 | KISH | 56.15 | OG | 136.98
| 9b | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 2 | 463.51 |  | KISH/PW-09 | New | 5 |  | N-3 | KISH | 134.76 | OG | 328.75
| 9c | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 77.25 |  | KISH/PW-09 | New | 4 |  | N-3 | KISH | 22.46 | OG | 54.79
10 | 10a | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 114 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3 |  | N-4 | KISH | 14.22 | OG | 99.78
| 10b | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 1 | 152 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5 |  | N-4 | KISH | 18.96 | OG | 133.04
| 10c | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | Km | 11.98 | 617.94 | 0 | KISH/PW-10 | New | 11 | 121988 | N-4 | KISH | 211.56 | OG | 406.38
11 | 11a | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 |  | KISH/PW-11 | New | 3 |  | N-4 | KISH | 134.1 | OG | 140.4
12 | 12a | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | Km | 10.757 | 422.65 |  | KISH/PW-12 | New | 7 | 371757.99 | N-4 | KISH | 104.15 | OG | 318.5
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 10 | 576.67 |  | KISH/PW-13 | New | 11 | 215922 | N-5 | KISH | 86.55 | OG | 490.12
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | Km | 14.12 | 511.3 |  | KISH/PW-16 | New | 11 | 143610.85 | N-5 | KISH | 248.13 | OG | 263.17
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 25 | 274.46 |  | KISH/PW-17 | New | 1 |  | N-5 | KISH | 117.08 | OG | 157.38
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 5 | 177.44 |  | KISH/PW-17 | New | 4 |  | N-5 | KISH | 82.41 | OG | 95.03
19 | 19a | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 1065 |  | KISH/PW-19 | New | 7 | 577753.68 | N-5 | KISH | 296.36 | OG | 768.64
20 | 20a | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 15 | 118.56 |  | KISH/PW-20 | New | 1 |  | N-2 | KISH | 4.91 | OG | 113.65
| 20b | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 |  | KISH/PW-20 | New | 4 |  | N-2 | KISH | 32.21 | OG | 10.39
| 20c | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 |  | KISH/PW-20 | New | 5 |  | N-2 | KISH | 93.225 | OG | 84.775
| 20d | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 7 | 55.33 |  | KISH/PW-20 | New | 1 |  | N-3 | KISH |  | OG | 55.33
| 20e | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 |  | KISH/PW-20 | New | 4 |  | N-3 | KISH | 32.21 | OG | 10.39
| 20f | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 2 | 356 |  | KISH/PW-20 | New | 5 |  | N-3 | KISH | 186.46 | OG | 169.54
| 20g | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 14 | 110.66 |  | KISH/PW-20 | New | 1 |  | N-4 | KISH |  | OG | 110.66
| 20h | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 2 | 85.22 |  | KISH/PW-20 | New | 4 |  | N-4 | KISH | 64.22 | OG | 21
| 20i | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 |  | KISH/PW-20 | New | 5 |  | N-4 | KISH | 93.225 | OG | 84.775
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 |  | KISH/PW-21 | New | 3 |  | N-6 | KISH | 0 | OG | 225
| 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 10 | 478.31 |  | KISH/PW-21 | New | 11 | 121065.93 | N-8 | KISH | 0 | OG | 478.31
22 | 22a | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | nos. | 6 | 72.88 |  | KISH/PW-22 | New | 1 |  | N-10 | KISH | 0 | OG | 72.88
| 22b | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | nos. | 3 | 116.03 |  | KISH/PW-22 | New | 4 |  | N-11 | KISH | 0 | OG | 116.03
| 22c | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 |  | KISH/PW-22 | New | 5 |  | N-12 | KISH | 0 | OG | 194.91
| 22d | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 |  | KISH/PW-22 | New | 7 | 146641.43 | N-13 | KISH | 0 | OG | 209.47
| 22e | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 11 | 252.89 |  | KISH/PW-22 | New | 11 | 91984.7 | N-14 | KISH | 0 | OG | 252.89
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 567.12 |  | KISH/PW-23 | New | 3 |  | N-7 | KISH | 0 | OG | 567.12
| 23b | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 4.51 | 105.29 |  | KISH/PW-23 | New | 11 | 51688.691 | N-7 | KISH | 0 | OG | 105.29
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | nos. | 15 | 124.68 |  | KISH/PW-25 | New | 1 |  | N-8 | KISH | 0 | OG | 124.68
| 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 |  | KISH/PW-25 | New | 3 |  | N-8 | KISH | 304.53 | OG | 92.43
| 25c | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 |  | KISH/PW-25 | New | 5 |  | N-8 | KISH | 23.35 | OG | 126.795
| 25d | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 |  | KISH/PW-25 | New | 7 | 342244.7 | N-8 | KISH | 190.84 | OG | 234.14
Sub-Total | [5 empty] | 11527.875 | [7 empty] | 4258.56 |  | 7269.315
1 | 1a | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 1 | 45 |  | KISH/PW-01 |  | 2 |  |  |  | 0 | P | 45
| 1b | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 1.22 | 48.08 |  | KISH/PW-01 |  | 8 |  |  |  | 0 | P | 48.08
| 1c | PW-01 4 Nos. Rehabilitation Haor | Re-sectioning of Full Embankment | Km | 0 | 0 |  | KISH/PW-01 |  | 9 |  |  |  | 0 | P | 0
| 1d | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 2.151 | 84.76 |  | KISH/PW-01 |  | 8 |  |  |  | 0 | P | 84.76
| 1e | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 8.175 | 322.16 |  | KISH/PW-01 |  | 8 |  |  |  | 0 | P | 322.16
2 | 2a | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 |  | KISH/PW-02 |  | 3 |  |  |  | 103.45 | P | 20
| 2b | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | Km | 11.095 | 211.74 |  | KISH/PW-02 |  | 7 |  |  |  | 196.26 | P | 15.48
| 2c | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | Km | 0.315 | 14.81 |  | KISH/PW-02 |  | 11 |  |  |  | 11.01 | P | 3.8
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 |  | KISH/PW-03 |  | 3 |  |  |  | 149.3 | P | 6.21
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | Km | 6.471 | 256.87 |  | KISH/PW-04 |  | 11 |  |  |  | 246.65 | P | 10.22
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 |  | KISH/PW-05 |  | 3 |  |  |  | 141.59 | P | 51.9
6 | 6a | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 232.99 |  | KISH/PW-06 |  | 3 |  |  |  | 206.98 | P | 26.01
7 | 7a | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | Km | 25.7 | 854.17 |  | KISH/PW-07 |  | 7 |  |  |  | 514.22 | P | 339.95
| 7b | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | Km | 0.8 | 91 |  | KISH/PW-07 |  | 11 |  |  |  | 0 | P | 91
11 | 7c | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | Km | 10.86 | 557.63 |  | KISH/PW-11 |  | 11 |  |  |  | 320.79 | P | 236.84
12 | 12a | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 |  | KISH/PW-12 |  | 3 |  |  |  | 181.28 | P | 46.21
| 12b | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 |  | KISH/PW-12 |  | 3 |  |  |  | 241.72 | P | 61.61
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 246.15 |  | KISH/PW-13 |  | 3 |  |  |  | 215.59 | P | 30.56
| 13b | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 180.96 |  | KISH/PW-13 |  | 3 |  |  |  | 158.49 | P | 22.47
14 | 14a | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 176.58 |  | KISH/PW-14 |  | 3 |  |  |  | 164.5 | P | 12.08
| 14b | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-14 |  | 3 |  |  |  | 0 | P | 0
| 14c | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 16.9 | 680.42 |  | KISH/PW-14 |  | 11 |  |  |  | 516.29 | P | 164.13
15 | 15a | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of 6.00 m causeway | nos. | 1 | 166.9 |  | KISH/PW-15 |  | 5 |  |  |  | 0 | P | 166.9
| 15b | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 9 | 616.92 |  | KISH/PW-15 |  | 11 |  |  |  | 333.94 | P | 282.98
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 |  | KISH/PW-16 |  | 3 |  |  |  | 323.54 | P | 80.96
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 600 |  | KISH/PW-17 |  | 3 |  |  |  | 403.5 | P | 196.5
| 17b | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 |  | KISH/PW-17 |  | 3 |  |  |  | 0 | P | 115.24
| 17c | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 13.17 | 550.04 |  | KISH/PW-17 |  | 11 |  |  |  | 420.64 | P | 129.4
18 | 18a | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 1 | 300 |  | KISH/PW-18 |  | 5 |  |  |  | 182 | p | 118
| 18b | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.m width Causeway | nos. | 1 | 274.54 |  | KISH/PW-18 |  | 5 |  |  |  | 166.64 | p | 107.9
| 18c | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 |  | KISH/PW-18 |  | 7 |  |  |  | 361.81 | P | 253.79
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 160 |  | KISH/PW-21 |  | 3 |  |  |  | 0 | P | 160
| 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | nos. | 5 | 125 |  | KISH/PW-21 |  | 12 |  |  |  | 0 | P | 125
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | nos. | 4 | 41.87 |  | KISH/PW-23 |  | 1 |  |  |  | 0 | P | 41.87
| 23b | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | nos. | 1 | 39.54 |  | KISH/PW-23 |  | 4 |  |  |  | 0 | P | 39.54
| 23c | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 |  | KISH/PW-23 |  | 7 |  |  |  | 0 | P | 32.63
24 | 24a | BWDB/Kish/HFMLIP/PW-24 Dakshiner Haor | Const. of Submersible Embankment | Km | 19.843 | 918.58 |  | KISH/PW-24 |  | 11 |  |  |  | 787.65 | P | 130.93
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | nos. | 1 | 43.25 |  | KISH/PW-25 |  | 4 |  |  |  | 0 | P | 43.25
| 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 |  | KISH/PW-25 |  | 5 |  |  |  | 0 | P | 450.435
26 | 26a | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Re-excavation of Khal (New) | Km | 22.7 | 486.56 |  | KISH/PW-26 |  | 7 |  |  |  | 216.24 | P | 270.32
| 26b | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Const. of Submersible Embankment | Km | 0.54 | 22.72 |  | KISH/PW-26 |  | 11 |  |  |  | 0 | P | 22.72
27 | 27a | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 314 |  | KISH/PW-27 |  | 3 |  |  |  | 0 | P | 314
| 27b | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-27 |  | 3 |  |  |  | 0 | P | 0
| 27c | BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | nos. | 4 | 195 |  | KISH/PW-27 |  | 4 |  |  |  | 0 | P | 195
| 27d | BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | nos. | 1 | 294 |  | KISH/PW-27 |  | 5 |  |  |  | 0 | P | 294
| 27e | BWDB/Kish/HFMLIP/PW-27 | Const. of 4.0 m width Causeway | nos. | 1 | 160 |  | KISH/PW-27 |  | 5 |  |  |  | 0 | P | 160
28 | 28a | BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 60 | 1298.8 |  | KISH/PW-28 |  | 15 |  |  |  | 116.5 | P | 1182.3
Sub-Total | [5 empty] | 13232.715 | [7 empty] | 6680.58 |  | 6552.135
Grand-Total | [5 empty] | 24760.59 | [7 empty] | 10939.14 |  | 13821.45

## Regulatos
Projected Cost of Running Works At Kishoregonj WD Division
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | Km | 10.383 | 533.94 | 11 | 432.69 | OG | 101.25
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 | 3 | 179.54 | OG | 18.46
4 | 4b | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 | 3 | 231.82 | OG | 23.83
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | Km | 12.214 | 577.36 | 11 | 349.59 | OG | 227.77
6 | 6a | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | Km | 20 | 557.44 | 7 | 512.85 | OG | 44.59
9 | 9a | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 193.13 | 5 | 56.15 | OG | 136.98
9 | 9b | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 2 | 463.51 | 5 | 134.76 | OG | 328.75
9 | 9c | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 77.25 | 4 | 22.46 | OG | 54.79
10 | 10a | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 114 | 3 | 14.22 | OG | 99.78
10 | 10b | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 1 | 152 | 5 | 18.96 | OG | 133.04
10 | 10c | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | Km | 11.98 | 617.94 | 11 | 211.56 | OG | 406.38
11 | 11a | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 | 3 | 134.1 | OG | 140.4
12 | 12a | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | Km | 10.757 | 422.65 | 7 | 104.15 | OG | 318.5
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 10 | 576.67 | 11 | 86.55 | OG | 490.12
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | Km | 14.12 | 511.3 | 11 | 248.13 | OG | 263.17
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 25 | 274.46 | 1 | 117.08 | OG | 157.38
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 5 | 177.44 | 4 | 82.41 | OG | 95.03
19 | 19a | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 1065 | 7 | 296.36 | OG | 768.64
20 | 20a | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 15 | 118.56 | 1 | 4.91 | OG | 113.65
20 | 20b | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
20 | 20c | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 | 5 | 93.225 | OG | 84.775
20 | 20d | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 7 | 55.33 | 1 |  | OG | 55.33
20 | 20e | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
20 | 20f | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 2 | 356 | 5 | 186.46 | OG | 169.54
20 | 20g | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 14 | 110.66 | 1 |  | OG | 110.66
20 | 20h | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 2 | 85.22 | 4 | 64.22 | OG | 21
20 | 20i | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 | 5 | 93.225 | OG | 84.775
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 | 3 | 0 | OG | 225
21 | 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 10 | 478.31 | 11 | 0 | OG | 478.31
22 | 22a | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | nos. | 6 | 72.88 | 1 | 0 | OG | 72.88
22 | 22b | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | nos. | 3 | 116.03 | 4 | 0 | OG | 116.03
22 | 22c | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 | 5 | 0 | OG | 194.91
22 | 22d | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 | 7 | 0 | OG | 209.47
22 | 22e | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 11 | 252.89 | 11 | 0 | OG | 252.89
22 | 22f | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 567.12 | 3 | 0 | OG | 567.12
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 4.51 | 105.29 | 11 | 0 | OG | 105.29
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | nos. | 15 | 124.68 | 1 | 0 | OG | 124.68
25 | 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 | 3 | 304.53 | OG | 92.43
25 | 25c | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 | 5 | 23.35 | OG | 126.795
25 | 25d | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 | 7 | 190.84 | OG | 234.14
Total |  |  |  |  | 250.434
Sub-Total | [5 empty] | 11527.875 |  | 4258.56 |  | 7269.315
1 | 1a | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 1 | 45 | 2 | 0 | P | 45
1 | 1b | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 1.22 | 48.08 | 8 | 0 | P | 48.08
1 | 1c | PW-01 4 Nos. Rehabilitation Haor | Re-sectioning of Full Embankment | Km | 0 | 0 | 9 | 0 | P | 0
1 | 1d | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 2.151 | 84.76 | 8 | 0 | P | 84.76
1 | 1e | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 8.175 | 322.16 | 8 | 0 | P | 322.16
2 | 2a | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 | 3 | 103.45 | P | 20
2 | 2b | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | Km | 11.095 | 211.74 | 7 | 196.26 | P | 15.48
2 | 2c | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | Km | 0.315 | 14.81 | 11 | 11.01 | P | 3.8
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 | 3 | 149.3 | P | 6.21
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | Km | 6.471 | 256.87 | 11 | 246.65 | P | 10.22
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 | 3 | 141.59 | P | 51.9
6 | 6a | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 232.99 | 3 | 206.98 | P | 26.01
7 | 7a | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | Km | 25.7 | 854.17 | 7 | 514.22 | P | 339.95
7 | 7b | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | Km | 0.8 | 91 | 11 | 0 | P | 91
11 | 7c | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | Km | 10.86 | 557.63 | 11 | 320.79 | P | 236.84
12 | 12a | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 | 3 | 181.28 | P | 46.21
12 | 12b | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 | 3 | 241.72 | P | 61.61
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 246.15 | 3 | 215.59 | P | 30.56
13 | 13b | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 180.96 | 3 | 158.49 | P | 22.47
14 | 14a | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 176.58 | 3 | 164.5 | P | 12.08
14 | 14b | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 0 | 0 | 3 | 0 | P | 0
14 | 14c | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 16.9 | 680.42 | 11 | 516.29 | P | 164.13
15 | 15a | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of 6.00 m causeway | nos. | 1 | 166.9 | 5 | 0 | P | 166.9
15 | 15b | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 9 | 616.92 | 11 | 333.94 | P | 282.98
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 | 3 | 323.54 | P | 80.96
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 600 | 3 | 403.5 | P | 196.5
17 | 17b | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 | 3 | 0 | P | 115.24
17 | 17c | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 13.17 | 550.04 | 11 | 420.64 | P | 129.4
18 | 18a | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 1 | 300 | 5 | 182 | p | 118
18 | 18b | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.m width Causeway | nos. | 1 | 274.54 | 5 | 166.64 | p | 107.9
18 | 18c | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 | 7 | 361.81 | P | 253.79
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 160 | 3 | 0 | P | 160
21 | 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | nos. | 5 | 125 | 12 | 0 | P | 125
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | nos. | 4 | 41.87 | 1 | 0 | P | 41.87
23 | 23b | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | nos. | 1 | 39.54 | 4 | 0 | P | 39.54
23 | 23c | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 | 7 | 0 | P | 32.63
24 | 24a | BWDB/Kish/HFMLIP/PW-24 Dakshiner Haor | Const. of Submersible Embankment | Km | 19.843 | 918.58 | 11 | 787.65 | P | 130.93
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | nos. | 1 | 43.25 | 4 | 0 | P | 43.25
25 | 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 | 5 | 0 | P | 450.435
26 | 26a | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Re-excavation of Khal (New) | Km | 22.7 | 486.56 | 7 | 216.24 | P | 270.32
26 | 26b | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Const. of Submersible Embankment | Km | 0.54 | 22.72 | 11 | 0 | P | 22.72
27 | 27a | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 314 | 3 | 0 | P | 314
27 | 27b | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 0 | 0 | 3 | 0 | P | 0
27 | 27c | BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | nos. | 4 | 195 | 4 | 0 | P | 195
27 | 27d | BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | nos. | 1 | 294 | 5 | 0 | P | 294
27 | 27e | BWDB/Kish/HFMLIP/PW-27 | Const. of 4.0 m width Causeway | nos. | 1 | 160 | 5 | 0 | P | 160
28 | 28a | BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 60 | 1298.8 | 15 | 116.5 | P | 1182.3
Sub-Total | [5 empty] | 13232.715 |  | 6680.58 |  | 6552.135
Grand-Total | [5 empty] | 24760.59 |  | 10939.14 |  | 13821.45

## Stucture_Summary
Irrigation Inlet :82 Contract Value:756.57 Paid Bill:121.99 Amount Payable:634.58
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 25 | 274.46 | 1 | 117.08 | OG | 157.38
20 | 20a | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 15 | 118.56 | 1 | 4.91 | OG | 113.65
20 | 20d | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 7 | 55.33 | 1 | 0 | OG | 55.33
20 | 20g | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 14 | 110.66 | 1 | 0 | OG | 110.66
22 | 22a | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | nos. | 6 | 72.88 | 1 | 0 | OG | 72.88
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | nos. | 15 | 124.68 | 1 | 0 | OG | 124.68
Sub-Total Inlet |  |  |  |  | 82 | 756.57 |  | 121.99 |  | 634.58
Regulator:9 Contract Value:2031.23 Paid Bill:864.21 Amount Payable:1167.02
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 | 3 | 179.54 | OG | 18.46
4 | 4b | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 | 3 | 231.82 | OG | 23.83
10 | 10a | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 114 | 3 | 14.22 | OG | 99.78
11 | 11a | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 | 3 | 134.1 | OG | 140.4
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 | 3 | 0 | OG | 225
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Construction of 2-V Mozilla Khal Regulator | nos. | 1 | 298.3 | 3 | 0 | OG | 298.3
23 | 23b | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Construction of 2-V Noaparakhali Khal Regulator | nos. | 1 | 230.33 | 3 | 0 | OG | 230.33
25 | 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 | 3 | 304.53 | OG | 92.43
Sub-Total Regulator |  |  |  |  | 9 | 1992.74 |  | 864.21 |  | 1128.53
Box Drainage Outlet:13 Contract Value:541.14 Paid Bill:233.51 Amount Payable:307.63
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
9 | 9c | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 77.25 | 4 | 22.46 | OG | 54.79
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 5 | 177.44 | 4 | 82.41 | OG | 95.03
20 | 20b | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
20 | 20e | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
20 | 20h | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 2 | 85.22 | 4 | 64.22 | OG | 21
22 | 22b | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | nos. | 3 | 116.03 | 4 | 0 | OG | 116.03
Sub-Total Box Drainage Outlet |  |  |  |  | 13 | 541.14 |  | 233.51 |  | 307.63
Causeway:10 Contract Value:1865.695 Paid Bill:606.13 Amount Payable:1259.57
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
9 | 9a | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 193.13 | 5 | 56.15 | OG | 136.98
9 | 9b | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 2 | 463.51 | 5 | 134.76 | OG | 328.75
10 | 10b | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 1 | 152 | 5 | 18.96 | OG | 133.04
20 | 20c | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 | 5 | 93.225 | OG | 84.775
20 | 20f | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 2 | 356 | 5 | 186.46 | OG | 169.54
20 | 20i | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 1 | 178 | 5 | 93.225 | OG | 84.775
22 | 22c | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 | 5 | 0 | OG | 194.91
25 | 25c | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 | 5 | 23.35 | OG | 126.795
Sub-Total Causeway |  |  |  |  | 10 | 1865.695 |  | 606.13 |  | 1259.565
Khal/River:74.61km Contract Value:2679.54 Paid Bill:1104.20 Amount Payable:1575.34
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
6 | 6a | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | Km | 20 | 557.44 | 7 | 512.85 | OG | 44.59
12 | 12a | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | Km | 10.757 | 422.65 | 7 | 104.15 | OG | 318.5
19 | 19a | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 1065 | 7 | 296.36 | OG | 768.64
22 | 22d | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 | 7 | 0 | OG | 209.47
25 | 25d | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 | 7 | 190.84 | OG | 234.14
Sub-Total Khal/River |  |  |  |  | 74.61 | 2679.54 |  | 1104.2 |  | 1575.34
Submersible Embankment:84.21 km Contract Value:3653.70 Paid Bill:1328.52 Amount Payable:2325.18
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | Km | 10.383 | 533.94 | 11 | 432.69 | OG | 101.25
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | Km | 12.214 | 577.36 | 11 | 349.59 | OG | 227.77
10 | 10c | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | Km | 11.98 | 617.94 | 11 | 211.56 | OG | 406.38
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 10 | 576.67 | 11 | 86.55 | OG | 490.12
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | Km | 14.12 | 511.3 | 11 | 248.13 | OG | 263.17
21 | 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 10 | 478.31 | 11 | 0 | OG | 478.31
22 | 22e | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 11 | 252.89 | 11 | 0 | OG | 252.89
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 4.51 | 105.29 | 11 | 0 | OG | 105.29
Sub-Total Submersible Embankment |  |  |  |  | 84.207 | 3653.7 |  | 1328.52 |  | 2325.18
[8 empty] | Inlet | 82 | 634.58
[8 empty] | Regulator | 9 | 1128.53
[8 empty] | Outlet | 13 | 307.63
[8 empty] | Causeway | 10 | 1259.57
[8 empty] | Khal/River | 74.61 | 1575.34
[8 empty] | Sub Emb | 84.21 | 2325.18
7230.83

## Sheet2
SL No | Pacakge No | Name | Length (Km) | Excavation (Cum) | Contract Value(Lakh) | Billed Amount (Lakh) | Remaining Amount (Lakh)
1 | 6 | Katakhali Khal | 3.8 | 74324.94 | 69.51 | 512.85
2 |  | Samarbari Khal | 3.89 | 104440.21 | 102.18
3 |  | Mahinhandra Khal | 0.9 | 30196.5 | 28.84
4 |  | Kata Khal | 0.5 | 17387.24 | 16.45
5 |  | Kurigai Khal | 7.35 | 236589.38 | 231.8
6 |  | Beri Gang | 3.56 | 114768.75 | 112.46
20 | 12 | Lalpur Khal | 3.99 | 155824.8 | 166.7 | 104.15
21 |  | Naluar Khal | 0.6 | 16559.58 | 17.47
22 |  | Maherkona Khal | 3 | 90975.58 | 98.06
23 |  | Nabinpur Khal | 2.8 | 104525.74 | 109.32
24 |  | Jalalpur | 0.367 | 3872.29 | 4.3
7 | 19 | Bera Chapra | 15.82 | 322130.67 | 540.2 | 296.36
8 |  | Ataplal | 7.111 | 255623.014 | 428.3
9 | 22 | Sajna Khal | 1 | 14902.18 | 21.69 | 0
10 |  | Chandpur Khal | 0.7 | 23058.89 | 32.74
11 |  | Baduti Khal | 1 | 4822.21 | 7.67
12 |  | Kanala Khal | 0.584 | 6670.13 | 9.84
13 |  | Kursi Khal | 2.9 | 69778.75 | 99.77
14 |  | Bamuna Khal | 1.4 | 9766.9 | 14.93
15 |  | Chouganga Khal | 1.9 | 1977.99 | 4.59
16 |  | Maora Khal | 1.7 | 11989.43 | 18.3
17 |  | Burimara Khal | 0.439 | 3655.55 | 5.51
18 | 25 | Bantai River | 1.65 | 49532.84 | 54.4 | 190.84
19 |  | Shankir Khal | 8.895 | 292711.87 | 320.03
|  |  | 75.856 | 2016085.434 | 2515.06
SL No | Pacakge No | Name | Length (Km) | Excavation (Cum) | Contract Value(Lakh) | Billed Amount (Lakh) | Remaining Amount (Lakh)
1 | 6 | Katakhali Khal | 3.8 | 74324.94 | 69.51
2 | 6 | Samarbari Khal | 3.89 | 104440.21 | 102.18
3 | 6 | Mahinhandra Khal | 0.9 | 30196.5 | 28.84
4 | 6 | Kata Khal | 0.5 | 17387.24 | 16.45
5 | 6 | Kurigai Khal | 7.35 | 236589.38 | 231.8
6 | 6 | Beri Gang | 3.56 | 114768.75 | 112.46
20 | 12 | Lalpur Khal | 3.99 | 155824.8 | 166.7
21 | 12 | Naluar Khal | 0.6 | 16559.58 | 17.47
22 | 12 | Maherkona Khal | 3 | 90975.58 | 98.06
23 | 12 | Nabinpur Khal | 2.8 | 104525.74 | 109.32
24 | 12 | Jalalpur | 0.367 | 3872.29 | 4.3
7 | 19 | Bera Chapra | 15.82 | 322130.67 | 540.2
8 | 19 | Ataplal | 7.111 | 255623.014 | 428.3
9 | 22 | Sajna Khal | 1 | 14902.18 | 21.69
10 | 22 | Chandpur Khal | 0.7 | 23058.89 | 32.74
11 | 22 | Baduti Khal | 1 | 4822.21 | 7.67
12 | 22 | Kanala Khal | 0.584 | 6670.13 | 9.84
13 | 22 | Kursi Khal | 2.9 | 69778.75 | 99.77
14 | 22 | Bamuna Khal | 1.4 | 9766.9 | 14.93
15 | 22 | Chouganga Khal | 1.9 | 1977.99 | 4.59
16 | 22 | Maora Khal | 1.7 | 11989.43 | 18.3
17 | 22 | Burimara Khal | 0.439 | 3655.55 | 5.51
18 | 25 | Bantai River | 1.65 | 49532.84 | 54.4
19 | 25 | Shankir Khal | 8.895 | 292711.87 | 320.03
|  |  | 75.856 | 2016085.434 | 2515.06