## Immediate_Actions
Sl No | Pack Name | Structue Name | Length | Contract Value | STC Code | Bill Paid | Remaining Bill | FSE Name | Cell Phone No | Work Completion Probability | Value of Workdone | Value of work Payable | Required Immediate Action
1 | 3 | Const. of Submersible Embankment | 10.383 Km | 533.94 | 11 | 432.69 | 101.25 | Abul Latif | 01712840981 | 0-1:1km To Be Startted 1-9:8Km Complete 9-10.383:1.383 Km To be startted | 411.3956 | -21.2944 | 1.Immediate Start of Work in Some Places
2 | 5 | Const. of Submersible Embankment | 12.214 Km | 577.36 | 11 | 349.59 | 227.77 | Abdul Latif | 01712840981 | 0-4:4 Km Complete 4-5.3:1.3 Km On going 5.3-6.5:1.2 Km GAP due to River Erosion 6.5-9.0:2.5 Km 2nd Layer Complete 9-10:1Km 1st Layer 10-12:2Km Not Started | 361.6181 | 12.0281 | 1.Immediate Start of Work in Some Places
3 | 10 | Const. of Submersible Embankment | 11.98 Km | 617.94 | 11 | 211.56 | 406.38 | Amirul Islam | 01719255232 | 0:5:5Km Not Started Due to Local Problem 5-10:Completed 10-11.98Km:Not Started | 257.9 | 46.34 | 1.Immediate Start of Work in Some Places
4 | 12 | Lalpur Khal -3.99 Km | 3.99 Km | 166.7 | 7 | 43.86 | 122.84 | Amirul Islam | 01719255232 | Not Yet Started |  | -43.86 | 1.Immediate Start of Works
|  | Maherkona Khal-3.00 Km | 3.00 Km | 98.06 | 7 | 25.8 | 72.26 | Amirul Islam | 01719255232 | 3.00-1.50:1.5 Km Completed 1.50-0.00:On Going | 49.03 | 23.23 | 1.Expedite Work
|  | Nabinpur Khal-2.8 Km | 2.8 Km | 109.32 | 7 | 28.76 | 80.56 | Amirul Islam | 01719255232 | Complete | 109.32 | 80.56
5 | 13 | Const. of Submersible Embankment | 10 Km | 576.67 | 11 | 86.55 | 490.12 | Munshi | 01712696439 | 0-4:4Km LA Problem Not Started 4-6:2Km Completed 6-10:4km 3rd Layer | 288.34 | 201.79 | 1.Immediate Start of work in 0-4Km
6 | 16 | Const. of Submersible Embankment | 14.12 Km | 511.3 | 11 | 248.13 | 263.17 | Khalilur Rahman | 01764762777 |  |  | -248.13
7 | 19 | Bera Chapra River-15.82 Km | 15.82 Km | 540.2 | 7 | 165.3 | 374.9 | Munshi | 01712696439 | Mobiliztion Yet Not Completed | 0 | -165.3 | 1.Contractor is slothful. 2.Need Immediate Mobilization 3.If Not Mobilize Contract Termination 4.If Mobilize Deployment of Personnel for Daily Progress Monitoring
|  | Ataplal River-7.111 Km | 7.11 Km | 428.3 | 7 | 131.06 | 297.24 | Munshi | 01712696439 | Mobiliztion Yet Not Completed | 0 | -131.06 | 1.Contractor is slothful. 2.Need Immediate Mobilization 3.If Not Mobilize Contract Termination 4.If Mobilize Deployment of Personnel for Daily Progress Monitoring
8 | 20 | Const. of 4.0 m width Causeway at Chitra Khal | 4m | 133.79 | 5 | 88.79 | 45 | Abul Latif | 01712840981 | Block Placing Going On | 100.3425 | 11.5525
|  | Const. of 4.0 m width Causeway at Nabunpur Khal | 4m | 187.82 | 5 | 73.24 | 114.58 | Abul Latif | 01712840981 | Block Placing Going On | 140.865 | 67.625
|  | Const. of 4.0 m width Causeway at Dipjuri Khal | 4m | 181.18 | 5 | 131.39 | 49.79 | Abul Latif | 01712840981 | Block Placing Going On | 135.885 | 4.495
|  | Const. of 4.0 m width Causeway at Sudhi Khal | 4m | 133.84 | 5 | 73.8 | 60.04 | Abul Latif | 01712840981 | Block Manufacturing | 80.304 | 6.504 | 1.Immediate Start of CC Block Manufacturing
9 | 21 | Const. of Submersible Embankment | 10 Km | 478.31 | 11 | 0 | 478.31 | Khalilur Rahman | 01764762777 | Work Not Strated On But Excavator Mobilized | 0 | 0
10 | 22 | Box Drainage Outlet at Km 19.5 | 1-vent | 36.66 | 4 | 0 | 36.66 | Khalilur Rahman | 01764762777 | Work will be started soon | 0 | 0 | 1.Settingup Layout
|  | Box Drainage Outlet at Km 22.5 | 1-vent | 36.66 | 4 | 0 | 36.66 | Khalilur Rahman | 01764762777 | Work will be started soon | 0 | 0 | 1.Settingup Layout
|  | Box Drainage Outlet at Km 23.6 | 1-vent | 36.66 | 4 | 0 | 36.66 | Khalilur Rahman | 01764762777 | Work will be started soon | 0 | 0 | 1.Settingup Layout
|  | Const. of 4.0 m width Causeway | 4m | 194.91 | 5 | 0 | 194.91 | Khalilur Rahman | 01764762777 | Material is On Site work will be started soon. | 0 | 0 | 1.Settingup Layout
|  | Kursi Khal -2.9 Km | 2.9 Km | 99.97 | 7 | 0 | 99.97 | Khalilur Rahman | 01764762777 | Not Yet Started | 0 | 0 | 1.ImmediateStart of Work
|  | Const. of Submersible Embankment | 11 Km | 252.89 | 11 | 0 | 252.89 | Khalilur Rahman | 01764762777 | 1st Layer althrough | 68.97 | 68.97
11 | 23 | Construction of 2-V Mozilla Khal Regulator | 2-vent | 298.3 | 3 | 0 | 298.3 | Anil | 01715332085 | Work On Going | 119.32 | 119.32 | 1.Preparation of Realistic Work Programme to Finish The Work
|  | Construction of 2-V Noaparakhali Khal Regulator | 2-vent | 230.33 | 3 | 0 | 230.33 | Anil | 01715332085 | Work On Going | 92.132 | 92.132 | 1.Preparation of Realistic Work Programme to Finish The Work
|  | Const. of Submersible Embankment | 4.51 Km | 105.29 | 11 | 0 | 105.29 | Anil | 01715332085 | Althrough 1st Layer 2nd Layer Going on | 42.116 | 42.116
12 | 25 | Shankir Khal -8.895 Km | 8.895 Km | 320.03 | 7 | 163.11 | 156.92 | Khalilur Rahman | 01764762777 | 0-8:7.6 Km complete with 400m gap and 8-8.800:Yet to be started | 276.3895 | 113.2795 | 1.Immediate Completion of Work
|  | Const. of New Regulators 5 vent (1.50mx1.80m) | 5-Vent | 396.96 | 3 | 304.53 | 92.43 | Khalilur Rahman | 01764762777 | Structure Almost Complete | 297.72 | -6.81 | 1.Immediate Start of CC Block Manufacturing2.Due to Conbtractual Problem There is Dispute about CA for CCBlock whethere Shgringles or Crushed Stone To be Used 3.Work is pedding due to Indecision of Competent Authority
|  | Const. of 4.0 m width Causeway | 4m | 150.145 | 5 | 23.35 | 126.795 | Khalilur Rahman | 01764762777 |  | 120.116 | 96.766 | 1.Immediate Start of CC Block Manufacturing2.Due to Conbtractual Problem There is Dispute about CA for CCBlock whethere Shgringles or Crushed Stone To be Used 3.Work is pedding due to Indecision of Competent Authority
Sub-Total |  |  |  | 7433.535 |  | 2581.51 | 4852.025 |  |  |  | 2951.7637 | 370.2537