## Package_wise_str_df
Package_No | Item | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | WMG_OFF | Gate_Repair
KISH-01 | Mobilization | 0 | 0.0902 | 0 | 0 | 0.9098 | 0 | 0 | 0 | 0 | 0 | 0
KISH-02 | Mobilization | 0 | 0 | 0.3592 | 0.6066 | 0 | 0 | 0 | 0.0342 | 0 | 0 | 0
KISH-03 | Mobilization | 0 | 0 | 0.2256 | 0 | 0 | 0 | 0 | 0.7744 | 0 | 0 | 0
KISH-04 | Mobilization | 0 | 0 | 0.6385 | 0 | 0 | 0 | 0 | 0.3615 | 0 | 0 | 0
KISH-05 | Mobilization | 0 | 0 | 0.2478 | 0 | 0 | 0 | 0 | 0.7522 | 0 | 0 | 0
KISH-06 | Mobilization | 0 | 0 | 0.2942 | 0.7058 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-07 | Mobilization | 0 | 0 | 0 | 0.9138 | 0 | 0 | 0 | 0.0862 | 0 | 0 | 0
KISH-09 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-10 | Mobilization | 0 | 0 | 0.3009 | 0 | 0 | 0 | 0 | 0.6991 | 0 | 0 | 0
KISH-11 | Mobilization | 0 | 0 | 0.3299 | 0 | 0 | 0 | 0 | 0.6701 | 0 | 0 | 0
KISH-12 | Mobilization | 0 | 0 | 0.5699 | 0.4301 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-13 | Mobilization | 0 | 0 | 0.4248 | 0 | 0 | 0 | 0 | 0.5752 | 0 | 0 | 0
KISH-14 | Mobilization | 0 | 0 | 0.206 | 0 | 0 | 0 | 0 | 0.794 | 0 | 0 | 0
KISH-15 | Mobilization | 0 | 0 | 0.2129 | 0 | 0 | 0 | 0 | 0.7871 | 0 | 0 | 0
KISH-16 | Mobilization | 0 | 0 | 0.3438 | 0 | 0 | 0 | 0 | 0.6562 | 0 | 0 | 0
KISH-17 | Mobilization | 0.175 | 0 | 0.4743 | 0 | 0 | 0 | 0 | 0.3508 | 0 | 0 | 0
KISH-18 | Mobilization | 0 | 0 | 0.588 | 0.412 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-19 | Mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-20 | Mobilization | 0.2897 | 0 | 0.7103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-21 | Mobilization | 0 | 0 | 0.5153 | 0 | 0 | 0 | 0 | 0.3547 | 0.1299 | 0 | 0
KISH-22 | Mobilization | 0 | 0 | 0.424 | 0.2481 | 0 | 0 | 0 | 0.3279 | 0 | 0 | 0
KISH-23 | Mobilization | 0.0823 | 0 | 0.7347 | 0.0424 | 0 | 0 | 0 | 0.1406 | 0 | 0 | 0
KISH-24 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
KISH-25 | Mobilization | 0.0672 | 0 | 0.7206 | 0.2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-26 | Mobilization | 0 | 0 | 0 | 0.9537 | 0 | 0 | 0 | 0.0463 | 0 | 0 | 0
KISH-27 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NETR-01 | Mobilization | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NETR-02 | Mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
NETR-03 | Mobilization | 0 | 0.4483 | 0 | 0 | 0 | 0.5181 | 0.0336 | 0 | 0 | 0 | 0
NETR-04 | Mobilization | 0 | 0 | 0 | 0 | 0.7364 | 0 | 0.2636 | 0 | 0 | 0 | 0
NETR-05 | Mobilization | 0 | 0 | 0.9519 | 0 | 0 | 0 | 0.0481 | 0 | 0 | 0 | 0
NETR-06 | Mobilization | 0.0268 | 0 | 0.1338 | 0.8086 | 0 | 0 | 0 | 0 | 0.0308 | 0 | 0
NETR-07 | Mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NETR-08 | Mobilization | 0.0417 | 0 | 0.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-01 | Mobilization | 0.0073 | 0 | 0.2159 | 0.1836 | 0 | 0 | 0 | 0.5932 | 0 | 0 | 0
SUNM-02 | Mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-03 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-04 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
SUNM-05 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-06 | Mobilization | 0.0833 | 0 | 0.0286 | 0.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI-01 | Mobilization | 0 | 0 | 0.2538 | 0 | 0.5472 | 0 | 0.199 | 0 | 0 | 0 | 0
HOBI-02 | Mobilization | 0 | 0 | 0.2215 | 0 | 0.142 | 0 | 0.6366 | 0 | 0 | 0 | 0
HOBI-04 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
HOBI-05 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI-06 | Mobilization | 0.0953 | 0 | 0.9047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI-07 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-28/Lot-1 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KISH-28/Lot-2 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KISH-28/Lot-3 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KISH-28/Lot-4 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0

## Sheet1
id | Code | Description
57 | 4111306 | Construction of Irrigation Inlet (New Haors) | 4111306_Construction of Irrigation Inlet (New Haors)
58 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 4111307_ Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects)
59 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 4111307_ Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors)
60 | 4111307 | Re-excavation of Khal/River (New Haors) | 4111307_ Re-excavation of Khal/River (New Haors)
61 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 4111201_ Re-excavation of Khal/River (Rehabilitation Sub-Projects)
62 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 4111201_ Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects)
63 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 4111201_ Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects)
64 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 4111201_Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum)
65 | 4111201 | Rehabilitation of Regulator (New Haors) | 4111201_ Rehabilitation of Regulator (New Haors)
66 | 4111201 | Construction of WMG Office | 4111201_Construction of WMG Office
67 | 4111201 | O&M During Construction | 4111201_O&M During Construction

## Sheet5
| 7146.032 | 156388 |  |  | Khal | Box
| 2175338.384 | 582066.296 |  |  | 2651098.73 | 3807686.27 | 6458785 |  | Chtra Khal CW | 3058698.583
| 442686.376 | 132743.207 |  |  | 0.41046 | 0.58954 |  |  | Nabinpur Khal CW | 3991659.935
| 25927.941 | 2610.381 |  | GoB | 331387.7 | 475961.3 |  |  | Dipjuri KHal CW | 2816996.163
total | 2651098.733 | 71523.693 |  | RPA | 2319711.03 | 3331724.97 | 5651436 |  | Sudhi Khal CW | 3363880.156
|  | 769684.617 |  |  | 2651098.73 |  |  |  | Box Sluice | 808976.339 | DF | GoB | RPA
|  | 776580.144 | [6 empty] | Sub-Total Structure | 14040211.176 | 0.93161 | 1755026.3105 | 12285185.1049
|  | 2491596.338 | [6 empty] | Irrigation Inlet | 1030629.567 | 0.068386 | 128828.6895 | 901800.8951
|  |  | 2491596.338 | [6 empty] | 15070840.743 |  | 1883855 | 13186986 | 15070841
Kish-22 1st IPC
[9 empty] | Embankment | Khal |  |  | DF | GoB | RPA
[9 empty] | 5478066.24 | 6284471.15 | Embankment | 5478066.24 | 0.45355 | 616282.5073 | 4313977.0978
[10 empty] | 315745.97 | Khal | 6600217.12 | 0.54645 | 742524.4927 | 5197670.9022
[8 empty] | Total | 5478066.24 | 6600217.12 |  |  | 1 | 1358807 | 9511648
[8 empty] | GT |  | 12078283.36
Kish-22 2nd IPC
[9 empty] | Embankment | Khal |  |  | DF | GoB | RPA
[9 empty] | 5478066.24 | 6284471.15 | Embankment | 5478066.24 | 0.45355 | 68476.0357 | 479330.4359
[10 empty] | 315745.97 | Khal | 6600217.12 | 0.54645 | 82502.9643 | 577518.5641
[8 empty] | Total | 5478066.24 | 6600217.12 |  |  | 1 | 150979 | 1056849 | 1207828
[8 empty] | GT |  | 12078283.36
Kis -17 9th RA Bill
[11 empty] | Embankment | 5923319.27
[11 empty] | Block Road | 317931.49
[11 empty] | Total | 6241250.76 |  |  |  | DF | GoB | RPA
[11 empty] | Bagdia Khal Regulator | 1361092.04 |  | Emb | 6241250.76 | 0.33151 | 769465.2938 | 5386258.0511
[11 empty] | Neora Khal Regulator | 0 |  | Reg/Box | 6996164.259 | 0.37161 | 862536.3399 | 6037755.4942
[11 empty] | Pipe Inlet | 5589090.31 |  | Inlet | 5589090.31 | 0.29687 | 689062.3663 | 4823437.4548
[11 empty] | Box Drainage Outlet | 5635072.219 |  |  | 18826505.329 | 1 | 2321064 | 16247451
[11 empty] | Total | 12585254.569
[11 empty] | GT | 18826505.329
[11 empty] | Kish -10 4th RA Bill |  | DF
[11 empty] | EMB | 4734271.736 | 0.52055 | 591783.8037 | 4142488.1874
[11 empty] | Regulator | 4360514.774 | 0.47945 | 545064.1963 | 3815450.8126
[12 empty] | 9094786.51 | 1 | 1136848 | 7957939 | 9094787
[11 empty] | Kish -11 4th RA Bill |  | DF
[11 empty] | EMB | 0 | 0.52055 | 591783.8037 | 4142488.1874
[11 empty] | Regulator | 3214491.54 | 0.47945 | 545064.1963 | 3815450.8126
[13 empty] | 1 | 1136848 | 7957939 | 9094787
[11 empty] | Kish -25 5th RA Bill |  |  |  | DF | GoB | RPA
[11 empty] | Khal | 5702443.78 | Khal | 5702443.78 | 0.4773 | 712805.5214 | 4989638.1727
[11 empty] | Regulator | 6070081.27 | Regulator | 6244931.4 | 0.5227 | 780616.4786 | 5464314.8273
[11 empty] | Mobilization | 174850.13 |  |  | 1 | 1493422 | 10453953
[11 empty] | Regulator | 6244931.4
11947375.18
[11 empty] | Kish -13 5th RA Bill |  |  |  | DF | GoB | RPA
[11 empty] | Emb | 4129593.08 | Khal | 5702443.78 | 0.4773 | 712805.5214 | 4989638.1727
[11 empty] | Regulator |  | Regulator | 6244931.4 | 0.5227 | 780616.4786 | 5464314.8273
[11 empty] | Mobilization | 174850.13 |  |  | 1 | 1493422 | 10453953
[11 empty] | Regulator | 6244931.4
11947375.18

## Sheet3
|  | EMB | Khal
|  | 17644936.1 | 204301.34
|  | -166123.08 | 98414.79
|  | 4900152.1 | 3557905.85
|  | 286245 | 866744.93
|  | 619378.33 | 161285.36
|  | 23284588.45 | 15775.98
|  | 28737182.92 | 14288.02
|  | 5452594.47 | 53423.24
4972139.51
| Khal | Emb
| 875966.733 | 46900.13
| 906433.664 | 2590080.18
| 1782400.397 | 1949709.13
| 7172327.33 | 1366206.83
| 5389926.933 | 739134.85
379009.28
600581.7
7671622.1
358/Kish-06 13th/Final RA Bill | 5035264.49 |  |  | 1253692.11 | 786119.575 | 5502837.025

## Sheet2
372/Kish-25 7th RA Bill | 2004423.12 | 2200388.38 |  |  | 27775 |  | 529073 | 4232587
363/Kish-24 8th/Final RA Bill |  |  |  |  | 10277493 |  | 1284687 | 8992806
358/Kish-06 13th/Final RA Bill |  | 5035264.49 |  |  |  | 1253692.11 | 786119.575 | 5502837.025
364/Kish-02 7th RA Bill |  | 1360415.54 |  |  | 455742.37 | 1831376.254 | 455942 | 3191592
376/Kish-23 5th RA Bill | 5389926.93 | 1782400.4 |  |  |  |  | 896541 | 6275786
365/Kish-19 6th RA Bill |  |  |  |  | 3499306 |  | 437413 | 3061893
366/Netr-01 6th RA Bill |  |  |  | 20826914 |  |  | 2603364 | 18223550
367/Netr-02 5th RA Bill |  |  | 3669874 |  |  |  | 458734 | 3211140
368/Netr-03 6th RA Bill |  |  |  | 24327546 |  |  | 3040943 | 21286603

## IPC_Dist
Sl No | IPCNo | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | Wmg_Office | Gate_Repair | Total | Gob | Rpa | Package No | IPC No | Month
1 | 75/hobi-06 3rd Bill |  |  | 2821414 | [9 empty] | 394997.96 | 2426416.04 | HOBI-06 | 3 | 10
2 | 124/kish-02 5th Bill |  |  | 663266.62 |  |  |  |  | 855983.51 |  |  |  |  | 230293 | 1414656 | KISH-02 | 5 | 12
3 | 142/kish-09 2nd Bill |  |  | 7908184 | [9 empty] | 1107145 | 6801038.24 | KISH-09 | 2 | 12
4 | 143/kish-18 3rd Bill |  |  | 3391138.5 | 8657627.44 | [8 empty] | 1686827.24 | 10361938 | KISH-18 | 3 | 12
5 | 149/kish-17 5th Bill | 654830.495 |  | 1764444.173 |  |  |  |  | 5957470.4 |  |  |  |  | 1725298.82 | 10598264.18 | KISH-17 | 5 | 12
6 | 171/kish-12 2nd Bill |  |  | 9832217.68 | 5030725.98 | [8 empty] | 2727631.34 | 16755449.66 | KISH-12 | 2 | 1
7 | 174/hobi-02 1st Bill | [7 empty] | 21355835 |  |  |  |  | 3010816.9 | 18495018.1 | HOBI-02 | 1 | 1
8 | 182/kish-18 4th Bill |  |  | 3103589.69 | 8782672.1 | [8 empty] | 1530743.06 | 9403135.94 | KISH-18 | 4 | 1
9 | 196/kish-25 1st Bill |  |  | 9825070 | [9 empty] | 1375509.8 | 8449560.2 | KISH-25 | 1 | 1
10 | 197(/Sunm-1)-04 1st Bill | [7 empty] | 50574985.8 |  |  |  |  | 7210009.52 | 44290058.48 | SUNM-04 | 1 | 1
11 | 199/kish-06 7 th Bill |  |  | 4766083.62 | 1203653.29 | [8 empty] | 776065.81 | 5193671.19 | KISH-06 | 7 | 1
12 | 203/hobi-01 1st Bill | [6 empty] | 22578857.2 | [5 empty] | 3227703.22 | 19827319.78 | HOBI-01 | 1 | 2
13 | 209/hobi-06 4th Bill |  |  | 16525157 | [9 empty] | 2432171.98 | 14940485.02 | KISH-06 | 4 | 2
14 | 215/kish-16 6th Bill | [7 empty] | 5353824.14 |  |  |  |  | 749535.36 | 4604288.64 | KISH-16 | 6 | 2
15 | 214/kish-19 2nd Bill |  |  |  | 7212480 | [8 empty] | 1009747.2 | 6202732.8 | KISH-19 | 2 | 2
16 | 223/netr-2 1st Bill |  |  |  |  | 7994231.791 | [7 empty] | 1128992.48 | 6935239.52 | NETR-02 | 1 | 2
17 | 225/hobi-02 2nd Bill | [6 empty] | 20423243 | [5 empty] | 2859254.02 | 17563988.98 | HOBI-02 | 2 | 2
18 | 226/hobi-04 3rd Bill | [7 empty] | 11032342 |  |  |  |  | 1544527.88 | 9487814.12 | HOBI-04 | 3 | 2
19 | 233/kish-15 3rd Bill | [7 empty] | 5159158.9 |  |  |  |  | 928648.52 | 4230510.38 | KISH-15 | 3 | 2
20 | 235(/Sunm-1)-04 2nd Bill | [7 empty] | 36727928 |  |  |  |  | 5141909.92 | 31586018 | SUNM-04 | 2 | 2
21 | 234(/Sunm-1)-06 1st Bill |  |  | 23143511 | [9 empty] | 3254296.92 | 19990681.08 | SUNM-06 | 1 | 2
22 | 232/kish-18 5th Bill |  |  |  | 16844694 | [8 empty] | 2358257 | 14486436 | KISH-18 | 5 | 2
23 | 236/kish-12 3th Bill |  |  | 7363341 | 2935665.5 | [8 empty] | 1458117.64 | 8957008.36 | KISH-12 | 3 | 2
24 | 237(Sunm-2)-01 1st Bill | [7 empty] | 14437096 |  |  |  |  | 2108632.82 | 12953030 | SUNM-01 | 1 | 2
25 | 238/kish-20 2nd Bill |  |  | 21019787.43 | [9 empty] | 3006151.4 | 18466358.6 | KISH-20 | 2 | 2
26 | 246/kish-17 6th Bill | [7 empty] | 15753462 |  |  |  |  | 2205484.68 | 13547977.32 | KISH-17 | 6 | 2
27 | 253/Netr-6 1st Bill |  |  |  | 2017067 | [8 empty] | 282389.38 | 1734677.62 | NETR-06 | 1 | 2
28 | 254/Netr-4 1st Bill |  |  |  | 19766138 | [8 empty] | 3755566.22 | 16010571.78 | NETR-04 | 1 | 2
29 | 257/kish-09 3th Bill |  |  | 12158123 | [9 empty] | 1580555.99 | 10577567.01 | KISH-09 | 3 | 2
30 | 265/kish-06 8th Bill |  |  | 2366092 | [9 empty] | 309991.96 | 2056100.04 | KISH-06 | 8 | 2
31 | 266/kish-26 3th Bill |  |  |  | 7400966 | [8 empty] | 962126 | 6438840 | KISH-26 | 3 | 3
32 | 267/Netr-1 2nd Bill | [5 empty] | 24987347 | [6 empty] | 3498228.58 | 21489118.42 | NETR-01 | 2 | 3
33 | 269/kish-19 3th Bill |  |  |  | 7803383 | [8 empty] | 1093173.62 | 6715209.38 | KISH-19 | 3 | 3
34 | 275(Sunm-1)-06 2nd Bill |  |  | 22263325 | [9 empty] | 3116865.5 | 19146459.5 | SUNM-06 | 2 | 3
35 | 272/kish-07 7th Bill |  |  |  | 5347170 | [8 empty] | 695132.1 | 4652037.9 | KISH-07 | 7 | 3
36 | 276/kish-12 4th Bill |  |  |  | 6516132 | [8 empty] | 912258.48 | 5603873.52 | KISH-12 | 4 | 3
37 | 279/Hobi-06 5th Bill |  |  | 34492037 | [9 empty] | 4972035.18 | 30542501.82 | HOBI-06 | 5 | 3
38 | 273/Hobi-05 1st Bill |  |  | 5197170 | [9 empty] | 695132.1 | 4652037.9 | HOBI-05 | 1 | 3
39 | 277/Hobi-01 2nd Bill |  |  |  |  | 33925772 | [7 empty] | 4781808.08 | 29373963.92 | HOBI-01 | 2 | 3
40 | 274/Netr-2 2nd Bill |  |  |  |  | 15079860 | [7 empty] | 2111180.4 | 12968679.6 | NETR-02 | 2 | 3
41 | 280/kish-18 6th Bill |  |  | 4552593.85 | 2907886.21 | [8 empty] | 953825.4625 | 6180789.24 | KISH-18 | 6 | 3
42 | 288(Sunm-1)-03 1st Bill |  |  | 26816203.76 | [9 empty] | 3754312.24 | 23062203.76 | SUNM-03 | 1 | 3
43 | 289/Netr-6 2nd Bill |  |  |  | 11969055 | [8 empty] | 1675667.7 | 10293387.3 | NETR-06 | 2 | 4
44 | 298/kish-06 9th Bill |  |  | 2292340 | [9 empty] | 298004.2 | 1994335.8 | KISH-06 | 9 | 4
45 | 299/kish-16 7th Bill | [7 empty] | 3478937 |  |  |  |  | 487051.18 | 2991885.82 | KISH-16 | 7 | 4
46 | 307/kish-25 2nd Bill |  |  | 15241072.86 | 6925871.8 | [8 empty] | 3212163.22 | 19731859.78 | KISH-25 | 2 | 4
47 | 312(Sunm-1)-06 3rd Bill |  |  | 10168500 | [9 empty] | 1423590 | 8744910 | SUNM-06 | 3 | 4
48 | 313(Sunm-1)-04 3rd Bill | [7 empty] | 15531785 |  |  |  |  | 2174449.9 | 13357335.1 | SUNM-04 | 3 | 4
49 | 312(Sunm-1)-01 2nd Bill |  |  |  | 17378179.19 |  |  |  | 12267921.66 |  |  |  |  | 4186325.78 | 25716001.22 | SUNM-01 | 2 | 4
50 | 311/Netr-3 1st Bill | [6 empty] | 14683526 | [5 empty] | 2083693.64 | 12799832.36 | NETR-03 | 1 | 4
51 | 325/kish-26 4th Bill |  |  |  | 3264155 | [8 empty] | 437340.15 | 2926814.85 | KISH-26 | 4 | 5
52 | 326/kish-12 5th Bill |  |  | 6038020.19 | 350222.81 | [8 empty] | 894354.02 | 5493888.98 | KISH-12 | 5 | 5
53 | 327/kish-19 4th Bill |  |  |  | 3574390 | [8 empty] | 500414.6 | 3073975.4 | KISH-19 | 4 | 5
54 | 351/Netr-04 2nd Bill |  |  |  |  | 14918906 | [7 empty] | 2088646.84 | 12830259.16 | NETR-04 | 2 | 5
55 | 352/kish-18 7th Bill |  |  | 3809899.07 | 5431835.93 | [8 empty] | 1293842.9 | 7947892 | KISH-18 | 7 | 5
56 | 366/kish-25 3rd Bill |  |  | 5853043.08 | 5592440.87 | [8 empty] | 1602367.76 | 9843116.24 | KISH-25 | 3 | 5
57 | 361/Netr-6 3rd Bill |  |  |  | 9057764 | [8 empty] | 1268086.96 | 7789677.04 | NETR-06 | 3 | 5
58 | 362/kish-12 6th Bill |  |  | 1929546.15 | 1982473.85 | [8 empty] | 547682.8 | 3364337.2 | KISH-12 | 6 | 5
59 | 365/Netr-7 3rd Bill |  |  |  | 14870448 | [8 empty] | 123862.72 | 13046585.28 | NETR-07 | 3 | 5
60 | 367/kish-17 7th Bill | 1581058 |  | 11403081 | [9 empty] | 1817779.46 | 11166359.54 | KISH-17 | 7 | 5
61 | 363/Hobi-06 6th Bill |  |  | 24452184 | [9 empty] | 3577306.76 | 21974878.24 | HOBI-06 | 6 | 5
62 | 360/Netr-03 2nd Bill |  |  |  |  | 10190150 | [7 empty] | 1426261 | 8763529 | NETR-03 | 2 | 5
63 | 364(Sunm-2)-02 1st Bill |  |  |  | 14674324 | [8 empty] | 2101471.96 | 12909042.04 | SUNM-02 | 1 | 5
65 | 368/hobi-05 2nd Bill |  |  |  | 6575000 | [8 empty] | 920500 | 5654500 | HOBI-05 | 2 | 5
66 | 370/kish-09 4th Bill |  |  | 5946562.77 | [9 empty] | 756830 | 5673258 | KISH-09 | 4 | 6
67 | 379/hobi-01 3rd Bill | [6 empty] | 8404669 | [5 empty] | 1176653.66 | 7228015.34 | HOBI-01 | 3 | 6
68 | 380/hobi-05 2nd Bill |  |  | 1642962 | [9 empty] | 230014.68 | 1412947.32 | HOBI-05 | 2 | 6
69 | 383/kish-06 10th Bill |  |  | 2757459 | [9 empty] | 358469.67 | 2398989.33 | HOBI-06 | 10 | 6
70 | 415/kish-07 8th Bill | [7 empty] | 4689243 |  |  |  |  | 609601.59 | 4079641.41 | KISH-07 | 8 | 6
71 | 416/hobi-01 4th Bill | [6 empty] | 6240271 | [5 empty] | 873637.94 | 5366633.06 | HOBI-01 | 4 | 6
72 | 419(Sunm-2)-06 4th Bill |  |  | 13101081 | [9 empty] | 1834151.34 | 11266929.66 | SUNM-06 | 4 | 6
73 | 420/hobi-02 2nd Bill | [6 empty] | 16716505 | [5 empty] | 2340310.7 | 14376194.3 | HOBI-02 | 2 | 6
74 | 423/Netr-02 3rd Bill |  |  |  |  | 11023612.63 | [7 empty] | 1568890.82 | 9637472.1 | NETR-02 | 3 | 6
75 | 422/Netr-07 4th Bill |  |  |  | 3705998 | [8 empty] | 518839.72 | 3187158.28 | NETR-07 | 4 | 6
76 | 424/Netr-04 3rd Bill |  |  |  |  | 14995121.96 | [7 empty] | 2167640 | 13315506 | NETR-04 | 4 | 6
77 | 425/hobi-04 4th Bill | [7 empty] | 4342523.94 |  |  |  |  | 676010.2 | 4152632.68 | HOBI-04 | 4 | 6
78 | 426/kish-04 5th Bill | 366417.97 | [6 empty] | 3872617.9 |  |  |  |  | 597982.7 | 3673322.3 | KISH-04 | 5 | 6
79 | 430/kish-06 11th Bill |  |  | 3995166 | [9 empty] | 519371.58 | 3475794 | KISH-06 | 11 | 6
80 | 477/kish-05 4th Bill |  |  | 8495777.032 |  |  |  |  | 4715931.82 |  |  |  |  | 1650964.12 | 11048759.88 | KISH-05 | 5 | 6
81 | 470(Sunm-1)-03 2nd Bill |  |  | 4436884 | [9 empty] | 621163.76 | 3815720.24 | SUNM-03 | 2 | 6
82 | 476/kish-20 3rd Bill | 491243.985 |  | 19959771.015 | [9 empty] | 2863142.1 | 17587872.9 | KISH-20 | 3 | 6
83 | 431(Sunm-2)-01 3rd Bill | 13597054.679 | [6 empty] | 3250310.77 |  |  |  |  | 2358631.1 | 14488733.9 | SUNM-01 | 3 | 6
84 | 474/Netr-01 3rd Bill | [5 empty] | 11681236 | [6 empty] | 1635373.04 | 10045862.96 | NETR-01 | 3 | 6
85 | 478/Netr-03 3rd Bill | [6 empty] | 3836480 | [5 empty] | 537107.2 | 3299372.8 | NETR-03 | 3 | 6
86 | 435/kish-14 7th Bill |  |  | 10766653.29 |  |  |  |  | 5035726.724 |  |  |  |  | 2212333.2 | 13590046.8 | KISH-14 | 7 | 6
87 | 471/kish-28 4th Bill | [9 empty] | 4209533 |  |  | 547239.29 | 3662293.71 | KISH-28/Lot-1 | 4 | 6
88 | 461/kish-25 4th Bill |  |  | 1092242.61 | 6565980.71 | [8 empty] | 1072151.22 | 6586071.78 | KISH-25 | 4 | 6
89 | 450/kish-26 5th Bill |  |  |  | 2772925 | [8 empty] | 360480.25 | 2412444.75 | KISH-25 | 5 | 6
90 | 479/kish-2 6th Bill |  |  | 1865950.84 | 1241270.59 |  |  |  | 22426.7 |  |  |  |  | 427536.34 | 2626294.66 | KISH-26 | 6 | 6
91 | 475/kish-15 5th Bill | [7 empty] | 5676932 |  |  |  |  | 738001.16 | 4938930.84 | KISH-15 | 5 | 6
92 | 473/kish-16 8th Bill |  |  | 120705.26 |  |  |  |  | 116300.225 |  |  |  |  | 274463.7 | 1685991.3 | KISH-16 | 8 | 6
93 | 469/kish-19 5th Bill |  |  |  | 7385702.57 | [8 empty] | 1101691.92 | 6767536.08 | KISH-19 | 5 | 6
94 | 472/kish-17 8th Bill | 795781.3 |  | 1039759.708 |  |  |  |  | 5168075.669 |  |  |  |  | 980506.38 | 6023110.62 | KISH-17 | 8 | 6

## Mobilization_Dist
Sl No | IPCNo | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | Wmg_Office | Gate_Repair | Total | Gob | Rpa | Package No | IPC No | Month
1 | 75/hobi-06 3rd Bill |  |  | 2821414 | [8 empty] | 0 | 0 | 0 | HOBI-06 | 3 | 10
2 | 124/kish-02 5th Bill |  |  | 788965.62 |  |  |  |  | 855983.51 |  |  |  | 125699 | 17597.86 | 108101.14 | KISH-02 | 5 | 12
3 | 142/kish-09 2nd Bill |  |  | 7908184 | [8 empty] | 0 | 0 | 0 | KISH-09 | 2 | 12
4 | 143/kish-18 3rd Bill |  |  | 3391138.5 | 8657627.44 | [7 empty] | 0 | 0 | 0 | KISH-18 | 3 | 12
5 | 149/kish-17 5th Bill | 654830.495 |  | 1764444.173 |  |  |  |  | 5957470.4 |  |  |  | 0 | 0 | 0 | KISH-17 | 5 | 12
6 | 171/kish-12 2nd Bill |  |  | 9832217.68 | 5030725.98 | [7 empty] | 0 | 0 | 0 | KISH-12 | 2 | 1
7 | 174/hobi-02 1st Bill |  |  |  |  | 21505835 | [6 empty] | 150000 | 21000 | 129000 | HOBI-02 | 1 | 1
8 | 182/kish-18 4th Bill |  |  | 3103589.69 | 8782672.1 | [7 empty] | 0 | 0 | 0 | KISH-18 | 4 | 1
9 | 196/kish-25 1st Bill |  |  | 9825070 | [8 empty] | 0 | 0 | 0 | KISH-25 | 1 | 1
10 | 197(/Sunm-1)-04 1st Bill | [7 empty] | 51500068 |  |  |  | 925082.2 | 129511.508 | 795570.692 | SUNM-04 | 1 | 1
11 | 199/kish-06 7 th Bill |  |  | 4766083.62 | 1203653.29 | [7 empty] | 0 | 0 | 0 | KISH-06 | 7 | 1
12 | 203/hobi-01 1st Bill | [5 empty] | 23055022.97 | [5 empty] | 476165.12 | 66663.1168 | 409502.0032 | HOBI-01 | 1 | 2
13 | 209/hobi-06 4th Bill |  |  | 17372657 | [8 empty] | 847500 | 118650 | 728850 | KISH-06 | 4 | 2
14 | 215/kish-16 6th Bill | [7 empty] | 5353824.14 |  |  |  | 0 | 0 | 0 | KISH-16 | 6 | 2
15 | 214/kish-19 2nd Bill |  |  |  | 7212480 | [7 empty] | 0 | 0 | 0 | KISH-19 | 2 | 2
16 | 223/netr-2 1st Bill |  |  |  |  | 8064231.791 | [6 empty] | 70000 | 9800 | 60200 | NETR-02 | 1 | 2
17 | 225/hobi-02 2nd Bill | [6 empty] | 20423243 |  |  |  |  | 0 | 0 | 0 | HOBI-02 | 2 | 2
18 | 226/hobi-04 3rd Bill | [7 empty] | 11032342 |  |  |  | 0 | 0 | 0 | HOBI-04 | 3 | 2
19 | 233/kish-15 3rd Bill | [7 empty] | 5159158.9 |  |  |  | 0 | 0 | 0 | KISH-15 | 3 | 2
20 | 235(/Sunm-1)-04 2nd Bill | [7 empty] | 36727928 |  |  |  | 0 | 0 | 0 | SUNM-04 | 2 | 2
21 | 234(/Sunm-1)-06 1st Bill |  |  | 23244978 | [8 empty] | 101467 | 14205.38 | 87261.62 | SUNM-06 | 1 | 2
22 | 232/kish-18 5th Bill |  |  |  | 16844694 | [7 empty] | 0 | 0 | 0 | KISH-18 | 5 | 2
23 | 236/kish-12 3th Bill |  |  | 7363341 | 3051784.77 | [7 empty] | 116119.27 | 16256.6978 | 99862.5722 | KISH-12 | 3 | 2
24 | 237(Sunm-2)-01 1st Bill | [7 empty] | 15061663 |  |  |  | 624567 | 87439.38 | 537127.62 | SUNM-01 | 1 | 2
25 | 238/kish-20 2nd Bill |  |  | 21472510 | [8 empty] | 452722.57 | 63381.1598 | 389341.4102 | KISH-20 | 2 | 2
26 | 246/kish-17 6th Bill | [7 empty] | 15753462 |  |  |  | 0 | 0 | 0 | KISH-17 | 6 | 2
27 | 253/Netr-6 1st Bill |  |  |  | 2017067 | [7 empty] | 0 | 0 | 0 | NETR-06 | 1 | 2
28 | 254/Netr-4 1st Bill |  |  |  | 19766138 | [7 empty] | 0 | 0 | 0 | NETR-04 | 1 | 2
29 | 257/kish-09 3th Bill |  |  | 12158123 | [8 empty] | 0 | 0 | 0 | KISH-09 | 3 | 2
30 | 265/kish-06 8th Bill |  |  | 2366092 | [8 empty] | 0 | 0 | 0 | KISH-06 | 8 | 2
31 | 266/kish-26 3th Bill |  |  |  | 7400966 | [7 empty] | 0 | 0 | 0 | KISH-26 | 3 | 3
32 | 267/Netr-1 2nd Bill | [5 empty] | 24987347 | [5 empty] | 0 | 0 | 0 | NETR-01 | 2 | 3
33 | 269/kish-19 3th Bill |  |  |  | 7803383 | [7 empty] | 0 | 0 | 0 | KISH-19 | 3 | 3
34 | 275(Sunm-1)-06 2nd Bill |  |  | 22263325 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 2 | 3
35 | 272/kish-07 7th Bill |  |  |  | 5347170 | [7 empty] | 0 | 0 | 0 | KISH-07 | 7 | 3
36 | 276/kish-12 4th Bill |  |  |  | 6516132 | [7 empty] | 0 | 0 | 0 | KISH-12 | 4 | 3
37 | 279/Hobi-06 5th Bill |  |  | 35514537 | [8 empty] | 1022500 | 143150 | 879350 | HOBI-06 | 5 | 3
38 | 273/Hobi-05 1st Bill |  |  | 5347170 | [8 empty] | 150000 | 21000 | 129000 | HOBI-05 | 1 | 3
39 | 277/Hobi-01 2nd Bill | [6 empty] | 34155772 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 2 | 3
40 | 274/Netr-2 2nd Bill |  |  |  |  | 15079860 | [6 empty] | 230000 | 32200 | 197800 | NETR-02 | 2 | 3
41 | 280/kish-18 6th Bill |  |  | 4552593.85 | 3078009.85 | [7 empty] | 170123.64 | 23817.3096 | 146306.3304 | KISH-18 | 6 | 3
42 | 288(Sunm-1)-03 1st Bill |  |  | 26816203.76 | [8 empty] | 0 | 0 | 0 | SUNM-03 | 1 | 3
43 | 289/Netr-6 2nd Bill |  |  |  | 11969055 | [7 empty] | 0 | 0 | 0 | NETR-06 | 2 | 4
44 | 298/kish-06 9th Bill |  |  | 2292340 | [8 empty] | 0 | 0 | 0 | KISH-06 | 9 | 4
45 | 299/kish-16 7th Bill | [7 empty] | 3478937 |  |  |  | 0 | 0 | 0 | KISH-16 | 7 | 4
46 | 307/kish-25 2nd Bill |  |  | 15241072.86 | 7702950.48 | [7 empty] | 777078.66 | 108791.0124 | 668287.6476 | KISH-25 | 2 | 4
47 | 312(Sunm-1)-06 3rd Bill |  |  | 10168500 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 3 | 4
48 | 313(Sunm-1)-04 3rd Bill | [7 empty] | 15531785 |  |  |  | 0 | 0 | 0 | SUNM-04 | 3 | 4
49 | 312(Sunm-1)-01 2nd Bill |  |  |  | 17634405.79 |  |  |  | 12267921.66 |  |  |  | 256226 | 35871.64 | 220354.36 | SUNM-01 | 2 | 4
50 | 311/Netr-3 1st Bill | [6 empty] | 14883526 |  |  |  |  | 200000 | 28000 | 172000 | NETR-03 | 1 | 4
51 | 325/kish-26 4th Bill |  |  |  | 3264155 | [7 empty] | 0 | 0 | 0 | KISH-26 | 4 | 5
52 | 326/kish-12 5th Bill |  |  | 6038020.19 | 350222.81 | [7 empty] | 0 | 0 | 0 | KISH-12 | 5 | 5
53 | 327/kish-19 4th Bill |  |  |  | 3574390 | [7 empty] | 0 | 0 | 0 | KISH-19 | 4 | 5
54 | 351/Netr-04 2nd Bill |  |  |  |  | 14918906 | [6 empty] | 0 | 0 | 0 | NETR-04 | 2 | 5
55 | 352/kish-18 7th Bill |  |  | 3809899.07 | 5431835.93 | [7 empty] | 0 | 0 | 0 | KISH-18 | 7 | 5
56 | 366/kish-25 3rd Bill |  |  | 5853043.08 | 5592440.87 | [7 empty] | 0 | 0 | 0 | KISH-25 | 3 | 5
57 | 361/Netr-6 3rd Bill |  |  |  | 9057764 | [7 empty] | 0 | 0 | 0 | NETR-06 | 3 | 5
58 | 362/kish-12 6th Bill |  |  | 1929546.15 | 1982473.85 | [7 empty] | 0 | 0 | 0 | KISH-12 | 6 | 5
59 | 365/Netr-7 3rd Bill |  |  |  | 15170448 | [7 empty] | 300000 | 42000 | 258000 | NETR-07 | 3 | 5
60 | 367/kish-17 7th Bill | 1581058 |  | 11403081 | [8 empty] | 0 | 0 | 0 | KISH-17 | 7 | 5
61 | 363/Hobi-06 6th Bill |  |  | 25552184 | [8 empty] | 1100000 | 154000 | 946000 | HOBI-06 | 6 | 5
62 | 360/Netr-03 2nd Bill |  |  |  |  | 10190150 | [6 empty] | 0 | 0 | 0 | NETR-03 | 2 | 5
63 | 364(Sunm-2)-02 1st Bill |  |  |  | 15010514 | [7 empty] | 336190 | 47066.6 | 289123.4 | SUNM-02 | 1 | 5
65 | 368/hobi-05 2nd Bill |  |  |  | 6575000 | [7 empty] | 0 | 0 | 0 | HOBI-05 | 2 | 5
66 | 370/kish-09 4th Bill |  |  | 6430088 | [8 empty] | 483525.23 | 67693.5322 | 415831.6978 | KISH-09 | 4 | 6
67 | 379/hobi-01 3rd Bill | [6 empty] | 8404669 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 3 | 6
68 | 380/hobi-05 2nd Bill |  |  | 1642962 | [8 empty] | 0 | 0 | 0 | HOBI-05 | 2 | 6
69 | 383/kish-06 10th Bill |  |  | 2757459 | [8 empty] | 0 | 0 | 0 | HOBI-06 | 10 | 6
70 | 415/kish-07 8th Bill | [7 empty] | 4689243 |  |  |  | 0 | 0 | 0 | KISH-07 | 8 | 6
71 | 416/hobi-01 4th Bill | [6 empty] | 6240271 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 4 | 6
72 | 419(Sunm-2)-06 4th Bill |  |  | 13101081 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 4 | 6
73 | 420/hobi-02 2nd Bill | [6 empty] | 16716505 |  |  |  |  | 0 | 0 | 0 | HOBI-02 | 2 | 6
74 | 423/Netr-02 3rd Bill |  |  |  |  | 11206363 | [6 empty] | 182750.37 | 25585.0518 | 157165.3182 | NETR-02 | 3 | 6
75 | 422/Netr-07 4th Bill |  |  |  | 3705998 | [7 empty] | 0 | 0 | 0 | NETR-07 | 4 | 6
77 | 425/hobi-04 4th Bill | [6 empty] | 4828643 |  |  |  |  | 486119.06 | 68056.6684 | 418062.3916 | HOBI-04 | 4 | 6
78 | 426/kish-04 5th Bill | 366417.97 | [5 empty] | 3904887.04 |  |  |  |  | 32269.14 | 4517.6796 | 27751.4604 | KISH-04 | 5 | 6
79 | 430/kish-06 11th Bill |  |  | 3995166 | [8 empty] | 0 | 0 | 0 | KISH-06 | 11 | 6
80 | 477/kish-05 4th Bill |  |  | 8736715.472 |  |  |  |  | 4715931.82 |  |  |  | 240938.44 | 33731.3816 | 207207.0584 | KISH-05 | 5 | 6
81 | 470(Sunm-1)-03 2nd Bill |  |  | 4436884 | [8 empty] | 0 | 0 | 0 | SUNM-03 | 2 | 6
82 | 476/kish-20 3rd Bill | 491243.985 |  | 19959771.015 | [8 empty] | 0 | 0 | 0 | KISH-20 | 3 | 6
83 | 431(Sunm-2)-01 3rd Bill | 13597054.679 | [6 empty] | 3250310.77 |  |  |  | 0 | 0 | 0 | SUNM-01 | 3 | 6
84 | 474/Netr-01 3rd Bill | [5 empty] | 11681236 | [5 empty] | 0 | 0 | 0 | NETR-01 | 3 | 6
85 | 478/Netr-03 3rd Bill | [6 empty] | 3836480 |  |  |  |  | 0 | 0 | 0 | NETR-03 | 3 | 6
86 | 435/kish-14 7th Bill |  |  | 10766653.29 |  |  |  |  | 5035726.724 |  |  |  | 0 | 0 | 0 | KISH-14 | 7 | 6
87 | 471/kish-28 4th Bill | [9 empty] | 4209533 |  | 0 | 0 | 0 | KISH-28/Lot-1 | 4 | 6
88 | 461/kish-25 4th Bill |  |  | 1092242.61 | 6565980.71 | [7 empty] | 0 | 0 | 0 | KISH-25 | 4 | 6
89 | 450/kish-26 5th Bill |  |  |  | 2772925 | [7 empty] | 0 | 0 | 0 | KISH-25 | 5 | 6
90 | 479/kish-2 6th Bill |  |  | 1865950.84 | 1241270.59 |  |  |  | 22426.7 |  |  |  | 0 | 0 | 0 | KISH-26 | 6 | 6
91 | 475/kish-15 5th Bill | [7 empty] | 5676932 |  |  |  | 0 | 0 | 0 | KISH-15 | 5 | 6
92 | 473/kish-16 8th Bill |  |  | 120705.26 |  |  |  |  | 116300.225 |  |  |  | 0 | 0 | 0 | KISH-16 | 8 | 6
93 | 469/kish-19 5th Bill |  |  |  | 7869228 | [7 empty] | 483525.43 | 67693.5602 | 415831.8698 | KISH-19 | 5 | 6
94 | 472/kish-17 8th Bill | 795781.3 |  | 1039759.708 |  |  |  |  | 5168075.669 |  |  |  | 0 | 0 | 0 | KISH-17 | 8 | 6

## Mobilization_Dist_prep
Sl No | IPCNo | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | Wmg_Office | Gate_Repair | Total | Gob | Rpa | Package No | IPC No | Month
1 | 75/hobi-06 3rd Bill |  |  | 2821414 | [8 empty] | 0 | 0 | 0 | HOBI-06 | 3 | 10
2 | 124/kish-02 5th Bill |  |  | 788965.62 |  |  |  |  | 855983.51 |  |  |  | 125699 | 17597.86 | 108101.14 | KISH-02 | 5 | 12
3 | 142/kish-09 2nd Bill |  |  | 7908184 | [8 empty] | 0 | 0 | 0 | KISH-09 | 2 | 12
4 | 143/kish-18 3rd Bill |  |  | 3391138.5 | 8657627.44 | [7 empty] | 0 | 0 | 0 | KISH-18 | 3 | 12
5 | 149/kish-17 5th Bill | 654830.495 |  | 1764444.173 |  |  |  |  | 5957470.4 |  |  |  | 0 | 0 | 0 | KISH-17 | 5 | 12
6 | 171/kish-12 2nd Bill |  |  | 9832217.68 | 5030725.98 | [7 empty] | 0 | 0 | 0 | KISH-12 | 2 | 1
7 | 174/hobi-02 1st Bill |  |  |  |  | 21505835 | [6 empty] | 150000 | 21000 | 129000 | HOBI-02 | 1 | 1
8 | 182/kish-18 4th Bill |  |  | 3103589.69 | 8782672.1 | [7 empty] | 0 | 0 | 0 | KISH-18 | 4 | 1
9 | 196/kish-25 1st Bill |  |  | 9825070 | [8 empty] | 0 | 0 | 0 | KISH-25 | 1 | 1
10 | 197(/Sunm-1)-04 1st Bill | [7 empty] | 51500068 |  |  |  | 925082.2 | 129511.508 | 795570.692 | SUNM-04 | 1 | 1
11 | 199/kish-06 7 th Bill |  |  | 4766083.62 | 1203653.29 | [7 empty] | 0 | 0 | 0 | KISH-06 | 7 | 1
12 | 203/hobi-01 1st Bill | [5 empty] | 23055022.97 | [5 empty] | 476165.12 | 66663.1168 | 409502.0032 | HOBI-01 | 1 | 2
13 | 209/hobi-06 4th Bill |  |  | 17372657 | [8 empty] | 847500 | 118650 | 728850 | KISH-06 | 4 | 2
14 | 215/kish-16 6th Bill | [7 empty] | 5353824.14 |  |  |  | 0 | 0 | 0 | KISH-16 | 6 | 2
15 | 214/kish-19 2nd Bill |  |  |  | 7212480 | [7 empty] | 0 | 0 | 0 | KISH-19 | 2 | 2
16 | 223/netr-2 1st Bill |  |  |  |  | 8064231.791 | [6 empty] | 70000 | 9800 | 60200 | NETR-02 | 1 | 2
17 | 225/hobi-02 2nd Bill | [6 empty] | 20423243 |  |  |  |  | 0 | 0 | 0 | HOBI-02 | 2 | 2
18 | 226/hobi-04 3rd Bill | [7 empty] | 11032342 |  |  |  | 0 | 0 | 0 | HOBI-04 | 3 | 2
19 | 233/kish-15 3rd Bill | [7 empty] | 5159158.9 |  |  |  | 0 | 0 | 0 | KISH-15 | 3 | 2
20 | 235(/Sunm-1)-04 2nd Bill | [7 empty] | 36727928 |  |  |  | 0 | 0 | 0 | SUNM-04 | 2 | 2
21 | 234(/Sunm-1)-06 1st Bill |  |  | 23244978 | [8 empty] | 101467 | 14205.38 | 87261.62 | SUNM-06 | 1 | 2
22 | 232/kish-18 5th Bill |  |  |  | 16844694 | [7 empty] | 0 | 0 | 0 | KISH-18 | 5 | 2
23 | 236/kish-12 3th Bill |  |  | 7363341 | 3051784.77 | [7 empty] | 116119.27 | 16256.6978 | 99862.5722 | KISH-12 | 3 | 2
24 | 237(Sunm-2)-01 1st Bill | [7 empty] | 15061663 |  |  |  | 624567 | 87439.38 | 537127.62 | SUNM-01 | 1 | 2
25 | 238/kish-20 2nd Bill |  |  | 21472510 | [8 empty] | 452722.57 | 63381.1598 | 389341.4102 | KISH-20 | 2 | 2
26 | 246/kish-17 6th Bill | [7 empty] | 15753462 |  |  |  | 0 | 0 | 0 | KISH-17 | 6 | 2
27 | 253/Netr-6 1st Bill |  |  |  | 2017067 | [7 empty] | 0 | 0 | 0 | NETR-06 | 1 | 2
28 | 254/Netr-4 1st Bill |  |  |  | 19766138 | [7 empty] | 0 | 0 | 0 | NETR-04 | 1 | 2
29 | 257/kish-09 3th Bill |  |  | 12158123 | [8 empty] | 0 | 0 | 0 | KISH-09 | 3 | 2
30 | 265/kish-06 8th Bill |  |  | 2366092 | [8 empty] | 0 | 0 | 0 | KISH-06 | 8 | 2
31 | 266/kish-26 3th Bill |  |  |  | 7400966 | [7 empty] | 0 | 0 | 0 | KISH-26 | 3 | 3
32 | 267/Netr-1 2nd Bill | [5 empty] | 24987347 | [5 empty] | 0 | 0 | 0 | NETR-01 | 2 | 3
33 | 269/kish-19 3th Bill |  |  |  | 7803383 | [7 empty] | 0 | 0 | 0 | KISH-19 | 3 | 3
34 | 275(Sunm-1)-06 2nd Bill |  |  | 22263325 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 2 | 3
35 | 272/kish-07 7th Bill |  |  |  | 5347170 | [7 empty] | 0 | 0 | 0 | KISH-07 | 7 | 3
36 | 276/kish-12 4th Bill |  |  |  | 6516132 | [7 empty] | 0 | 0 | 0 | KISH-12 | 4 | 3
37 | 279/Hobi-06 5th Bill |  |  | 35514537 | [8 empty] | 1022500 | 143150 | 879350 | HOBI-06 | 5 | 3
38 | 273/Hobi-05 1st Bill |  |  | 5347170 | [8 empty] | 150000 | 21000 | 129000 | HOBI-05 | 1 | 3
39 | 277/Hobi-01 2nd Bill | [6 empty] | 34155772 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 2 | 3
40 | 274/Netr-2 2nd Bill |  |  |  |  | 15079860 | [6 empty] | 230000 | 32200 | 197800 | NETR-02 | 2 | 3
41 | 280/kish-18 6th Bill |  |  | 4552593.85 | 3078009.85 | [7 empty] | 170123.64 | 23817.3096 | 146306.3304 | KISH-18 | 6 | 3
42 | 288(Sunm-1)-03 1st Bill |  |  | 26816203.76 | [8 empty] | 0 | 0 | 0 | SUNM-03 | 1 | 3
43 | 289/Netr-6 2nd Bill |  |  |  | 11969055 | [7 empty] | 0 | 0 | 0 | NETR-06 | 2 | 4
44 | 298/kish-06 9th Bill |  |  | 2292340 | [8 empty] | 0 | 0 | 0 | KISH-06 | 9 | 4
45 | 299/kish-16 7th Bill | [7 empty] | 3478937 |  |  |  | 0 | 0 | 0 | KISH-16 | 7 | 4
46 | 307/kish-25 2nd Bill |  |  | 15241072.86 | 7702950.48 | [7 empty] | 777078.66 | 108791.0124 | 668287.6476 | KISH-25 | 2 | 4
47 | 312(Sunm-1)-06 3rd Bill |  |  | 10168500 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 3 | 4
48 | 313(Sunm-1)-04 3rd Bill | [7 empty] | 15531785 |  |  |  | 0 | 0 | 0 | SUNM-04 | 3 | 4
49 | 312(Sunm-1)-01 2nd Bill |  |  |  | 17634405.79 |  |  |  | 12267921.66 |  |  |  | 256226 | 35871.64 | 220354.36 | SUNM-01 | 2 | 4
50 | 311/Netr-3 1st Bill | [6 empty] | 14883526 |  |  |  |  | 200000 | 28000 | 172000 | NETR-03 | 1 | 4
51 | 325/kish-26 4th Bill |  |  |  | 3264155 | [7 empty] | 0 | 0 | 0 | KISH-26 | 4 | 5
52 | 326/kish-12 5th Bill |  |  | 6038020.19 | 350222.81 | [7 empty] | 0 | 0 | 0 | KISH-12 | 5 | 5
53 | 327/kish-19 4th Bill |  |  |  | 3574390 | [7 empty] | 0 | 0 | 0 | KISH-19 | 4 | 5
54 | 351/Netr-04 2nd Bill |  |  |  |  | 14918906 | [6 empty] | 0 | 0 | 0 | NETR-04 | 2 | 5
55 | 352/kish-18 7th Bill |  |  | 3809899.07 | 5431835.93 | [7 empty] | 0 | 0 | 0 | KISH-18 | 7 | 5
56 | 366/kish-25 3rd Bill |  |  | 5853043.08 | 5592440.87 | [7 empty] | 0 | 0 | 0 | KISH-25 | 3 | 5
57 | 361/Netr-6 3rd Bill |  |  |  | 9057764 | [7 empty] | 0 | 0 | 0 | NETR-06 | 3 | 5
58 | 362/kish-12 6th Bill |  |  | 1929546.15 | 1982473.85 | [7 empty] | 0 | 0 | 0 | KISH-12 | 6 | 5
59 | 365/Netr-7 3rd Bill |  |  |  | 15170448 | [7 empty] | 300000 | 42000 | 258000 | NETR-07 | 3 | 5
60 | 367/kish-17 7th Bill | 1581058 |  | 11403081 | [8 empty] | 0 | 0 | 0 | KISH-17 | 7 | 5
61 | 363/Hobi-06 6th Bill |  |  | 25552184 | [8 empty] | 1100000 | 154000 | 946000 | HOBI-06 | 6 | 5
62 | 360/Netr-03 2nd Bill |  |  |  |  | 10190150 | [6 empty] | 0 | 0 | 0 | NETR-03 | 2 | 5
63 | 364(Sunm-2)-02 1st Bill |  |  |  | 15010514 | [7 empty] | 336190 | 47066.6 | 289123.4 | SUNM-02 | 1 | 5
65 | 368/hobi-05 2nd Bill |  |  |  | 6575000 | [7 empty] | 0 | 0 | 0 | HOBI-05 | 2 | 5
66 | 370/kish-09 4th Bill |  |  | 6430088 | [8 empty] | 483525.23 | 67693.5322 | 415831.6978 | KISH-09 | 4 | 6
67 | 379/hobi-01 3rd Bill | [6 empty] | 8404669 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 3 | 6
68 | 380/hobi-05 2nd Bill |  |  | 1642962 | [8 empty] | 0 | 0 | 0 | HOBI-05 | 2 | 6
69 | 383/kish-06 10th Bill |  |  | 2757459 | [8 empty] | 0 | 0 | 0 | HOBI-06 | 10 | 6
70 | 415/kish-07 8th Bill | [7 empty] | 4689243 |  |  |  | 0 | 0 | 0 | KISH-07 | 8 | 6
71 | 416/hobi-01 4th Bill | [6 empty] | 6240271 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 4 | 6
72 | 419(Sunm-2)-06 4th Bill |  |  | 13101081 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 4 | 6
73 | 420/hobi-02 2nd Bill | [6 empty] | 16716505 |  |  |  |  | 0 | 0 | 0 | HOBI-02 | 2 | 6
74 | 423/Netr-02 3rd Bill |  |  |  |  | 11206363 | [6 empty] | 182750.37 | 25585.0518 | 157165.3182 | NETR-02 | 3 | 6
75 | 422/Netr-07 4th Bill |  |  |  | 3705998 | [7 empty] | 0 | 0 | 0 | NETR-07 | 4 | 6
79 | 430/kish-06 11th Bill |  |  | 3995166 | [8 empty] | 0 | 0 | 0 | KISH-06 | 11 | 6
80 | 477/kish-05 4th Bill |  |  | 8736715.472 |  |  |  |  | 4715931.82 |  |  |  | 240938.44 | 33731.3816 | 207207.0584 | KISH-05 | 5 | 6
81 | 470(Sunm-1)-03 2nd Bill |  |  | 4436884 | [8 empty] | 0 | 0 | 0 | SUNM-03 | 2 | 6
82 | 476/kish-20 3rd Bill | 491243.985 |  | 19959771.015 | [8 empty] | 0 | 0 | 0 | KISH-20 | 3 | 6
83 | 431(Sunm-2)-01 3rd Bill | 13597054.679 | [6 empty] | 3250310.77 |  |  |  | 0 | 0 | 0 | SUNM-01 | 3 | 6
84 | 474/Netr-01 3rd Bill | [5 empty] | 11681236 | [5 empty] | 0 | 0 | 0 | NETR-01 | 3 | 6
85 | 478/Netr-03 3rd Bill | [6 empty] | 3836480 |  |  |  |  | 0 | 0 | 0 | NETR-03 | 3 | 6
86 | 435/kish-14 7th Bill |  |  | 10766653.29 |  |  |  |  | 5035726.724 |  |  |  | 0 | 0 | 0 | KISH-14 | 7 | 6
87 | 471/kish-28 4th Bill | [9 empty] | 4209533 |  | 0 | 0 | 0 | KISH-28/Lot-1 | 4 | 6
88 | 461/kish-25 4th Bill |  |  | 1092242.61 | 6565980.71 | [7 empty] | 0 | 0 | 0 | KISH-25 | 4 | 6
89 | 450/kish-26 5th Bill |  |  |  | 2772925 | [7 empty] | 0 | 0 | 0 | KISH-25 | 5 | 6
90 | 479/kish-2 6th Bill |  |  | 1865950.84 | 1241270.59 |  |  |  | 22426.7 |  |  |  | 0 | 0 | 0 | KISH-26 | 6 | 6
91 | 475/kish-15 5th Bill | [7 empty] | 5676932 |  |  |  | 0 | 0 | 0 | KISH-15 | 5 | 6
92 | 473/kish-16 8th Bill |  |  | 120705.26 |  |  |  |  | 116300.225 |  |  |  | 0 | 0 | 0 | KISH-16 | 8 | 6
93 | 469/kish-19 5th Bill |  |  |  | 7869228 | [7 empty] | 483525.43 | 67693.5602 | 415831.8698 | KISH-19 | 5 | 6
94 | 472/kish-17 8th Bill | 795781.3 |  | 1039759.708 |  |  |  |  | 5168075.669 |  |  |  | 0 | 0 | 0 | KISH-17 | 8 | 6
77 | 425/hobi-04 4th Bill | [6 empty] | 4828643 |  |  |  |  | 486119.06 | 68056.6684 | 418062.3916 | HOBI-04 | 4 | 6
78 | 426/kish-04 5th Bill | 366417.97 | [5 empty] | 3904887.04 |  |  |  |  | 32269.14 | 4517.6796 | 27751.4604 | KISH-04 | 5 | 6

## Package_wise_cost
PackageNo | IPC1 | IPC2 | IPC3 | IPC4 | IPC5 | IPC6 | IPC7 | IPC8 | IPC9 | IPC10 | IPC11 | IPC12 | IPC13 | IPC14 | IPC15 | IPC16 | IPC17 | IPC18 | IPC19 | IPC20 | Total
KISH-01
KISH-02
KISH-03
KISH-04
KISH-05
KISH-06
KISH-07
KISH-09
KISH-10
KISH-11
KISH-12
KISH-13
KISH-14
KISH-15
KISH-16
KISH-17
KISH-18
KISH-19
KISH-20
KISH-21
KISH-22
KISH-23
KISH-24
KISH-25
KISH-26
KISH-27
KISH-28/Lot-1
KISH-28/Lot-2
KISH-28/Lot-3
KISH-28/Lot-4
HOBI-01
HOBI-02
HOBI-04
HOBI-05
HOBI-06
HOBI-07
HOBI-08
NETR-01
NETR-02
NETR-03
NETR-04
NETR-05
NETR-06
NETR-07
NETR-08
SUNM-01
SUNM-02
SUNM-03
SUNM-04
SUNM-05
SUNM-06
GT-01
GT-02
GT-03

## Monthly_Rpa
PackageNo | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Inlet
Reg_Rehab_Rehab
Reg_CW_Box
Khal_Riv_New
Khal_Riv_Rehab
Full_Emb_Rehab
Sub_Emb_Rehab
Sub_Emb_Const
Reg_Rehab_New
Wmg_Office
Gate_Repair

## Monthly_Gob
PackageNo | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Inlet
Reg_Rehab_Rehab
Reg_CW_Box
Khal_Riv_New
Khal_Riv_Rehab
Full_Emb_Rehab
Sub_Emb_Rehab
Sub_Emb_Const
Reg_Rehab_New
Wmg_Office
Gate_Repair