## Revised_2nd
8.0 Economic code wise comparison of cost summary between the 1st Revised DPP and proposed 2nd Revised DPP | [27 empty] | (BDT in Lakh)
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3111327 | Overtime Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111338 | Other Allowance |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Supplies and Services
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | 1 Item | 100 | 100 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 1 Item | 2596.27 | 2596.27 |  | 0 | 0 |  |  |  | 1 Item | 2874.35 | 2874.35 |  | 0 | 0 |  |  |  |  | 278.08 | 278.08 |  | 0 | 0
| 3211119 | Postage |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3211115 | Water |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3211113 | Electricity |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3243102 | Gas & Fuel |  | 1 Item | 200 | 200 |  | 0 | 0 |  |  |  | 1 Item | 40 | 40 |  | 0 | 0 |  |  |  |  | -160 | -160 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 170 | 170 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255102 | Printing & Binding |  | 1 Item | 35 | 35 |  | 0 | 0 |  |  |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | -30 | -30 |  | 0 | 0
| 3211127 | Books & Periodicals |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 1 Item | 238.54 | 0 |  | 238.54 | 0 |  |  |  | 1 Item | 119 | 0 |  | 119 | 0 |  |  |  |  | -119.54 | 0 |  | -119.54 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 1 Item | 398.41 | 47.81 |  | 350.6 | 0 |  |  |  | 1 Item | 536.7 | 64.4 |  | 472.3 | 0 |  |  |  |  | 138.29 | 16.59 |  | 121.7 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 1 Item | 2533.34 | 304 |  | 2229.34 | 0 |  |  |  | 1 Item | 3130.1 | 373.9 |  | 2756.2 | 0 |  |  |  |  | 596.76 | 69.9 |  | 526.86 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1 Item | 1321.68 | 158.6 |  | 1163.08 | 0 |  |  |  | 1 Item | 1331.2 | 159.7 |  | 1171.5 | 0 |  |  |  |  | 9.52 | 1.1 |  | 8.42 | 0
| 3211109 | Casual labour/Job worker |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 22 | 22 |  | 0 | 0 |  |  |  |  | 7 | 7 |  | 0 | 0
| 3256103 | Consumable Stores |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 71+234 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM | 56+532 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM |  | 0 | 0 |  | 0 | 0
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 30 | 30 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3257104 | Survey |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255101 | Computer Consumables |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  | 1 Item | 60 | 60 |  | 0 | 0 |  |  |  |  | 10 | 10 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Repair, Maintenance & Rehabilitation
| 3258101 | Motor Vehicles |  | L.S. | 100 | 100 |  | 0 | 0 |  |  |  | L.S. | 125 | 125 |  | 0 | 0 |  |  |  |  | 25 | 25 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258103 | Computers & office equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -15 | -15 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3258105 | Engineering Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) |  | 104 | 362.5 | 43.5 |  | 319 | 0 |  |  |  | 86 | 405.55 | 56.777 |  | 348.773 | 0 |  |  |  |  | 43.05 | 13.277 |  | 29.773 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  | L.S. | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
Sub-total : (a) Revenue Component: |  |  |  |  | 18774.14 | 6572.18 |  | 4300.56 | 7901.4 |  |  |  |  | 19562.3 | 6793.127 |  | 4867.773 | 7901.4 |  |  |  |  | 788.16 | 220.947 |  | 567.213 | 0
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos | 35 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos | 45 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos | 6 | 100 | 100 |  | 0 | 0 |  |  | Nos | 5 | 90 | 90 |  | 0 | 0 |  |  | Nos |  | -10 | -10 |  | 0 | 0
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos | 7 | 5 | 5 |  | 0 | 0 |  |  | Nos | 2 | 1 | 1 |  | 0 | 0 |  |  | Nos |  | -4 | -4 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos | 6 | 6 | 6 |  | 0 | 0 |  |  | Nos | 3 | 3 | 3 |  | 0 | 0 |  |  | Nos |  | -3 | -3 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos | 30 | 19.5 | 19.5 |  | 0 | 0 |  |  | Nos | 37 | 24.5 | 24.5 |  | 0 | 0 |  |  | Nos |  | 5 | 5 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 11 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos | 11 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos | 11 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos | 17 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | LS | 50 | 50 |  | 0 | 0 |  |  |  | LS | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 4112303 | Aircooler | Nos | 15 | 15 | 15 |  | 0 | 0 |  |  | Nos | 15 | 15 | 15 | 1054.22 | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Ori |  |  | Pro |  | Diff
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | ha | 470 | 24000 | 24000 |  | 0 | 0 |  |  | ha | 470 | 18386.72 | 18386.72 |  | 0 | 0 |  |  | ha |  | -5613.28 | -5613.28 |  | 0 | 0 |  |  |  | #REF! | #REF! | #REF! | 50 | 371 | 421 | #REF!
Construction and Works:
|  | Irrigation Infrastructures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos | 131 | 1261 | 151.32 |  | 1109.68 | 0 |  |  | Nos | 119 | 1220.46 | 170.8644 |  | 1049.5956 | 0 |  |  | Nos | 12 | -40.54 | 19.5444 |  | -60.0844 | 0
|  | Drainage Structures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos | 7(2+5) | 1515 | 181.8 |  | 1333.2 | 0 |  |  | Nos | 5 | 1172.62 | 164.1668 |  | 1008.4532 | 0 |  |  | Nos | 2 | -342.38 | -17.6332 |  | -324.7468 | 0 |  |  | #DIV/0! | 978.5 | 18871.5 | 19850 | 3398 | 24917 | 28315 | 8465
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos | 137(57+35+14) | 20311 | 2437.32 |  | 17873.68 | 0 |  |  | Nos | 111 | 18421.37 | 2578.9918 |  | 15842.3782 | 0 |  |  | Nos | 26 | -1889.63 | 141.6718 |  | -2031.3018 | 0 |  |  | #DIV/0! | 131 | 2528 | 2659 | 455 | 3337 | 3792 | 1133
| 4111307 | Re-excavation of Khal/River (New Haors) | Km | 318 | 9729 | 1167.48 |  | 8561.52 | 0 |  |  | Km | 336.214 | 10184.13 | 1425.7782 |  | 8758.3518 | 0 |  |  | Km | -18.214 | 455.13 | 258.2982 |  | 196.8318 | 0 |  |  | #REF!
|  | Others | [27 empty] | #DIV/0! | 18 | 360 | 378 | 65 | 475.36 | 540.36 | 162.36
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | Km | 143 | 2515 | 301.8 |  | 2213.2 | 0 |  |  | Km | 108.974 | 3398.89 | 475.8446 |  | 2923.0454 | 0 |  |  | Km | 34.026 | 883.89 | 174.0446 |  | 709.8454 | 0 |  |  | #DIV/0! | 3 | 60 | 63 | 11 | 80 | 91 | 28
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | Km | 84.31 | 2550 | 306 |  | 2244 | 0 |  |  | Km | 67.11 | 2035.43 | 284.9602 |  | 1750.4698 | 0 |  |  | Km | 17.2 | -514.57 | -21.0398 |  | -493.5302 | 0 |  |  | #DIV/0! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | Km | 87.03 | 1785 | 214.2 |  | 1570.8 | 0 |  |  | Km | 62.662 | 1748.43 | 244.7802 |  | 1503.6498 | 0 |  |  | Km | 24.368 | -36.57 | 30.5802 |  | -67.1502 | 0 |  |  | #DIV/0!
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 261.238 | 21445.23 | 9315.3802 |  | 12129.8498 | 0 |  |  | Km | 2.002 | 9492.73 | 7881.0802 |  | 1611.6498 | 0 |  |  | #REF!
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos | 8 | 166 | 19.92 |  | 146.08 | 0 |  |  | Nos | 7 | 146.69 | 20.5366 |  | 126.1534 | 0 |  |  | Nos | 1 | -19.31 | 0.6166 |  | -19.9266 | 0 |  |  | #REF! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
| 4111201 | Threshing Floor Construction | Nos |  | 0 | 0 |  | 0 | 0 |  |  | Nos | 5 | 225 | 31.5 |  | 193.5 | 0 |  |  | Nos | -5 | 225 | 31.5 |  | 193.5 | 0
| 4111201 | Construction of WMG Office | Nos | 60 | 1380 | 165.6 |  | 1214.4 | 0 |  |  | Nos | 55 | 1618 | 226.52 |  | 1391.48 | 0 |  |  | Nos | 5 | 238 | 60.92 |  | 177.08 | 0 |  |  |  | 726.6 | 14031.95 | 14758.55 | 2526 | 18527 | 21053 | 6294.45
| 4111201 | O&M During Construction | Iten | L.S | 200 | 200 |  | 0 | 0 |  |  | Iten | 1 | 120 | 120 |  | 0 | 0 |  |  | Iten |  | -80 | -80 |  | 0 | 0 |  |  |  | #REF! | #REF! | #REF! | 6889 | 50521.36 | 57410.36 | #REF!
Sub-total : (b) Capital Component: |  |  |  |  | 78430.72 | 31645.96 |  | 46784.76 | 0 |  |  |  |  | 81177.19 | 34500.263 |  | 46676.927 | 0 |  |  |  |  | 2746.47 | 2854.303 |  | -107.833 | 0
Total Cost (a+b) : |  |  |  |  | 97204.86 | 38218.14 |  | 51085.32 | 7901.4 |  |  |  |  | 100739.49 | 41293.39 |  | 51544.7 | 7901.4 |  |  |  |  | 3534.63 | 3075.25 |  | 459.38 | 0
| 0 | (c) Physical Contingency ( Lump sum): | Item | L.S. | 258 | 100 |  | 158 | 0 |  |  | Item | L.S. | 30.51 | 30.51 |  | 0 | 0 |  |  | Item |  | -227.49 | -69.49 |  | -158 | 0
| 0 | (d) Price Contingency (Lump sum): | Item | L.S. | 402.14 | 100.76 |  | 301.38 | 0 |  |  | Item | L.S. | 10 | 10 |  | 0 | 0 |  |  | Item |  | -392.14 | -90.76 |  | -301.38 | 0
|  | Grand Total : (a)+(b)+(c)+(d): |  |  | 97865 | 38418.9 |  | 51544.7 | 7901.4 |  |  |  |  | 100780 | 41333.9 |  | 51544.7 | 7901.4 |  |  |  |  | 2915 | 2915 |  | -2.16e-12 | 0
* DOSA, CONTASA, SAFE, IMPREST etc.
|  |  |  | c+d | 53527 | 6423.24 |  | 47103.76 | [5 empty] | 62021.8 | 14996.1 |  | 47025.7 |  |  | 0 |  |  | 8494.8 | 8572.86 |  | -78.06
|  |  |  | Phy.Works | 53727 | 6623.24 |  | 47103.76 |  |  |  |  | Phy.Works | 61916.8 | 15084.6 |  | 46832.2 |  |  | 0 |  | Phy.Works | 8189.8 | 8461.36 |  | -271.56
|  |  |  | c+d+works |  | 13046.48 |  | 94207.52 | [6 empty] | 30080.7 |  | 93857.9 |  |  | 0
|  |  |  | other |  | 25372.42 |  | 3981.56 | [8 empty] | 4519
[8 empty] | 98189.08 | [8 empty] | 98376.9
[9 empty] | Reh | [7 empty] | Reh | 0
[9 empty] | New | [7 empty] | New | #REF!
[5 empty] | 4253.43 | [8 empty] | 4998 |  |  | 4400 | 0
#REF!
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 254.207 | 16526.21 | 4527.399 |  | 11998.811 | 0 |  |  | Km | -9.033 | 4573.71 | 3093.099 |  | 1480.611 | 0

## 9.Detil Phasing
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2019 (Year 1 to Year-5) † | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-21 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | Part | 1.01 | 1.01 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 3111327 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 3111338 | Other Allowance |  |  | 36.61 | 36.61 |  | 0 | 0 |  |  |  |  | Part | 14 | 14 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 58.54 | 58.54 |  | 0 | 0 |  |  |  |  | Part | 14.97 | 14.97 |  | 0 | 0 |  |  |  |  | Part | 28.8176 | 28.8176 |  | 0 | 0 |  |  |  |  | Part | 17.6624 | 17.6624 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 116.67 | 116.67 |  | 0 | 0 |  |  |  |  | Part | 34.21 | 34.21 |  | 0 | 0 |  |  |  |  | Part | 58.3544 | 58.3544 |  | 0 | 0 |  |  |  |  | Part | 35.7656 | 35.7656 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1603.18 | 1603.18 |  | 0 | 0 |  |  |  |  | Part | 177.18 | 177.18 |  | 0 | 0 |  |  |  |  | Part | 634.52 | 634.52 |  | 0 | 0 |  |  |  |  | Part | 459.48 | 459.48 |  | 0 | 0
| 3211119 | Postage |  | Part | 0.77 | 0.77 |  | 0 | 0 |  |  |  |  | Part | 0.48 | 0.48 |  | 0 | 0 |  |  |  |  | Part | 2.175 | 2.175 |  | 0 | 0 |  |  |  |  | Part | 1.575 | 1.575 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | Part | 0.97 | 0.97 |  | 0 | 0 |  |  |  |  | Part | 0.07 | 0.07 |  | 0 | 0 |  |  |  |  | Part | 2.4156 | 2.4156 |  | 0 | 0 |  |  |  |  | Part | 1.5444 | 1.5444 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | Part | 0.44 | 0.44 |  | 0 | 0 |  |  |  |  | Part | 0.1 | 0.1 |  | 0 | 0 |  |  |  |  | Part | 2.497 | 2.497 |  | 0 | 0 |  |  |  |  | Part | 1.962 | 1.962 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | Part | 11.92 | 11.92 |  | 0 | 0 | [5 empty] | 0.17 | 0.17 |  | 0 | 0 | [5 empty] | 4.9833 | 4.9833 |  | 0 | 0 | [5 empty] | 2.9267 | 2.9267 |  | 0 | 0
| 3211115 | Water |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 0.55 | 0.55 |  | 0 | 0 |  |  |  |  | Part | 2.0313 | 2.0313 |  | 0 | 0 |  |  |  |  | Part | 1.2987 | 1.2987 |  | 0 | 0
| 3211113 | Electricity |  | Part | 8.74 | 8.74 |  | 0 | 0 |  |  |  |  | Part | 2.89 | 2.89 |  | 0 | 0 |  |  |  |  | Part | 4.609 | 4.609 |  | 0 | 0 |  |  |  |  | Part | 3.771 | 3.771 |  | 0 | 0
| 3243102 | Gas & Fuel |  | Part | 17.52 | 17.52 |  | 0 | 0 |  |  |  |  | Part | 4.02 | 4.02 |  | 0 | 0 |  |  |  |  | Part | 11.2545 | 11.2545 |  | 0 | 0 |  |  |  |  | Part | 7.1955 | 7.1955 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | Part | 64.59 | 64.59 |  | 0 | 0 |  |  |  |  | Part | 24.18 | 24.18 |  | 0 | 0 |  |  |  |  | Part | 46.3068 | 46.3068 |  | 0 | 0 |  |  |  |  | Part | 34.9332 | 34.9332 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | Part | 1.16 | 1.16 |  | 0 | 0 |  |  |  |  | Part | 0.91 | 0.91 |  | 0 | 0 |  |  |  |  | Part | 0.51205 | 0.51205 |  | 0 | 0 | [5 empty] | 0.41895 | 0.41895 |  | 0 | 0
| 3255102 | Printing & Binding |  | Part | 34.16 | 34.16 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 9.355 | 9.355 |  | 0 | 0 |  |  |  |  | Part | 5.981 | 5.981 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | Part | 49.91 | 49.91 |  | 0 | 0 |  |  |  |  | Part | 19.95 | 19.95 |  | 0 | 0 |  |  |  |  | Part | 31.5869 | 31.5869 |  | 0 | 0 |  |  |  |  | Part | 18.5511 | 18.5511 |  | 0 | 0
| 3211127 | Books & Periodicals |  | Part | 0.28 | 0.28 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 119 | 0 |  | 119 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 301.5 | 22.54 |  | 278.96 | 0 |  |  |  |  | Part | 22.21 | 2.3809 |  | 19.8291 | 0 |  |  |  |  | Part | 127.794 | 13.6995 |  | 114.0945 | 0 |  |  |  |  | Part | 85.196 | 9.133 |  | 76.063 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1346.63 | 80.34 |  | 1266.29 | 0 |  |  |  |  | Part | 338.12 | 36.2465 |  | 301.8735 | 0 |  |  |  |  | Part | 910.5705 | 97.6132 |  | 812.9573 | 0 |  |  |  |  | Part | 534.7795 | 57.3284 |  | 477.4511 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 578.2 | 35.47 |  | 542.73 | 0 |  |  |  |  | Part | 82.97 | 8.8944 |  | 74.0756 | 0 |  |  |  |  | Part | 368.5165 | 39.505 |  | 329.0115 | 0 |  |  |  |  | Part | 301.5135 | 32.3222 |  | 269.1913 | 0
| 3211109 | Casual labour/Job worker |  | Part | 10.96 | 10.96 |  | 0 | 0 |  |  |  |  | Part | 3.49 | 3.49 |  | 0 | 0 |  |  |  |  | Part | 4.681 | 4.681 |  | 0 | 0 |  |  |  |  | Part | 2.869 | 2.869 |  | 0 | 0
| 3256103 | Consumable Stores |  | Part | 3.74 | 3.74 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5168.01 | 0 |  | 0 | 5168.01 |  |  |  | MM | Part | 450 | 0 |  | 0 | 450 |  |  |  | MM | Part | 1374.571 | 0 |  | 0 | 1374.571 |  |  |  | MM | Part | 878.824 | 0 |  | 0 | 878.824
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 12.73 | 12.73 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 8.2766 | 8.2766 |  | 0 | 0 |  |  |  |  | Part | 5.9934 | 5.9934 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  |  | 1.29 | 1.29 |  | 0 | 0 |  |  |  |  | Part | 0.41 | 0.41 |  | 0 | 0 | [5 empty] | 8.3 | 8.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  |  | 1.3 | 1.3 |  | 0 | 0 |  |  |  |  | Part | 0.41 | 0.41 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0
| 3257104 | Survey |  | Part | 85.02 | 85.02 |  | 0 | 0 |  |  |  |  | Part | 30 | 30 |  | 0 | 0 |  |  |  |  | Part | 26.7786 | 26.7786 |  | 0 | 0 |  |  |  |  | Part | 20.2014 | 20.2014 |  | 0 | 0
| 3255101 | Computer Consumables |  | Part | 20.47 | 20.47 |  | 0 | 0 |  |  |  |  | Part | 10 | 10 |  | 0 | 0 |  |  |  |  | Part | 16.242 | 16.242 |  | 0 | 0 |  |  |  |  | Part | 13.2889 | 13.2889 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 875.46 | 875.46 |  | 0 | 0 |  |  |  |  | Part | 299.96 | 299.96 |  | 0 | 0 |  |  |  |  | Part | 299.0163 | 299.0163 |  | 0 | 0 |  |  |  |  | Part | 225.5737 | 225.5737 |  | 0 | 0
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | Part | 61.4 | 61.4 |  | 0 | 0 |  |  |  |  | Part | 14.97 | 14.97 |  | 0 | 0 |  |  |  |  | Part | 26.7481 | 26.7481 |  | 0 | 0 |  |  |  |  | Part | 21.8849 | 21.8849 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | Part | 3.2 | 3.2 |  | 0 | 0 |  |  |  |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 3.414 | 3.414 |  | 0 | 0 |  |  |  |  | Part | 2.276 | 2.276 |  | 0 | 0
| 3258103 | Computers & office equipments |  | Part | 5.34 | 5.34 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | Part | 1.22 | 1.22 |  | 0 | 0 |  |  |  |  | Part | 1.99 | 1.99 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  |  | 14.53 | 14.53 |  | 0 | 0 |  |  |  |  | Part | 4.95 | 4.95 |  | 0 | 0 |  |  |  |  | Part | 11.9016 | 11.9016 |  | 0 | 0 |  |  |  |  | Part | 8.6184 | 8.6184 |  | 0 | 0
| 3258105 | Engineering Equipments |  | Part | 1.39 | 1.39 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
|  | Drainage Structures : | [12 empty] | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 95.03 | 10.83 |  | 84.2 | 0 |  |  |  | Nos. | Part | 33.17 | 4.8826 |  | 28.2874 | 0 |  |  |  | Nos. | Part | 174.7305 | 25.7203 |  | 149.0102 | 0 | [5 empty] | 102.6195 | 15.1056 |  | 87.5139 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.39 | 2.39 |  | 0 | 0 |  |  |  | Nos. | Part | 0.38 | 0.38 |  | 0 | 0 |  |  |  | Nos. | Part | 1.3603 | 1.3603 |  | 0 | 0 |  |  |  | Nos. | Part | 0.8697 | 0.8697 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  |  | 7.48 | 7.48 |  | 0 | 0 |  |  |  |  | Part | 1.49 | 1.49 |  | 0 | 0 |  |  |  |  | Part | 17.3768 | 17.3768 |  | 0 | 0 |  |  |  |  | Part | 13.6532 | 13.6532 |  | 0 | 0
(a) Sub-total Revenue Component: |  |  |  |  | 10624.85 | 3284.66 |  | 2172.18 | 5168.01 | [5 empty] | 1601.51 | 727.4444 |  | 424.0656 | 450 | [5 empty] | 4430.6344 | 1531.99 |  | 1524.0735 | 1374.571 | [5 empty] | 2875.3086 | 1086.2652 |  | 910.2193 | 878.824
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 18.03 | 18.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 28.71 | 28.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.97 | 8.97 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 2 nos. | 1 | 1 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.21 | 0.21 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.5 | 20.5 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) |  |  | 3 | 3 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 9.49 | 9.49 | 70 | 0 | 0 | [5 empty] | 5 | 5 |  | 0 | 0 | [5 empty] | 35.51 | 35.51 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 | 72 | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 5.03 | 5.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 | 73 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 3.87 | 3.87 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 | 74 | 0 | 0 |  |  |  | No. | 1 no. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.3 | 1.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 | 75 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.17 | 1.17 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | Part | 45.32 | 45.32 | 76 | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.8954 | 2.8954 |  | 0 | 0 |  |  |  |  | Part | 1.7746 | 1.7746 |  | 0 | 0
| 4112303 | Aircooler | Nos. | 4 nos. | 9.73 | 9.73 | 77 | 0 | 0 |  |  |  | Nos. | 6 nos. | 2.99 | 2.99 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 1.3908 | 1.3908 |  | 0 | 0 | [5 empty] | 0.8892 | 0.8892 |  | 0 | 0
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) |  |  | 14323.6 | 14323.6 | 79 | 0 | 0 |  |  |  | ha. | Part | 1000 | 1000 |  | 0 | 0 |  |  |  | ha. | Part | 1531.56 | 1531.56 |  | 0 | 0 |  |  |  | ha. |  | 1531.56 | 1531.56 |  | 0 | 0
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) |  |  | 116.72 | 16.34 | 82 | 100.38 | 0 | [5 empty] | 192.22 | 26.9108 |  | 165.3092 | 0 |  |  |  | Nos. | 131 | 528.6816 | 74.0154 |  | 454.6662 | 0 | [5 empty] | 382.8384 | 53.5974 |  | 329.241 | 0
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 | 84 | 0 | 0 |  |  |  | No. | Part | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 668.3934 | 93.5751 |  | 574.8183 | 0 | [5 empty] | 504.2266 | 70.5917 |  | 433.6349 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 6143.66 | 889.49 | 85 | 5254.17 | 0 |  |  |  | Nos. | Part | 4075.22 | 570.5308 |  | 3504.6892 | 0 |  |  |  | Nos. | Part | 4347.3197 | 608.6248 |  | 3738.6949 | 0 |  |  |  | Nos. | Part | 3855.1703 | 539.7238 |  | 3315.4465 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) |  |  | 6011.48 | 791.08 | 86 | 5220.4 | 0 |  |  |  | Km. | Part | 2673.22 | 374.2508 |  | 2298.9692 | 0 |  |  |  | Km. | Part | 839.6808 | 117.5553 |  | 722.1255 | 0 |  |  |  | Km. | Part | 659.7492 | 92.3649 |  | 567.3843 | 0
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) |  |  | 455.04 | 64.36 | 88 | 390.68 | 0 |  |  |  | Km. | Part | 726.54 | 101.7156 |  | 624.8244 | 0 |  |  |  | Km. | Part | 1219.5205 | 170.7329 |  | 1048.7876 | 0 | [5 empty] | 997.7895 | 139.6905 |  | 858.099 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) |  |  | 452.46 | 63.49 | 89 | 388.97 | 0 |  |  |  | Km. | Part | 253.65 | 35.511 |  | 218.139 | 0 |  |  |  | Km. | Part | 771.0056 | 107.9408 |  | 663.0648 | 0 | [5 empty] | 558.3144 | 78.164 |  | 480.1504 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) |  |  | 341.85 | 48.84 | 90 | 293.01 | 0 |  |  |  | Km. | Part | 179.68 | 25.1552 |  | 154.5248 | 0 |  |  |  | Km. | Part | 674.795 | 94.4713 |  | 580.3237 | 0 | [5 empty] | 552.105 | 77.2947 |  | 474.8103 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  |  | 6127.06 | 779.02 | 91 | 5348.04 | 0 |  |  |  | Km. | Part | 2923.61 | 409.3054 |  | 2514.3046 | 0 |  |  |  | Km. | Part | 7188.8448 | 1006.4383 |  | 6182.4065 | 0 |  |  |  | Km. |  | 5205.7152 | 728.8001 |  | 4476.9151 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 | 92 | 63.49 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 |  |  |  | Nos. |  | 40.3865 | 5.6541 |  | 34.7324 | 0 |  |  |  | Nos. |  | 33.0435 | 4.6261 |  | 28.4174 | 0
| 4111201 | Threshing Floor Construction |  |  | 0 | 0 | 93 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 123.75 | 17.325 |  | 106.425 | 0 | [5 empty] | 101.25 | 14.175 |  | 87.075 | 0
| 4111201 | Construction of WMG Office |  |  | 42.09 | 5.47 | 94 | 36.62 | 0 |  |  |  | Nos. | Part | 93.33 | 13.0662 |  | 80.2638 | 0 |  |  |  | Nos. |  | 845.0706 | 118.3099 |  | 726.7607 | 0 |  |  |  | Nos. |  | 637.5094 | 89.2513 |  | 548.2581 | 0
| 4111201 | O&M During Construction |  |  | 0 | 0 | 95 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 66 | 9.24 |  | 56.76 | 0 | [5 empty] | 54 | 7.56 |  | 46.44 | 0
(b)Sub-total Capital Component: |  |  |  |  | 34937.27 | 17841.51 |  | 17095.76 | 0 | [5 empty] | 12125.46 | 2564.4358 |  | 9561.0242 | 0 | [5 empty] | 19038.7247 | 4149.159 |  | 14889.5657 | 0 | [5 empty] | 15075.9353 | 3430.0634 |  | 11645.8719 | 0
Total Cost (a+b) : |  |  |  |  | 45562.12 | 21126.17 |  | 19267.94 | 5168.01 | [5 empty] | 13726.97 | 3291.8802 |  | 9985.0898 | 450 | [5 empty] | 23469.3591 | 5681.149 |  | 16413.6392 | 1374.571 | [5 empty] | 17951.2439 | 4516.3286 |  | 12556.0912 | 878.824
| 0 | (c) Physical Contingency ( Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 16.1703 | 16.1703 |  | 0 | 0 | [5 empty] | 14.3397 | 14.3397 |  | 0 | 0
| 0 | (d) Price Contingency (Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 5.4 | 5.4 |  | 0 | 0 | [5 empty] | 4.6 | 4.6 |  | 0 | 0
Grand Total (a+b+c+d) : |  |  |  |  | 45562.12 | 21126.17 |  | 19267.94 | 5168.01 | [5 empty] | 13726.97 | 3291.8802 |  | 9985.0898 | 450 | [5 empty] | 23490.9294 | 5702.7193 |  | 16413.6392 | 1374.571 | [5 empty] | 17970.1836 | 4535.2683 |  | 12556.0912 | 878.824
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17
100750.203
59289.09

## 9.Detil Phasing_2
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2020 (Year 1 to Year-6) † | [9 empty] | FY: 2020-2021 (Year-7) | [9 empty] | FY: 2021-22 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | Part | 1.51 | 1.51 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 3111327 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 3111338 | Other Allowance |  |  | 50.61 | 50.61 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 73.523 | 73.523 |  | 0 | 0 |  |  |  |  | Part | 28.8176 | 28.8176 |  | 0 | 0 |  |  |  |  | Part | 17.6624 | 17.6624 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 150.88 | 150.88 |  | 0 | 0 |  |  |  |  | Part | 58.3544 | 58.3544 |  | 0 | 0 |  |  |  |  | Part | 35.7656 | 35.7656 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1780.35 | 1780.35 |  | 0 | 0 |  |  |  |  | Part | 634.52 | 634.52 |  | 0 | 0 |  |  |  |  | Part | 459.48 | 459.48 |  | 0 | 0
| 3211119 | Postage |  | Part | 1.25 | 1.25 |  | 0 | 0 |  |  |  |  | Part | 2.175 | 2.175 |  | 0 | 0 |  |  |  |  | Part | 1.575 | 1.575 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | Part | 1.04 | 1.04 |  | 0 | 0 |  |  |  |  | Part | 2.4156 | 2.4156 |  | 0 | 0 |  |  |  |  | Part | 1.5444 | 1.5444 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | Part | 0.541 | 0.541 |  | 0 | 0 |  |  |  |  | Part | 2.497 | 2.497 |  | 0 | 0 |  |  |  |  | Part | 1.962 | 1.962 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | Part | 12.09 | 12.09 |  | 0 | 0 | [5 empty] | 4.9833 | 4.9833 |  | 0 | 0 | [5 empty] | 2.9267 | 2.9267 |  | 0 | 0
| 3211115 | Water |  | Part | 1.67 | 1.67 |  | 0 | 0 |  |  |  |  | Part | 2.0313 | 2.0313 |  | 0 | 0 |  |  |  |  | Part | 1.2987 | 1.2987 |  | 0 | 0
| 3211113 | Electricity |  | Part | 11.62 | 11.62 |  | 0 | 0 |  |  |  |  | Part | 4.609 | 4.609 |  | 0 | 0 |  |  |  |  | Part | 3.771 | 3.771 |  | 0 | 0
| 3243102 | Gas & Fuel |  | Part | 21.55 | 21.55 |  | 0 | 0 |  |  |  |  | Part | 11.2545 | 11.2545 |  | 0 | 0 |  |  |  |  | Part | 7.1955 | 7.1955 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | Part | 88.76 | 88.76 |  | 0 | 0 |  |  |  |  | Part | 46.3068 | 46.3068 |  | 0 | 0 |  |  |  |  | Part | 34.9332 | 34.9332 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | Part | 2.07 | 2.07 |  | 0 | 0 |  |  |  |  | Part | 0.51205 | 0.51205 |  | 0 | 0 |  |  |  |  | Part | 0.41895 | 0.41895 |  | 0 | 0
| 3255102 | Printing & Binding |  | Part | 34.664 | 34.664 |  | 0 | 0 |  |  |  |  | Part | 9.355 | 9.355 |  | 0 | 0 |  |  |  |  | Part | 5.981 | 5.981 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | Part | 69.862 | 69.862 |  | 0 | 0 |  |  |  |  | Part | 31.5869 | 31.5869 |  | 0 | 0 |  |  |  |  | Part | 18.5511 | 18.5511 |  | 0 | 0
| 3211127 | Books & Periodicals |  | Part | 0.48 | 0.48 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 119 | 0 |  | 119 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 323.71 | 25.25 |  | 298.46 | 0 |  |  |  |  | Part | 127.794 | 23.4885 |  | 104.3055 | 0 |  |  |  |  | Part | 85.196 | 15.659 |  | 69.537 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1684.75 | 114.81 |  | 1569.94 | 0 |  |  |  |  | Part | 910.5705 | 163.2653 |  | 747.3052 | 0 |  |  |  |  | Part | 534.7795 | 95.886 |  | 438.8935 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 661.17 | 42.58 |  | 618.59 | 0 |  |  |  |  | Part | 368.5165 | 64.4167 |  | 304.0998 | 0 |  |  |  |  | Part | 301.5135 | 52.7046 |  | 248.8089 | 0
| 3211109 | Casual labour/Job worker |  | Part | 14.45 | 14.45 |  | 0 | 0 |  |  |  |  | Part | 4.681 | 4.681 |  | 0 | 0 |  |  |  |  | Part | 2.869 | 2.869 |  | 0 | 0
| 3256103 | Consumable Stores |  | Part | 6.74 | 6.74 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5648.005 | 0 |  | 0 | 5648.005 |  |  |  | MM | Part | 1374.571 | 0 |  | 0 | 1374.571 |  |  |  | MM | Part | 878.824 | 0 |  | 0 | 878.824
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 15.73 | 15.73 |  | 0 | 0 |  |  |  |  | Part | 8.2766 | 8.2766 |  | 0 | 0 |  |  |  |  | Part | 5.9934 | 5.9934 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  |  | 1.7 | 1.7 |  | 0 | 0 |  |  |  |  | Part | 8.3 | 8.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  |  | 1.71 | 1.71 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0
| 3257104 | Survey |  | Part | 115.02 | 115.02 |  | 0 | 0 |  |  |  |  | Part | 26.7786 | 26.7786 |  | 0 | 0 |  |  |  |  | Part | 20.2014 | 20.2014 |  | 0 | 0
| 3255101 | Computer Consumables |  | Part | 30.469 | 30.469 |  | 0 | 0 |  |  |  |  | Part | 16.242 | 16.242 |  | 0 | 0 |  |  |  |  | Part | 13.2889 | 13.2889 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 1175.41 | 1175.41 |  | 0 | 0 |  |  |  |  | Part | 299.0163 | 299.0163 |  | 0 | 0 |  |  |  |  | Part | 225.5737 | 225.5737 |  | 0 | 0
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | Part | 76.367 | 76.367 |  | 0 | 0 |  |  |  |  | Part | 26.7481 | 26.7481 |  | 0 | 0 |  |  |  |  | Part | 21.8849 | 21.8849 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | Part | 4.31 | 4.31 |  | 0 | 0 |  |  |  |  | Part | 3.414 | 3.414 |  | 0 | 0 |  |  |  |  | Part | 2.276 | 2.276 |  | 0 | 0
| 3258103 | Computers & office equipments |  | Part | 8.34 | 8.34 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | Part | 3.22 | 3.22 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  |  | 19.48 | 19.48 |  | 0 | 0 |  |  |  |  | Part | 11.9016 | 11.9016 |  | 0 | 0 |  |  |  |  | Part | 8.6184 | 8.6184 |  | 0 | 0
| 3258105 | Engineering Equipments |  | Part | 3.39 | 3.39 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 128.2 | 14.98 |  | 113.22 | 0 |  |  |  | Nos. | Part | 174.7305 | 26.3319 |  | 148.3986 | 0 |  |  |  | Nos. | Part | 102.6195 | 15.4648 |  | 87.1547 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.77 | 2.77 |  | 0 | 0 |  |  |  | Nos. | Part | 1.3603 | 1.3603 |  | 0 | 0 |  |  |  | Nos. | Part | 0.8697 | 0.8697 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  |  | 8.97 | 8.97 |  | 0 | 0 |  |  |  |  | Part | 17.3768 | 17.3768 |  | 0 | 0 |  |  |  |  | Part | 13.6532 | 13.6532 |  | 0 | 0
(a) Sub-total Revenue Component: |  |  |  |  | 12256.361 | 4008.146 |  | 2600.21 | 5648.005 | [5 empty] | 4430.6344 | 1632.9544 |  | 1423.1091 | 1374.571 | [5 empty] | 2875.3086 | 1152.0903 |  | 844.3942 | 878.824
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 18.03 | 18.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 28.71 | 28.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.97 | 8.97 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 2 nos. | 0.79 | 0.79 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.21 | 0.21 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.5 | 20.5 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) |  |  | 3 | 3 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 14.49 | 14.49 | 70 | 0 | 0 | [5 empty] | 35.51 | 35.51 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 | 72 | 0 | 0 |  |  |  | Nos. | 3 nos. | 5.03 | 5.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 | 73 | 0 | 0 |  |  |  | Nos. | 4 nos. | 3.87 | 3.87 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 | 74 | 0 | 0 |  |  |  | No. | 1 no. | 1.3 | 1.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 | 75 | 0 | 0 |  |  |  | Nos. | 4 nos. | 1.17 | 1.17 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | Part | 45.33 | 45.33 | 76 | 0 | 0 |  |  |  |  | Part | 2.8954 | 2.8954 |  | 0 | 0 |  |  |  |  | Part | 1.7746 | 1.7746 |  | 0 | 0
| 4112303 | Aircooler | Nos. | 4 nos. | 12.72 | 12.72 | 77 | 0 | 0 |  |  |  | Nos. | 6 nos. | 1.3908 | 1.3908 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.8892 | 0.8892 |  | 0 | 0
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) |  |  | 15323.6 | 15323.6 | 79 | 0 | 0 |  |  |  | ha. | Part | 1531.56 | 1531.56 |  | 0 | 0 |  |  |  | ha. | Part | 1531.56 | 1531.56 |  | 0 | 0
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) |  |  | 308.94 | 40.42 | 82 | 268.52 | 0 | [5 empty] | 528.6816 | 75.6543 |  | 453.0273 | 0 |  |  |  | Nos. | 131 | 382.8384 | 54.7842 |  | 328.0542 | 0
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 | 84 | 0 | 0 |  |  |  | No. | Part | 668.3934 | 93.5751 |  | 574.8183 | 0 |  |  |  | No. | Part | 504.2266 | 70.5917 |  | 433.6349 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 10218.88 | 1398.89 | 85 | 8819.99 | 0 |  |  |  | Nos. | Part | 4347.3197 | 625.5793 |  | 3721.7404 | 0 |  |  |  | Nos. | Part | 3855.1703 | 554.759 |  | 3300.4113 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) |  |  | 8684.7 | 1125.23 | 86 | 7559.47 | 0 |  |  |  | Km. | Part | 839.6808 | 168.272 |  | 671.4088 | 0 |  |  |  | Km. | Part | 659.7492 | 132.2137 |  | 527.5355 | 0
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) |  |  | 1181.58 | 155.18 | 88 | 1026.4 | 0 |  |  |  | Km. | Part | 1219.5205 | 176.3427 |  | 1043.1778 | 0 |  |  |  | Km. | Part | 997.7895 | 144.2804 |  | 853.5091 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) |  |  | 706.11 | 95.2 | 89 | 610.91 | 0 |  |  |  | Km. | Part | 771.0056 | 110.0225 |  | 660.9831 | 0 |  |  |  | Km. | Part | 558.3144 | 79.6715 |  | 478.6429 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) |  |  | 521.53 | 71.3 | 90 | 450.23 | 0 |  |  |  | Km. | Part | 674.795 | 95.416 |  | 579.379 | 0 |  |  |  | Km. | Part | 552.105 | 78.0676 |  | 474.0374 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  |  | 9050.67 | 1144.47 | 91 | 7906.2 | 0 |  |  |  | Km. | Part | 7188.8448 | 4738.8865 |  | 2449.9583 | 0 |  |  |  | Km. | Part | 5205.7152 | 3431.94 |  | 1773.77 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 | 92 | 63.49 | 0 |  |  |  | Nos. |  | 40.3865 | 5.9207 |  | 34.4658 | 0 |  |  |  | Nos. |  | 33.0435 | 4.8442 |  | 28.1993 | 0
| 4111201 | Threshing Floor Construction |  |  | 0 | 0 | 93 | 0 | 0 | [5 empty] | 123.75 | 17.325 |  | 106.425 | 0 | [5 empty] | 101.25 | 14.175 |  | 87.075 | 0
| 4111201 | Construction of WMG Office |  |  | 135.42 | 17.14 | 94 | 118.28 | 0 |  |  |  | Nos. | Part | 845.0706 | 119.324 |  | 725.7466 | 0 |  |  |  | Nos. |  | 637.5094 | 90.0163 |  | 547.4931 | 0
| 4111201 | O&M During Construction |  |  | 0 | 0 | 95 | 0 | 0 | [5 empty] | 66 | 66 |  | 0 | 0 |  |  |  |  | Part | 54 | 54 |  | 0 | 0
(b)Sub-total Capital Component: |  |  |  |  | 47062.53 | 20239.04 |  | 26823.49 | 0 | [5 empty] | 19038.7247 | 8017.5942 |  | 11021.1305 | 0 | [5 empty] | 15075.9353 | 6243.5674 |  | 8832.3627 | 0
Total Cost (a+b) : |  |  |  |  | 59318.891 | 24247.186 |  | 29423.7 | 5648.005 | [5 empty] | 23469.3591 | 9650.5486 |  | 12444.2396 | 1374.571 | [5 empty] | 17951.2439 | 7395.6577 |  | 9676.7569 | 878.824
| 0 | (c) Physical Contingency ( Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 16.1703 | 16.1703 |  | 0 | 0 | [5 empty] | 14.3397 | 14.3397 |  | 0 | 0
| 0 | (d) Price Contingency (Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 5.4 | 5.4 |  | 0 | 0 | [5 empty] | 4.6 | 4.6 |  | 0 | 0
Grand Total (a+b+c+d) : |  |  |  |  | 59318.891 | 24247.186 |  | 29423.7 | 5648.005 | [5 empty] | 23490.9294 | 9672.1189 |  | 12444.2396 | 1374.571 | [5 empty] | 17970.1836 | 7414.5974 |  | 9676.7569 | 878.824
59318.891
[5 empty] | 59318.897 | [9 empty] | 23490.9294 |  | 23.1682 |  | 8.4128e-12 | [5 empty] | 17970.1836 |  |  |  | 0.0052
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17 |  |  |  |  | -0.006 | [9 empty] | 0 | [9 empty] | 0
59318.897
0.006

## Annex -I
Annexure - I
Loaction wise Cost Breakdown
SL No | Division | District | Upazila/Thana/City Corporation/Pourosava) | Major Items/Compoments (With Quantity: 1st Revised/2nd Revised) | Estimated Cost (Taka in Lakh) |  | Comment
[5 empty] | 1st Revised | 2nd Revised
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
|  | Kishoreganj | Kishoreganj Sadar, Austagram, Bajitpur, Katiadi, Hussainpur, Itna, Mithamoin, Kuliarchar, Karimganj, Nikili, Pakundia & Tarail | Rehabilitation of Full Embankment (6 km./0 km.) | 10 | 0 | Cost increases.
1. | Dhaka |  |  | Construction of New Submesible Embankment (165.185 km./158.165 km.) | 8405.5 | 16646.89
|  |  |  | Replacement of Regulator Gates (13 nos./13 nos.) | 27.5 | 55.55
|  |  |  | Installation of New Regulators (33 nos/24 Nos.) | 7974 | 5743.73
|  |  |  | Re-excavation of Khal/River(Rehab.) (20.00 km/11.551 km.) | 180 | 496.55
|  |  |  | Re-excavation of Khal/River (New) (171.126 km/162.065 km.) | 4989 | 4590.03
|  |  |  | Construction of Bridge | 10 | 0
|  |  |  | Construction of Causeway (15 Nos/15 Nos.) | 2835 | 3991
|  |  |  | Construction of Box Drainage Outlet (14 Nos/19 Nos.) | 565 | 666.98 |  |  |  | K | 45 | 52
|  |  |  | Construction of Irrigation Inlet (86 Nos./78 Nos.) | 827 | 794.19 |  |  |  | M | 1 | 1
|  |  |  | Rehab. of Regulator (5 no./5 Nos.) | 125 | 125 |  |  |  | N | 25 | 11
|  |  |  | Threshing Floor Construction (0 Nos/5 Nos) | 0 | 225 |  |  |  | S | 9 | 20
|  |  |  | Construction of WMG office (60 Nos./60 Nos.) | 1380 | 1618 |  |  |  | B | 2 | 1
|  |  |  | O&M during Construction at Kishoregonj | 100 | 120
|  |  |  | Sub Total : | 27428 | 35072.92 |  | 0.51229 | 56.44%
2 | Mymensingh | Mymensingh | Nandail | Replacement of Regulator Gates (2 nos./0 nos.) | 5 | 0 | Cost increases.
|  |  |  | Re-excavation of Khal/River (Rehab.) (5.00 km/0.00 km.) | 75 | 0
|  |  |  | Sub Total : | 80 | 0 |  | 0.14942 | 0 |  | 35072.92
3 | Mymensingh | Netrokona | Netrokona Sadar, Atpara, Borhatta, Khalijuri, Kalmakanda, Kendua, Madan, Mohonganjand Purbadhala. | Rehabilitation of Full Embankment (61.21 km./67.11 km.) | 2110 | 2035.43 | Cost decreases.
|  |  |  | Rehabilitation of Submergible Embankment (19.60 km./13.31 km.) | 410 | 383
|  |  |  | Construction of New Embankment (2.80 km./3.071 km.) | 128 | 57.25
|  |  |  | Replacement of Regulator Gates (56 nos./56 nos.) | 140 | 140
|  |  |  | Installation of New Regulators (6 nos/6 Nos.) | 1385 | 1642.1
|  |  |  | Re-excavation of Khal/River (Rehab.) (80.64 km/74.416 km.) | 1468 | 1990
|  |  |  | Re-excavation of Khal/River (New) (36.00.00 km/35.31 km.) | 1560 | 1365
|  |  |  | Construction of Box Drainage Outlet (7Nos /7 Nos.) | 280 | 383
|  |  |  | Construction of Irrigation Inlet (5 no./5 Nos.) | 50 | 53.92
|  |  |  | Rehab. of Regulator (1 Nos./1 Nos.) | 20 | 389.57
|  |  |  | Re-installation of Regulators (1 Nos./1 nos.) | 420 | 12
|  |  |  | Sub Total : | 7971 | 8451.27 |  | 14.89% | 13.6%
4 | Sylhet | Sunamganj | Sunamganj Sadar, Chhatak, Dharma-pasha, Jamalganj and South Sunamganj | Construction of New Embankment (71.44 km./55.025 km.) | 2229 | 3579.6 | Cost increases.
|  |  |  | Installation of New Regulators (11 nos/4 Nos.) | 2131 | 1154.78
|  |  |  | Re-excavation of Khal/River (New) (70.92 km/116.551 km.) | 1936 | 3302.34
|  |  |  | Construction of Causeway (16 no/8 Nos.) | 1825 | 1850.07
|  |  |  | Construction of Pipe/Box Sluice/Drainage Outlet (14 Nos /8 Nos.) | 500 | 346.76
|  |  |  | Construction of Irrigation Inlet (25 Nos/21 Nos.) | 250 | 238.35
|  |  |  | Rehab of Regulator (1 Nos/0 Nos) | 10
|  |  |  | Sub Total : | 8881 | 10471.9 |  | 16.59% | 16.85%
5 | Sylhet | Habiganj | Habiganj Sadar, Azmeriganj, Bahubal and Baniachang | Rehabilitation of Full Embankment (18.10 m/0 km.) | 430 | 0 | Cost increases.
|  |  |  | Rehabilitation of Submergible Embankment (67.43 km./49.712 km.) | 1375 | 1365.43
|  |  |  | Construction of New Embankment (23.82 km./23.82 km.) | 1190 | 1161.49
|  |  |  | Replacement of Regulator Gates (31 nos./13 nos.) | 90 | 35
|  |  |  | Re-installation of Regulators/Causeway (6 nos./4 Nos.) | 1095 | 783.05
|  |  |  | Installation of New Regulators (7 Nos/6 Nos.) | 1340 | 1091.95
|  |  |  | Re-excavation of Khal/River (Rehab.) (37.36 km/23.007 km.) | 830 | 912.34
|  |  |  | Re-excavation of Khal/River (New) (40.159 km/30.058 km.) | 1019 | 926.76
|  |  |  | Construction of Causeway (4 Nos/8 Nos.) | 916 | 1011
|  |  |  | Construction of Pipe/Box Sluice/Drainage Outlet (9 no/9 Nos.) | 550 | 540
|  |  |  | Construction of Irrigation Inlet (15 Nos/15 Nos.) | 134 | 134
|  |  |  | Rehab. of Regulator (1 Nos /1 Nos.) | 11 | 9.69
|  |  |  | O&M during Construction at Hobigonj, Sunamgonj & Netrokona | 100 | 0
|  |  |  | Sub Total : | 9080 | 7970.71 |  | 16.96% | 12.83%
6 | Chittagong | Brahmanbaria | Banchharampur | Rehabilitation of Full Embankment (0 km/0.00 km.) | 0 |  | Cost decreases.
|  |  |  | Re-installation of Regulators (0 nos./0 no.) | 0
|  |  |  | Replacement of Regulator Gates (4 Nos/4 nos.) | 0 | 175
|  |  |  | Re-excavation of Khal/River (Rehab.) (0 km/0.00 km.) | 100
|  |  |  | Sub Total : | 100 | 175 |  | 0.18678 | 0.28161
|  |  |  | Total Estimated cost of civil works | 53540 | 62141.8

## Sheet3
1.51 | 1.51 | 0 | 0
0 | 0 | 0 | 0
50.61 | 50.61 | 0 | 0
73.53 | 73.523 | 0 | 0
150.88 | 150.88 | 0 | 0
1780.35 | 1780.35 | 0 | 0
1.25 | 1.25 | 0 | 0
1.04 | 1.04 | 0 | 0
0.541 | 0.541 | 0 | 0
12.09 | 12.09 | 0 | 0
1.67 | 1.67 | 0 | 0
11.62 | 11.62 | 0 | 0
21.55 | 21.55 | 0 | 0
88.76 | 88.76 | 0 | 0
2.069 | 2.07 | 0 | 0
34.664 | 34.664 | 0 | 0
69.862 | 69.862 | 0 | 0
0.48 | 0.48 | 0 | 0
0 | 0 | 0 | 0
323.71 | 25.25 | 298.46 | 0
1684.75 | 114.81 | 1569.94 | 0
661.17 | 42.58 | 618.59 | 0
14.45 | 14.45 | 0 | 0
6.74 | 6.74 | 0 | 0
5648.005 | 0 | 0 | 5648.005
15.73 | 15.73 | 0 | 0
1.7 | 1.7 | 0 | 0
1.71 | 1.71 | 0 | 0
115.02 | 115.02 | 0 | 0
30.469 | 30.469 | 0 | 0
1175.41 | 1175.41 | 0 | 0

## Annex-II
Year wise Financial and Physical Target Plan | [16 empty] | Annexure-II | [11 empty] | Annexure-II
Name of the Project : Haor Flood Management and Livelihood Improvement Project.(BWDB Part)
Name of agency/Division/Ministry: Bangladesh Water Development Board / Ministry of Water Resources
Economic Code | Economic Sub-Code (In detail) | Sub Code Description (In detail) | Total Physical & Financial Target |  |  |  |  | FY: 2014-15 (Year-1) |  |  | FY: 2015-16 (Year-2) |  |  | FY: 2016-17 (Year-3) |  |  | FY: 2017-18 (Year-4) |  |  | FY: 2018-19 (Year-5) |  |  | FY: 2019-20 (Year-6) |  |  | FY: 2020-21 (Year-7) |  |  | FY: 2021-22 (Year-8)
|  |  | Unit | Unit Cost | Quantity | Total Cost (Taka in Lac) | Weight | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical
[9 empty] | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.3 | 6 | 0.0003 | 0.13 | 2.6 | 0.00013 | 0.28 | 5.6 | 0.00028 | 0.3 | 6 | 0.0003 | 0.5 | 10 | 0.0005 | 2.0242 | 40.484 | 0.0020242 | 1.4658 | 29.316 | 0.0014658 | 100 | 0.005 | 10 |  |  | 5 | 0
| 3111327 | Overtime Allowance | Item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 63 | 0.0063 | 3.7 | 37 | 0.0037 | 100 | 0.01 | 11 |  |  | 10 | 0
| 3111338 | Other Allowance | Item | 140 | 1 Item | 140 | 0.00139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 17.8571 | 0.024821 | 11.61 | 8.2929 | 0.011527 | 14 | 10 | 0.0139 | 53.634 | 38.31 | 0.053251 | 35.756 | 25.54 | 0.035501 | 100 | 0.139 | 12 |  |  | 140 | 0
|  | Supplies and services: | [34 empty] | 0 | 0
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | Item | 120 | 1 Item | 120 | 0.00119 | 0.99 | 0.825 | 0.00098175 | 11.92 | 9.9333 | 0.011821 | 14.98 | 12.4833 | 0.014855 | 17.96 | 14.9667 | 0.01781 | 12.7 | 10.5833 | 0.012594 | 14.97 | 12.475 | 0.014845 | 28.8176 | 24.0147 | 0.028577 | 17.6624 | 14.7187 | 0.017515 | 100 | 0.11802 | 14 |  |  | 120 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | Months | 245 | 1 Item | 245 | 0.00243 | 0 | 0 | 0 | 16.25 | 6.6327 | 0.016117 | 31.35 | 12.7959 | 0.031094 | 34.86 | 14.2286 | 0.034575 | 34.21 | 13.9633 | 0.033931 | 34.21 | 13.9633 | 0.033931 | 58.3544 | 23.8181 | 0.057878 | 35.7656 | 14.5982 | 0.035474 | 100 | 0.243 | 15 | 245 | 100 | 245 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | Item | 2874.35 | 1 Item | 2874.35 | 0.02852 | 223.75 | 7.7844 | 0.22201 | 464.64 | 16.165 | 0.46103 | 327.7 | 11.4008 | 0.32515 | 337.33 | 11.7359 | 0.33471 | 249.75 | 8.6889 | 0.24781 | 177.18 | 6.1642 | 0.1758 | 634.52 | 22.0753 | 0.62959 | 459.48 | 15.9855 | 0.45591 | 100 | 2.63 | 16 |  |  | 2874.35 | 0
| 3211119 | Postage | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.05 | 1 | 5e-05 | 0.13 | 2.6 | 0.00013 | 0.22 | 4.4 | 0.00022 | 0.37 | 7.4 | 0.00037 | 0.48 | 9.6 | 0.00048 | 2.175 | 43.5 | 0.002175 | 1.575 | 31.5 | 0.001575 | 100 | 0.005 | 17 |  |  | 5 | 0
| 3211120 | Telephones/Telegram/Teleprinter | Item | 5 | 1 Item | 5 | 5e-05 | 0.21 | 4.2 | 0.00021 | 0.24 | 4.8 | 0.00024 | 0.29 | 5.8 | 0.00029 | 0.15 | 3 | 0.00015 | 0.08 | 1.6 | 8e-05 | 0.07 | 1.4 | 7e-05 | 2.4156 | 48.312 | 0.0024156 | 1.5444 | 30.888 | 0.0015444 | 100 | 0.00479 | 18 |  |  | 5 | 0
| 3211117 | Telex/Fax/Internet | Item | 5 | 1 Item | 5 | 5e-05 | 0.25 | 5 | 0.00025 | 0.001 | 0.02 | 1e-06 | 0.09 | 1.8 | 9e-05 | 0.05 | 1 | 5e-05 | 0.05 | 1 | 5e-05 | 0.1 | 2 | 0.0001 | 2.497 | 49.9408 | 0.002497 | 1.962 | 39.2392 | 0.001962 | 100 | 0.00475 | 19 |  |  | 5 | 0
| 3221104 | Registration Fee (Vehicles) | Item | 20 | 1 Item | 20 | 0.0002 | 1.1 | 5.5 | 0.0011 | 8.37 | 41.85 | 0.00837 | 0.08 | 0.4 | 8e-05 | 0 | 0 | 0 | 2.37 | 11.85 | 0.00237 | 0.17 | 0.85 | 0.00017 | 4.9833 | 24.9165 | 0.0049833 | 2.9267 | 14.6335 | 0.0029267 | 100 | 0.0189 | 20 |  |  | 20 | 0
| 3211115 | Water | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.12 | 2.4 | 0.00012 | 0.23 | 4.6 | 0.00023 | 0.37 | 7.4 | 0.00037 | 0.4 | 8 | 0.0004 | 0.55 | 11 | 0.00055 | 2.0313 | 40.626 | 0.0020313 | 1.2987 | 25.974 | 0.0012987 | 100 | 0.005 | 21 |  |  | 5 | 0
| 3211113 | Electricity | Item | 20 | 1 Item | 20 | 0.0002 | 0.19 | 0.95 | 0.00019 | 1.67 | 8.35 | 0.00167 | 1.78 | 8.9 | 0.00178 | 2.31 | 11.55 | 0.00231 | 2.78 | 13.9 | 0.00278 | 2.89 | 14.45 | 0.00289 | 4.609 | 23.045 | 0.004609 | 3.771 | 18.855 | 0.003771 | 100 | 0.01981 | 22 |  |  | 20 | 0
| 3243102 | Gas & Fuel | Item | 40 | 1 Item | 40 | 0.0004 | 0.94 | 2.35 | 0.00094 | 3.7 | 9.25 | 0.0037 | 3 | 7.5 | 0.003 | 4 | 10 | 0.004 | 5.89 | 14.725 | 0.00589 | 4.02 | 10.05 | 0.00402 | 11.2545 | 28.1363 | 0.011255 | 7.1955 | 17.9887 | 0.0071955 | 100 | 0.03906 | 23 |  |  | 40 | 0
| 3243101 | Petrol and Lubricant | Item | 170 | 1 Item | 170 | 0.00169 | 0.62 | 0.36471 | 0.00061635 | 6.99 | 4.1118 | 0.0069489 | 18.97 | 11.1588 | 0.018858 | 18 | 10.5882 | 0.017894 | 20 | 11.7647 | 0.019882 | 24.18 | 14.2235 | 0.024038 | 46.3068 | 27.2393 | 0.046034 | 34.9332 | 20.5489 | 0.034728 | 100 | 0.16838 | 24 |  |  | 170 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) | Item | 3 | 1 Item | 3 | 3e-05 | 0.08 | 2.6667 | 8e-05 | 0.749 | 24.9667 | 0.000749 | 0.01 | 0.33333 | 1e-05 | 0.22 | 7.3333 | 0.00022 | 0.1 | 3.3333 | 0.0001 | 0.91 | 30.3333 | 0.00091 | 0.51205 | 17.0683 | 0.00051205 | 0.41895 | 13.965 | 0.00041895 | 100 | 0.00292 | 25 |  |  | 3 | 0
| 3255102 | Printing & Binding | Item | 50 | 1 Item | 50 | 0.0005 | 0.2 | 0.4 | 0.0002 | 6.994 | 13.988 | 0.006994 | 16.99 | 33.98 | 0.01699 | 6 | 12 | 0.006 | 3.98 | 7.96 | 0.00398 | 0.5 | 1 | 0.0005 | 9.355 | 18.7099 | 0.009355 | 5.981 | 11.9621 | 0.005981 | 100 | 0.0498 | 26 |  |  | 50 | 0
| 3255104 | Stationery, Seals & Stamps | Item | 120 | 1 Item | 120 | 0.00119 | 0.97 | 0.80833 | 0.00096192 | 6.972 | 5.81 | 0.0069139 | 11.2 | 9.3333 | 0.011107 | 12.79 | 10.6583 | 0.012683 | 17.98 | 14.9833 | 0.01783 | 19.95 | 16.625 | 0.019784 | 31.5869 | 26.3224 | 0.031324 | 18.5511 | 15.4592 | 0.018396 | 100 | 0.11804 | 27 |  |  | 120 | 0
| 3211127 | Books & Periodicals | Item | 2 | 1 Item | 2 | 2e-05 | 0 | 0 | 0 | 0.1 | 5 | 0.0001 | 0.03 | 1.5 | 3e-05 | 0.05 | 2.5 | 5e-05 | 0.1 | 5 | 0.0001 | 0.2 | 10 | 0.0002 | 0.8816 | 44.08 | 0.0008816 | 0.6384 | 31.92 | 0.0006384 | 100 | 0.002 | 28 |  |  | 2 | 0
|  | Training Expenditure | [34 empty] | 0 | 0
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | Item | 119 | 1 Item | 119 | 0.00118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 100 | 0.118 | 0 | 0 | 0 | 100 | 0.118 | 30 |  |  | 119 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 536.7 | 1 Item | 536.7 | 0.00533 | 0 | 0 | 0 | 9.22 | 1.7179 | 0.0091564 | 29.86 | 5.5636 | 0.029654 | 86.55 | 16.1263 | 0.085953 | 175.87 | 32.7688 | 0.17466 | 22.21 | 4.1383 | 0.022057 | 127.794 | 23.8111 | 0.12691 | 85.196 | 15.874 | 0.084609 | 100 | 0.533 | 31 |  |  | 536.7 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 3130.1 | 1 Item | 3130.1 | 0.03106 | 0 | 0 | 0 | 0 | 0 | 0 | 199.49 | 6.3733 | 0.19795 | 524.89 | 16.7691 | 0.52085 | 622.25 | 19.8796 | 0.61746 | 338.12 | 10.8022 | 0.33552 | 910.5705 | 29.0908 | 0.90356 | 534.7795 | 17.0851 | 0.53066 | 100 | 3.106 | 32 |  |  | 3130.1 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1331.2 | 1 Item | 1331.2 | 0.01321 | 0 | 0 | 0 | 0 | 0 | 0 | 119.7 | 8.9919 | 0.11878 | 224.29 | 16.8487 | 0.22257 | 234.21 | 17.5939 | 0.23242 | 82.97 | 6.2327 | 0.082334 | 368.5165 | 27.683 | 0.36569 | 301.5135 | 22.6498 | 0.2992 | 100 | 1.321 | 33 |  |  | 1331.2 | 0
| 3211109 | Casual labour/Job worker | MM | 22 | 1 Item | 22 | 0.00022 | 0.25 | 1.1364 | 0.00025 | 2.11 | 9.5909 | 0.00211 | 2.35 | 10.6818 | 0.00235 | 2 | 9.0909 | 0.002 | 4.25 | 19.3182 | 0.00425 | 3.49 | 15.8636 | 0.00349 | 4.681 | 21.2773 | 0.004681 | 2.869 | 13.0409 | 0.002869 | 100 | 0.02175 | 34 |  |  | 22 | 0
| 3256103 | Consumable Stores |  | 15 | 1 Item | 15 | 0.00015 | 0 | 0 | 0 | 0.99 | 6.6 | 0.00099 | 0.75 | 5 | 0.00075 | 1 | 6.6667 | 0.001 | 1 | 6.6667 | 0.001 | 3 | 20 | 0.003 | 4.7908 | 31.9387 | 0.0047908 | 3.4692 | 23.128 | 0.0034692 | 100 | 0.015 | 35 |  |  | 15 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 0 | 56+532 | 7901.4 | 0.0784 | 849.67 | 10.7534 | 0.84307 | 1849.425 | 23.4063 | 1.8351 | 1123.15 | 14.2146 | 1.1144 | 689.33 | 8.7242 | 0.68397 | 686.43 | 8.6874 | 0.6811 | 450 | 5.6952 | 0.4465 | 1374.571 | 17.3965 | 1.3639 | 878.824 | 11.1224 | 0.87199 | 100 | 6.9969 | 36 |  |  | 7901.4 | 0
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | item | 30 | 1 Item | 30 | 0.0003 | 0.4 | 1.3333 | 0.0004 | 1.33 | 4.4333 | 0.00133 | 1.5 | 5 | 0.0015 | 4.5 | 15 | 0.0045 | 5 | 16.6667 | 0.005 | 3 | 10 | 0.003 | 8.2766 | 27.5887 | 0.0082766 | 5.9934 | 19.978 | 0.0059934 | 100 | 0.0296 | 37 |  |  | 30 | 0
| 3111332 | b) Interim Evaluation | item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27 | 2.7 | 0.00027 | 0.25 | 2.5 | 0.00025 | 0.77 | 7.7 | 0.00077 | 0.41 | 4.1 | 0.00041 | 8.3 | 83 | 0.0083 | 0 | 0 | 0 | 100 | 0.01 | 38 |  |  | 10 | 0
| 3111332 | c) Progress Monitoring | item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 3 | 0.0003 | 0.25 | 2.5 | 0.00025 | 0.75 | 7.5 | 0.00075 | 0.41 | 4.1 | 0.00041 | 4.145 | 41.45 | 0.004145 | 4.145 | 41.45 | 0.004145 | 100 | 0.01 | 39 |  |  | 10 | 0
| 3257104 | Survey | item | 162 | 1 Item | 162 | 0.00161 | 0 | 0 | 0 | 7.62 | 4.7037 | 0.007573 | 17.47 | 10.784 | 0.017362 | 30 | 18.5185 | 0.029815 | 29.93 | 18.4753 | 0.029745 | 30 | 18.5185 | 0.029815 | 26.7786 | 16.53 | 0.026613 | 20.2014 | 12.47 | 0.020077 | 100 | 0.161 | 40 |  |  | 162 | 0
| 3255101 | Computer Consumables | item | 60 | 1 Item | 60 | 0.0006 | 0.49 | 0.81667 | 0.00049 | 1.499 | 2.4983 | 0.001499 | 4.5 | 7.5 | 0.0045 | 6.48 | 10.8 | 0.00648 | 7.5 | 12.5 | 0.0075 | 10 | 16.6667 | 0.01 | 16.242 | 27.0701 | 0.016242 | 13.2889 | 22.1483 | 0.013289 | 100 | 0.05951 | 41 |  |  | 60 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | item | 1700 | 1 Item | 1700 | 0.01687 | 0 | 0 | 0 | 84.31 | 4.9594 | 0.083665 | 227.97 | 13.41 | 0.22623 | 263.24 | 15.4847 | 0.26123 | 299.93 | 17.6429 | 0.29764 | 299.96 | 17.6447 | 0.29767 | 299.0163 | 17.5892 | 0.29673 | 225.5737 | 13.269 | 0.22385 | 100 | 1.687 | 42 |  |  | 1700 | 0
|  | Repair, Maintenance & Rehabilitation: | [34 empty] | 0 | 0
| 3258101 | Motor Vehicles |  | 125 | L.S. | 125 | 0.00124 | 0.98 | 0.784 | 0.00097216 | 5.967 | 4.7736 | 0.0059193 | 12 | 9.6 | 0.011904 | 21.99 | 17.592 | 0.021814 | 20.46 | 16.368 | 0.020296 | 14.97 | 11.976 | 0.01485 | 26.7481 | 21.3985 | 0.026534 | 21.8849 | 17.5079 | 0.02171 | 100 | 0.12303 | 44 |  |  | 125 | 0
| 3258102 | Furnitures & Fixtures |  | 10 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0.49 | 4.9 | 0.00049 | 0.74 | 7.4 | 0.00074 | 0.98 | 9.8 | 0.00098 | 0.99 | 9.9 | 0.00099 | 1.11 | 11.1 | 0.00111 | 3.414 | 34.14 | 0.003414 | 2.276 | 22.76 | 0.002276 | 100 | 0.01 | 45 |  |  | 10 | 0
| 3258103 | Computers & office equipments |  | 15 | L.S. | 15 | 0.00015 | 0 | 0 | 0 | 0.5 | 3.3333 | 0.0005 | 0.85 | 5.6667 | 0.00085 | 2 | 13.3333 | 0.002 | 1.99 | 13.2667 | 0.00199 | 3 | 20 | 0.003 | 3.9294 | 26.196 | 0.0039294 | 2.7306 | 18.204 | 0.0027306 | 100 | 0.015 | 46 |  |  | 15 | 0
| 3258105 | Machineries & Equipments |  | 10 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0.22 | 2.2 | 0.00022 | 0.01 | 0.1 | 1e-05 | 0.5 | 5 | 0.0005 | 0.5 | 5 | 0.0005 | 1.99 | 19.9 | 0.00199 | 4.1358 | 41.358 | 0.0041358 | 2.6442 | 26.442 | 0.0026442 | 100 | 0.01 | 47 |  |  | 10 | 0
| 3258107 | Office Building : Repair & Maintenance |  | 25 | L.S. | 25 | 0.00025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.98 | 39.92 | 0.00998 | 10 | 40 | 0.01 | 0 | 0 | 0 | 2.9618 | 11.8472 | 0.0029618 | 2.0582 | 8.2328 | 0.0020582 | 100 | 0.025 | 48 |  |  | 25 | 0
| 3258106 | Residential Building : Repair & Maintenance |  | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.95 | 22.375 | 0.00895 | 5.58 | 13.95 | 0.00558 | 4.95 | 12.375 | 0.00495 | 11.9016 | 29.754 | 0.011902 | 8.6184 | 21.546 | 0.0086184 | 100 | 0.04 | 49 |  |  | 40 | 0
| 3258105 | Engineering Equipments |  | 20 | L.S. | 20 | 0.0002 | 0 | 0 | 0 | 0.09 | 0.45 | 9e-05 | 0.3 | 1.5 | 0.0003 | 0.5 | 2.5 | 0.0005 | 0.5 | 2.5 | 0.0005 | 2 | 10 | 0.002 | 9.1355 | 45.6775 | 0.0091355 | 7.4745 | 37.3725 | 0.0074745 | 100 | 0.02 | 50 |  |  | 20 | 0
|  | Drainage Structures : | [31 empty] | 51 |  |  | 0 | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | 405.55 | 86 | 405.55 | 0.00402 | 0 | 0 | 0 | 0 | 0 | 0 | 59.7 | 14.7207 | 0.059177 | 24.34 | 6.0017 | 0.024127 | 10.99 | 2.7099 | 0.010894 | 33.17 | 8.179 | 0.03288 | 174.7305 | 43.0848 | 0.1732 | 102.6195 | 25.3038 | 0.10172 | 100 | 0.402 | 52 |  |  | 405.55 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | 5 | L.S. | 5 | 5e-05 | 0 | 0 | 0 | 0.9 | 18 | 0.0009 | 0 | 0 | 0 | 0.75 | 15 | 0.00075 | 0.74 | 14.8 | 0.00074 | 0.38 | 7.6 | 0.00038 | 1.3603 | 27.206 | 0.0013603 | 0.8697 | 17.394 | 0.0008697 | 100 | 0.005 | 53 |  |  | 5 | 0
| 3258107 | Others : Repair & Maintenance |  | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 6.25 | 0.0025 | 4.98 | 12.45 | 0.00498 | 1.49 | 3.725 | 0.00149 | 17.3768 | 43.442 | 0.017377 | 13.6532 | 34.133 | 0.013653 | 100 | 0.04 | 54 |  |  | 40 | 0
(a)Sub-total Revenue Component: | [5 empty] | 19562.3 | 0.19415 | 1081.09 | 45.6728 | 1.0727 | 2493.737 |  | 2.4746 | 2227.87 |  | 2.2109 | 2364.86 |  | 2.3471 | 2487.29 |  | 2.4687 | 1601.51 |  | 1.5895 | 4430.6344 |  | 4.3975 | 2875.3086 |  | 2.8539 |  |  | 55 |  |  | 19562.3 | 0
(b) Capital Component: | [36 empty] | 0 | 0
|  | Acquisition of Assets: | [34 empty] | 0 | 0
|  | Motor Vehicle : | [34 empty] | 0 | 0
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 70.25 | 10 | 702.5 | 0.00697 | 346.3 | 49.2954 | 0.34359 | 138.6 | 19.7295 | 0.13751 | 0 | 0 | 0 | 122 | 17.3665 | 0.12104 | 0 | 0 | 0 | 0 | 0 | 0 | 95.6 | 13.6085 | 0.094852 | 0 | 0 | 0 | 100 | 0.35341 | 59 |  |  | 702.5 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 1.52 | 45 | 68.25 | 0.00068 | 5.83 | 8.5421 | 0.0058086 | 26.31 | 38.5495 | 0.026214 | 10.08 | 14.7692 | 0.010043 | 8 | 11.7216 | 0.0079707 | 0 | 0 | 0 | 0 | 0 | 0 | 18.03 | 26.4176 | 0.017964 | 0 | 0 | 0 | 100 | 0.062191 | 60 |  |  | 68.25 | 0
|  | Water Transport : | [34 empty] | 0 | 0
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 18 | 5 | 90 | 0.00089 | 0 | 0 | 0 | 0 | 0 | 0 | 40.29 | 44.7667 | 0.039842 | 21 | 23.3333 | 0.020767 | 0 | 0 | 0 | 0 | 0 | 0 | 28.71 | 31.9 | 0.028391 | 0 | 0 | 0 | 100 | 0.089 | 62 |  |  | 90 | 0
|  | Mechinary & Other Equipment | [30 empty] | 0 | 63 |  |  | 0 | 0
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 1.28 | 7 | 8.97 | 9e-05 | 3.73 | 41.5831 | 0.0037425 | 2.74 | 30.5463 | 0.0027492 | 2.5 | 27.8707 | 0.0025084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.0052575 | 64 |  |  | 8.97 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 0.5 | 2 | 1 | 1e-05 | 0.79 | 79 | 0.00079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 21 | 0.00021 | 0 | 0 | 0 | 100 | 0.00021 | 65 |  |  | 1 | 0
|  | Engineering Equipments | [31 empty] | 66 |  |  | 0 | 0
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Sets | 20.5 | 17 | 20.5 | 0.0002 | 0 | 0 | 0 | 5.55 | 27.0732 | 0.0054146 | 11.15 | 54.3902 | 0.010878 | 3.8 | 18.5366 | 0.0037073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.02 | 67 |  |  | 20.5 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos. | 1 | 3 | 3 | 3e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 100 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.003 | 68 |  |  | 3 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | Nos. | 0 | L.S | 50 | 0.0005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.89 | 15.78 | 0.00789 | 1.6 | 3.2 | 0.0016 | 5 | 10 | 0.005 | 35.51 | 71.02 | 0.03551 | 0 | 0 | 0 | 100 | 0.05 | 69 |  |  | 50 | 0
|  | Computers & Accessories | [34 empty] | 0 | 0
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 0.66 | 37 | 24.5 | 0.00024 | 3.88 | 15.8367 | 0.0038008 | 7.14 | 29.1429 | 0.0069943 | 6.18 | 25.2245 | 0.0060539 | 2.27 | 9.2653 | 0.0022237 | 0 | 0 | 0 | 0 | 0 | 0 | 5.03 | 20.5306 | 0.0049273 | 0 | 0 | 0 | 100 | 0.020199 | 71 |  |  | 24.5 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 1.25 | 11 | 13.75 | 0.00014 | 3.744 | 27.2291 | 0.0038121 | 0 | 0 | 0 | 2.986 | 21.7164 | 0.0030403 | 3.15 | 22.9091 | 0.0032073 | 0 | 0 | 0 | 0 | 0 | 0 | 3.87 | 28.1455 | 0.0039404 | 0 | 0 | 0 | 100 | 0.010188 | 72 |  |  | 13.75 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | No. | 0.75 | 2 | 1.5 | 1e-05 | 0 | 0 | 0 | 0.2 | 13.3333 | 0.00013333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 86.6667 | 0.00086667 | 0 | 0 | 0 | 100 | 0.001 | 73 |  |  | 1.5 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 0.31 | 17 | 5.25 | 5e-05 | 2.97 | 56.5714 | 0.0028286 | 0.2 | 3.8095 | 0.00019048 | 0 | 0 | 0 | 0.91 | 17.3333 | 0.00086667 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 22.2857 | 0.0011143 | 0 | 0 | 0 | 100 | 0.0021714 | 74 |  |  | 5.25 | 0
| 4112314 | Furnitures & Fixtures | item | 50 | LS | 50 | 0.0005 | 7.96 | 15.92 | 0.00796 | 8.45 | 16.9 | 0.00845 | 8.99 | 17.98 | 0.00899 | 9.96 | 19.92 | 0.00996 | 9.97 | 19.94 | 0.00997 | 0 | 0 | 0 | 2.8954 | 5.7908 | 0.0028954 | 1.7746 | 3.5492 | 0.0017746 | 100 | 0.04204 | 75 |  |  | 50 | 0
| 4112303 | Aircooler | Nos. | 1 | 15 | 15 | 0.00015 | 0 | 0 | 0 | 0 | 0 | 0 | 3.77 | 25.1333 | 0.00377 | 2 | 13.3333 | 0.002 | 3.96 | 26.4 | 0.00396 | 2.99 | 19.9333 | 0.00299 | 1.3908 | 9.272 | 0.0013908 | 0.8892 | 5.928 | 0.0008892 | 100 | 0.015 | 76 |  |  | 15 | 0
|  | Acquisition/Purchase of lands and landed properties of Assets: | [34 empty] | 0 | 0
| 4141101 | Land Acquisition ( 470 hectare) | ha | 39.12 | 470 | 18386.72 | 0.18244 | 0 | 0 | 0 | 0 | 0 | 0 | 4649.65 | 25.2881 | 4.6136 | 5794.05 | 31.5121 | 5.7491 | 3879.9 | 21.1016 | 3.8498 | 1000 | 5.4387 | 0.99224 | 1531.56 | 8.3297 | 1.5197 | 1531.56 | 8.3297 | 1.5197 | 100 | 18.244 | 78 |  |  | 18386.72 | 0
|  | Construction and Works: | [34 empty] | 0 | 0
|  | Irrigation Infrastructurs : | [34 empty] | 0 | 0
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos. | 10.26 | 119 | 1220.46 | 0.01211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 116.72 | 9.5636 | 0.11582 | 192.22 | 15.7498 | 0.19073 | 528.6816 | 43.3182 | 0.52458 | 382.8384 | 31.3684 | 0.37987 | 100 | 1.211 | 81 |  |  | 1220.46 | 0
|  | Drainage Structures : | [34 empty] | 0 | 0
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos. | 234.52 | 5 | 1172.62 | 0.01164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668.3934 | 57 | 0.66348 | 504.2266 | 43 | 0.50052 | 100 | 1.164 | 83 |  |  | 1172.62 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 165.96 | 111 | 18421.37 | 0.18279 | 0 | 0 | 0 | 0 | 0 | 0 | 293.15 | 1.5914 | 0.29088 | 2773.9 | 15.0581 | 2.7525 | 3076.61 | 16.7013 | 3.0528 | 4075.22 | 22.1222 | 4.0437 | 4347.3197 | 23.5993 | 4.3137 | 3855.1703 | 20.9277 | 3.8254 | 100 | 18.279 | 84 |  |  | 18421.37 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) | km | 30.29 | 336.214 | 10184.13 | 0.10105 | 0 | 0 | 0 | 0 | 0 | 0 | 349.16 | 3.4285 | 0.34645 | 840.8 | 8.256 | 0.83427 | 4821.52 | 47.3435 | 4.7841 | 2673.22 | 26.2489 | 2.6524 | 839.6808 | 8.245 | 0.83316 | 659.7492 | 6.4782 | 0.65462 | 100 | 10.105 | 85 |  |  | 10184.13 | 0
|  | Others: | [34 empty] | 0 | 0
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | km | 31.19 | 108.974 | 3398.89 | 0.03373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.04 | 13.3879 | 0.45157 | 726.54 | 21.3758 | 0.72101 | 1219.5205 | 35.88 | 1.2102 | 997.7895 | 29.3563 | 0.99019 | 100 | 3.373 | 87 |  |  | 3398.89 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | km | 30.33 | 67.11 | 2035.43 | 0.0202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452.46 | 22.2292 | 0.44903 | 253.65 | 12.4617 | 0.25173 | 771.0056 | 37.8792 | 0.76516 | 558.3144 | 27.4298 | 0.55408 | 100 | 2.02 | 88 |  |  | 2035.43 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | km | 27.9 | 62.662 | 1748.43 | 0.01735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341.85 | 19.5518 | 0.33922 | 179.68 | 10.2766 | 0.1783 | 674.795 | 38.5943 | 0.66961 | 552.105 | 31.5772 | 0.54786 | 100 | 1.735 | 89 |  |  | 1748.43 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | km | 0 | 261.238 | 21445.23 | 0.21275 | 0 | 0 | 0 | 0 | 0 | 0 | 336.91 | 1.571 | 0.33424 | 3910 | 18.2325 | 3.879 | 1880.15 | 8.7672 | 1.8652 | 2923.61 | 13.6329 | 2.9004 | 7188.8448 | 33.5219 | 7.1318 | 5205.7152 | 24.2745 | 5.1644 | 100 | 21.275 | 90 |  |  | 21445.23 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos. | 20.96 | 7 | 146.69 | 0.00146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 73.26 | 49.9421 | 0.072915 | 0 | 0 | 0 | 40.3865 | 27.5319 | 0.040197 | 33.0435 | 22.5261 | 0.032888 | 100 | 0.146 | 91 |  |  | 146.69 | 0
| 4111201 | Threshing Floor Construction | Nos. | 45 | 5 | 225 | 0.00223 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 123.75 |  |  | 101.25 |  |  |  |  | 92 |  |  | 225 | 0
| 4111201 | Construction of WMG Office | Nos. | 29.42 | 55 | 1618 | 0.01605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.09 | 2.6014 | 0.041752 | 93.33 | 5.7682 | 0.09258 | 845.0706 | 52.2293 | 0.83828 | 637.5094 | 39.4011 | 0.63239 | 100 | 1.605 | 93 |  |  | 1618 | 0
| 4111201 | O&M During Construction | item | 0 | 1 | 120 | 0.00119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 55 | 0.06545 | 54 | 45 | 0.05355 | 100 | 0.119 | 94 |  |  | 120 | 0
|  | (b) Sub-total Capital Component: |  |  |  | 81177.19 | 0.80545 | 375.204 |  | 0.37233 | 189.19 |  | 0.18766 | 5714.816 | 263.73 | 5.6703 | 13502.73 |  | 13.3974 | 15155.13 |  | 15.0377 | 12125.46 |  | 12.0311 | 19038.7247 |  | 18.7674 | 15075.9353 |  | 14.8581 |  |  | 95 |  |  | 81177.19 | 0
|  | Total Cost (a+b) : |  |  |  | 100739.49 | 0.9996 | 1456.294 |  | 1.4451 | 2682.927 |  | 2.6623 | 7942.686 | 263.73 | 7.8811 | 15867.59 |  | 15.7445 | 17642.42 |  | 17.5065 | 13726.97 |  | 13.6207 | 23469.3591 |  | 23.1649 | 17951.2439 |  | 17.712 |  |  | 96 |  |  | 100739.49 | 0
| 0 | (c) Physical Contingency ( Lump sum): | item | 0 | L.S. | 30.51 | 0.0003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.1703 | 53 | 0.0159 | 14.3397 | 47 | 0.0141 | 100 | 0.03 | 97 |  |  | 30.51 | 0
| 0 | (d) Price Contingency (Lump sum): | item | 0 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 54 | 0.0054 | 4.6 | 46 | 0.0046 | 100 | 0.01 | 98 |  |  | 10 | 0
|  | Grand Total (a+b+c+d) : |  |  |  | 100780 | 1 | 1456.294 |  | 1.4451 | 2682.927 |  | 2.6623 | 7942.686 |  | 7.8811 | 15867.59 |  | 15.7445 | 17642.42 |  | 17.5065 | 13726.97 |  | 13.6207 | 23490.9294 |  | 23.1862 | 17970.1836 |  | 17.7307 |  |  | 99 |  | 98.3319 | 100780
# Weight of each item = |  | (Est. cost of each respective item)
(Total cost of all Physical items)
# Physical Percentage of item = |  | Quantity/number targeted in each year |  |  |  |  | x 100
Total quantity/number of respective item for whole project period
# Physical % of total Project = |  | Weight of each item x % of item
[10 empty] | 1.445 |  |  | 2.6622 |  |  | 7.8812 |  |  | 15.7448 |  |  | 17.5059 |  |  | 13.6207 |  |  | 23.3091 |  |  | 17.8311 |  | 100
[6 empty] | 100780 |  | 1456.294 |  |  | 4139.221 |  |  | 12081.907 |  |  | 27949.497 |  |  | 45591.917 |  |  | 59318.887
59318.887

## Inves._Cost
Investment Cost
Name of the Project : |  |  | Haor Flood Management and Livelihood Improvement Project.(BWDB Part)(Revised)
Name of agency/Division/Ministry : |  |  | Bangladesh Water Development Board / Ministry of Water Resources
(In Lakh Taka)
Budget Head | Economic Code/ Sub Code | Code/Sub Code Description | Total Project Cost | Financial | [7 empty] | CF | Economic
|  |  |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8 |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | 5 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.902 | 0 | 0.2706 | 0.11726 | 0.25256 | 0.2706 | 0.451 | 1.8258 | 1.3222
| 3111327 | Overtime Allowance | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6826 | 3.3374
| 3111338 | Other Allowance | 140 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.902 | 0 | 0 | 0 | 22.55 | 10.4722 | 12.628 | 48.3779 | 32.2519
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 120 | 0.99 | 11.92 | 14.98 | 17.96 | 12.7 | 14.97 | 28.8176 | 17.6624 | 0.902 | 0.89298 | 10.7518 | 13.512 | 16.1999 | 11.4554 | 13.5029 | 25.9935 | 15.9315
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.21 | 58.3544 | 35.7656 | 0.812 | 0 | 13.195 | 25.4562 | 28.3063 | 27.7785 | 27.7785 | 47.3838 | 29.0417
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2874.35 | 223.75 | 464.64 | 327.7 | 337.33 | 249.75 | 177.18 | 634.52 | 459.48 | 0.812 | 181.685 | 377.2877 | 266.0924 | 273.912 | 202.797 | 143.8702 | 515.2302 | 373.0978
| 3211119 | Postage | 5 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.48 | 2.175 | 1.575 | 0.812 | 0 | 0.0406 | 0.10556 | 0.17864 | 0.30044 | 0.38976 | 1.7661 | 1.2789
| 3211120 | Telephones/Telegram/Teleprinter | 5 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.07 | 2.4156 | 1.5444 | 0.812 | 0.17052 | 0.19488 | 0.23548 | 0.1218 | 0.06496 | 0.05684 | 1.9615 | 1.2541
| 3211117 | Telex/Fax/Internet | 5 | 0.25 | 0.001 | 0.09 | 0.05 | 0.05 | 0.1 | 2.497 | 1.962 | 0.812 | 0.203 | 0.000812 | 0.07308 | 0.0406 | 0.0406 | 0.0812 | 2.0276 | 1.5931
| 3221104 | Registration Fee (Vehicles) | 20 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 0.17 | 4.9833 | 2.9267 | 0.812 | 0.8932 | 6.7964 | 0.06496 | 0 | 1.9244 | 0.13804 | 4.0464 | 2.3765
| 3211115 | Water | 5 | 0 | 0.12 | 0.23 | 0.37 | 0.4 | 0.55 | 2.0313 | 1.2987 | 0.812 | 0 | 0.09744 | 0.18676 | 0.30044 | 0.3248 | 0.4466 | 1.6494 | 1.0545
| 3211113 | Electricity | 20 | 0.19 | 1.67 | 1.78 | 2.31 | 2.78 | 2.89 | 4.609 | 3.771 | 0.812 | 0.15428 | 1.356 | 1.4454 | 1.8757 | 2.2574 | 2.3467 | 3.7425 | 3.0621
| 3243102 | Gas & Fuel | 40 | 0.94 | 3.7 | 3 | 4 | 5.89 | 4.02 | 11.2545 | 7.1955 | 0.812 | 0.76328 | 3.0044 | 2.436 | 3.248 | 4.7827 | 3.2642 | 9.1387 | 5.8427
| 3243101 | Petrol and Lubricant | 170 | 0.62 | 6.99 | 18.97 | 18 | 20 | 24.18 | 46.3068 | 34.9332 | 0.72 | 0.4464 | 5.0328 | 13.6584 | 12.96 | 14.4 | 17.4096 | 33.3409 | 25.1519
| 3221108 | Insurance/Bank Charges (including Vehicles) | 3 | 0.08 | 0.749 | 0.01 | 0.22 | 0.1 | 0.91 | 0.51205 | 0.41895 | 0.902 | 0.07216 | 0.6756 | 0.00902 | 0.19844 | 0.0902 | 0.82082 | 0.46187 | 0.37789
| 3255102 | Printing & Binding | 50 | 0.2 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.355 | 5.981 | 0.812 | 0.1624 | 5.6791 | 13.7959 | 4.872 | 3.2318 | 0.406 | 7.5962 | 4.8566
| 3255104 | Stationery, Seals & Stamps | 120 | 0.97 | 6.972 | 11.2 | 12.79 | 17.98 | 19.95 | 31.5869 | 18.5511 | 0.812 | 0.78764 | 5.6613 | 9.0944 | 10.3855 | 14.5998 | 16.1994 | 25.6486 | 15.0635
| 3211127 | Books & Periodicals | 2 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.812 | 0 | 0.0812 | 0.02436 | 0.0406 | 0.0812 | 0.1624 | 0.71586 | 0.51838
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 107.338 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 536.7 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 22.21 | 127.794 | 85.196 | 0.902 | 0 | 8.3164 | 26.9337 | 78.0681 | 158.6347 | 20.0334 | 115.2702 | 76.8468 | 536.7 | 484.1034 | 0.902 | 484.1034
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 3130.1 | 0 | 0 | 199.49 | 524.89 | 622.25 | 338.12 | 910.5705 | 534.7795 | 0.902 | 0 | 0 | 179.94 | 473.4508 | 561.2695 | 304.9842 | 821.3346 | 482.3711 | 3130.1 | 2823.3502 | 0.902 | 2823.3502
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 1331.2 | 0 | 0 | 119.7 | 224.29 | 234.21 | 82.97 | 368.5165 | 301.5135 | 0.902 | 0 | 0 | 107.9694 | 202.3096 | 211.2574 | 74.8389 | 332.4019 | 271.9652 | 1331.2 | 1200.7424 | 0.902 | 1200.7424
| 3211109 | Casual labour/Job worker | 22 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.49 | 4.681 | 2.869 | 0.902 | 0.2255 | 1.9032 | 2.1197 | 1.804 | 3.8335 | 3.148 | 4.2223 | 2.5878
| 3256103 | Consumable Stores | 15 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.812 | 0 | 0.80388 | 0.609 | 0.812 | 0.812 | 2.436 | 3.8901 | 2.817 | 15 | 12.18 | 0.812 | 12.18
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 7901.4 | 849.67 | 1849.425 | 1123.15 | 689.33 | 686.43 | 450 | 1374.571 | 878.824 | 0.902 | 766.4023 | 1668.1814 | 1013.0813 | 621.7757 | 619.1599 | 405.9 | 1239.863 | 792.6993 | 7901.4 | 7127.0628 | 0.902 | 7127.0628
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 30 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 3 | 8.2766 | 5.9934 | 0.902 | 0.3608 | 1.1997 | 1.353 | 4.059 | 4.51 | 2.706 | 7.4655 | 5.406 | 30 | 27.06 | 0.902 | 27.06
| 3111332 | b) Interim Evaluation | 10 | 0 | 0 | 0.27 | 0.25 | 0.77 | 0.41 | 8.3 | 0 | 0.902 | 0 | 0 | 0.24354 | 0.2255 | 0.69454 | 0.36982 | 7.4866 | 0
| 3111332 | c) Progress Monitoring | 10 | 0 | 0 | 0.3 | 0.25 | 0.75 | 0.41 | 4.145 | 4.145 | 0.902 | 0 | 0 | 0.2706 | 0.2255 | 0.6765 | 0.36982 | 3.7388 | 3.7388
| 3257104 | Survey | 162 | 0 | 7.62 | 17.47 | 30 | 29.93 | 30 | 26.7786 | 20.2014 | 0.902 | 0 | 6.8732 | 15.7579 | 27.06 | 26.9969 | 27.06 | 24.1543 | 18.2217
| 3255101 | Computer Consumables | 60 | 0.49 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.242 | 13.2889 | 0.902 | 0.44198 | 1.3521 | 4.059 | 5.845 | 6.765 | 9.02 | 14.6503 | 11.9866 | 60 | 54.12 | 0.902 | 54.12
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 | 0 | 84.31 | 227.97 | 263.24 | 299.93 | 299.96 | 299.0163 | 225.5737 | 0.86 | 0 | 72.5066 | 196.0542 | 226.3864 | 257.9398 | 257.9656 | 257.154 | 193.9934 |  | 1462 | 0.86
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles | 125 | 0.98 | 5.967 | 12 | 21.99 | 20.46 | 14.97 | 26.7481 | 21.8849 | 0.86 | 0.8428 | 5.1316 | 10.32 | 18.9114 | 17.5956 | 12.8742 | 23.0034 | 18.821
| 3258102 | Furnitures & Fixtures | 10 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 1.11 | 3.414 | 2.276 | 0.86 | 0 | 0.4214 | 0.6364 | 0.8428 | 0.8514 | 0.9546 | 2.936 | 1.9574
| 3258103 | Computers & office equipments | 15 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.86 | 0 | 0.43 | 0.731 | 1.72 | 1.7114 | 2.58 | 3.3793 | 2.3483
| 3258105 | Machineries & Equipments | 10 | 0 | 0.22 | 0.01 | 0.5 | 0.5 | 1.99 | 4.1358 | 2.6442 | 0.86 | 0 | 0.1892 | 0.0086 | 0.43 | 0.43 | 1.7114 | 3.5568 | 2.274 | 10 | 8.6 | 0.86 | 8.6
| 3258107 | Office Building : Repair & Maintenance | 25 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.765 | 0 | 0 | 0 | 7.6347 | 7.65 | 0 | 2.2658 | 1.5745 | 25 | 19.125 | 0.765 | 19.125
| 3258106 | Residential Building : Repair & Maintenance | 40 | 0 | 0 | 0 | 8.95 | 5.58 | 4.95 | 11.9016 | 8.6184 | 0.765 | 0 | 0 | 0 | 6.8467 | 4.2687 | 3.7868 | 9.1047 | 6.5931 | 40 | 30.6 | 0.765 | 30.6
| 3258105 | Engineering Equipments | 20 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.86 | 0 | 0.0774 | 0.258 | 0.43 | 0.43 | 1.72 | 7.8565 | 6.4281
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 405.55 | 0 | 0 | 59.7 | 24.34 | 10.99 | 33.17 | 174.7305 | 102.6195 | 0.812 | 0 | 0 | 48.4764 | 19.7641 | 8.9239 | 26.934 | 141.8812 | 83.327 | 405.55 | 329.3066 | 0.812 | 329.3066
| 3258128 | Water Transport : Repair of Speedboat(s) | 5 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.38 | 1.3603 | 0.8697 | 0.812 | 0 | 0.7308 | 0 | 0.609 | 0.60088 | 0.30856 | 1.1046 | 0.7062 | 5 | 4.06 | 0.812 | 4.06
| 3258107 | Others : Repair & Maintenance | 40 | 0 | 0 | 0 | 2.5 | 4.98 | 1.49 | 17.3768 | 13.6532 | 0.902 | 0 | 0 | 0 | 2.255 | 4.492 | 1.344 | 15.6739 | 12.3152 | 40 | 36.08 | 0.902 | 36.08
| (a)Sub-total Revenue Component: |  | 19562.3 | 1081.09 | 2493.737 | 2227.87 | 2364.86 | 2487.29 | 1601.51 | 4430.6344 | 2875.3086 |  | 954.5043 | 2198.2426 | 1955.1289 | 2076.9077 | 2194.3755 | 1400.9975 | 3886.3211 | 2516.391 | 19562.3 | 17182.8686 | 0 | 12156.3904
(b) Capital Component:
Acquisition of Assets:
|  | Motor Vehicle : | [18 empty] | 0 | 0 | 0 | 0
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 | 346.3 | 138.6 | 0 | 122 | 0 | 0 | 95.6 | 0 | 0.68 | 235.484 | 94.248 | 0 | 82.96 | 0 | 0 | 65.008 | 0 | 702.5 | 477.7 | 0.68 | 477.7
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 68.25 | 5.83 | 26.31 | 10.08 | 8 | 0 | 0 | 18.03 | 0 | 0.68 | 3.9644 | 17.8908 | 6.8544 | 5.44 | 0 | 0 | 12.2604 | 0 | 68.25 | 46.41 | 0.68 | 46.41
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 90 | 0 | 0 | 40.29 | 21 | 0 | 0 | 28.71 | 0 | 0.68 | 0 | 0 | 27.3972 | 14.28 | 0 | 0 | 19.5228 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 | 3.73 | 2.74 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0.812 | 3.0288 | 2.2249 | 2.03 | 0 | 0 | 0 | 0 | 0 | 8.97 | 7.2836 | 0.812 | 7.2836
| 4112316 | Fax -2 nos (PMO 2 Nos.). | 1 | 0.79 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0 | 0.812 | 0.64148 | 0 | 0 | 0 | 0 | 0 | 0.17052 | 0 | 1 | 0.812 | 0.812 | 0.812
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 | 0 | 5.55 | 11.15 | 3.8 | 0 | 0 | 0 | 0 | 0.68 | 0 | 3.774 | 7.582 | 2.584 | 0 | 0 | 0 | 0 | 20.5 | 13.94 | 0.68 | 13.94
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0.68 | 0 | 0 | 0 | 2.04 | 0 | 0 | 0 | 0 | 3 | 2.04 | 0.68 | 2.04
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 50 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 35.51 | 0 | 0.68 | 0 | 0 | 0 | 5.3652 | 1.088 | 3.4 | 24.1468 | 0 | 50 | 34 | 0.68 | 34
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 24.5 | 3.88 | 7.14 | 6.18 | 2.27 | 0 | 0 | 5.03 | 0 | 0.812 | 3.1506 | 5.7977 | 5.0182 | 1.8432 | 0 | 0 | 4.0844 | 0 | 24.5 | 19.894 | 0.812 | 19.894
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 3.87 | 0 | 0.812 | 3.0401 | 0 | 2.4246 | 2.5578 | 0 | 0 | 3.1424 | 0 | 13.75 | 11.165 | 0.812 | 11.165
| 4112202 | A3 Combo Printer 2 no ( PMO) | 1.5 | 0 | 0.2 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0.812 | 0 | 0.1624 | 0 | 0 | 0 | 0 | 1.0556 | 0 | 1.5 | 1.218 | 0.812 | 1.218
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 1.17 | 0 | 0.812 | 2.4116 | 0.1624 | 0 | 0.73892 | 0 | 0 | 0.95004 | 0
| 4112314 | Furnitures & Fixtures | 50 | 7.96 | 8.45 | 8.99 | 9.96 | 9.97 | 0 | 2.8954 | 1.7746 | 0.812 | 6.4635 | 6.8614 | 7.2999 | 8.0875 | 8.0956 | 0 | 2.3511 | 1.441
| 4112303 | Aircooler | 15 | 0 | 0 | 3.77 | 2 | 3.96 | 2.99 | 1.3908 | 0.8892 | 0.812 | 0 | 0 | 3.0612 | 1.624 | 3.2155 | 2.4279 | 1.1293 | 0.72203
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | 18386.72 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 1000 | 1531.56 | 1531.56 | 0.902 | 0 | 0 | 4193.9843 | 5226.2331 | 3499.6698 | 902 | 1381.4671 | 1381.4671 | 18386.72 | 16584.8214 | 0.902 | 16584.8214
Construction and Works:
|  | Irrigation Infrastructurs : | [18 empty] | 0 | 0 | 0 | 0
| 4111306 | Construction of Irrigation Inlet (New Haors) | 1220.46 | 0 | 0 | 0 | 0 | 116.72 | 192.22 | 528.6816 | 382.8384 | 0.902 | 0 | 0 | 0 | 0 | 105.2814 | 173.3824 | 476.8708 | 345.3202 | 1310 | 996.91 | 0.761 | 996.91
|  | Drainage Structures : | [18 empty] | 0 | 0 | 0 | 0
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 1172.62 | 0 | 0 | 0 | 0 | 0 | 0 | 668.3934 | 504.2266 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 511.321 | 385.7333 | 1172.62 | 897.0543 | 0.765 | 897.0543
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 18421.37 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 4075.22 | 4347.3197 | 3855.1703 | 0.765 | 0 | 0 | 224.2597 | 2122.0335 | 2353.6067 | 3117.5433 | 3325.6996 | 2949.2053 | 18421.37 | 14092.348 | 0.765 | 14092.348
| 4111307 | Re-excavation of Khal/River (New Haors) | 10184.13 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 2673.22 | 839.6808 | 659.7492 | 0.761 | 0 | 0 | 265.7108 | 639.8488 | 3669.1767 | 2034.3204 | 638.9971 | 502.0691 | 10184.13 | 7750.1229 | 0.761 | 7750.1229
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 3398.89 | 0 | 0 | 0 | 0 | 455.04 | 726.54 | 1219.5205 | 997.7895 | 0.761 | 0 | 0 | 0 | 0 | 346.2854 | 552.8969 | 928.0551 | 759.3178 | 3398.89 | 2586.5553 | 0.761 | 2586.5553
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 2035.43 | 0 | 0 | 0 | 0 | 452.46 | 253.65 | 771.0056 | 558.3144 | 0.761 | 0 | 0 | 0 | 0 | 344.3221 | 193.0276 | 586.7353 | 424.8773 | 2035.43 | 1548.9622 | 0.761 | 1548.9622
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 1748.43 | 0 | 0 | 0 | 0 | 341.85 | 179.68 | 674.795 | 552.105 | 0.761 | 0 | 0 | 0 | 0 | 260.1479 | 136.7365 | 513.519 | 420.1519 | 1748.43 | 1330.5552 | 0.761 | 1330.5552
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 21445.23 | 0 | 0 | 336.91 | 3910 | 1880.15 | 2923.61 | 7188.8448 | 5205.7152 | 0.761 | 0 | 0 | 256.3885 | 2975.51 | 1430.7942 | 2224.8672 | 5470.7109 | 3961.5493 | 21445.23 | 16319.82 | 0.761 | 16319.82
| 4111201 | Rehabilitation of Regulator (New Haors) | 146.69 | 0 | 0 | 0 | 0 | 73.26 | 0 | 40.3865 | 33.0435 | 0.761 | 0 | 0 | 0 | 0 | 55.7509 | 0 | 30.7341 | 25.1461 | 146.69 | 111.6311 | 0.761 | 111.6311
| 4111201 | Threshing Floor Construction | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 123.75 | 101.25 | 2.761 | 0 | 0 | 0 | 0 | 0 | 0 | 341.6738 | 279.5513
| 4111201 | Construction of WMG Office | 1618 | 0 | 0 | 0 | 0 | 42.09 | 93.33 | 845.0706 | 637.5094 | 0.765 | 0 | 0 | 0 | 0 | 32.1989 | 71.3975 | 646.479 | 487.6947 | 1618 | 1237.77 | 0.765 | 1237.77
| 4111201 | O&M During Construction | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 54 | 0.761 | 0 | 0 | 0 | 0 | 0 | 0 | 50.226 | 41.094 | 120 | 91.32 | 0.761 | 91.32
|  | (b) Sub-total Capital Component: | 81177.19 | 375.204 | 189.19 | 5714.816 | 13502.73 | 15155.13 | 12125.46 | 19038.7247 | 15075.9353 |  | 258.1845 | 131.1216 | 5002.0108 | 11091.1461 | 12109.633 | 9411.9998 | 15036.31 | 11965.3404
|  | Total Cost (a+b) : | 100739.49 | 1456.294 | 2682.927 | 7942.686 | 15867.59 | 17642.42 | 13726.97 | 23469.3591 | 17951.2439 |  | 1212.6888 | 2329.3642 | 6957.1397 | 13168.0538 | 14304.0085 | 10812.9973 | 18922.6312 | 14481.7314
| 0 | (c) Physical Contingency ( Lump sum): | 30.51 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1703 | 14.3397 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 12.3703 | 10.9699
| 0 | (d) Price Contingency (Lump sum): | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total (a+b+c+d) : | 100780 | 1456.294 | 2682.927 | 7942.686 | 15867.59 | 17642.42 | 13726.97 | 23490.9294 | 17970.1836 |  | 1212.6888 | 2329.3642 | 6957.1397 | 13168.0538 | 14304.0085 | 10812.9973 | 18935.0014 | 14492.7013 | 82211.9549 | 100780
|  |  |  | 1456.294 | 2682.927 | 7942.686 | 15867.59 | 17642.42 | 13726.97 | 23490.9294 | 17970.1836
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Crop. Pattern
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
PRE - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic | ML | Seed | Urea | TSP | MP
1. | Boro (L) | 47000 | 3.5 | 164500 | 10000 | 10050 | 16450 | 16532.25 | 5405000 | 1880000 | 9400000 | 7520000 | 4700000
2. | Boro (HYV) | 125000 | 4 | 500000 | 11000 | 11055 | 55000 | 55275 | 18750000 | 5000000 | 37500000 | 30000000 | 18750000
| Total : | 172000 | - | - | - | - | 71450 | 71807.25 | 24155000 | 6880000 | 46900000 | 37520000 | 23450000
|  | Cropping Intensity = |  | 110%
|  | Total Paddy Production = |  |  | 664500 | mt.
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
POST - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic
1. | Boro (HYV) | 280500 | 5.5 | 1542750 | 10000 | 10050 | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
| Total : | 280500 | - | - | - | - | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
|  | Cropping Intensity = |  | 179.357 | %
|  | Total Paddy Production = |  |  | 1542750 | mt.
|  | Incremental Paddy Production = |  |  | 878250 | mt.
Variable Cost of Cultivation
PRE - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 24155000 | 100 | 75 | 24155 | 18116.25
2. | Power Tiller | - | - | - | - | 6880 | 6205.76
3. | Seed/Seedlings
a) | Paddy | mt. | 6880 | 30000 | 27060 | 2064 | 1861.728
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
d) | Mustard | mt. | 0 | 50000 | 45100 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 46900 | 8000 | 12000 | 3752 | 5628
b) | T.S.P. | mt. | 37520 | 22000 | 33000 | 8254.4 | 12381.6
c) | M.P. | mt. | 23450 | 18000 | 27000 | 4221 | 6331.5
5. | Insecticide | - | - | - | - | 200 | 180.4
6. | Irrigation Cost | - | - | - | - | 500 | 750
| Total | - | - | - | - | 49526.4 | 50705.238
POST - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 43477500 | 100 | 75 | 43477.5 | 32608.125
2. | Power Tiller | - | - | - | - | 11220 | 10120.44
3. | Seed/Seedlings
a) | Paddy | mt. | 11220 | 30000 | 27060 | 3366 | 3036.132
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
c) | Onion | mt. | 0 | 50000 | 45100 | 0 | 0
d) | Jute | mt. | 0 | 50000 | 45100 | 0 | 0
e) | Vegetables | mt. | 0 | 20000 | 18040 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 84150 | 8000 | 12000 | 6732 | 10098
|  | mt. | 34.61 | 22000 | 19844 | 7.6142 | 6.868
b) | T.S.P. | mt. | 67320 | 22000 | 33000 | 14810.4 | 22215.6
|  | mt. | 34.61 | 200 | 180.4 | 0.06922 | 0.062436
c) | M.P. | mt. | 42075 | 18000 | 27000 | 7573.5 | 11360.25
|  |  | 0 | - | -
|  |  | 0 |  | 0 | 0 | 0
5. | Insecticide | - | - | - | - | 500 | 451
6. | Irrigation Cost | - | - | - | - | 1000 | 1500
| Total | - | - | - |  | 88687.0834 | 91396.4774
| Incremental Farm Labour = |  | 19322500 | mandays
FIXED COST
A. | PRE - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
B. | POST - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
SUMMARY OF BENEFIT
A. | POST - PROJECT CONDITION
|  |  |  | Financial |  |  | Economic
1. | Gross Production Value |  |  | 154275 |  |  | 155046.375
2. | Cost of cultivation
| i) Variable Cost |  |  | 88687.0834 |  |  | 91396.4774
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (A1-A2) |  |  | 65587.9166 |  |  | 63649.8976
B. | PRE - PROJECT CONDITION
1. | Gross Production Value |  |  | 71450 |  |  | 71807.25
2. | Cost of cultivation
| i) Variable Cost |  |  | 49526.4 |  |  | 50705.238
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (B1-B2) |  |  | 21923.6 |  |  | 21102.012
C. | Net Incremental Benefit from Agriculture (A3-B3) |  |  | 43664.3166 |  |  | 42547.8856

## FIRR
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.294 | 0 | 1456.294 | 0 | 0 | 0 | -1456.294
2 | 2682.927 | 0 | 2682.927 | 0 | 0 | 0 | -2682.927
3 | 7942.686 | 0 | 7942.686 | 0 | 0 | 0 | -7942.686
4 | 15867.59 | 0 | 15867.59 | 0 | 0 | 0 | -15867.59
5 | 17642.42 | 0 | 17642.42 | 0 | 0 | 0 | -17642.42
6 | 13726.97 | 0 | 13726.97 | 21832.1583 | 0 | 21832.1583 | 8105.1883
7 | 23490.9294 | 0 | 23490.9294 | 26198.5899 | 0 | 26198.5899 | 2707.6605
8 | 17970.1836 | 0 | 17970.1836 | 30565.0216 | 0 | 30565.0216 | 12594.838
9 |  | 670 | 670 | 34931.4533 | 0 | 34931.4533 | 34261.4533
10 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
11 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
12 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
13 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
14 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
15 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
16 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
17 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
18 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
19 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
20 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
21 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
22 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
23 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
24 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
25 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
26 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
27 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
28 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
29 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
30 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
NPV @12% | 54025.9151 | 2068.6546 | 56094.5698 | 166922.8114 | 0 | 166922.8114 | 110828.2416
All calculations are based on project period of 30 years
FIRR base case |  |  | 33.5%
Benefit Cost Ratio |  |  | 2.9757
NPV @12% |  |  | 110828.2416

## EIRR
Computation of Internal Rate of Return
(Economic)
(In Lakh Taka)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1212.6888 | 0 | 1212.6888 | 0 | 0 | 0 | -1212.6888
2 | 2329.3642 | 0 | 2329.3642 | 0 | 0 | 0 | -2329.3642
3 | 6957.1397 | 0 | 6957.1397 | 0 | 0 | 0 | -6957.1397
4 | 13168.0538 | 0 | 13168.0538 | 0 | 0 | 0 | -13168.0538
5 | 14304.0085 | 0 | 14304.0085 | 0 | 0 | 0 | -14304.0085
6 | 10812.9973 | 0 | 10812.9973 | 21273.9428 | 0 | 21273.9428 | 10460.9455
7 | 18935.0014 | 0 | 18935.0014 | 25528.7313 | 0 | 25528.7313 | 6593.7299
8 | 14492.7013 | 0 | 14492.7013 | 29783.5199 | 0 | 29783.5199 | 15290.8186
9 |  | 604.34 | 604.34 | 34038.3084 | 0 | 34038.3084 | 33433.9684
10 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
11 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
12 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
13 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
14 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
15 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
16 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
17 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
18 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
19 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
20 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
21 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
22 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
23 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
24 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
25 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
26 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
27 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
28 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
29 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
30 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
NPV @12% | 44273.4751 | 1865.9265 | 46139.4015 | 162654.8457 | 0 | 162654.8457 | 116515.4442
All calculations are based on project period of 30 years
EIRR base case |  |  | 38.09%
Benefit Cost Ratio |  |  | 3.5253
NPV @12% |  |  | 110049.79

## Annex-IV
Annexure-IV
Revised Amortization Schedule
Name of Project |  | : Haor Flood Management & Livelihood Improvement Project (BWDB Part)
Total Investment |  | : BDT 100780.00 Lakh |  |  |  | 102234
Loan Portion |  | : BDT 59529.60 Lakh
Loan Period |  | : 40 Years Including 10 Uears grace Period
Trate of Investment |  | : 0.01% per annum
(Taka in Lac)
Year | Beginning Principal Amount | Yearly Fixed Amount to be Paid (Principal) | Yearly Interes to be Paid | Total Payment (Principal + Interest) | Ending Principal Balance |  |  | 2014-15
1 | 2 | 3 | 4 | 5= (3+4) | 6=(2-3) |  |  | GoB | RPA | DPA | Total
11 | 59529.6 | 1984.32 | 5.953 | 1990.273 | 57545.28 |  | Rev | 231.42 |  | 849.67 | 1081.09
12 | 57545.28 | 1984.32 | 5.7545 | 1990.0745 | 55560.96 |  | Cap | 375.2 |  |  | 375.2
13 | 55560.96 | 1984.32 | 5.5561 | 1989.8761 | 53576.64 |  | Total | 606.62 | 0 | 849.67 | 1456.29
14 | 53576.64 | 1984.32 | 5.3577 | 1989.6777 | 51592.32
15 | 51592.32 | 1984.32 | 5.1592 | 1989.4792 | 49608 |  |  | 2015-16
16 | 49608 | 1984.32 | 4.9608 | 1989.2808 | 47623.68 |  |  | GoB | RPA | DPA | Total
17 | 47623.68 | 1984.32 | 4.7624 | 1989.0824 | 45639.36 |  | Rev | 635.09 | 9.22 | 1849.43 | 2493.74
18 | 45639.36 | 1984.32 | 4.5639 | 1988.8839 | 43655.04 |  | Cap | 189.19 |  |  | 189.19
19 | 43655.04 | 1984.32 | 4.3655 | 1988.6855 | 41670.72 |  | Total | 824.28 | 9.22 | 1849.43 | 2682.93
20 | 41670.72 | 1984.32 | 4.1671 | 1988.4871 | 39686.4 |  | Cum | 1430.9 | 9.22 | 2699.1 | 4139.22
21 | 39686.4 | 1984.32 | 3.9686 | 1988.2886 | 37702.08
22 | 37702.08 | 1984.32 | 3.7702 | 1988.0902 | 35717.76
23 | 35717.76 | 1984.32 | 3.5718 | 1987.8918 | 33733.44 |  |  | 2016-17
24 | 33733.44 | 1984.32 | 3.3733 | 1987.6933 | 31749.12 |  |  | GoB | RPA | DPA | Total
25 | 31749.12 | 1984.32 | 3.1749 | 1987.4949 | 29764.8 |  | Rev | 703.95 | 401.59 | 1093.15 | 2198.69
26 | 29764.8 | 1984.32 | 2.9765 | 1987.2965 | 27780.48 |  | Cap | 4854.6 | 860.19 |  | 5714.79
27 | 27780.48 | 1984.32 | 2.778 | 1987.098 | 25796.16 |  | Total | 5558.55 | 1261.78 | 1093.15 | 7913.48
28 | 25796.16 | 1984.32 | 2.5796 | 1986.8996 | 23811.84 |  | Cum | 6989.45 | 1271 | 3792.25 | 12052.7
29 | 23811.84 | 1984.32 | 2.3812 | 1986.7012 | 21827.52
30 | 21827.52 | 1984.32 | 2.1828 | 1986.5028 | 19843.2 |  | ADP | 2017-18
31 | 19843.2 | 1984.32 | 1.9843 | 1986.3043 | 17858.88 |  |  | GoB | RPA | DPA | Total
32 | 17858.88 | 1984.32 | 1.7859 | 1986.1059 | 15874.56 |  | Rev | 700 | 800 | 800 | 2300
33 | 15874.56 | 1984.32 | 1.5875 | 1985.9075 | 13890.24 |  | Cap | 10300 | 7400 |  | 17700
34 | 13890.24 | 1984.32 | 1.389 | 1985.709 | 11905.92 |  | Total | 11000 | 8200 | 800 | 20000
35 | 11905.92 | 1984.32 | 1.1906 | 1985.5106 | 9921.6
36 | 9921.6 | 1984.32 | 0.99216 | 1985.3122 | 7937.28 |  |  | July2016-Mar17
37 | 7937.28 | 1984.32 | 0.79373 | 1985.1137 | 5952.96 |  |  | GoB | RPA | DPA | Total
38 | 5952.96 | 1984.32 | 0.5953 | 1984.9153 | 3968.64 |  | Rev | -166.51 | 790.78 | -1899.1 | -1274.83
39 | 3968.64 | 1984.32 | 0.39686 | 1984.7169 | 1984.32 |  | Cap | 9735.61 | 7400 | 0 | 17135.61
40 | 1984.32 | 1984.32 | 0.19843 | 1984.5184 | 6.8212e-12 |  | Total | 9569.1 | 8190.78 | -1899.1 | 15860.78
Total |  | 59529.6 | 92.2709 | 59621.8709
Apr2017-June17
[8 empty] | GoB | RPA | DPA | Total
[7 empty] | Rev | 870.46 | -389.19 | 2992.25 | 3473.52
[7 empty] | Cap | -4881.01 | -6539.81 | 0 | -11420.82
[7 empty] | Total | -4010.55 | -6929 | 2992.25 | -7947.3

## FIRR_Backup
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.29 | 0 | 1456.29 | 0 | 0 | 0 | -1456.29
2 | 2652.93 | 0 | 2652.93 | 0 | 0 | 0 | -2652.93
3 | 7942.666 | 0 | 7942.666 | 0 | 0 | 0 | -7942.666
4 | 15866.4 | 0 | 15866.4 | 0 | 0 | 0 | -15866.4
5 | 17642.414 | 0 | 17642.414 | 0 | 0 | 0 | -17642.414
6 | 24717.06 | 0 | 24717.06 | 21832.1583 | 0 | 21832.1583 | -2884.9017
7 | 18586.3447 | 0 | 18586.3447 | 26198.5899 | 0 | 26198.5899 | 7612.2452
8 | 12971.6853 | 0 | 12971.6853 | 30565.0216 | 0 | 30565.0216 | 17593.3363
9 |  | 670 | 670 | 34931.4533 | 0 | 34931.4533 | 34261.4533
10 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
11 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
12 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
13 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
14 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
15 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
16 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
17 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
18 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
19 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
20 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
21 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
22 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
23 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
24 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
25 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
26 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
27 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
28 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
29 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
30 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
NPV @12% | 55331.7512 | 2068.6546 | 57400.4058 | 166922.8114 | 0 | 166922.8114 | 109522.4056
All calculations are based on project period of 30 years
FIRR base case |  |  | 32.6%
Benefit Cost Ratio |  |  | 2.908
NPV @12% |  |  | 109522.4056

## Package_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [19 empty] | 2
KISH/PW-02 | [19 empty] | 3
KISH/PW-03 | [19 empty] | 4
KISH/PW-04 | [19 empty] | 5
KISH/PW-05 | [19 empty] | 6
KISH/PW-06 | [19 empty] | 7
KISH/PW-07 | [19 empty] | 8
KISH/PW-09 | [19 empty] | 9
KISH/PW-10 | [19 empty] | 10
KISH/PW-11 | [19 empty] | 11
KISH/PW-12 | [19 empty] | 12
KISH/PW-13 | [19 empty] | 13
KISH/PW-14 | [19 empty] | 14
KISH/PW-15 | [19 empty] | 15
KISH/PW-16 | [19 empty] | 16
KISH/PW-17 | [19 empty] | 17
KISH/PW-18 | [19 empty] | 18
KISH/PW-19 | [19 empty] | 19
KISH/PW-20 | [19 empty] | 20
KISH/PW-21 | [19 empty] | 21
KISH/PW-22 | [19 empty] | 22
KISH/PW-23 | [19 empty] | 23
KISH/PW-24 | [19 empty] | 24
KISH/PW-25 | [19 empty] | 25
KISH/PW-26 | [19 empty] | 26
KISH/PW-27 | [19 empty] | 27
KISH/PW-28 | [19 empty] | 28
KISH/PW-29 | [19 empty] | 29
KISH/PW-30 | [19 empty] | 30
KISH/PW-31 | [19 empty] | 31
KISH/PW-32 | [19 empty] | 32
KISH/PW-33 | [19 empty] | 33
HOBI/PW-01 | [19 empty] | 34
HOBI/PW-02 | [19 empty] | 35
HOBI/PW-04 | [19 empty] | 36
HOBI/PW-05 | [19 empty] | 37
HOBI/PW-06 | [19 empty] | 38
HOBI/PW-07 | [19 empty] | 39
HOBI/PW-08 | [19 empty] | 40
NETR/PW-01 | [19 empty] | 41
NETR/PW-02 | [19 empty] | 42
NETR/PW-03 | [19 empty] | 43
NETR/PW-04 | [19 empty] | 44
NETR/PW-05 | [19 empty] | 45
NETR/PW-06 | [19 empty] | 46
NETR/PW-07 | [19 empty] | 47
NETR/PW-08 | [19 empty] | 48
SUNM/PW-01 | [19 empty] | 49
SUNM/PW-02 | [19 empty] | 50
SUNM/PW-03 | [19 empty] | 51
SUNM/PW-04 | [19 empty] | 52
SUNM/PW-05 | [19 empty] | 53
SUNM/PW-06 | [19 empty] | 54
SUNM/PW-07 | [19 empty] | 55
BRAH/PW-01 | [19 empty] | 56
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Package_wise_cost
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [18 empty] | 0 | 2
KISH/PW-02 | [18 empty] | 0 | 3
KISH/PW-03 | [18 empty] | 0 | 4
KISH/PW-04 | [18 empty] | 0 | 5
KISH/PW-05 | [18 empty] | 0 | 6
KISH/PW-06 | [18 empty] | 0 | 7
KISH/PW-07 | [18 empty] | 0 | 8
KISH/PW-09 | [18 empty] | 0 | 9
KISH/PW-10 | [18 empty] | 0 | 10
KISH/PW-11 | [18 empty] | 0 | 11
KISH/PW-12 | [18 empty] | 0 | 12
KISH/PW-13 | [18 empty] | 0 | 13
KISH/PW-14 | [18 empty] | 0 | 14
KISH/PW-15 | [18 empty] | 0 | 15
KISH/PW-16 | [18 empty] | 0 | 16
KISH/PW-17 | [18 empty] | 0 | 17
KISH/PW-18 | [18 empty] | 0 | 18
KISH/PW-19 | [18 empty] | 0 | 19
KISH/PW-20 | [18 empty] | 0 | 20
KISH/PW-21 | [18 empty] | 0 | 21
KISH/PW-22 | [18 empty] | 0 | 22
KISH/PW-23 | [18 empty] | 0 | 23
KISH/PW-24 | [18 empty] | 0 | 24
KISH/PW-25 | [18 empty] | 0 | 25
KISH/PW-26 | [18 empty] | 0 | 26
KISH/PW-27 | [18 empty] | 0 | 27
KISH/PW-28 | [18 empty] | 0 | 28
KISH/PW-29 | [18 empty] | 0 | 29
KISH/PW-30 | [18 empty] | 0 | 30
KISH/PW-31 | [18 empty] | 0 | 31
KISH/PW-32 | [18 empty] | 0 | 32
KISH/PW-33 | [18 empty] | 0 | 33
HOBI/PW-01 | [18 empty] | 0 | 34
HOBI/PW-02 | [18 empty] | 0 | 35
HOBI/PW-04 | [18 empty] | 0 | 36
HOBI/PW-05 | [18 empty] | 0 | 37
HOBI/PW-06 | [18 empty] | 0 | 38
HOBI/PW-07 | [18 empty] | 0 | 39
HOBI/PW-08 | [18 empty] | 0 | 40
NETR/PW-01 | [18 empty] | 0 | 41
NETR/PW-02 | [18 empty] | 0 | 42
NETR/PW-03 | [18 empty] | 0 | 43
NETR/PW-04 | [18 empty] | 0 | 44
NETR/PW-05 | [18 empty] | 0 | 45
NETR/PW-06 | [18 empty] | 0 | 46
NETR/PW-07 | [18 empty] | 0 | 47
NETR/PW-08 | [18 empty] | 0 | 48
SUNM/PW-01 | [18 empty] | 0 | 49
SUNM/PW-02 | [18 empty] | 0 | 50
SUNM/PW-03 | [18 empty] | 0 | 51
SUNM/PW-04 | [18 empty] | 0 | 52
SUNM/PW-05 | [18 empty] | 0 | 53
SUNM/PW-06 | [18 empty] | 0 | 54
SUNM/PW-07 | [18 empty] | 0 | 55
BRAH/PW-01 | [18 empty] | 0 | 56
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Haor_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
Chandpur Haor Sub-Project | N-1 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
Nunnir Haor Sub-Project | N-2 | 15 | 0 | 6 | 3 | 2 | 0 | 20 | 0 | 0 | 0 | 29.418 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3
Boro Haor Sub-Project | N-3 | 7 | 0 | 0 | 0 | 4 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4
Noapara Haor Sub-Project | N-4 | 14 | 0 | 4 | 2 | 2 | 0 | 10.757 | 0 | 0 | 0 | 23.29 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
Naogaon Haor Sub-Project | N-5 | 25 | 0 | 6 | 5 | 3 | 0 | 48.968 | 0 | 0 | 0 | 70.395 | 0 | 0 | 20 | 0 | 0 | 0 |  | 6
Badla Haor Sub-Project | N-6 | 6 | 0 | 2 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 21 | 5 | 0 | 0 | 0 | 0 | 0 |  | 7
Chatal Haor Sub-Project | N-7 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8
Dakhshiner Haor Sub-Project | N-8 | 15 | 0 | 1 | 1 | 3 | 0 | 11 | 0 | 0 | 0 | 22.048 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
Suniar Haor Sub-Project | N-9 | 0 | 0 | 2 | 4 | 2 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10
Mokhar Haor Sub-Project | N-10 | 15 | 0 | 6 | 9 | 5 | 0 | 30.058 | 0 | 0 | 0 | 23.815 | 1 | 0 | 0 | 0 | 0 | 0 |  | 11
Ganesh Haor Sub-Project | N-11 | 2 | 0 | 3 | 2 | 0 | 0 | 11.97 | 0 | 0 | 0 | 3.071 | 1 | 0 | 0 | 0 | 0 | 0 |  | 12
Dharmapasha Rui Beel Sub-Project | N-12 | 15 | 0 | 4 | 6 | 4 | 0 | 87.983 | 0 | 0 | 0 | 38.465 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
Dhakua Haor Sub-Project | N-14 | 9 | 0 | 2 | 7 | 6 | 0 | 50.508 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 16
Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 17
Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 18
Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 19
Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 20
Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21
Aralia Khal Sub-Project | R-7 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3.312 | 0 | 26.952 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 22
Bashira River Re-excavation Sub-Project | R-8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
Dampara Water Management Scheme | R-9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13.27 | 35.52 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 24
Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.98 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 25
Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.133 | 10.69 | 3.56 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 26
Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.195 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 27
Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 28
Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 29
Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 30
All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2 |  | 31
Total |  | 127 | 5 | 39 | 43 | 32 | 0 | 342.584 | 108.974 | 67.11 | 57.912 | 254.207 | 7 | 0 | 20 | 60 | 86 | 2 | 0

## distribution_of_cost
Item | costcode | rindex | 1st Revised | 2nd revised | difference
Office Administration | 1 | 2 | 5403.27 | 5360.27 | -43
Fuel & Lubricant | 2 | 3 | 350 | 210 | -140
Training and Livelihood | 3 | 4 | 4491.97 | 5236.54 | 744.57
Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
Repair & Maintenance | 5 | 6 | 265 | 290 | 25
Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22 | -12
Land Acquisition | 7 | 8 | 24000 | 20000 | -4000
Civilworks | 8 | 9 | 53727 | 60687.03 | 6960.03
contingency | 9 | 10 | 660.14 | 40 | -620.14
Total |  |  | 97865 | 100779.46 | 2914.46
2914.46
0 | Office Administration | 1 | 2 | 5403.27 | 5360.27 | -43
1 | Fuel & Lubricant | 2 | 3 | 350 | 210 | -140
2 | Training and Livelihood | 3 | 4 | 4491.97 | 5236.54 | 744.57
3 | Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
4 | Repair & Maintenance | 5 | 6 | 265 | 290 | 25
5 | Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22 | -12
6 | Land Acquisition | 7 | 8 | 24000 | 20000 | -4000
7 | Civilworks | 8 | 9 | 53727 | 60687.03 | 6960.03
8 | contingency | 9 | 10 | 660.14 | 40 | -620.14