## Revised_2nd
8.0 Economic code wise comparison of cost summary between the 1st Revised DPP and proposed 2nd Revised DPP | [27 empty] | (BDT in Lakh)
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3111327 | Overtime Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111338 | Other Allowance |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Supplies and Services
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | 1 Item | 100 | 100 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 1 Item | 2596.27 | 2596.27 |  | 0 | 0 |  |  |  | 1 Item | 2874.35 | 2874.35 |  | 0 | 0 |  |  |  |  | 278.08 | 278.08 |  | 0 | 0
| 3211119 | Postage |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3211115 | Water |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3211113 | Electricity |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3243102 | Gas & Fuel |  | 1 Item | 200 | 200 |  | 0 | 0 |  |  |  | 1 Item | 40 | 40 |  | 0 | 0 |  |  |  |  | -160 | -160 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 170 | 170 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255102 | Printing & Binding |  | 1 Item | 35 | 35 |  | 0 | 0 |  |  |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | -30 | -30 |  | 0 | 0
| 3211127 | Books & Periodicals |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 1 Item | 238.54 | 0 |  | 238.54 | 0 |  |  |  | 1 Item | 119 | 0 |  | 119 | 0 |  |  |  |  | -119.54 | 0 |  | -119.54 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 1 Item | 398.41 | 47.81 |  | 350.6 | 0 |  |  |  | 1 Item | 536.7 | 64.4 |  | 472.3 | 0 |  |  |  |  | 138.29 | 16.59 |  | 121.7 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 1 Item | 2533.34 | 304 |  | 2229.34 | 0 |  |  |  | 1 Item | 2957.63 | 354.92 |  | 2602.71 | 0 |  |  |  |  | 424.29 | 50.92 |  | 373.37 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1 Item | 1321.68 | 158.6 |  | 1163.08 | 0 |  |  |  | 1 Item | 1043.61 | 125.23 |  | 918.38 | 0 |  |  |  |  | -278.07 | -33.37 |  | -244.7 | 0
| 3211109 | Casual labour/Job worker |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 22 | 22 |  | 0 | 0 |  |  |  |  | 7 | 7 |  | 0 | 0
| 3256103 | Consumable Stores |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 71+234 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM | 56+532 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM |  | 0 | 0 |  | 0 | 0
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 30 | 30 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3257104 | Survey |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255101 | Computer Consumables |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  | 1 Item | 60 | 60 |  | 0 | 0 |  |  |  |  | 10 | 10 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Repair, Maintenance & Rehabilitation
| 3258101 | Motor Vehicles |  | L.S. | 100 | 100 |  | 0 | 0 |  |  |  | L.S. | 125 | 125 |  | 0 | 0 |  |  |  |  | 25 | 25 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258103 | Computers & office equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -15 | -15 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3258105 | Engineering Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) |  | 104 | 362.5 | 43.5 |  | 319 | 0 |  |  |  | 86 | 404.24 | 56.5936 |  | 347.6464 | 0 |  |  |  |  | 41.74 | 13.0936 |  | 28.6464 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  | L.S. | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
Sub-total : (a) Revenue Component: |  |  |  |  | 18774.14 | 6572.18 |  | 4300.56 | 7901.4 |  |  |  |  | 19100.93 | 6739.4936 |  | 4460.0364 | 7901.4 |  |  |  |  | 326.79 | 167.3136 |  | 159.4764 | 0
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos | 35 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos | 45 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos | 6 | 100 | 100 |  | 0 | 0 |  |  | Nos | 5 | 90 | 90 |  | 0 | 0 |  |  | Nos |  | -10 | -10 |  | 0 | 0
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos | 7 | 5 | 5 |  | 0 | 0 |  |  | Nos | 2 | 1 | 1 |  | 0 | 0 |  |  | Nos |  | -4 | -4 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos | 6 | 6 | 6 |  | 0 | 0 |  |  | Nos | 3 | 3 | 3 |  | 0 | 0 |  |  | Nos |  | -3 | -3 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos | 30 | 19.5 | 19.5 |  | 0 | 0 |  |  | Nos | 33 | 22.5 | 22.5 |  | 0 | 0 |  |  | Nos |  | 3 | 3 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 11 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos | 14 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos | 11 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos | 17 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | LS | 50 | 50 |  | 0 | 0 |  |  |  | LS | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 4112303 | Aircooler | Nos | 15 | 15 | 15 |  | 0 | 0 |  |  | Nos | 15 | 15 | 15 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Ori |  |  | Pro |  | Diff
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | ha | 470 | 24000 | 24000 |  | 0 | 0 |  |  | ha | 470 | 20000 | 20000 |  | 0 | 0 |  |  | ha |  | -4000 | -4000 |  | 0 | 0 |  |  |  | #REF! | #REF! | #REF! | 50 | 371 | 421 | #REF!
Construction and Works:
|  | Irrigation Infrastructures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos | 131 | 1261 | 151.32 |  | 1109.68 | 0 |  |  | Nos | 117 | 1209.54 | 169.3356 |  | 1040.2044 | 0 |  |  | Nos |  | -51.46 | 18.0156 |  | -69.4756 | 0
|  | Drainage Structures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos | 7(2+5) | 1515 | 181.8 |  | 1333.2 | 0 |  |  | Nos | 5 | 1175.5 | 164.57 |  | 1010.93 | 0 |  |  | Nos |  | -339.5 | -17.23 |  | -322.27 | 0 |  |  | #DIV/0! | 978.5 | 18871.5 | 19850 | 3398 | 24917 | 28315 | 8465
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos | 137(57+35+14) | 20311 | 2437.32 |  | 17873.68 | 0 |  |  | Nos | 111 | 18595.49 | 2603.3686 |  | 15992.1214 | 0 |  |  | Nos |  | -1715.51 | 166.0486 |  | -1881.5586 | 0 |  |  | #DIV/0! | 131 | 2528 | 2659 | 455 | 3337 | 3792 | 1133
| 4111307 | Re-excavation of Khal/River (New Haors) | Km | 318 | 9729 | 1167.48 |  | 8561.52 | 0 |  |  | Km | 335.364 | 10194.13 | 1427.1782 |  | 8766.9518 | 0 |  |  | Km |  | 465.13 | 259.6982 |  | 205.4318 | 0 |  |  | #REF!
|  | Others | [19 empty] | 0 | [7 empty] | #DIV/0! | 18 | 360 | 378 | 65 | 475.36 | 540.36 | 162.36
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | Km | 143 | 2515 | 301.8 |  | 2213.2 | 0 |  |  | Km | 108.974 | 3397.94 | 475.7116 |  | 2922.2284 | 0 |  |  | Km |  | 882.94 | 173.9116 |  | 709.0284 | 0 |  |  | #DIV/0! | 3 | 60 | 63 | 11 | 80 | 91 | 28
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | Km | 84.31 | 2550 | 306 |  | 2244 | 0 |  |  | Km | 67.11 | 2035.43 | 284.9602 |  | 1750.4698 | 0 |  |  | Km |  | -514.57 | -21.0398 |  | -493.5302 | 0 |  |  | #DIV/0! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | Km | 87.03 | 1785 | 214.2 |  | 1570.8 | 0 |  |  | Km | 61.21 | 1747.81 | 244.6934 |  | 1503.1166 | 0 |  |  | Km |  | -37.19 | 30.4934 |  | -67.6834 | 0 |  |  | #DIV/0!
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 261.653 | 19669.71 | 6805.8482 |  | 12863.8618 | 0 |  |  | Km |  | 7717.21 | 5371.5482 |  | 2345.6618 | 0 |  |  | #REF!
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos | 8 | 166 | 19.92 |  | 146.08 | 0 |  |  | Nos | 7 | 160.79 | 22.5106 |  | 138.2794 | 0 |  |  | Nos |  | -5.21 | 2.5906 |  | -7.8006 | 0 |  |  | #REF! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
| 4111201 | Threshing Floor Construction | Nos |  | 0 | 0 |  | 0 | 0 |  |  | Nos | 5 | 225 | 31.5 |  | 193.5 | 0 |  |  | Nos |  | 225 | 31.5 |  | 193.5 | 0
| 4111201 | Construction of WMG Office | Nos | 60 | 1380 | 165.6 |  | 1214.4 | 0 |  |  | Nos | 30 | 1050 | 147 |  | 903 | 0 |  |  | Nos |  | -330 | -18.6 |  | -311.4 | 0 |  |  |  | 726.6 | 14031.95 | 14758.55 | 2526 | 18527 | 21053 | 6294.45
| 4111201 | O&M During Construction | Iten | L.S | 200 | 200 |  | 0 | 0 |  |  | Iten | 1 | 100 | 100 |  | 0 | 0 |  |  | Iten |  | -100 | -100 |  | 0 | 0 |  |  |  | #REF! | #REF! | #REF! | 6889 | 50521.36 | 57410.36 | #REF!
Sub-total : (b) Capital Component: |  |  |  |  | 78430.72 | 31645.96 |  | 46784.76 | 0 |  |  |  |  | 80613.56 | 33528.8964 |  | 47084.6636 | 0 |  |  |  |  | 2182.84 | 1882.9364 |  | 299.9036 | 0
Total Cost (a+b) : |  |  |  |  | 97204.86 | 38218.14 |  | 51085.32 | 7901.4 |  |  |  |  | 99714.49 | 40268.39 |  | 51544.7 | 7901.4 |  |  |  |  | 2509.63 | 2050.25 |  | 459.38 | 0
| 0 | (c) Physical Contingency ( Lump sum): | Item | L.S. | 258 | 100 |  | 158 | 0 |  |  | Item | L.S. | 49.51 | 49.51 |  | 0 | 0 |  |  | Item |  | -208.49 | -50.49 |  | -158 | 0
| 0 | (d) Price Contingency (Lump sum): | Item | L.S. | 402.14 | 100.76 |  | 301.38 | 0 |  |  | Item | L.S. | 10 | 10 |  | 0 | 0 |  |  | Item |  | -392.14 | -90.76 |  | -301.38 | 0
|  | Grand Total : (a)+(b)+(c)+(d): |  |  | 97865 | 38418.9 |  | 51544.7 | 7901.4 |  |  |  |  | 99774 | 40327.9 |  | 51544.7 | 7901.4 |  |  |  |  | 1909 | 1909 |  | -1.4779e-12 | 0
* DOSA, CONTASA, SAFE, IMPREST etc.
|  |  |  | c+d | 53527 | 6423.24 |  | 47103.76 | [5 empty] | 59865.58 | 12433.27 |  | 47432.31 |  |  | 0 |  |  | 6338.58 | 6010.03 |  | 328.55
|  |  |  | Phy.Works | 53727 | 6623.24 |  | 47103.76 |  |  |  |  | Phy.Works | 59740.58 | 12501.77 |  | 47238.81 |  |  | 0 |  | Phy.Works | 6013.58 | 5878.53 |  | 135.05
|  |  |  | c+d+works |  | 13046.48 |  | 94207.52 | [6 empty] | 24935.04 |  | 94671.12 |  |  | 0
|  |  |  | other |  | 25372.42 |  | 3981.56 | [8 empty] | 4112.39
[8 empty] | 98189.08 | [8 empty] | 98783.51
[9 empty] | Reh | [7 empty] | Reh | 0
[9 empty] | New | [7 empty] | New | #REF!
[5 empty] | 4253.43 | [8 empty] | 4537.94 |  |  | 3993.39 | 0
#REF!
46784.76
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 254.207 | 16526.21 | 4527.399 |  | 11998.811 | 0 |  |  | Km | -9.033 | 4573.71 | 3093.099 |  | 1480.611 | 0

## 9.Detil Phasing
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2019 (Year 1 to Year-5) † | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-21 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | Part | 1.01 | 1.01 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 3111327 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 3111338 | Other Allowance |  |  | 36.61 | 36.61 |  | 0 | 0 |  |  |  |  | Part | 14 | 14 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 58.54 | 58.54 |  | 0 | 0 |  |  |  |  | Part | 14.97 | 14.97 |  | 0 | 0 |  |  |  |  | Part | 28.8176 | 28.8176 |  | 0 | 0 |  |  |  |  | Part | 17.6624 | 17.6624 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 116.67 | 116.67 |  | 0 | 0 |  |  |  |  | Part | 34.21 | 34.21 |  | 0 | 0 |  |  |  |  | Part | 58.3544 | 58.3544 |  | 0 | 0 |  |  |  |  | Part | 35.7656 | 35.7656 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1603.18 | 1603.18 |  | 0 | 0 |  |  |  |  | Part | 177.18 | 177.18 |  | 0 | 0 |  |  |  |  | Part | 634.52 | 634.52 |  | 0 | 0 |  |  |  |  | Part | 459.48 | 459.48 |  | 0 | 0
| 3211119 | Postage |  | Part | 0.77 | 0.77 |  | 0 | 0 |  |  |  |  | Part | 0.48 | 0.48 |  | 0 | 0 |  |  |  |  | Part | 2.175 | 2.175 |  | 0 | 0 |  |  |  |  | Part | 1.575 | 1.575 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | Part | 0.97 | 0.97 |  | 0 | 0 |  |  |  |  | Part | 0.07 | 0.07 |  | 0 | 0 |  |  |  |  | Part | 2.4156 | 2.4156 |  | 0 | 0 |  |  |  |  | Part | 1.5444 | 1.5444 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | Part | 0.44 | 0.44 |  | 0 | 0 |  |  |  |  | Part | 0.1 | 0.1 |  | 0 | 0 |  |  |  |  | Part | 2.497 | 2.497 |  | 0 | 0 |  |  |  |  | Part | 1.962 | 1.962 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | Part | 11.92 | 11.92 |  | 0 | 0 | [5 empty] | 0.17 | 0.17 |  | 0 | 0 | [5 empty] | 4.9833 | 4.9833 |  | 0 | 0 | [5 empty] | 2.9267 | 2.9267 |  | 0 | 0
| 3211115 | Water |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 0.55 | 0.55 |  | 0 | 0 |  |  |  |  | Part | 2.0313 | 2.0313 |  | 0 | 0 |  |  |  |  | Part | 1.2987 | 1.2987 |  | 0 | 0
| 3211113 | Electricity |  | Part | 8.74 | 8.74 |  | 0 | 0 |  |  |  |  | Part | 2.89 | 2.89 |  | 0 | 0 |  |  |  |  | Part | 4.609 | 4.609 |  | 0 | 0 |  |  |  |  | Part | 3.771 | 3.771 |  | 0 | 0
| 3243102 | Gas & Fuel |  | Part | 17.52 | 17.52 |  | 0 | 0 |  |  |  |  | Part | 4.02 | 4.02 |  | 0 | 0 |  |  |  |  | Part | 11.2545 | 11.2545 |  | 0 | 0 |  |  |  |  | Part | 7.1955 | 7.1955 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | Part | 64.59 | 64.59 |  | 0 | 0 |  |  |  |  | Part | 24.18 | 24.18 |  | 0 | 0 |  |  |  |  | Part | 46.3068 | 46.3068 |  | 0 | 0 |  |  |  |  | Part | 34.9332 | 34.9332 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | Part | 1.16 | 1.16 |  | 0 | 0 |  |  |  |  | Part | 0.91 | 0.91 |  | 0 | 0 |  |  |  |  | Part | 0.51205 | 0.51205 |  | 0 | 0 | [5 empty] | 0.41895 | 0.41895 |  | 0 | 0
| 3255102 | Printing & Binding |  | Part | 34.16 | 34.16 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 9.355 | 9.355 |  | 0 | 0 |  |  |  |  | Part | 5.981 | 5.981 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | Part | 49.91 | 49.91 |  | 0 | 0 |  |  |  |  | Part | 19.95 | 19.95 |  | 0 | 0 |  |  |  |  | Part | 31.5869 | 31.5869 |  | 0 | 0 |  |  |  |  | Part | 18.5511 | 18.5511 |  | 0 | 0
| 3211127 | Books & Periodicals |  | Part | 0.28 | 0.28 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 119 | 0 |  | 119 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 301.5 | 22.54 |  | 278.96 | 0 |  |  |  |  | Part | 22.21 | 2.3809 |  | 19.8291 | 0 |  |  |  |  | Part | 127.794 | 13.6995 |  | 114.0945 | 0 |  |  |  |  | Part | 85.196 | 9.133 |  | 76.063 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1346.63 | 80.34 |  | 1266.29 | 0 |  |  |  |  | Part | 338.12 | 36.2465 |  | 301.8735 | 0 |  |  |  |  | Part | 801.9144 | 85.9652 |  | 715.9492 | 0 |  |  |  |  | Part | 470.9656 | 50.4875 |  | 420.4781 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 578.2 | 35.47 |  | 542.73 | 0 |  |  |  |  | Part | 82.97 | 8.8944 |  | 74.0756 | 0 |  |  |  |  | Part | 210.342 | 22.5487 |  | 187.7933 | 0 |  |  |  |  | Part | 172.098 | 18.4489 |  | 153.6491 | 0
| 3211109 | Casual labour/Job worker |  | Part | 10.96 | 10.96 |  | 0 | 0 |  |  |  |  | Part | 3.49 | 3.49 |  | 0 | 0 |  |  |  |  | Part | 4.681 | 4.681 |  | 0 | 0 |  |  |  |  | Part | 2.869 | 2.869 |  | 0 | 0
| 3256103 | Consumable Stores |  | Part | 3.74 | 3.74 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5168.01 | 0 |  | 0 | 5168.01 |  |  |  | MM | Part | 450 | 0 |  | 0 | 450 |  |  |  | MM | Part | 1374.571 | 0 |  | 0 | 1374.571 |  |  |  | MM | Part | 878.824 | 0 |  | 0 | 878.824
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 12.73 | 12.73 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 8.2766 | 8.2766 |  | 0 | 0 |  |  |  |  | Part | 5.9934 | 5.9934 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  |  | 1.29 | 1.29 |  | 0 | 0 |  |  |  |  | Part | 0.41 | 0.41 |  | 0 | 0 | [5 empty] | 8.3 | 8.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  |  | 1.3 | 1.3 |  | 0 | 0 |  |  |  |  | Part | 0.41 | 0.41 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0
| 3257104 | Survey |  | Part | 85.02 | 85.02 |  | 0 | 0 |  |  |  |  | Part | 30 | 30 |  | 0 | 0 |  |  |  |  | Part | 26.7786 | 26.7786 |  | 0 | 0 |  |  |  |  | Part | 20.2014 | 20.2014 |  | 0 | 0
| 3255101 | Computer Consumables |  | Part | 20.47 | 20.47 |  | 0 | 0 |  |  |  |  | Part | 10 | 10 |  | 0 | 0 |  |  |  |  | Part | 16.242 | 16.242 |  | 0 | 0 |  |  |  |  | Part | 13.2889 | 13.2889 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 875.46 | 875.46 |  | 0 | 0 |  |  |  |  | Part | 299.96 | 299.96 |  | 0 | 0 |  |  |  |  | Part | 299.0163 | 299.0163 |  | 0 | 0 |  |  |  |  | Part | 225.5737 | 225.5737 |  | 0 | 0
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | Part | 61.4 | 61.4 |  | 0 | 0 |  |  |  |  | Part | 14.97 | 14.97 |  | 0 | 0 |  |  |  |  | Part | 26.7481 | 26.7481 |  | 0 | 0 |  |  |  |  | Part | 21.8849 | 21.8849 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | Part | 3.2 | 3.2 |  | 0 | 0 |  |  |  |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 3.414 | 3.414 |  | 0 | 0 |  |  |  |  | Part | 2.276 | 2.276 |  | 0 | 0
| 3258103 | Computers & office equipments |  | Part | 5.34 | 5.34 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | Part | 1.22 | 1.22 |  | 0 | 0 |  |  |  |  | Part | 1.99 | 1.99 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  |  | 14.53 | 14.53 |  | 0 | 0 |  |  |  |  | Part | 4.95 | 4.95 |  | 0 | 0 |  |  |  |  | Part | 11.9016 | 11.9016 |  | 0 | 0 |  |  |  |  | Part | 8.6184 | 8.6184 |  | 0 | 0
| 3258105 | Engineering Equipments |  | Part | 1.39 | 1.39 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
|  | Drainage Structures : | [12 empty] | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 95.03 | 10.83 |  | 84.2 | 0 |  |  |  | Nos. | Part | 33.17 | 4.8826 |  | 28.2874 | 0 |  |  |  | Nos. | Part | 173.9052 | 25.5988 |  | 148.3064 | 0 | [5 empty] | 102.1348 | 15.0342 |  | 87.1006 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.39 | 2.39 |  | 0 | 0 |  |  |  | Nos. | Part | 0.38 | 0.38 |  | 0 | 0 |  |  |  | Nos. | Part | 1.3603 | 1.3603 |  | 0 | 0 |  |  |  | Nos. | Part | 0.8697 | 0.8697 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  |  | 7.48 | 7.48 |  | 0 | 0 |  |  |  |  | Part | 1.49 | 1.49 |  | 0 | 0 |  |  |  |  | Part | 17.3768 | 17.3768 |  | 0 | 0 |  |  |  |  | Part | 13.6532 | 13.6532 |  | 0 | 0
(a) Sub-total Revenue Component: |  |  |  |  | 10624.85 | 3284.66 |  | 2172.18 | 5168.01 | [5 empty] | 1601.51 | 727.4444 |  | 424.0656 | 450 | [5 empty] | 4162.9785 | 1503.2642 |  | 1285.1434 | 1374.571 | [5 empty] | 2681.5945 | 1065.4797 |  | 737.2907 | 878.824
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 18.03 | 18.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 28.71 | 28.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.97 | 8.97 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 2 nos. | 1 | 1 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.21 | 0.21 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.5 | 20.5 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) |  |  | 3 | 3 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 9.49 | 9.49 | 70 | 0 | 0 | [5 empty] | 5 | 5 |  | 0 | 0 | [5 empty] | 35.51 | 35.51 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 | 72 | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 3.03 | 3.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 | 73 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 3.87 | 3.87 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 | 74 | 0 | 0 |  |  |  | No. | 1 no. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.3 | 1.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 | 75 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.17 | 1.17 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | Part | 45.32 | 45.32 | 76 | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.8954 | 2.8954 |  | 0 | 0 |  |  |  |  | Part | 1.7746 | 1.7746 |  | 0 | 0
| 4112303 | Aircooler | Nos. | 4 nos. | 9.73 | 9.73 | 77 | 0 | 0 |  |  |  | Nos. | 6 nos. | 2.99 | 2.99 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 1.3908 | 1.3908 |  | 0 | 0 | [5 empty] | 0.8892 | 0.8892 |  | 0 | 0
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) |  |  | 14323.6 | 14323.6 | 79 | 0 | 0 |  |  |  | ha. | Part | 1000 | 1000 |  | 0 | 0 |  |  |  | ha. | Part | 2338.2 | 2338.2 |  | 0 | 0 |  |  |  | ha. |  | 2338.2 | 2338.2 |  | 0 | 0
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) |  |  | 116.72 | 16.34 | 82 | 100.38 | 0 | [5 empty] | 192.22 | 26.9108 |  | 165.3092 | 0 |  |  |  | Nos. | 131 | 522.348 | 73.1287 |  | 449.2193 | 0 | [5 empty] | 378.252 | 52.9553 |  | 325.2967 | 0
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 | 84 | 0 | 0 |  |  |  | No. | Part | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 670.035 | 93.8049 |  | 576.2301 | 0 | [5 empty] | 505.465 | 70.7651 |  | 434.6999 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 6143.66 | 889.49 | 85 | 5254.17 | 0 |  |  |  | Nos. | Part | 4075.22 | 570.5308 |  | 3504.6892 | 0 |  |  |  | Nos. | Part | 4439.6033 | 621.5445 |  | 3818.0588 | 0 |  |  |  | Nos. | Part | 3937.0067 | 551.1809 |  | 3385.8258 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) |  |  | 6011.48 | 791.08 | 86 | 5220.4 | 0 |  |  |  | Km. | Part | 2673.22 | 374.2508 |  | 2298.9692 | 0 |  |  |  | Km. | Part | 845.2808 | 118.3393 |  | 726.9415 | 0 |  |  |  | Km. | Part | 664.1492 | 92.9809 |  | 571.1683 | 0
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) |  |  | 455.04 | 64.36 | 88 | 390.68 | 0 |  |  |  | Km. | Part | 726.54 | 101.7156 |  | 624.8244 | 0 |  |  |  | Km. | Part | 1218.998 | 170.6597 |  | 1048.3383 | 0 | [5 empty] | 997.362 | 139.6307 |  | 857.7313 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) |  |  | 452.46 | 63.49 | 89 | 388.97 | 0 |  |  |  | Km. | Part | 253.65 | 35.511 |  | 218.139 | 0 |  |  |  | Km. | Part | 771.0056 | 107.9408 |  | 663.0648 | 0 | [5 empty] | 558.3144 | 78.164 |  | 480.1504 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) |  |  | 341.85 | 48.84 | 90 | 293.01 | 0 |  |  |  | Km. | Part | 179.68 | 25.1552 |  | 154.5248 | 0 |  |  |  | Km. | Part | 674.454 | 94.4236 |  | 580.0304 | 0 | [5 empty] | 551.826 | 77.2556 |  | 474.5704 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  |  | 6127.06 | 779.02 | 91 | 5348.04 | 0 |  |  |  | Km. | Part | 2923.61 | 409.3054 |  | 2514.3046 | 0 |  |  |  | Km. | Part | 6159.0432 | 862.266 |  | 5296.7772 | 0 |  |  |  | Km. |  | 4459.9968 | 624.3996 |  | 3835.5972 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 | 92 | 63.49 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 |  |  |  | Nos. |  | 48.1415 | 6.7398 |  | 41.4017 | 0 |  |  |  | Nos. |  | 39.3885 | 5.5144 |  | 33.8741 | 0
| 4111201 | Threshing Floor Construction |  |  | 0 | 0 | 93 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 123.75 | 17.325 |  | 106.425 | 0 | [5 empty] | 101.25 | 14.175 |  | 87.075 | 0
| 4111201 | Construction of WMG Office |  |  | 42.09 | 5.47 | 94 | 36.62 | 0 |  |  |  | Nos. | Part | 93.33 | 13.0662 |  | 80.2638 | 0 |  |  |  | Nos. |  | 521.3106 | 72.9835 |  | 448.3271 | 0 |  |  |  | Nos. |  | 393.2694 | 55.0577 |  | 338.2117 | 0
| 4111201 | O&M During Construction |  |  | 0 | 0 | 95 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 55 | 7.7 |  | 47.3 | 0 | [5 empty] | 45 | 6.3 |  | 38.7 | 0
(b)Sub-total Capital Component: |  |  |  |  | 34937.27 | 17841.51 |  | 17095.76 | 0 | [5 empty] | 12125.46 | 2564.4358 |  | 9561.0242 | 0 | [5 empty] | 18578.8862 | 4776.772 |  | 13802.1142 | 0 | [5 empty] | 14972.1438 | 4109.243 |  | 10862.9008 | 0
Total Cost (a+b) : |  |  |  |  | 45562.12 | 21126.17 |  | 19267.94 | 5168.01 | [5 empty] | 13726.97 | 3291.8802 |  | 9985.0898 | 450 | [5 empty] | 22741.8647 | 6280.0362 |  | 15087.2576 | 1374.571 | [5 empty] | 17653.7383 | 5174.7227 |  | 11600.1915 | 878.824
| 0 | (c) Physical Contingency ( Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 26.2403 | 26.2403 |  | 0 | 0 | [5 empty] | 23.2697 | 23.2697 |  | 0 | 0
| 0 | (d) Price Contingency (Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 5.4 | 5.4 |  | 0 | 0 | [5 empty] | 4.6 | 4.6 |  | 0 | 0
Grand Total (a+b+c+d) : |  |  |  |  | 45562.12 | 21126.17 |  | 19267.94 | 5168.01 | [5 empty] | 13726.97 | 3291.8802 |  | 9985.0898 | 450 | [5 empty] | 22773.505 | 6311.6765 |  | 15087.2576 | 1374.571 | [5 empty] | 17681.608 | 5202.5924 |  | 11600.1915 | 878.824
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17
99744.203
59289.09

## 9.Detil Phasing_2
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2020 (Year 1 to Year-6) † | [9 empty] | FY: 2020-2021 (Year-7) | [9 empty] | FY: 2021-22 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | Part | 1.51 | 1.51 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 3111327 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 3111338 | Other Allowance |  |  | 50.61 | 50.61 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 73.523 | 73.523 |  | 0 | 0 |  |  |  |  | Part | 28.8176 | 28.8176 |  | 0 | 0 |  |  |  |  | Part | 17.6624 | 17.6624 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 150.88 | 150.88 |  | 0 | 0 |  |  |  |  | Part | 58.3544 | 58.3544 |  | 0 | 0 |  |  |  |  | Part | 35.7656 | 35.7656 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1780.35 | 1780.35 |  | 0 | 0 |  |  |  |  | Part | 634.52 | 634.52 |  | 0 | 0 |  |  |  |  | Part | 459.48 | 459.48 |  | 0 | 0
| 3211119 | Postage |  | Part | 1.25 | 1.25 |  | 0 | 0 |  |  |  |  | Part | 2.175 | 2.175 |  | 0 | 0 |  |  |  |  | Part | 1.575 | 1.575 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | Part | 1.04 | 1.04 |  | 0 | 0 |  |  |  |  | Part | 2.4156 | 2.4156 |  | 0 | 0 |  |  |  |  | Part | 1.5444 | 1.5444 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | Part | 0.541 | 0.541 |  | 0 | 0 |  |  |  |  | Part | 2.497 | 2.497 |  | 0 | 0 |  |  |  |  | Part | 1.962 | 1.962 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | Part | 12.09 | 12.09 |  | 0 | 0 | [5 empty] | 4.9833 | 4.9833 |  | 0 | 0 | [5 empty] | 2.9267 | 2.9267 |  | 0 | 0
| 3211115 | Water |  | Part | 1.67 | 1.67 |  | 0 | 0 |  |  |  |  | Part | 2.0313 | 2.0313 |  | 0 | 0 |  |  |  |  | Part | 1.2987 | 1.2987 |  | 0 | 0
| 3211113 | Electricity |  | Part | 11.62 | 11.62 |  | 0 | 0 |  |  |  |  | Part | 4.609 | 4.609 |  | 0 | 0 |  |  |  |  | Part | 3.771 | 3.771 |  | 0 | 0
| 3243102 | Gas & Fuel |  | Part | 21.55 | 21.55 |  | 0 | 0 |  |  |  |  | Part | 11.2545 | 11.2545 |  | 0 | 0 |  |  |  |  | Part | 7.1955 | 7.1955 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | Part | 88.76 | 88.76 |  | 0 | 0 |  |  |  |  | Part | 46.3068 | 46.3068 |  | 0 | 0 |  |  |  |  | Part | 34.9332 | 34.9332 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | Part | 2.07 | 2.07 |  | 0 | 0 |  |  |  |  | Part | 0.51205 | 0.51205 |  | 0 | 0 |  |  |  |  | Part | 0.41895 | 0.41895 |  | 0 | 0
| 3255102 | Printing & Binding |  | Part | 34.664 | 34.664 |  | 0 | 0 |  |  |  |  | Part | 9.355 | 9.355 |  | 0 | 0 |  |  |  |  | Part | 5.981 | 5.981 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | Part | 69.862 | 69.862 |  | 0 | 0 |  |  |  |  | Part | 31.5869 | 31.5869 |  | 0 | 0 |  |  |  |  | Part | 18.5511 | 18.5511 |  | 0 | 0
| 3211127 | Books & Periodicals |  | Part | 0.48 | 0.48 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 119 | 0 |  | 119 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 323.71 | 25.25 |  | 298.46 | 0 |  |  |  |  | Part | 127.794 | 23.4885 |  | 104.3055 | 0 |  |  |  |  | Part | 85.196 | 15.659 |  | 69.537 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1684.75 | 114.81 |  | 1569.94 | 0 |  |  |  |  | Part | 801.9144 | 151.2411 |  | 650.6733 | 0 |  |  |  |  | Part | 470.9656 | 88.8241 |  | 382.1415 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 661.17 | 42.58 |  | 618.59 | 0 |  |  |  |  | Part | 210.342 | 45.4549 |  | 164.8871 | 0 |  |  |  |  | Part | 172.098 | 37.1904 |  | 134.9076 | 0
| 3211109 | Casual labour/Job worker |  | Part | 14.45 | 14.45 |  | 0 | 0 |  |  |  |  | Part | 4.681 | 4.681 |  | 0 | 0 |  |  |  |  | Part | 2.869 | 2.869 |  | 0 | 0
| 3256103 | Consumable Stores |  | Part | 6.74 | 6.74 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5648.005 | 0 |  | 0 | 5648.005 |  |  |  | MM | Part | 1374.571 | 0 |  | 0 | 1374.571 |  |  |  | MM | Part | 878.824 | 0 |  | 0 | 878.824
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 15.73 | 15.73 |  | 0 | 0 |  |  |  |  | Part | 8.2766 | 8.2766 |  | 0 | 0 |  |  |  |  | Part | 5.9934 | 5.9934 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  |  | 1.7 | 1.7 |  | 0 | 0 |  |  |  |  | Part | 8.3 | 8.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  |  | 1.71 | 1.71 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0
| 3257104 | Survey |  | Part | 115.02 | 115.02 |  | 0 | 0 |  |  |  |  | Part | 26.7786 | 26.7786 |  | 0 | 0 |  |  |  |  | Part | 20.2014 | 20.2014 |  | 0 | 0
| 3255101 | Computer Consumables |  | Part | 30.469 | 30.469 |  | 0 | 0 |  |  |  |  | Part | 16.242 | 16.242 |  | 0 | 0 |  |  |  |  | Part | 13.2889 | 13.2889 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 1175.41 | 1175.41 |  | 0 | 0 |  |  |  |  | Part | 299.0163 | 299.0163 |  | 0 | 0 |  |  |  |  | Part | 225.5737 | 225.5737 |  | 0 | 0
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | Part | 76.367 | 76.367 |  | 0 | 0 |  |  |  |  | Part | 26.7481 | 26.7481 |  | 0 | 0 |  |  |  |  | Part | 21.8849 | 21.8849 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | Part | 4.31 | 4.31 |  | 0 | 0 |  |  |  |  | Part | 3.414 | 3.414 |  | 0 | 0 |  |  |  |  | Part | 2.276 | 2.276 |  | 0 | 0
| 3258103 | Computers & office equipments |  | Part | 8.34 | 8.34 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | Part | 3.22 | 3.22 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  |  | 19.48 | 19.48 |  | 0 | 0 |  |  |  |  | Part | 11.9016 | 11.9016 |  | 0 | 0 |  |  |  |  | Part | 8.6184 | 8.6184 |  | 0 | 0
| 3258105 | Engineering Equipments |  | Part | 3.39 | 3.39 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 128.2 | 14.98 |  | 113.22 | 0 |  |  |  | Nos. | Part | 173.9052 | 26.2249 |  | 147.6803 | 0 |  |  |  | Nos. | Part | 102.1348 | 15.4019 |  | 86.7329 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.77 | 2.77 |  | 0 | 0 |  |  |  | Nos. | Part | 1.3603 | 1.3603 |  | 0 | 0 |  |  |  | Nos. | Part | 0.8697 | 0.8697 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  |  | 8.97 | 8.97 |  | 0 | 0 |  |  |  |  | Part | 17.3768 | 17.3768 |  | 0 | 0 |  |  |  |  | Part | 13.6532 | 13.6532 |  | 0 | 0
(a) Sub-total Revenue Component: |  |  |  |  | 12256.361 | 4008.146 |  | 2600.21 | 5648.005 | [5 empty] | 4162.9785 | 1601.8614 |  | 1186.5462 | 1374.571 | [5 empty] | 2681.5945 | 1129.4515 |  | 673.319 | 878.824
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 18.03 | 18.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 28.71 | 28.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.97 | 8.97 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 2 nos. | 0.79 | 0.79 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.21 | 0.21 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.5 | 20.5 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) |  |  | 3 | 3 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 14.49 | 14.49 | 70 | 0 | 0 | [5 empty] | 35.51 | 35.51 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 | 72 | 0 | 0 |  |  |  | Nos. | 3 nos. | 3.03 | 3.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 | 73 | 0 | 0 |  |  |  | Nos. | 4 nos. | 3.87 | 3.87 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 | 74 | 0 | 0 |  |  |  | No. | 1 no. | 1.3 | 1.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 | 75 | 0 | 0 |  |  |  | Nos. | 4 nos. | 1.17 | 1.17 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | Part | 45.33 | 45.33 | 76 | 0 | 0 |  |  |  |  | Part | 2.8954 | 2.8954 |  | 0 | 0 |  |  |  |  | Part | 1.7746 | 1.7746 |  | 0 | 0
| 4112303 | Aircooler | Nos. | 4 nos. | 12.72 | 12.72 | 77 | 0 | 0 |  |  |  | Nos. | 6 nos. | 1.3908 | 1.3908 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.8892 | 0.8892 |  | 0 | 0
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) |  |  | 15323.6 | 15323.6 | 79 | 0 | 0 |  |  |  | ha. | Part | 2338.2 | 2338.2 |  | 0 | 0 |  |  |  | ha. | Part | 2338.2 | 2338.2 |  | 0 | 0
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) |  |  | 308.94 | 40.42 | 82 | 268.52 | 0 | [5 empty] | 522.348 | 74.748 |  | 447.6 | 0 |  |  |  | Nos. | 131 | 378.252 | 54.1279 |  | 324.1241 | 0
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 | 84 | 0 | 0 |  |  |  | No. | Part | 670.035 | 93.8049 |  | 576.2301 | 0 |  |  |  | No. | Part | 505.465 | 70.7651 |  | 434.6999 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 10218.88 | 1398.89 | 85 | 8819.99 | 0 |  |  |  | Nos. | Part | 4439.6033 | 638.415 |  | 3801.1883 | 0 |  |  |  | Nos. | Part | 3937.0067 | 566.1416 |  | 3370.8651 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) |  |  | 8684.7 | 1125.23 | 86 | 7559.47 | 0 |  |  |  | Km. | Part | 845.2808 | 169.0562 |  | 676.2246 | 0 |  |  |  | Km. | Part | 664.1492 | 132.8298 |  | 531.3194 | 0
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) |  |  | 1181.58 | 155.18 | 88 | 1026.4 | 0 |  |  |  | Km. | Part | 1218.998 | 176.2671 |  | 1042.7309 | 0 |  |  |  | Km. | Part | 997.362 | 144.2185 |  | 853.1435 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) |  |  | 706.11 | 95.2 | 89 | 610.91 | 0 |  |  |  | Km. | Part | 771.0056 | 110.0225 |  | 660.9831 | 0 |  |  |  | Km. | Part | 558.3144 | 79.6715 |  | 478.6429 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) |  |  | 521.53 | 71.3 | 90 | 450.23 | 0 |  |  |  | Km. | Part | 674.454 | 95.3678 |  | 579.0862 | 0 |  |  |  | Km. | Part | 551.826 | 78.0282 |  | 473.7978 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  |  | 9050.67 | 1144.47 | 91 | 7906.2 | 0 |  |  |  | Km. | Part | 6159.0432 | 3283.3859 |  | 2875.6573 | 0 |  |  |  | Km. | Part | 4459.9968 | 2377.6243 |  | 2082.3725 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 | 92 | 63.49 | 0 |  |  |  | Nos. |  | 48.1415 | 7.0094 |  | 41.1321 | 0 |  |  |  | Nos. |  | 39.3885 | 5.735 |  | 33.6535 | 0
| 4111201 | Threshing Floor Construction |  |  | 0 | 0 | 93 | 0 | 0 | [5 empty] | 123.75 | 17.325 |  | 106.425 | 0 | [5 empty] | 101.25 | 14.175 |  | 87.075 | 0
| 4111201 | Construction of WMG Office |  |  | 135.42 | 17.14 | 94 | 118.28 | 0 |  |  |  | Nos. | Part | 521.3106 | 74.0261 |  | 447.2845 | 0 |  |  |  | Nos. |  | 393.2694 | 55.8443 |  | 337.4251 | 0
| 4111201 | O&M During Construction |  |  | 0 | 0 | 95 | 0 | 0 | [5 empty] | 55 | 55 |  | 0 | 0 |  |  |  |  | Part | 45 | 45 |  | 0 | 0
(b)Sub-total Capital Component: |  |  |  |  | 47062.53 | 20239.04 |  | 26823.49 | 0 | [5 empty] | 18578.8862 | 7324.3441 |  | 11254.5421 | 0 | [5 empty] | 14972.1438 | 5965.0249 |  | 9007.1189 | 0
Total Cost (a+b) : |  |  |  |  | 59318.891 | 24247.186 |  | 29423.7 | 5648.005 | [5 empty] | 22741.8647 | 8926.2054 |  | 12441.0883 | 1374.571 | [5 empty] | 17653.7383 | 7094.4763 |  | 9680.4379 | 878.824
|  | (c) Physical Contingency ( Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 26.2403 | 26.2403 |  | 0 | 0 | [5 empty] | 23.2697 | 23.2697 |  | 0 | 0
|  | (d) Price Contingency (Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 5.4 | 5.4 |  | 0 | 0 | [5 empty] | 4.6 | 4.6 |  | 0 | 0
Grand Total (a+b+c+d) : |  |  |  |  | 59318.891 | 24247.186 |  | 29423.7 | 5648.005 | [5 empty] | 22773.505 | 8957.8457 |  | 12441.0883 | 1374.571 | [5 empty] | 17681.608 | 7122.346 |  | 9680.4379 | 878.824
59318.891
[5 empty] | 59318.897 | [9 empty] | 22773.505 |  | 23.1682 |  | 6.5938e-12 | [5 empty] | 17681.608 |  |  |  | -9.6634e-12
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17 |  |  |  |  | -0.006 | [9 empty] | 0 | [9 empty] | 0
59318.897
0.006
|  |  |  | Total | Gob | RPA | DPA
|  |  | Allocation | 99774 | 40327.9 | 51544.7 | 7901.4
|  |  | 19-20 | 59318.891 | 24247.186 | 29423.7 | 5648.005
|  |  | 20-21 | 22773.505 | 8957.8457 | 12441.0883 | 1374.571
|  |  | 21-22 | 17681.608 | 7122.346 | 9680.4379 | 878.824
|  |  | TE | 99774.004 | 40327.3778 | 51545.2262 | 7901.4
|  |  | Diff | -0.004 | 0.52221 | -0.52621 | 0

## Sheet3
1.51 | 1.51 | 0 | 0
0 | 0 | 0 | 0
50.61 | 50.61 | 0 | 0
73.53 | 73.523 | 0 | 0
150.88 | 150.88 | 0 | 0
1780.35 | 1780.35 | 0 | 0
1.25 | 1.25 | 0 | 0
1.04 | 1.04 | 0 | 0
0.541 | 0.541 | 0 | 0
12.09 | 12.09 | 0 | 0
1.67 | 1.67 | 0 | 0
11.62 | 11.62 | 0 | 0
21.55 | 21.55 | 0 | 0
88.76 | 88.76 | 0 | 0
2.069 | 2.07 | 0 | 0
34.664 | 34.664 | 0 | 0
69.862 | 69.862 | 0 | 0
0.48 | 0.48 | 0 | 0
0 | 0 | 0 | 0
323.71 | 25.25 | 298.46 | 0
1684.75 | 114.81 | 1569.94 | 0
661.17 | 42.58 | 618.59 | 0
14.45 | 14.45 | 0 | 0
6.74 | 6.74 | 0 | 0
5648.005 | 0 | 0 | 5648.005
15.73 | 15.73 | 0 | 0
1.7 | 1.7 | 0 | 0
1.71 | 1.71 | 0 | 0
115.02 | 115.02 | 0 | 0
30.469 | 30.469 | 0 | 0
1175.41 | 1175.41 | 0 | 0

## Annex-II
Year wise Financial and Physical Target Plan | [16 empty] | Annexure-II | [11 empty] | Annexure-II
Name of the Project : Haor Flood Management and Livelihood Improvement Project.(BWDB Part)
Name of agency/Division/Ministry: Bangladesh Water Development Board / Ministry of Water Resources
Economic Code | Economic Sub-Code (In detail) | Sub Code Description (In detail) | Total Physical & Financial Target |  |  |  |  | FY: 2014-15 (Year-1) |  |  | FY: 2015-16 (Year-2) |  |  | FY: 2016-17 (Year-3) |  |  | FY: 2017-18 (Year-4) |  |  | FY: 2018-19 (Year-5) |  |  | FY: 2019-20 (Year-6) |  |  | FY: 2020-21 (Year-7) |  |  | FY: 2021-22 (Year-8)
|  |  | Unit | Unit Cost | Quantity | Total Cost (Taka in Lac) | Weight | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical
[9 empty] | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.3 | 6 | 0.0003 | 0.13 | 2.6 | 0.00013 | 0.28 | 5.6 | 0.00028 | 0.3 | 6 | 0.0003 | 0.5 | 10 | 0.0005 | 2.0242 | 40.484 | 0.0020242 | 1.4658 | 29.316 | 0.0014658 | 100 | 0.005 | 10 |  |  | 5 | 0
| 3111327 | Overtime Allowance | Item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 63 | 0.0063 | 3.7 | 37 | 0.0037 | 100 | 0.01 | 11 |  |  | 10 | 0
| 3111338 | Other Allowance | Item | 140 | 1 Item | 140 | 0.0014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 17.8571 | 0.025 | 11.61 | 8.2929 | 0.01161 | 14 | 10 | 0.014 | 53.634 | 38.31 | 0.053634 | 35.756 | 25.54 | 0.035756 | 100 | 0.14 | 12 |  |  | 140 | 0
|  | Supplies and services: | [34 empty] | 0 | 0
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | Item | 120 | 1 Item | 120 | 0.0012 | 0.99 | 0.825 | 0.00099 | 11.92 | 9.9333 | 0.01192 | 14.98 | 12.4833 | 0.01498 | 17.96 | 14.9667 | 0.01796 | 12.7 | 10.5833 | 0.0127 | 14.97 | 12.475 | 0.01497 | 28.8176 | 24.0147 | 0.028818 | 17.6624 | 14.7187 | 0.017662 | 100 | 0.11901 | 14 |  |  | 120 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | Months | 245 | 1 Item | 245 | 0.00246 | 0 | 0 | 0 | 16.25 | 6.6327 | 0.016316 | 31.35 | 12.7959 | 0.031478 | 34.86 | 14.2286 | 0.035002 | 34.21 | 13.9633 | 0.03435 | 34.21 | 13.9633 | 0.03435 | 58.3544 | 23.8181 | 0.058593 | 35.7656 | 14.5982 | 0.035912 | 100 | 0.246 | 15 | 245 | 100 | 245 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | Item | 2874.35 | 1 Item | 2874.35 | 0.02881 | 223.75 | 7.7844 | 0.22427 | 464.64 | 16.165 | 0.46571 | 327.7 | 11.4008 | 0.32846 | 337.33 | 11.7359 | 0.33811 | 249.75 | 8.6889 | 0.25033 | 177.18 | 6.1642 | 0.17759 | 634.52 | 22.0753 | 0.63599 | 459.48 | 15.9855 | 0.46054 | 100 | 2.6567 | 16 |  |  | 2874.35 | 0
| 3211119 | Postage | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.05 | 1 | 5e-05 | 0.13 | 2.6 | 0.00013 | 0.22 | 4.4 | 0.00022 | 0.37 | 7.4 | 0.00037 | 0.48 | 9.6 | 0.00048 | 2.175 | 43.5 | 0.002175 | 1.575 | 31.5 | 0.001575 | 100 | 0.005 | 17 |  |  | 5 | 0
| 3211120 | Telephones/Telegram/Teleprinter | Item | 5 | 1 Item | 5 | 5e-05 | 0.21 | 4.2 | 0.00021 | 0.24 | 4.8 | 0.00024 | 0.29 | 5.8 | 0.00029 | 0.15 | 3 | 0.00015 | 0.08 | 1.6 | 8e-05 | 0.07 | 1.4 | 7e-05 | 2.4156 | 48.312 | 0.0024156 | 1.5444 | 30.888 | 0.0015444 | 100 | 0.00479 | 18 |  |  | 5 | 0
| 3211117 | Telex/Fax/Internet | Item | 5 | 1 Item | 5 | 5e-05 | 0.25 | 5 | 0.00025 | 0.001 | 0.02 | 1e-06 | 0.09 | 1.8 | 9e-05 | 0.05 | 1 | 5e-05 | 0.05 | 1 | 5e-05 | 0.1 | 2 | 0.0001 | 2.497 | 49.9408 | 0.002497 | 1.962 | 39.2392 | 0.001962 | 100 | 0.00475 | 19 |  |  | 5 | 0
| 3221104 | Registration Fee (Vehicles) | Item | 20 | 1 Item | 20 | 0.0002 | 1.1 | 5.5 | 0.0011 | 8.37 | 41.85 | 0.00837 | 0.08 | 0.4 | 8e-05 | 0 | 0 | 0 | 2.37 | 11.85 | 0.00237 | 0.17 | 0.85 | 0.00017 | 4.9833 | 24.9165 | 0.0049833 | 2.9267 | 14.6335 | 0.0029267 | 100 | 0.0189 | 20 |  |  | 20 | 0
| 3211115 | Water | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.12 | 2.4 | 0.00012 | 0.23 | 4.6 | 0.00023 | 0.37 | 7.4 | 0.00037 | 0.4 | 8 | 0.0004 | 0.55 | 11 | 0.00055 | 2.0313 | 40.626 | 0.0020313 | 1.2987 | 25.974 | 0.0012987 | 100 | 0.005 | 21 |  |  | 5 | 0
| 3211113 | Electricity | Item | 20 | 1 Item | 20 | 0.0002 | 0.19 | 0.95 | 0.00019 | 1.67 | 8.35 | 0.00167 | 1.78 | 8.9 | 0.00178 | 2.31 | 11.55 | 0.00231 | 2.78 | 13.9 | 0.00278 | 2.89 | 14.45 | 0.00289 | 4.609 | 23.045 | 0.004609 | 3.771 | 18.855 | 0.003771 | 100 | 0.01981 | 22 |  |  | 20 | 0
| 3243102 | Gas & Fuel | Item | 40 | 1 Item | 40 | 0.0004 | 0.94 | 2.35 | 0.00094 | 3.7 | 9.25 | 0.0037 | 3 | 7.5 | 0.003 | 4 | 10 | 0.004 | 5.89 | 14.725 | 0.00589 | 4.02 | 10.05 | 0.00402 | 11.2545 | 28.1363 | 0.011255 | 7.1955 | 17.9887 | 0.0071955 | 100 | 0.03906 | 23 |  |  | 40 | 0
| 3243101 | Petrol and Lubricant | Item | 170 | 1 Item | 170 | 0.0017 | 0.62 | 0.36471 | 0.00062 | 6.99 | 4.1118 | 0.00699 | 18.97 | 11.1588 | 0.01897 | 18 | 10.5882 | 0.018 | 20 | 11.7647 | 0.02 | 24.18 | 14.2235 | 0.02418 | 46.3068 | 27.2393 | 0.046307 | 34.9332 | 20.5489 | 0.034933 | 100 | 0.16938 | 24 |  |  | 170 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) | Item | 3 | 1 Item | 3 | 3e-05 | 0.08 | 2.6667 | 8e-05 | 0.749 | 24.9667 | 0.000749 | 0.01 | 0.33333 | 1e-05 | 0.22 | 7.3333 | 0.00022 | 0.1 | 3.3333 | 0.0001 | 0.91 | 30.3333 | 0.00091 | 0.51205 | 17.0683 | 0.00051205 | 0.41895 | 13.965 | 0.00041895 | 100 | 0.00292 | 25 |  |  | 3 | 0
| 3255102 | Printing & Binding | Item | 50 | 1 Item | 50 | 0.0005 | 0.2 | 0.4 | 0.0002 | 6.994 | 13.988 | 0.006994 | 16.99 | 33.98 | 0.01699 | 6 | 12 | 0.006 | 3.98 | 7.96 | 0.00398 | 0.5 | 1 | 0.0005 | 9.355 | 18.7099 | 0.009355 | 5.981 | 11.9621 | 0.005981 | 100 | 0.0498 | 26 |  |  | 50 | 0
| 3255104 | Stationery, Seals & Stamps | Item | 120 | 1 Item | 120 | 0.0012 | 0.97 | 0.80833 | 0.00097 | 6.972 | 5.81 | 0.006972 | 11.2 | 9.3333 | 0.0112 | 12.79 | 10.6583 | 0.01279 | 17.98 | 14.9833 | 0.01798 | 19.95 | 16.625 | 0.01995 | 31.5869 | 26.3224 | 0.031587 | 18.5511 | 15.4592 | 0.018551 | 100 | 0.11903 | 27 |  |  | 120 | 0
| 3211127 | Books & Periodicals | Item | 2 | 1 Item | 2 | 2e-05 | 0 | 0 | 0 | 0.1 | 5 | 0.0001 | 0.03 | 1.5 | 3e-05 | 0.05 | 2.5 | 5e-05 | 0.1 | 5 | 0.0001 | 0.2 | 10 | 0.0002 | 0.8816 | 44.08 | 0.0008816 | 0.6384 | 31.92 | 0.0006384 | 100 | 0.002 | 28 |  |  | 2 | 0
|  | Training Expenditure | [34 empty] | 0 | 0
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | Item | 119 | 1 Item | 119 | 0.00119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 100 | 0.119 | 0 | 0 | 0 | 100 | 0.119 | 30 |  |  | 119 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 536.7 | 1 Item | 536.7 | 0.00538 | 0 | 0 | 0 | 9.22 | 1.7179 | 0.0092423 | 29.86 | 5.5636 | 0.029932 | 86.55 | 16.1263 | 0.08676 | 175.87 | 32.7688 | 0.1763 | 22.21 | 4.1383 | 0.022264 | 127.794 | 23.8111 | 0.1281 | 85.196 | 15.874 | 0.085402 | 100 | 0.538 | 31 |  |  | 536.7 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 2957.63 | 1 Item | 2957.63 | 0.02964 | 0 | 0 | 0 | 0 | 0 | 0 | 199.49 | 6.7449 | 0.19992 | 524.89 | 17.747 | 0.52602 | 622.25 | 21.0388 | 0.62359 | 338.12 | 11.4321 | 0.33885 | 801.9144 | 27.1134 | 0.80364 | 470.9656 | 15.9237 | 0.47198 | 100 | 2.964 | 32 |  |  | 2957.63 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1043.61 | 1 Item | 1043.61 | 0.01046 | 0 | 0 | 0 | 0 | 0 | 0 | 119.7 | 11.4698 | 0.11997 | 224.29 | 21.4917 | 0.2248 | 234.21 | 22.4423 | 0.23475 | 82.97 | 7.9503 | 0.08316 | 210.342 | 20.1552 | 0.21082 | 172.098 | 16.4906 | 0.17249 | 100 | 1.046 | 33 |  |  | 1043.61 | 0
| 3211109 | Casual labour/Job worker | MM | 22 | 1 Item | 22 | 0.00022 | 0.25 | 1.1364 | 0.00025 | 2.11 | 9.5909 | 0.00211 | 2.35 | 10.6818 | 0.00235 | 2 | 9.0909 | 0.002 | 4.25 | 19.3182 | 0.00425 | 3.49 | 15.8636 | 0.00349 | 4.681 | 21.2773 | 0.004681 | 2.869 | 13.0409 | 0.002869 | 100 | 0.02175 | 34 |  |  | 22 | 0
| 3256103 | Consumable Stores |  | 15 | 1 Item | 15 | 0.00015 | 0 | 0 | 0 | 0.99 | 6.6 | 0.00099 | 0.75 | 5 | 0.00075 | 1 | 6.6667 | 0.001 | 1 | 6.6667 | 0.001 | 3 | 20 | 0.003 | 4.7908 | 31.9387 | 0.0047908 | 3.4692 | 23.128 | 0.0034692 | 100 | 0.015 | 35 |  |  | 15 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 0 | 56+532 | 7901.4 | 0.07919 | 849.67 | 10.7534 | 0.85156 | 1849.425 | 23.4063 | 1.8535 | 1123.15 | 14.2146 | 1.1257 | 689.33 | 8.7242 | 0.69087 | 686.43 | 8.6874 | 0.68796 | 450 | 5.6952 | 0.451 | 1374.571 | 17.3965 | 1.3776 | 878.824 | 11.1224 | 0.88078 | 100 | 7.0674 | 36 |  |  | 7901.4 | 0
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | item | 30 | 1 Item | 30 | 0.0003 | 0.4 | 1.3333 | 0.0004 | 1.33 | 4.4333 | 0.00133 | 1.5 | 5 | 0.0015 | 4.5 | 15 | 0.0045 | 5 | 16.6667 | 0.005 | 3 | 10 | 0.003 | 8.2766 | 27.5887 | 0.0082766 | 5.9934 | 19.978 | 0.0059934 | 100 | 0.0296 | 37 |  |  | 30 | 0
| 3111332 | b) Interim Evaluation | item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27 | 2.7 | 0.00027 | 0.25 | 2.5 | 0.00025 | 0.77 | 7.7 | 0.00077 | 0.41 | 4.1 | 0.00041 | 8.3 | 83 | 0.0083 | 0 | 0 | 0 | 100 | 0.01 | 38 |  |  | 10 | 0
| 3111332 | c) Progress Monitoring | item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 3 | 0.0003 | 0.25 | 2.5 | 0.00025 | 0.75 | 7.5 | 0.00075 | 0.41 | 4.1 | 0.00041 | 4.145 | 41.45 | 0.004145 | 4.145 | 41.45 | 0.004145 | 100 | 0.01 | 39 |  |  | 10 | 0
| 3257104 | Survey | item | 162 | 1 Item | 162 | 0.00162 | 0 | 0 | 0 | 7.62 | 4.7037 | 0.00762 | 17.47 | 10.784 | 0.01747 | 30 | 18.5185 | 0.03 | 29.93 | 18.4753 | 0.02993 | 30 | 18.5185 | 0.03 | 26.7786 | 16.53 | 0.026779 | 20.2014 | 12.47 | 0.020201 | 100 | 0.162 | 40 |  |  | 162 | 0
| 3255101 | Computer Consumables | item | 60 | 1 Item | 60 | 0.0006 | 0.49 | 0.81667 | 0.00049 | 1.499 | 2.4983 | 0.001499 | 4.5 | 7.5 | 0.0045 | 6.48 | 10.8 | 0.00648 | 7.5 | 12.5 | 0.0075 | 10 | 16.6667 | 0.01 | 16.242 | 27.0701 | 0.016242 | 13.2889 | 22.1483 | 0.013289 | 100 | 0.05951 | 41 |  |  | 60 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | item | 1700 | 1 Item | 1700 | 0.01704 | 0 | 0 | 0 | 84.31 | 4.9594 | 0.084508 | 227.97 | 13.41 | 0.22851 | 263.24 | 15.4847 | 0.26386 | 299.93 | 17.6429 | 0.30064 | 299.96 | 17.6447 | 0.30067 | 299.0163 | 17.5892 | 0.29972 | 225.5737 | 13.269 | 0.2261 | 100 | 1.704 | 42 |  |  | 1700 | 0
|  | Repair, Maintenance & Rehabilitation: | [34 empty] | 0 | 0
| 3258101 | Motor Vehicles |  | 125 | L.S. | 125 | 0.00125 | 0.98 | 0.784 | 0.00098 | 5.967 | 4.7736 | 0.005967 | 12 | 9.6 | 0.012 | 21.99 | 17.592 | 0.02199 | 20.46 | 16.368 | 0.02046 | 14.97 | 11.976 | 0.01497 | 26.7481 | 21.3985 | 0.026748 | 21.8849 | 17.5079 | 0.021885 | 100 | 0.12402 | 44 |  |  | 125 | 0
| 3258102 | Furnitures & Fixtures |  | 10 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0.49 | 4.9 | 0.00049 | 0.74 | 7.4 | 0.00074 | 0.98 | 9.8 | 0.00098 | 0.99 | 9.9 | 0.00099 | 1.11 | 11.1 | 0.00111 | 3.414 | 34.14 | 0.003414 | 2.276 | 22.76 | 0.002276 | 100 | 0.01 | 45 |  |  | 10 | 0
| 3258103 | Computers & office equipments |  | 15 | L.S. | 15 | 0.00015 | 0 | 0 | 0 | 0.5 | 3.3333 | 0.0005 | 0.85 | 5.6667 | 0.00085 | 2 | 13.3333 | 0.002 | 1.99 | 13.2667 | 0.00199 | 3 | 20 | 0.003 | 3.9294 | 26.196 | 0.0039294 | 2.7306 | 18.204 | 0.0027306 | 100 | 0.015 | 46 |  |  | 15 | 0
| 3258105 | Machineries & Equipments |  | 10 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0.22 | 2.2 | 0.00022 | 0.01 | 0.1 | 1e-05 | 0.5 | 5 | 0.0005 | 0.5 | 5 | 0.0005 | 1.99 | 19.9 | 0.00199 | 4.1358 | 41.358 | 0.0041358 | 2.6442 | 26.442 | 0.0026442 | 100 | 0.01 | 47 |  |  | 10 | 0
| 3258107 | Office Building : Repair & Maintenance |  | 25 | L.S. | 25 | 0.00025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.98 | 39.92 | 0.00998 | 10 | 40 | 0.01 | 0 | 0 | 0 | 2.9618 | 11.8472 | 0.0029618 | 2.0582 | 8.2328 | 0.0020582 | 100 | 0.025 | 48 |  |  | 25 | 0
| 3258106 | Residential Building : Repair & Maintenance |  | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.95 | 22.375 | 0.00895 | 5.58 | 13.95 | 0.00558 | 4.95 | 12.375 | 0.00495 | 11.9016 | 29.754 | 0.011902 | 8.6184 | 21.546 | 0.0086184 | 100 | 0.04 | 49 |  |  | 40 | 0
| 3258105 | Engineering Equipments |  | 20 | L.S. | 20 | 0.0002 | 0 | 0 | 0 | 0.09 | 0.45 | 9e-05 | 0.3 | 1.5 | 0.0003 | 0.5 | 2.5 | 0.0005 | 0.5 | 2.5 | 0.0005 | 2 | 10 | 0.002 | 9.1355 | 45.6775 | 0.0091355 | 7.4745 | 37.3725 | 0.0074745 | 100 | 0.02 | 50 |  |  | 20 | 0
|  | Drainage Structures : | [31 empty] | 51 |  |  | 0 | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | 404.24 | 86 | 404.24 | 0.00405 | 0 | 0 | 0 | 0 | 0 | 0 | 59.7 | 14.7685 | 0.059812 | 24.34 | 6.0212 | 0.024386 | 10.99 | 2.7187 | 0.011011 | 33.17 | 8.2055 | 0.033232 | 173.9052 | 43.0203 | 0.17423 | 102.1348 | 25.2659 | 0.10233 | 100 | 0.405 | 52 |  |  | 404.24 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | 5 | L.S. | 5 | 5e-05 | 0 | 0 | 0 | 0.9 | 18 | 0.0009 | 0 | 0 | 0 | 0.75 | 15 | 0.00075 | 0.74 | 14.8 | 0.00074 | 0.38 | 7.6 | 0.00038 | 1.3603 | 27.206 | 0.0013603 | 0.8697 | 17.394 | 0.0008697 | 100 | 0.005 | 53 |  |  | 5 | 0
| 3258107 | Others : Repair & Maintenance |  | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 6.25 | 0.0025 | 4.98 | 12.45 | 0.00498 | 1.49 | 3.725 | 0.00149 | 17.3768 | 43.442 | 0.017377 | 13.6532 | 34.133 | 0.013653 | 100 | 0.04 | 54 |  |  | 40 | 0
(a)Sub-total Revenue Component: | [5 empty] | 19100.93 | 0.19141 | 1081.09 | 45.6728 | 1.0835 | 2493.737 |  | 2.4992 | 2227.87 |  | 2.2327 | 2364.86 |  | 2.3698 | 2487.29 |  | 2.4926 | 1601.51 |  | 1.6048 | 4162.9785 |  | 4.1713 | 2681.5945 |  | 2.6871 |  |  | 55 |  |  | 19100.93 | 0
(b) Capital Component: | [36 empty] | 0 | 0
|  | Acquisition of Assets: | [34 empty] | 0 | 0
|  | Motor Vehicle : | [34 empty] | 0 | 0
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 70.25 | 10 | 702.5 | 0.00704 | 346.3 | 49.2954 | 0.34704 | 138.6 | 19.7295 | 0.1389 | 0 | 0 | 0 | 122 | 17.3665 | 0.12226 | 0 | 0 | 0 | 0 | 0 | 0 | 95.6 | 13.6085 | 0.095804 | 0 | 0 | 0 | 100 | 0.35696 | 59 |  |  | 702.5 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 1.52 | 45 | 68.25 | 0.00068 | 5.83 | 8.5421 | 0.0058086 | 26.31 | 38.5495 | 0.026214 | 10.08 | 14.7692 | 0.010043 | 8 | 11.7216 | 0.0079707 | 0 | 0 | 0 | 0 | 0 | 0 | 18.03 | 26.4176 | 0.017964 | 0 | 0 | 0 | 100 | 0.062191 | 60 |  |  | 68.25 | 0
|  | Water Transport : | [34 empty] | 0 | 0
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 18 | 5 | 90 | 0.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 40.29 | 44.7667 | 0.04029 | 21 | 23.3333 | 0.021 | 0 | 0 | 0 | 0 | 0 | 0 | 28.71 | 31.9 | 0.02871 | 0 | 0 | 0 | 100 | 0.09 | 62 |  |  | 90 | 0
|  | Mechinary & Other Equipment | [30 empty] | 0 | 63 |  |  | 0 | 0
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 1.28 | 7 | 8.97 | 9e-05 | 3.73 | 41.5831 | 0.0037425 | 2.74 | 30.5463 | 0.0027492 | 2.5 | 27.8707 | 0.0025084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.0052575 | 64 |  |  | 8.97 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 0.5 | 2 | 1 | 1e-05 | 0.79 | 79 | 0.00079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 21 | 0.00021 | 0 | 0 | 0 | 100 | 0.00021 | 65 |  |  | 1 | 0
|  | Engineering Equipments | [31 empty] | 66 |  |  | 0 | 0
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Sets | 20.5 | 17 | 20.5 | 0.00021 | 0 | 0 | 0 | 5.55 | 27.0732 | 0.0056854 | 11.15 | 54.3902 | 0.011422 | 3.8 | 18.5366 | 0.0038927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.021 | 67 |  |  | 20.5 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos. | 1 | 3 | 3 | 3e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 100 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.003 | 68 |  |  | 3 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | Nos. | 0 | L.S | 50 | 0.0005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.89 | 15.78 | 0.00789 | 1.6 | 3.2 | 0.0016 | 5 | 10 | 0.005 | 35.51 | 71.02 | 0.03551 | 0 | 0 | 0 | 100 | 0.05 | 69 |  |  | 50 | 0
|  | Computers & Accessories | [34 empty] | 0 | 0
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 0.68 | 33 | 22.5 | 0.00023 | 3.88 | 17.2444 | 0.0039662 | 7.14 | 31.7333 | 0.0072987 | 6.18 | 27.4667 | 0.0063173 | 2.27 | 10.0889 | 0.0023204 | 0 | 0 | 0 | 0 | 0 | 0 | 3.03 | 13.4667 | 0.0030973 | 0 | 0 | 0 | 100 | 0.019034 | 71 |  |  | 22.5 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 0.98 | 14 | 13.75 | 0.00014 | 3.744 | 27.2291 | 0.0038121 | 0 | 0 | 0 | 2.986 | 21.7164 | 0.0030403 | 3.15 | 22.9091 | 0.0032073 | 0 | 0 | 0 | 0 | 0 | 0 | 3.87 | 28.1455 | 0.0039404 | 0 | 0 | 0 | 100 | 0.010188 | 72 |  |  | 13.75 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | No. | 0.75 | 2 | 1.5 | 2e-05 | 0 | 0 | 0 | 0.2 | 13.3333 | 0.00026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 86.6667 | 0.0017333 | 0 | 0 | 0 | 100 | 0.002 | 73 |  |  | 1.5 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 0.31 | 17 | 5.25 | 5e-05 | 2.97 | 56.5714 | 0.0028286 | 0.2 | 3.8095 | 0.00019048 | 0 | 0 | 0 | 0.91 | 17.3333 | 0.00086667 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 22.2857 | 0.0011143 | 0 | 0 | 0 | 100 | 0.0021714 | 74 |  |  | 5.25 | 0
| 4112314 | Furnitures & Fixtures | item | 50 | LS | 50 | 0.0005 | 7.96 | 15.92 | 0.00796 | 8.45 | 16.9 | 0.00845 | 8.99 | 17.98 | 0.00899 | 9.96 | 19.92 | 0.00996 | 9.97 | 19.94 | 0.00997 | 0 | 0 | 0 | 2.8954 | 5.7908 | 0.0028954 | 1.7746 | 3.5492 | 0.0017746 | 100 | 0.04204 | 75 |  |  | 50 | 0
| 4112303 | Aircooler | Nos. | 1 | 15 | 15 | 0.00015 | 0 | 0 | 0 | 0 | 0 | 0 | 3.77 | 25.1333 | 0.00377 | 2 | 13.3333 | 0.002 | 3.96 | 26.4 | 0.00396 | 2.99 | 19.9333 | 0.00299 | 1.3908 | 9.272 | 0.0013908 | 0.8892 | 5.928 | 0.0008892 | 100 | 0.015 | 76 |  |  | 15 | 0
|  | Acquisition/Purchase of lands and landed properties of Assets: | [34 empty] | 0 | 0
| 4141101 | Land Acquisition ( 470 hectare) | ha | 42.55 | 470 | 20000 | 0.20045 | 0 | 0 | 0 | 0 | 0 | 0 | 4649.65 | 23.2482 | 4.6601 | 5794.05 | 28.9703 | 5.8071 | 3879.9 | 19.3995 | 3.8886 | 1000 | 5 | 1.0022 | 2338.2 | 11.691 | 2.3435 | 2338.2 | 11.691 | 2.3435 | 100 | 20.045 | 78 |  |  | 20000 | 0
|  | Construction and Works: | [34 empty] | 0 | 0
|  | Irrigation Infrastructurs : | [34 empty] | 0 | 0
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos. | 10.34 | 117 | 1209.54 | 0.01212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 116.72 | 9.6499 | 0.11696 | 192.22 | 15.892 | 0.19261 | 522.348 | 43.1857 | 0.52341 | 378.252 | 31.2724 | 0.37902 | 100 | 1.212 | 81 |  |  | 1209.54 | 0
|  | Drainage Structures : | [34 empty] | 0 | 0
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos. | 235.1 | 5 | 1175.5 | 0.01178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670.035 | 57 | 0.67146 | 505.465 | 43 | 0.50654 | 100 | 1.178 | 83 |  |  | 1175.5 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 167.53 | 111 | 18595.49 | 0.18638 | 0 | 0 | 0 | 0 | 0 | 0 | 293.15 | 1.5765 | 0.29382 | 2773.9 | 14.9171 | 2.7802 | 3076.61 | 16.5449 | 3.0836 | 4075.22 | 21.9151 | 4.0845 | 4439.6033 | 23.8746 | 4.4498 | 3937.0067 | 21.1718 | 3.946 | 100 | 18.638 | 84 |  |  | 18595.49 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) | km | 30.4 | 335.364 | 10194.13 | 0.10217 | 0 | 0 | 0 | 0 | 0 | 0 | 349.16 | 3.4251 | 0.34994 | 840.8 | 8.2479 | 0.84269 | 4821.52 | 47.297 | 4.8323 | 2673.22 | 26.2231 | 2.6792 | 845.2808 | 8.2918 | 0.84718 | 664.1492 | 6.515 | 0.66564 | 100 | 10.217 | 85 |  |  | 10194.13 | 0
|  | Others: | [34 empty] | 0 | 0
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | km | 31.18 | 108.974 | 3397.94 | 0.03406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.04 | 13.3916 | 0.45612 | 726.54 | 21.3818 | 0.72826 | 1218.998 | 35.8746 | 1.2219 | 997.362 | 29.352 | 0.99973 | 100 | 3.406 | 87 |  |  | 3397.94 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | km | 30.33 | 67.11 | 2035.43 | 0.0204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452.46 | 22.2292 | 0.45348 | 253.65 | 12.4617 | 0.25422 | 771.0056 | 37.8792 | 0.77274 | 558.3144 | 27.4298 | 0.55957 | 100 | 2.04 | 88 |  |  | 2035.43 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | km | 28.55 | 61.21 | 1747.81 | 0.01752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341.85 | 19.5588 | 0.34267 | 179.68 | 10.2803 | 0.18011 | 674.454 | 38.5885 | 0.67607 | 551.826 | 31.5724 | 0.55315 | 100 | 1.752 | 89 |  |  | 1747.81 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | km | 0 | 261.653 | 19669.71 | 0.19717 | 0 | 0 | 0 | 0 | 0 | 0 | 336.91 | 1.7128 | 0.33772 | 3910 | 19.8783 | 3.9194 | 1880.15 | 9.5586 | 1.8847 | 2923.61 | 14.8635 | 2.9306 | 6159.0432 | 31.3123 | 6.1739 | 4459.9968 | 22.6744 | 4.4707 | 100 | 19.717 | 90 |  |  | 19669.71 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos. | 22.97 | 7 | 160.79 | 0.00161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 73.26 | 45.5625 | 0.073356 | 0 | 0 | 0 | 48.1415 | 29.9406 | 0.048204 | 39.3885 | 24.4969 | 0.03944 | 100 | 0.161 | 91 |  |  | 160.79 | 0
| 4111201 | Threshing Floor Construction | Nos. | 45 | 5 | 225 | 0.00226 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 123.75 |  |  | 101.25 |  |  |  |  | 92 |  |  | 225 | 0
| 4111201 | Construction of WMG Office | Nos. | 35 | 30 | 1050 | 0.01052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.09 | 4.0086 | 0.04217 | 93.33 | 8.8886 | 0.093508 | 521.3106 | 49.6486 | 0.5223 | 393.2694 | 37.4542 | 0.39402 | 100 | 1.052 | 93 |  |  | 1050 | 0
| 4111201 | O&M During Construction | item | 0 | 1 | 100 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0.055 | 45 | 45 | 0.045 | 100 | 0.1 | 94 |  |  | 100 | 0
|  | (b) Sub-total Capital Component: |  |  |  | 80613.56 | 0.80799 | 375.204 |  | 0.37595 | 189.19 |  | 0.18975 | 5714.816 | 264.0558 | 5.728 | 13502.73 |  | 13.5338 | 15155.13 |  | 15.1896 | 12125.46 |  | 12.1533 | 18578.8862 |  | 18.4977 | 14972.1438 |  | 14.905 |  |  | 95 |  |  | 80613.56 | 0
|  | Total Cost (a+b) : |  |  |  | 99714.49 | 0.9994 | 1456.294 |  | 1.4594 | 2682.927 |  | 2.689 | 7942.686 | 264.0558 | 7.9607 | 15867.59 |  | 15.9036 | 17642.42 |  | 17.6821 | 13726.97 |  | 13.7581 | 22741.8647 |  | 22.669 | 17653.7383 |  | 17.5921 |  |  | 96 |  |  | 99714.49 | 0
| 0 | (c) Physical Contingency ( Lump sum): | item | 0 | L.S. | 49.51 | 0.0005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 26.2403 | 53 | 0.0265 | 23.2697 | 47 | 0.0235 | 100 | 0.05 | 97 |  |  | 49.51 | 0
| 0 | (d) Price Contingency (Lump sum): | item | 0 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 54 | 0.0054 | 4.6 | 46 | 0.0046 | 100 | 0.01 | 98 |  |  | 10 | 0
|  | Grand Total (a+b+c+d) : |  |  |  | 99774 | 1 | 1456.294 |  | 1.4594 | 2682.927 |  | 2.689 | 7942.686 |  | 7.9607 | 15867.59 |  | 15.9036 | 17642.42 |  | 17.6821 | 13726.97 |  | 13.7581 | 22773.505 |  | 22.7009 | 17681.608 |  | 17.6202 |  |  | 99 |  | 98.3146 | 99774
# Weight of each item = |  | (Est. cost of each respective item)
(Total cost of all Physical items)
# Physical Percentage of item = |  | Quantity/number targeted in each year |  |  |  |  | x 100
Total quantity/number of respective item for whole project period
# Physical % of total Project = |  | Weight of each item x % of item
[10 empty] | 1.4596 |  |  | 2.689 |  |  | 7.9607 |  |  | 15.9035 |  |  | 17.6824 |  |  | 13.7581 |  |  | 22.8251 |  |  | 17.7217 |  | 100
[6 empty] | 99774 |  | 1456.294 |  |  | 4139.221 |  |  | 12081.907 |  |  | 27949.497 |  |  | 45591.917 |  |  | 59318.887
59318.887

## Inves._Cost
Investment Cost
Name of the Project : |  |  | Haor Flood Management and Livelihood Improvement Project.(BWDB Part)(Revised)
Name of agency/Division/Ministry : |  |  | Bangladesh Water Development Board / Ministry of Water Resources
(In Lakh Taka)
Budget Head | Economic Code/ Sub Code | Code/Sub Code Description | Total Project Cost | Financial | [7 empty] | CF | Economic
|  |  |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8 |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | 5 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.902 | 0 | 0.2706 | 0.11726 | 0.25256 | 0.2706 | 0.451 | 1.8258 | 1.3222
| 3111327 | Overtime Allowance | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6826 | 3.3374
| 3111338 | Other Allowance | 140 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.902 | 0 | 0 | 0 | 22.55 | 10.4722 | 12.628 | 48.3779 | 32.2519
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 120 | 0.99 | 11.92 | 14.98 | 17.96 | 12.7 | 14.97 | 28.8176 | 17.6624 | 0.902 | 0.89298 | 10.7518 | 13.512 | 16.1999 | 11.4554 | 13.5029 | 25.9935 | 15.9315
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.21 | 58.3544 | 35.7656 | 0.812 | 0 | 13.195 | 25.4562 | 28.3063 | 27.7785 | 27.7785 | 47.3838 | 29.0417
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2874.35 | 223.75 | 464.64 | 327.7 | 337.33 | 249.75 | 177.18 | 634.52 | 459.48 | 0.812 | 181.685 | 377.2877 | 266.0924 | 273.912 | 202.797 | 143.8702 | 515.2302 | 373.0978
| 3211119 | Postage | 5 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.48 | 2.175 | 1.575 | 0.812 | 0 | 0.0406 | 0.10556 | 0.17864 | 0.30044 | 0.38976 | 1.7661 | 1.2789
| 3211120 | Telephones/Telegram/Teleprinter | 5 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.07 | 2.4156 | 1.5444 | 0.812 | 0.17052 | 0.19488 | 0.23548 | 0.1218 | 0.06496 | 0.05684 | 1.9615 | 1.2541
| 3211117 | Telex/Fax/Internet | 5 | 0.25 | 0.001 | 0.09 | 0.05 | 0.05 | 0.1 | 2.497 | 1.962 | 0.812 | 0.203 | 0.000812 | 0.07308 | 0.0406 | 0.0406 | 0.0812 | 2.0276 | 1.5931
| 3221104 | Registration Fee (Vehicles) | 20 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 0.17 | 4.9833 | 2.9267 | 0.812 | 0.8932 | 6.7964 | 0.06496 | 0 | 1.9244 | 0.13804 | 4.0464 | 2.3765
| 3211115 | Water | 5 | 0 | 0.12 | 0.23 | 0.37 | 0.4 | 0.55 | 2.0313 | 1.2987 | 0.812 | 0 | 0.09744 | 0.18676 | 0.30044 | 0.3248 | 0.4466 | 1.6494 | 1.0545
| 3211113 | Electricity | 20 | 0.19 | 1.67 | 1.78 | 2.31 | 2.78 | 2.89 | 4.609 | 3.771 | 0.812 | 0.15428 | 1.356 | 1.4454 | 1.8757 | 2.2574 | 2.3467 | 3.7425 | 3.0621
| 3243102 | Gas & Fuel | 40 | 0.94 | 3.7 | 3 | 4 | 5.89 | 4.02 | 11.2545 | 7.1955 | 0.812 | 0.76328 | 3.0044 | 2.436 | 3.248 | 4.7827 | 3.2642 | 9.1387 | 5.8427
| 3243101 | Petrol and Lubricant | 170 | 0.62 | 6.99 | 18.97 | 18 | 20 | 24.18 | 46.3068 | 34.9332 | 0.72 | 0.4464 | 5.0328 | 13.6584 | 12.96 | 14.4 | 17.4096 | 33.3409 | 25.1519
| 3221108 | Insurance/Bank Charges (including Vehicles) | 3 | 0.08 | 0.749 | 0.01 | 0.22 | 0.1 | 0.91 | 0.51205 | 0.41895 | 0.902 | 0.07216 | 0.6756 | 0.00902 | 0.19844 | 0.0902 | 0.82082 | 0.46187 | 0.37789
| 3255102 | Printing & Binding | 50 | 0.2 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.355 | 5.981 | 0.812 | 0.1624 | 5.6791 | 13.7959 | 4.872 | 3.2318 | 0.406 | 7.5962 | 4.8566
| 3255104 | Stationery, Seals & Stamps | 120 | 0.97 | 6.972 | 11.2 | 12.79 | 17.98 | 19.95 | 31.5869 | 18.5511 | 0.812 | 0.78764 | 5.6613 | 9.0944 | 10.3855 | 14.5998 | 16.1994 | 25.6486 | 15.0635
| 3211127 | Books & Periodicals | 2 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.812 | 0 | 0.0812 | 0.02436 | 0.0406 | 0.0812 | 0.1624 | 0.71586 | 0.51838
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 107.338 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 536.7 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 22.21 | 127.794 | 85.196 | 0.902 | 0 | 8.3164 | 26.9337 | 78.0681 | 158.6347 | 20.0334 | 115.2702 | 76.8468 | 536.7 | 484.1034 | 0.902 | 484.1034
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 2957.63 | 0 | 0 | 199.49 | 524.89 | 622.25 | 338.12 | 801.9144 | 470.9656 | 0.902 | 0 | 0 | 179.94 | 473.4508 | 561.2695 | 304.9842 | 723.3268 | 424.811 | 2957.63 | 2667.7823 | 0.902 | 2667.7823
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 1043.61 | 0 | 0 | 119.7 | 224.29 | 234.21 | 82.97 | 210.342 | 172.098 | 0.902 | 0 | 0 | 107.9694 | 202.3096 | 211.2574 | 74.8389 | 189.7285 | 155.2324 | 1043.61 | 941.3362 | 0.902 | 941.3362
| 3211109 | Casual labour/Job worker | 22 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.49 | 4.681 | 2.869 | 0.902 | 0.2255 | 1.9032 | 2.1197 | 1.804 | 3.8335 | 3.148 | 4.2223 | 2.5878
| 3256103 | Consumable Stores | 15 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.812 | 0 | 0.80388 | 0.609 | 0.812 | 0.812 | 2.436 | 3.8901 | 2.817 | 15 | 12.18 | 0.812 | 12.18
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 7901.4 | 849.67 | 1849.425 | 1123.15 | 689.33 | 686.43 | 450 | 1374.571 | 878.824 | 0.902 | 766.4023 | 1668.1814 | 1013.0813 | 621.7757 | 619.1599 | 405.9 | 1239.863 | 792.6993 | 7901.4 | 7127.0628 | 0.902 | 7127.0628
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 30 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 3 | 8.2766 | 5.9934 | 0.902 | 0.3608 | 1.1997 | 1.353 | 4.059 | 4.51 | 2.706 | 7.4655 | 5.406 | 30 | 27.06 | 0.902 | 27.06
| 3111332 | b) Interim Evaluation | 10 | 0 | 0 | 0.27 | 0.25 | 0.77 | 0.41 | 8.3 | 0 | 0.902 | 0 | 0 | 0.24354 | 0.2255 | 0.69454 | 0.36982 | 7.4866 | 0
| 3111332 | c) Progress Monitoring | 10 | 0 | 0 | 0.3 | 0.25 | 0.75 | 0.41 | 4.145 | 4.145 | 0.902 | 0 | 0 | 0.2706 | 0.2255 | 0.6765 | 0.36982 | 3.7388 | 3.7388
| 3257104 | Survey | 162 | 0 | 7.62 | 17.47 | 30 | 29.93 | 30 | 26.7786 | 20.2014 | 0.902 | 0 | 6.8732 | 15.7579 | 27.06 | 26.9969 | 27.06 | 24.1543 | 18.2217
| 3255101 | Computer Consumables | 60 | 0.49 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.242 | 13.2889 | 0.902 | 0.44198 | 1.3521 | 4.059 | 5.845 | 6.765 | 9.02 | 14.6503 | 11.9866 | 60 | 54.12 | 0.902 | 54.12
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 | 0 | 84.31 | 227.97 | 263.24 | 299.93 | 299.96 | 299.0163 | 225.5737 | 0.86 | 0 | 72.5066 | 196.0542 | 226.3864 | 257.9398 | 257.9656 | 257.154 | 193.9934 |  | 1462 | 0.86
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles | 125 | 0.98 | 5.967 | 12 | 21.99 | 20.46 | 14.97 | 26.7481 | 21.8849 | 0.86 | 0.8428 | 5.1316 | 10.32 | 18.9114 | 17.5956 | 12.8742 | 23.0034 | 18.821
| 3258102 | Furnitures & Fixtures | 10 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 1.11 | 3.414 | 2.276 | 0.86 | 0 | 0.4214 | 0.6364 | 0.8428 | 0.8514 | 0.9546 | 2.936 | 1.9574
| 3258103 | Computers & office equipments | 15 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.86 | 0 | 0.43 | 0.731 | 1.72 | 1.7114 | 2.58 | 3.3793 | 2.3483
| 3258105 | Machineries & Equipments | 10 | 0 | 0.22 | 0.01 | 0.5 | 0.5 | 1.99 | 4.1358 | 2.6442 | 0.86 | 0 | 0.1892 | 0.0086 | 0.43 | 0.43 | 1.7114 | 3.5568 | 2.274 | 10 | 8.6 | 0.86 | 8.6
| 3258107 | Office Building : Repair & Maintenance | 25 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.765 | 0 | 0 | 0 | 7.6347 | 7.65 | 0 | 2.2658 | 1.5745 | 25 | 19.125 | 0.765 | 19.125
| 3258106 | Residential Building : Repair & Maintenance | 40 | 0 | 0 | 0 | 8.95 | 5.58 | 4.95 | 11.9016 | 8.6184 | 0.765 | 0 | 0 | 0 | 6.8467 | 4.2687 | 3.7868 | 9.1047 | 6.5931 | 40 | 30.6 | 0.765 | 30.6
| 3258105 | Engineering Equipments | 20 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.86 | 0 | 0.0774 | 0.258 | 0.43 | 0.43 | 1.72 | 7.8565 | 6.4281
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 404.24 | 0 | 0 | 59.7 | 24.34 | 10.99 | 33.17 | 173.9052 | 102.1348 | 0.812 | 0 | 0 | 48.4764 | 19.7641 | 8.9239 | 26.934 | 141.211 | 82.9335 | 404.24 | 328.2429 | 0.812 | 328.2429
| 3258128 | Water Transport : Repair of Speedboat(s) | 5 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.38 | 1.3603 | 0.8697 | 0.812 | 0 | 0.7308 | 0 | 0.609 | 0.60088 | 0.30856 | 1.1046 | 0.7062 | 5 | 4.06 | 0.812 | 4.06
| 3258107 | Others : Repair & Maintenance | 40 | 0 | 0 | 0 | 2.5 | 4.98 | 1.49 | 17.3768 | 13.6532 | 0.902 | 0 | 0 | 0 | 2.255 | 4.492 | 1.344 | 15.6739 | 12.3152 | 40 | 36.08 | 0.902 | 36.08
| (a)Sub-total Revenue Component: |  | 19100.93 | 1081.09 | 2493.737 | 2227.87 | 2364.86 | 2487.29 | 1601.51 | 4162.9785 | 2681.5945 |  | 954.5043 | 2198.2426 | 1955.1289 | 2076.9077 | 2194.3755 | 1400.9975 | 3644.9698 | 2341.7045 | 19100.93 | 16766.8308 | 0 | 11740.3526
(b) Capital Component:
Acquisition of Assets:
|  | Motor Vehicle : | [18 empty] | 0 | 0 | 0 | 0
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 | 346.3 | 138.6 | 0 | 122 | 0 | 0 | 95.6 | 0 | 0.68 | 235.484 | 94.248 | 0 | 82.96 | 0 | 0 | 65.008 | 0 | 702.5 | 477.7 | 0.68 | 477.7
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 68.25 | 5.83 | 26.31 | 10.08 | 8 | 0 | 0 | 18.03 | 0 | 0.68 | 3.9644 | 17.8908 | 6.8544 | 5.44 | 0 | 0 | 12.2604 | 0 | 68.25 | 46.41 | 0.68 | 46.41
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 90 | 0 | 0 | 40.29 | 21 | 0 | 0 | 28.71 | 0 | 0.68 | 0 | 0 | 27.3972 | 14.28 | 0 | 0 | 19.5228 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 | 3.73 | 2.74 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0.812 | 3.0288 | 2.2249 | 2.03 | 0 | 0 | 0 | 0 | 0 | 8.97 | 7.2836 | 0.812 | 7.2836
| 4112316 | Fax -2 nos (PMO 2 Nos.). | 1 | 0.79 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0 | 0.812 | 0.64148 | 0 | 0 | 0 | 0 | 0 | 0.17052 | 0 | 1 | 0.812 | 0.812 | 0.812
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 | 0 | 5.55 | 11.15 | 3.8 | 0 | 0 | 0 | 0 | 0.68 | 0 | 3.774 | 7.582 | 2.584 | 0 | 0 | 0 | 0 | 20.5 | 13.94 | 0.68 | 13.94
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0.68 | 0 | 0 | 0 | 2.04 | 0 | 0 | 0 | 0 | 3 | 2.04 | 0.68 | 2.04
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 50 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 35.51 | 0 | 0.68 | 0 | 0 | 0 | 5.3652 | 1.088 | 3.4 | 24.1468 | 0 | 50 | 34 | 0.68 | 34
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 22.5 | 3.88 | 7.14 | 6.18 | 2.27 | 0 | 0 | 3.03 | 0 | 0.812 | 3.1506 | 5.7977 | 5.0182 | 1.8432 | 0 | 0 | 2.4604 | 0 | 22.5 | 18.27 | 0.812 | 18.27
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 3.87 | 0 | 0.812 | 3.0401 | 0 | 2.4246 | 2.5578 | 0 | 0 | 3.1424 | 0 | 13.75 | 11.165 | 0.812 | 11.165
| 4112202 | A3 Combo Printer 2 no ( PMO) | 1.5 | 0 | 0.2 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0.812 | 0 | 0.1624 | 0 | 0 | 0 | 0 | 1.0556 | 0 | 1.5 | 1.218 | 0.812 | 1.218
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 1.17 | 0 | 0.812 | 2.4116 | 0.1624 | 0 | 0.73892 | 0 | 0 | 0.95004 | 0
| 4112314 | Furnitures & Fixtures | 50 | 7.96 | 8.45 | 8.99 | 9.96 | 9.97 | 0 | 2.8954 | 1.7746 | 0.812 | 6.4635 | 6.8614 | 7.2999 | 8.0875 | 8.0956 | 0 | 2.3511 | 1.441
| 4112303 | Aircooler | 15 | 0 | 0 | 3.77 | 2 | 3.96 | 2.99 | 1.3908 | 0.8892 | 0.812 | 0 | 0 | 3.0612 | 1.624 | 3.2155 | 2.4279 | 1.1293 | 0.72203
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | 20000 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 1000 | 2338.2 | 2338.2 | 0.902 | 0 | 0 | 4193.9843 | 5226.2331 | 3499.6698 | 902 | 2109.0564 | 2109.0564 | 20000 | 18040 | 0.902 | 18040
Construction and Works:
|  | Irrigation Infrastructurs : | [18 empty] | 0 | 0 | 0 | 0
| 4111306 | Construction of Irrigation Inlet (New Haors) | 1209.54 | 0 | 0 | 0 | 0 | 116.72 | 192.22 | 522.348 | 378.252 | 0.902 | 0 | 0 | 0 | 0 | 105.2814 | 173.3824 | 471.1579 | 341.1833 | 1310 | 996.91 | 0.761 | 996.91
|  | Drainage Structures : | [18 empty] | 0 | 0 | 0 | 0
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 1175.5 | 0 | 0 | 0 | 0 | 0 | 0 | 670.035 | 505.465 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 512.5768 | 386.6807 | 1175.5 | 899.2575 | 0.765 | 899.2575
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 18595.49 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 4075.22 | 4439.6033 | 3937.0067 | 0.765 | 0 | 0 | 224.2597 | 2122.0335 | 2353.6067 | 3117.5433 | 3396.2965 | 3011.8101 | 18595.49 | 14225.5499 | 0.765 | 14225.5499
| 4111307 | Re-excavation of Khal/River (New Haors) | 10194.13 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 2673.22 | 845.2808 | 664.1492 | 0.761 | 0 | 0 | 265.7108 | 639.8488 | 3669.1767 | 2034.3204 | 643.2587 | 505.4175 | 10194.13 | 7757.7329 | 0.761 | 7757.7329
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 3397.94 | 0 | 0 | 0 | 0 | 455.04 | 726.54 | 1218.998 | 997.362 | 0.761 | 0 | 0 | 0 | 0 | 346.2854 | 552.8969 | 927.6575 | 758.9925 | 3397.94 | 2585.8323 | 0.761 | 2585.8323
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 2035.43 | 0 | 0 | 0 | 0 | 452.46 | 253.65 | 771.0056 | 558.3144 | 0.761 | 0 | 0 | 0 | 0 | 344.3221 | 193.0276 | 586.7353 | 424.8773 | 2035.43 | 1548.9622 | 0.761 | 1548.9622
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 1747.81 | 0 | 0 | 0 | 0 | 341.85 | 179.68 | 674.454 | 551.826 | 0.761 | 0 | 0 | 0 | 0 | 260.1479 | 136.7365 | 513.2595 | 419.9396 | 1747.81 | 1330.0834 | 0.761 | 1330.0834
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 19669.71 | 0 | 0 | 336.91 | 3910 | 1880.15 | 2923.61 | 6159.0432 | 4459.9968 | 0.761 | 0 | 0 | 256.3885 | 2975.51 | 1430.7942 | 2224.8672 | 4687.0319 | 3394.0576 | 19669.71 | 14968.6493 | 0.761 | 14968.6493
| 4111201 | Rehabilitation of Regulator (New Haors) | 160.79 | 0 | 0 | 0 | 0 | 73.26 | 0 | 48.1415 | 39.3885 | 0.761 | 0 | 0 | 0 | 0 | 55.7509 | 0 | 36.6357 | 29.9746 | 160.79 | 122.3612 | 0.761 | 122.3612
| 4111201 | Threshing Floor Construction | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 123.75 | 101.25 | 2.761 | 0 | 0 | 0 | 0 | 0 | 0 | 341.6738 | 279.5513
| 4111201 | Construction of WMG Office | 1050 | 0 | 0 | 0 | 0 | 42.09 | 93.33 | 521.3106 | 393.2694 | 0.765 | 0 | 0 | 0 | 0 | 32.1989 | 71.3975 | 398.8026 | 300.8511 | 1050 | 803.25 | 0.765 | 803.25
| 4111201 | O&M During Construction | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 45 | 0.761 | 0 | 0 | 0 | 0 | 0 | 0 | 41.855 | 34.245 | 100 | 76.1 | 0.761 | 76.1
|  | (b) Sub-total Capital Component: | 80613.56 | 375.204 | 189.19 | 5714.816 | 13502.73 | 15155.13 | 12125.46 | 18578.8862 | 14972.1438 |  | 258.1845 | 131.1216 | 5002.0108 | 11091.1461 | 12109.633 | 9411.9998 | 14798.1948 | 11998.8
|  | Total Cost (a+b) : | 99714.49 | 1456.294 | 2682.927 | 7942.686 | 15867.59 | 17642.42 | 13726.97 | 22741.8647 | 17653.7383 |  | 1212.6888 | 2329.3642 | 6957.1397 | 13168.0538 | 14304.0085 | 10812.9973 | 18443.1646 | 14340.5045
| 0 | (c) Physical Contingency ( Lump sum): | 49.51 | 0 | 0 | 0 | 0 | 0 | 0 | 26.2403 | 23.2697 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 20.0738 | 17.8013
| 0 | (d) Price Contingency (Lump sum): | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total (a+b+c+d) : | 99774 | 1456.294 | 2682.927 | 7942.686 | 15867.59 | 17642.42 | 13726.97 | 22773.505 | 17681.608 |  | 1212.6888 | 2329.3642 | 6957.1397 | 13168.0538 | 14304.0085 | 10812.9973 | 18463.2384 | 14358.3058 | 81605.7964 | 99774
|  |  |  | 1456.294 | 2682.927 | 7942.686 | 15867.59 | 17642.42 | 13726.97 | 22773.505 | 17681.608
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Crop. Pattern
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
PRE - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic | ML | Seed | Urea | TSP | MP
1. | Boro (L) | 47000 | 3.5 | 164500 | 10000 | 10050 | 16450 | 16532.25 | 5405000 | 1880000 | 9400000 | 7520000 | 4700000
2. | Boro (HYV) | 125000 | 4 | 500000 | 11000 | 11055 | 55000 | 55275 | 18750000 | 5000000 | 37500000 | 30000000 | 18750000
| Total : | 172000 | - | - | - | - | 71450 | 71807.25 | 24155000 | 6880000 | 46900000 | 37520000 | 23450000
|  | Cropping Intensity = |  | 110%
|  | Total Paddy Production = |  |  | 664500 | mt.
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
POST - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic
1. | Boro (HYV) | 280500 | 5.5 | 1542750 | 10000 | 10050 | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
| Total : | 280500 | - | - | - | - | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
|  | Cropping Intensity = |  | 179.357 | %
|  | Total Paddy Production = |  |  | 1542750 | mt.
|  | Incremental Paddy Production = |  |  | 878250 | mt.
Variable Cost of Cultivation
PRE - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 24155000 | 100 | 75 | 24155 | 18116.25
2. | Power Tiller | - | - | - | - | 6880 | 6205.76
3. | Seed/Seedlings
a) | Paddy | mt. | 6880 | 30000 | 27060 | 2064 | 1861.728
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
d) | Mustard | mt. | 0 | 50000 | 45100 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 46900 | 8000 | 12000 | 3752 | 5628
b) | T.S.P. | mt. | 37520 | 22000 | 33000 | 8254.4 | 12381.6
c) | M.P. | mt. | 23450 | 18000 | 27000 | 4221 | 6331.5
5. | Insecticide | - | - | - | - | 200 | 180.4
6. | Irrigation Cost | - | - | - | - | 500 | 750
| Total | - | - | - | - | 49526.4 | 50705.238
POST - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 43477500 | 100 | 75 | 43477.5 | 32608.125
2. | Power Tiller | - | - | - | - | 11220 | 10120.44
3. | Seed/Seedlings
a) | Paddy | mt. | 11220 | 30000 | 27060 | 3366 | 3036.132
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
c) | Onion | mt. | 0 | 50000 | 45100 | 0 | 0
d) | Jute | mt. | 0 | 50000 | 45100 | 0 | 0
e) | Vegetables | mt. | 0 | 20000 | 18040 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 84150 | 8000 | 12000 | 6732 | 10098
|  | mt. | 34.61 | 22000 | 19844 | 7.6142 | 6.868
b) | T.S.P. | mt. | 67320 | 22000 | 33000 | 14810.4 | 22215.6
|  | mt. | 34.61 | 200 | 180.4 | 0.06922 | 0.062436
c) | M.P. | mt. | 42075 | 18000 | 27000 | 7573.5 | 11360.25
|  |  | 0 | - | -
|  |  | 0 |  | 0 | 0 | 0
5. | Insecticide | - | - | - | - | 500 | 451
6. | Irrigation Cost | - | - | - | - | 1000 | 1500
| Total | - | - | - |  | 88687.0834 | 91396.4774
| Incremental Farm Labour = |  | 19322500 | mandays
FIXED COST
A. | PRE - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
B. | POST - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
SUMMARY OF BENEFIT
A. | POST - PROJECT CONDITION
|  |  |  | Financial |  |  | Economic
1. | Gross Production Value |  |  | 154275 |  |  | 155046.375
2. | Cost of cultivation
| i) Variable Cost |  |  | 88687.0834 |  |  | 91396.4774
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (A1-A2) |  |  | 65587.9166 |  |  | 63649.8976
B. | PRE - PROJECT CONDITION
1. | Gross Production Value |  |  | 71450 |  |  | 71807.25
2. | Cost of cultivation
| i) Variable Cost |  |  | 49526.4 |  |  | 50705.238
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (B1-B2) |  |  | 21923.6 |  |  | 21102.012
C. | Net Incremental Benefit from Agriculture (A3-B3) |  |  | 43664.3166 |  |  | 42547.8856

## FIRR
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.294 | 0 | 1456.294 | 0 | 0 | 0 | -1456.294
2 | 2682.927 | 0 | 2682.927 | 0 | 0 | 0 | -2682.927
3 | 7942.686 | 0 | 7942.686 | 0 | 0 | 0 | -7942.686
4 | 15867.59 | 0 | 15867.59 | 0 | 0 | 0 | -15867.59
5 | 17642.42 | 0 | 17642.42 | 0 | 0 | 0 | -17642.42
6 | 13726.97 | 0 | 13726.97 | 21832.1583 | 0 | 21832.1583 | 8105.1883
7 | 22773.505 | 0 | 22773.505 | 26198.5899 | 0 | 26198.5899 | 3425.0849
8 | 17681.608 | 0 | 17681.608 | 30565.0216 | 0 | 30565.0216 | 12883.4136
9 |  | 670 | 670 | 34931.4533 | 0 | 34931.4533 | 34261.4533
10 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
11 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
12 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
13 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
14 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
15 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
16 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
17 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
18 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
19 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
20 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
21 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
22 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
23 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
24 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
25 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
26 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
27 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
28 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
29 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
30 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
NPV @12% | 53584.8379 | 2068.6546 | 55653.4926 | 166922.8114 | 0 | 166922.8114 | 111269.3189
All calculations are based on project period of 30 years
FIRR base case |  |  | 33.65%
Benefit Cost Ratio |  |  | 2.9993
NPV @12% |  |  | 111269.3189

## EIRR
Computation of Internal Rate of Return
(Economic)
(In Lakh Taka)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1212.6888 | 0 | 1212.6888 | 0 | 0 | 0 | -1212.6888
2 | 2329.3642 | 0 | 2329.3642 | 0 | 0 | 0 | -2329.3642
3 | 6957.1397 | 0 | 6957.1397 | 0 | 0 | 0 | -6957.1397
4 | 13168.0538 | 0 | 13168.0538 | 0 | 0 | 0 | -13168.0538
5 | 14304.0085 | 0 | 14304.0085 | 0 | 0 | 0 | -14304.0085
6 | 10812.9973 | 0 | 10812.9973 | 21273.9428 | 0 | 21273.9428 | 10460.9455
7 | 18463.2384 | 0 | 18463.2384 | 25528.7313 | 0 | 25528.7313 | 7065.4929
8 | 14358.3058 | 0 | 14358.3058 | 29783.5199 | 0 | 29783.5199 | 15425.2141
9 |  | 604.34 | 604.34 | 34038.3084 | 0 | 34038.3084 | 33433.9684
10 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
11 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
12 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
13 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
14 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
15 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
16 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
17 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
18 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
19 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
20 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
21 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
22 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
23 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
24 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
25 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
26 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
27 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
28 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
29 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
30 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
NPV @12% | 44005.7933 | 1865.9265 | 45871.7198 | 162654.8457 | 0 | 162654.8457 | 116783.1259
All calculations are based on project period of 30 years
EIRR base case |  |  | 38.19%
Benefit Cost Ratio |  |  | 3.5459
NPV @12% |  |  | 110049.79

## Annex-IV
Annexure-IV
Revised Amortization Schedule
Name of Project |  | : Haor Flood Management & Livelihood Improvement Project (BWDB Part)
Total Investment |  | : BDT 102234.00 Lakh |  |  |  | 102234
Loan Portion |  | : BDT 59529.60 Lakh
Loan Period |  | : 40 Years Including 10 Uears grace Period
Trate of Investment |  | : 0.01% per annum
(Taka in Lac)
Year | Beginning Principal Amount | Yearly Fixed Amount to be Paid (Principal) | Yearly Interes to be Paid | Total Payment (Principal + Interest) | Ending Principal Balance |  |  | 2014-15
1 | 2 | 3 | 4 | 5= (3+4) | 6=(2-3) |  |  | GoB | RPA | DPA | Total
11 | 59529.6 | 1984.32 | 5.953 | 1990.273 | 57545.28 |  | Rev | 231.42 |  | 849.67 | 1081.09
12 | 57545.28 | 1984.32 | 5.7545 | 1990.0745 | 55560.96 |  | Cap | 375.2 |  |  | 375.2
13 | 55560.96 | 1984.32 | 5.5561 | 1989.8761 | 53576.64 |  | Total | 606.62 | 0 | 849.67 | 1456.29
14 | 53576.64 | 1984.32 | 5.3577 | 1989.6777 | 51592.32
15 | 51592.32 | 1984.32 | 5.1592 | 1989.4792 | 49608 |  |  | 2015-16
16 | 49608 | 1984.32 | 4.9608 | 1989.2808 | 47623.68 |  |  | GoB | RPA | DPA | Total
17 | 47623.68 | 1984.32 | 4.7624 | 1989.0824 | 45639.36 |  | Rev | 635.09 | 9.22 | 1849.43 | 2493.74
18 | 45639.36 | 1984.32 | 4.5639 | 1988.8839 | 43655.04 |  | Cap | 189.19 |  |  | 189.19
19 | 43655.04 | 1984.32 | 4.3655 | 1988.6855 | 41670.72 |  | Total | 824.28 | 9.22 | 1849.43 | 2682.93
20 | 41670.72 | 1984.32 | 4.1671 | 1988.4871 | 39686.4 |  | Cum | 1430.9 | 9.22 | 2699.1 | 4139.22
21 | 39686.4 | 1984.32 | 3.9686 | 1988.2886 | 37702.08
22 | 37702.08 | 1984.32 | 3.7702 | 1988.0902 | 35717.76
23 | 35717.76 | 1984.32 | 3.5718 | 1987.8918 | 33733.44 |  |  | 2016-17
24 | 33733.44 | 1984.32 | 3.3733 | 1987.6933 | 31749.12 |  |  | GoB | RPA | DPA | Total
25 | 31749.12 | 1984.32 | 3.1749 | 1987.4949 | 29764.8 |  | Rev | 703.95 | 401.59 | 1093.15 | 2198.69
26 | 29764.8 | 1984.32 | 2.9765 | 1987.2965 | 27780.48 |  | Cap | 4854.6 | 860.19 |  | 5714.79
27 | 27780.48 | 1984.32 | 2.778 | 1987.098 | 25796.16 |  | Total | 5558.55 | 1261.78 | 1093.15 | 7913.48
28 | 25796.16 | 1984.32 | 2.5796 | 1986.8996 | 23811.84 |  | Cum | 6989.45 | 1271 | 3792.25 | 12052.7
29 | 23811.84 | 1984.32 | 2.3812 | 1986.7012 | 21827.52
30 | 21827.52 | 1984.32 | 2.1828 | 1986.5028 | 19843.2 |  | ADP | 2017-18
31 | 19843.2 | 1984.32 | 1.9843 | 1986.3043 | 17858.88 |  |  | GoB | RPA | DPA | Total
32 | 17858.88 | 1984.32 | 1.7859 | 1986.1059 | 15874.56 |  | Rev | 700 | 800 | 800 | 2300
33 | 15874.56 | 1984.32 | 1.5875 | 1985.9075 | 13890.24 |  | Cap | 10300 | 7400 |  | 17700
34 | 13890.24 | 1984.32 | 1.389 | 1985.709 | 11905.92 |  | Total | 11000 | 8200 | 800 | 20000
35 | 11905.92 | 1984.32 | 1.1906 | 1985.5106 | 9921.6
36 | 9921.6 | 1984.32 | 0.99216 | 1985.3122 | 7937.28 |  |  | July2016-Mar17
37 | 7937.28 | 1984.32 | 0.79373 | 1985.1137 | 5952.96 |  |  | GoB | RPA | DPA | Total
38 | 5952.96 | 1984.32 | 0.5953 | 1984.9153 | 3968.64 |  | Rev | -166.51 | 790.78 | -1899.1 | -1274.83
39 | 3968.64 | 1984.32 | 0.39686 | 1984.7169 | 1984.32 |  | Cap | 9735.61 | 7400 | 0 | 17135.61
40 | 1984.32 | 1984.32 | 0.19843 | 1984.5184 | 6.8212e-12 |  | Total | 9569.1 | 8190.78 | -1899.1 | 15860.78
Total |  | 59529.6 | 92.2709 | 59621.8709
Apr2017-June17
[8 empty] | GoB | RPA | DPA | Total
[7 empty] | Rev | 870.46 | -389.19 | 2992.25 | 3473.52
[7 empty] | Cap | -4881.01 | -6539.81 | 0 | -11420.82
[7 empty] | Total | -4010.55 | -6929 | 2992.25 | -7947.3

## FIRR_Backup
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.29 | 0 | 1456.29 | 0 | 0 | 0 | -1456.29
2 | 2652.93 | 0 | 2652.93 | 0 | 0 | 0 | -2652.93
3 | 7942.666 | 0 | 7942.666 | 0 | 0 | 0 | -7942.666
4 | 15866.4 | 0 | 15866.4 | 0 | 0 | 0 | -15866.4
5 | 17642.414 | 0 | 17642.414 | 0 | 0 | 0 | -17642.414
6 | 24717.06 | 0 | 24717.06 | 21832.1583 | 0 | 21832.1583 | -2884.9017
7 | 18586.3447 | 0 | 18586.3447 | 26198.5899 | 0 | 26198.5899 | 7612.2452
8 | 12971.6853 | 0 | 12971.6853 | 30565.0216 | 0 | 30565.0216 | 17593.3363
9 |  | 670 | 670 | 34931.4533 | 0 | 34931.4533 | 34261.4533
10 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
11 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
12 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
13 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
14 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
15 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
16 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
17 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
18 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
19 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
20 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
21 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
22 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
23 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
24 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
25 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
26 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
27 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
28 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
29 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
30 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
NPV @12% | 55331.7512 | 2068.6546 | 57400.4058 | 166922.8114 | 0 | 166922.8114 | 109522.4056
All calculations are based on project period of 30 years
FIRR base case |  |  | 32.6%
Benefit Cost Ratio |  |  | 2.908
NPV @12% |  |  | 109522.4056

## Package_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [19 empty] | 2
KISH/PW-02 | [19 empty] | 3
KISH/PW-03 | [19 empty] | 4
KISH/PW-04 | [19 empty] | 5
KISH/PW-05 | [19 empty] | 6
KISH/PW-06 | [19 empty] | 7
KISH/PW-07 | [19 empty] | 8
KISH/PW-09 | [19 empty] | 9
KISH/PW-10 | [19 empty] | 10
KISH/PW-11 | [19 empty] | 11
KISH/PW-12 | [19 empty] | 12
KISH/PW-13 | [19 empty] | 13
KISH/PW-14 | [19 empty] | 14
KISH/PW-15 | [19 empty] | 15
KISH/PW-16 | [19 empty] | 16
KISH/PW-17 | [19 empty] | 17
KISH/PW-18 | [19 empty] | 18
KISH/PW-19 | [19 empty] | 19
KISH/PW-20 | [19 empty] | 20
KISH/PW-21 | [19 empty] | 21
KISH/PW-22 | [19 empty] | 22
KISH/PW-23 | [19 empty] | 23
KISH/PW-24 | [19 empty] | 24
KISH/PW-25 | [19 empty] | 25
KISH/PW-26 | [19 empty] | 26
KISH/PW-27 | [19 empty] | 27
KISH/PW-28 | [19 empty] | 28
KISH/PW-29 | [19 empty] | 29
KISH/PW-30 | [19 empty] | 30
KISH/PW-31 | [19 empty] | 31
KISH/PW-32 | [19 empty] | 32
KISH/PW-33 | [19 empty] | 33
HOBI/PW-01 | [19 empty] | 34
HOBI/PW-02 | [19 empty] | 35
HOBI/PW-04 | [19 empty] | 36
HOBI/PW-05 | [19 empty] | 37
HOBI/PW-06 | [19 empty] | 38
HOBI/PW-07 | [19 empty] | 39
HOBI/PW-08 | [19 empty] | 40
NETR/PW-01 | [19 empty] | 41
NETR/PW-02 | [19 empty] | 42
NETR/PW-03 | [19 empty] | 43
NETR/PW-04 | [19 empty] | 44
NETR/PW-05 | [19 empty] | 45
NETR/PW-06 | [19 empty] | 46
NETR/PW-07 | [19 empty] | 47
NETR/PW-08 | [19 empty] | 48
SUNM/PW-01 | [19 empty] | 49
SUNM/PW-02 | [19 empty] | 50
SUNM/PW-03 | [19 empty] | 51
SUNM/PW-04 | [19 empty] | 52
SUNM/PW-05 | [19 empty] | 53
SUNM/PW-06 | [19 empty] | 54
SUNM/PW-07 | [19 empty] | 55
BRAH/PW-01 | [19 empty] | 56
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Package_wise_cost
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [18 empty] | 0 | 2
KISH/PW-02 | [18 empty] | 0 | 3
KISH/PW-03 | [18 empty] | 0 | 4
KISH/PW-04 | [18 empty] | 0 | 5
KISH/PW-05 | [18 empty] | 0 | 6
KISH/PW-06 | [18 empty] | 0 | 7
KISH/PW-07 | [18 empty] | 0 | 8
KISH/PW-09 | [18 empty] | 0 | 9
KISH/PW-10 | [18 empty] | 0 | 10
KISH/PW-11 | [18 empty] | 0 | 11
KISH/PW-12 | [18 empty] | 0 | 12
KISH/PW-13 | [18 empty] | 0 | 13
KISH/PW-14 | [18 empty] | 0 | 14
KISH/PW-15 | [18 empty] | 0 | 15
KISH/PW-16 | [18 empty] | 0 | 16
KISH/PW-17 | [18 empty] | 0 | 17
KISH/PW-18 | [18 empty] | 0 | 18
KISH/PW-19 | [18 empty] | 0 | 19
KISH/PW-20 | [18 empty] | 0 | 20
KISH/PW-21 | [18 empty] | 0 | 21
KISH/PW-22 | [18 empty] | 0 | 22
KISH/PW-23 | [18 empty] | 0 | 23
KISH/PW-24 | [18 empty] | 0 | 24
KISH/PW-25 | [18 empty] | 0 | 25
KISH/PW-26 | [18 empty] | 0 | 26
KISH/PW-27 | [18 empty] | 0 | 27
KISH/PW-28 | [18 empty] | 0 | 28
KISH/PW-29 | [18 empty] | 0 | 29
KISH/PW-30 | [18 empty] | 0 | 30
KISH/PW-31 | [18 empty] | 0 | 31
KISH/PW-32 | [18 empty] | 0 | 32
KISH/PW-33 | [18 empty] | 0 | 33
HOBI/PW-01 | [18 empty] | 0 | 34
HOBI/PW-02 | [18 empty] | 0 | 35
HOBI/PW-04 | [18 empty] | 0 | 36
HOBI/PW-05 | [18 empty] | 0 | 37
HOBI/PW-06 | [18 empty] | 0 | 38
HOBI/PW-07 | [18 empty] | 0 | 39
HOBI/PW-08 | [18 empty] | 0 | 40
NETR/PW-01 | [18 empty] | 0 | 41
NETR/PW-02 | [18 empty] | 0 | 42
NETR/PW-03 | [18 empty] | 0 | 43
NETR/PW-04 | [18 empty] | 0 | 44
NETR/PW-05 | [18 empty] | 0 | 45
NETR/PW-06 | [18 empty] | 0 | 46
NETR/PW-07 | [18 empty] | 0 | 47
NETR/PW-08 | [18 empty] | 0 | 48
SUNM/PW-01 | [18 empty] | 0 | 49
SUNM/PW-02 | [18 empty] | 0 | 50
SUNM/PW-03 | [18 empty] | 0 | 51
SUNM/PW-04 | [18 empty] | 0 | 52
SUNM/PW-05 | [18 empty] | 0 | 53
SUNM/PW-06 | [18 empty] | 0 | 54
SUNM/PW-07 | [18 empty] | 0 | 55
BRAH/PW-01 | [18 empty] | 0 | 56
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Haor_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
Chandpur Haor Sub-Project | N-1 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
Nunnir Haor Sub-Project | N-2 | 15 | 0 | 6 | 3 | 2 | 0 | 20 | 0 | 0 | 0 | 29.418 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3
Boro Haor Sub-Project | N-3 | 7 | 0 | 0 | 0 | 4 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4
Noapara Haor Sub-Project | N-4 | 14 | 0 | 4 | 2 | 2 | 0 | 10.757 | 0 | 0 | 0 | 23.29 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
Naogaon Haor Sub-Project | N-5 | 25 | 0 | 6 | 5 | 3 | 0 | 48.968 | 0 | 0 | 0 | 70.395 | 0 | 0 | 20 | 0 | 0 | 0 |  | 6
Badla Haor Sub-Project | N-6 | 6 | 0 | 2 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 21 | 5 | 0 | 0 | 0 | 0 | 0 |  | 7
Chatal Haor Sub-Project | N-7 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8
Dakhshiner Haor Sub-Project | N-8 | 15 | 0 | 1 | 1 | 3 | 0 | 11 | 0 | 0 | 0 | 22.048 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
Suniar Haor Sub-Project | N-9 | 0 | 0 | 2 | 4 | 2 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10
Mokhar Haor Sub-Project | N-10 | 15 | 0 | 6 | 9 | 5 | 0 | 30.058 | 0 | 0 | 0 | 23.815 | 1 | 0 | 0 | 0 | 0 | 0 |  | 11
Ganesh Haor Sub-Project | N-11 | 2 | 0 | 3 | 2 | 0 | 0 | 11.97 | 0 | 0 | 0 | 3.071 | 1 | 0 | 0 | 0 | 0 | 0 |  | 12
Dharmapasha Rui Beel Sub-Project | N-12 | 15 | 0 | 4 | 6 | 4 | 0 | 87.983 | 0 | 0 | 0 | 38.465 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
Dhakua Haor Sub-Project | N-14 | 9 | 0 | 2 | 7 | 6 | 0 | 50.508 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 16
Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 17
Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 18
Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 19
Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 20
Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21
Aralia Khal Sub-Project | R-7 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3.312 | 0 | 26.952 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 22
Bashira River Re-excavation Sub-Project | R-8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
Dampara Water Management Scheme | R-9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13.27 | 35.52 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 24
Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.98 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 25
Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.133 | 10.69 | 3.56 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 26
Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.195 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 27
Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 28
Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 29
Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 30
All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2 |  | 31
Total |  | 127 | 5 | 39 | 43 | 32 | 0 | 342.584 | 108.974 | 67.11 | 57.912 | 254.207 | 7 | 0 | 20 | 60 | 86 | 2 | 0

## distribution_of_cost
Item | costcode | rindex | 1st Revised | 2nd revised | difference
Office Administration | 1 | 2 | 5403.27 | 5360.27 | -43
Fuel & Lubricant | 2 | 3 | 350 | 210 | -140
Training and Livelihood | 3 | 4 | 4491.97 | 5236.54 | 744.57
Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
Repair & Maintenance | 5 | 6 | 265 | 290 | 25
Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22 | -12
Land Acquisition | 7 | 8 | 24000 | 20000 | -4000
Civilworks | 8 | 9 | 53727 | 60687.03 | 6960.03
contingency | 9 | 10 | 660.14 | 40 | -620.14
Total |  |  | 97865 | 100779.46 | 2914.46
2914.46
0 | Office Administration | 1 | 2 | 5403.27 | 5360.27 | -43
1 | Fuel & Lubricant | 2 | 3 | 350 | 210 | -140
2 | Training and Livelihood | 3 | 4 | 4491.97 | 5236.54 | 744.57
3 | Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
4 | Repair & Maintenance | 5 | 6 | 265 | 290 | 25
5 | Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22 | -12
6 | Land Acquisition | 7 | 8 | 24000 | 20000 | -4000
7 | Civilworks | 8 | 9 | 53727 | 60687.03 | 6960.03
8 | contingency | 9 | 10 | 660.14 | 40 | -620.14