## Resource_List
Code | Name | Unit
101 | Mixture Machine | Nos
102 | Excavator | Nos
103 | Compaction Ruller | Nos
104 | Form Work | Nos
201 | Cement | Bag
202 | Sand 1.5 FM | cum
203 | Stone Chips | cum
204 | Geotextile Filter | sqm
205 | Filter Sand | cum
206 | Peagravel | cum
207 | CC Block | Nos
301 | Labor | m-day
401 | Labor payment | BDT Lac

## Resources_Consumption
Code | Name | Unit | NS101 | 40-190-05 | 40-190-15 | 40-190-35 | 40-190-40 | 40-190-50 | NS105 | 16-240 | 40-550-10 | 40-500-40 | 40-530-30 | NS106 | NS102 | 16-510 | 40-450 | 16-470 | 40-380-20 | 48-100
101 | Mixture Machine | Nos | 0 | 0.0037037 | 0.0061728 | 0.0031546 | 0.0015798 | 0.0013333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Excavator | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0033 | 0 | 0 | 0 | 0 | 0 | 0.0033 | 0.0033 | 0.0033 | 0.0033 | 0
103 | Compaction Ruller | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0013158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Form Work | Nos | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | Cement | Bag | 0 | 0.38448 | 0.6408 | 0.32809 | 0.16404 | 0.13841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | Sand 1.5 FM | cum | 0 | 0.033375 | 0.055625 | 0.02848 | 0.01424 | 0.012015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | Stone Chips | cum | 0 | 0.073209 | 0.12202 | 0.062472 | 0.031236 | 0.026355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | Filter Sand | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | Geotextile Filter | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | Peagravel | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | CC Block | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
208 | Geobag | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
209 | Turfing Sod | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
301 | Labor | m-day | 0.7 | 0.11111 | 0.18519 | 0.094637 | 0.047393 | 0.04 | 0.4 | 0.1 | 0.18 | 0.018 | 0.18 | 0.0057143 | 0.7 | 0.1 | 0.1 | 0.1 | 0.016327 | 0.02
401 | Labor payment | BDT Thousand | 210 | 33 | 56 | 29 | 14 | 12 | 120 | 60 | 54 | 5.4 | 54 | 1.72 | 210 | 60 | 60 | 60 | 5 | 6

## WBS3
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | -1 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9

## Main
Name | Start | Finish | Allocation_Sheet_Name | Site Name
Type_A_211M_724_To_935_S | 1 | 87 | Type_A_211M_724_To_935_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M724 to M935=211M under HFMLIP
Type_A_50M_965_TO_1015_S | 1 | 87 | Type_A_50M_965_TO_1015_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M965 to M1015=50M under HFMLIP
Type_A_40M_4500_TO_4570_S | 1 | 87 | Type_A_40M_4500_TO_4570_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment in between M4500 to M4570=40M under HFMLIP
Type_A_40M_35020_TO_35100_S | 1 | 87 | Type_A_40M_35020_TO_35100_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment in between M35020 to M35100=40M
FF_30M_at_KM_1000_S | 1 | 87 | FF_30M_at_KM_1000_S | Construction of 30M Flood Fuse on Submersible Embankment M1000 to M1030 of Dharmapasha Ruibeel Project under HFMLIP
FF_15M_at_KM_4520_S | 1 | 87 | FF_15M_at_KM_4520_S | Construction of 15M Flood Fuse on Submersible Embankment M4520 of Dharmapasha Ruibeel Project under HFMLIP
FF_15M_at_KM_35050_S | 1 | 87 | FF_15M_at_KM_35050_S | Construction of 15M Flood Fuse on Submersible Embankment M35050 of Dharmapasha Ruibeel Project under HFMLIP
T_B5_724M_M0_TO_M724_S | 1 | 87 | T_B5_724M_M0_TO_M724_S | Type B5 slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M0 to M724=724M under HFMLIP
T_B5_1165M_1015_TO_2180_S | 1 | 87 | T_B5_1165M_1015_TO_2180_S | Type B5 slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M1015 to M2180=1165M under HFMLIP
T_B5_1150M_9200_TO_10350_S | 1 | 87 | T_B5_1150M_9200_TO_10350_S | Type B5 slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M9200 to M10350=1150M under HFMLIP

## Type_A_211M_724_To_935_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 14 | 1 | Nos | 33338 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 8 | 1 | Nos | 5012 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 40 | 1 | Cum | 6974 | 16-240
6 | Placing Sand Filter | 17 | 4,5 | Cum | 560 | 40-550-10
7 | Placing Geotextile Filter | 17 | 4,5 | sqm | 6098 | 40-500-40
8 | Placing Pea Gravel Filter | 17 | 4,5 | Cum | 560 | 40-530-30
9 | Placing CC Block | 17 | 4,5 | Nos | 38350 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## Type_A_50M_965_TO_1015_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 1188 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 7900 | 40-190-40 | 9088
4 | Curing | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 1653 | 16-240
6 | Placing Sand Filter | 7 | 4,5 | Cum | 133 | 40-550-10
7 | Placing Geotextile Filter | 7 | 4,5 | sqm | 1445 | 40-500-40
8 | Placing Pea Gravel Filter | 7 | 4,5 | Cum | 133 | 40-530-30
9 | Placing CC Block | 7 | 4,5 | Nos | 9088 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## Type_A_40M_4500_TO_4570_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 950 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 4151 | 40-190-40
4 | Curing | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 330 | 16-240
6 | Placing Sand Filter | 4 | 4,5 | Cum | 68 | 40-550-10
7 | Placing Geotextile Filter | 4 | 4,5 | sqm | 770 | 40-500-40
8 | Placing Pea Gravel Filter | 4 | 4,5 | Cum | 68 | 40-530-30
9 | Placing CC Block | 4 | 4,5 | Nos | 5101 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## Type_A_40M_35020_TO_35100_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 950 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 4151 | 40-190-40
4 | Curing | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 330 | 16-240
6 | Placing Sand Filter | 4 | 4,5 | Cum | 68 | 40-550-10
7 | Placing Geotextile Filter | 4 | 4,5 | sqm | 770 | 40-500-40
8 | Placing Pea Gravel Filter | 4 | 4,5 | Cum | 68 | 40-530-30
9 | Placing CC Block | 4 | 4,5 | Nos | 5101 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## FF_30M_at_KM_1000_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | CC Block Manufacture(50X50X50) | 17 | 1 | Nos | 2670 | 40-190-15
3 | CC Block Manufacture(50X50X30) | 18 | 1 | Nos | 4795 | 40-190-05
4 | CC Block Manufacture(40X40X40) | 12 | 1 | Nos | 3563 | 40-190-35
5 | CC Block Manufacture(40X40X20) | 5 | 1 | Nos | 2655 | 40-190-40
6 | Curing | 21 | 2,3,4,5 | percent | 100 | NS105
7 | Ring Bundh construction | 7 | 1 | Cum | 2052 | 40-450
8 | Excavation | 9 | 1 | Cum | 2524 | 16-510
9 | Embankment Construction | 15 | 7 | Cum | 1751 | 16-240
10 | Placing Sand Filter | 13 | 9 | Cum | 361 | 40-550-10
11 | Placing Geotextile Filter | 13 | 9 | sqm | 2457 | 40-500-40
12 | Placing Pea Gravel Filter | 13 | 9 | Cum | 480 | 40-530-30
13 | Geo Bag Placing(175) Kg | 13 | 9 | Nos | 4021 | 40-380-20
14 | Placing CC Block | 13 | 9 | Nos | 13683 | NS106
15 | Ring Bundh Removal | 7 | 14 | percent | 1641 | 16-470
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100 | NS102

## FF_15M_at_KM_4520_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1356 | 40-190-15
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 2951 | 40-190-05
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781 | 40-190-35
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917 | 40-190-40
6 | Curing | 21 | 2,3,4,5 | percent | 100 | NS105
7 | Ring Bundh construction | 5 | 1 | Cum | 1482 | 40-450
8 | Excavation | 4 | 1 | Cum | 1193 | 16-510
9 | Embankment Construction | 15 | 7 | Cum | 1022 | 16-240
10 | Placing Sand Filter | 9 | 9 | Cum | 268 | 40-550-10
11 | Placing Geotextile Filter | 9 | 9 | sqm | 1837 | 40-500-40
12 | Placing Pea Gravel Filter | 9 | 9 | Cum | 358 | 40-530-30
13 | Geo Bag Placing(175) Kg | 9 | 9 | Nos | 1851 | 40-380-20
14 | Placing CC Block | 9 | 9 | Nos | 10005 | NS106
15 | Ring Bundh Removal | 5 | 14 | percent | 1185 | 16-470
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100 | NS102

## FF_15M_at_KM_35050_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1356 | 40-190-15
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 2951 | 40-190-05
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781 | 40-190-35
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917 | 40-190-40
6 | Curing | 21 | 2,3,4,5 | percent | 100 | NS105
7 | Ring Bundh construction | 5 | 1 | Cum | 1482 | 40-450
8 | Excavation | 4 | 1 | Cum | 1193 | 16-510
9 | Embankment Construction | 15 | 7 | Cum | 1022 | 16-240
10 | Placing Sand Filter | 9 | 9 | Cum | 268 | 40-550-10
11 | Placing Geotextile Filter | 9 | 9 | sqm | 1837 | 40-500-40
12 | Placing Pea Gravel Filter | 9 | 9 | Cum | 358 | 40-530-30
13 | Placing CC Block | 9 | 9 | Nos | 10005 | NS106
14 | Ring Bundh Removal | 4 | 13 | percent | 1185 | 16-470
15 | Ancilary Work for Site Completion | 7 | 14 | Percent | 100 | NS102

## T_B5_724M_M0_TO_M724_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 3495 | 16-240
3 | Placing Geotextile Filter | 17 | 2 | sqm | 11251 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 17 | 2 | Nos | 3388 | 40-380-20
5 | Close Turfing | 17 | 2 | sqm | 9842 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_1165M_1015_TO_2180_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 30 | 1 | Cum | 5623 | 16-240
3 | Placing Geotextile Filter | 36 | 2 | sqm | 18105 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 26 | 2 | Nos | 5451 | 40-380-20
5 | Close Turfing | 26 | 2 | percent | 15836 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## T_B5_1150M_9200_TO_10350_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 5551 | 16-240
3 | Placing Geotextile Filter | 27 | 2 | sqm | 17871 | 40-500-40
4 | Geo Bag Placing(125 Kg) | 27 | 2 | Nos | 5380 | 40-380-20
5 | Close Turfing | 27 | 2 | percent | 15632 | 48-100
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100 | NS102

## RS_850M_4600_TO_7800_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 3366 | 16-240
3 | Close Turfing | 30 | 2 | sqm | 11722 | 48-100
4 | Ancilary Work for Site Completion | 7 | 3 | Percent | 100 | NS102

## RS_3850M_M25200_TO_M36630_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 30 | 1 | Cum | 15246 | 16-240
3 | Close Turfing | 40 | 2 | sqm | 53092 | 48-100
4 | Ancilary Work for Site Completion | 7 | 3 | Percent | 100 | NS102

## Equipment Production Rate
CC Bock | L | B | H | Relative Size wrt 30X30X30 | Standard Production Rate | Block/machine |  | code
50X50X50 | 50 | 50 | 50 | 4.6296 | 750 | 162 | 0.0061728 | 40-190-15
50X50X30 | 50 | 50 | 30 | 2.7778 | 750 | 270 | 0.0037037 | 40-190-05
40X40X40 | 40 | 40 | 40 | 2.3704 | 750 | 317 | 0.0031546 | 40-190-35
40X40X20 | 40 | 40 | 20 | 1.1852 | 750 | 633 | 0.0015798 | 40-190-40
30X30X30 | 30 | 30 | 30 | 1 | 750 | 750 | 0.0013333 | 40-190-50
|  |  |  | Equipment |  | Daily Prod(8hrs)
|  |  |  | Excavator |  | 300
|  |  |  | Roller |  | 760 | 0.0013158
|  |  |  | Mixuture Machie |  | 17
CC Block Placing
Block Size | L | B | H | Realtive Area | Standard Prod/Day | Daily Production
50X50X30 | 50 | 50 | 30 | 1.5625 | 1400 | 896
50X50X20 | 50 | 50 | 30 | 1.5625 | 1400 | 896
40X40X40 | 40 | 40 | 40 | 1 | 1400 | 1400
40X40X20 | 40 | 40 | 20 | 1 | 1400 | 1400
30X30X30 | 30 | 30 | 30 | 0.5625 | 1400 | 2489
175 kg geobag |  |  |  | 245/day by group 20 incld bed prep

## Block Placing Production Rate
1 Group | 20 Labour
Dayliy Placing Including Bed Preparation for 40X40X20 CC Block | 1400 | Nos
unit area of block | 0.16 | sqm
Bed Area | 224 | sqm
Sand Filter 100mm thick | 22.4 | cum
Geo Textile Filter | 224 | sqm
Gravel Filter | 22.4 | cum