## Structure_Type
| Items | Initial | Code | Payment_30_06_2020 | DPP_Item
0 | Construction of Irrigation Inlet | IRRI_C | 1 | 291.81 | Inlet
1 | Rehab Regulator Rehab Haor | REG_R_REHAB | 2 | 0 | Reg_Rehab_Rehab
2 | Regulator | REG_C | 3 | 6503.97 | Reg_CW_Box
3 | Box Drainage Outlet | DROU_C | 4 | 0 | Reg_CW_Box
4 | Causeway | CW_C | 5 | 0 | Reg_CW_Box
5 | Bridge | BRI_C | 6 | 0 | Reg_CW_Box
6 | Khal_River Reexcavation(New Haor) | REX_KH_RIV_NEW | 7 | 2546.54 | Khal_Riv_New
7 | Khal_River Reexcavation(Rehab Haor) | REX_KH_RIV_REHAB | 8 | 51.09 | Khal_Riv_Rehab
8 | Embankment Rehablitation | EMB_R | 9 | 0 | Full_Emb_Rehab
9 | Submersible Embankment Rehabilitation | SEMB_R | 10 | 0 | Sub_Emb_Rehab
10 | Submersible Embankment Construction | SEMB_C | 11 | 5833.04 | Sub_Emb_Const
11 | Rehab Regulator New Haor | REG_R_NEW | 12 | 0 | Reg_Rehab_New
12 | Thrashing Floor Construction | THF_CONS | 14 | 0 | Thr_Fl_Cost
13 | Construction of WMG | WMG_OFF | 15 | 0 | Wmg_Office
14 | M&E GATE Repair | GATE_REP | 16 | 0 | Gate_Repair

## Projection_Info
| Package Name | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
0 | BWDB/Kish/HFMLIP/ PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 | 40.94 | 1 | 1 | KISH/PW-01 | Rehab | 8 | 0 | R-2 | KISH
1 | BWDB/Kish/HFMLIP/ PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 | 35.88 | 1 | 1 | KISH/PW-01 | Rehab | 8 | 1 | R-1 | KISH
2 | BWDB/Kish/HFMLIP/ PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 | 19.18 | 0 | 1 | KISH/PW-01 | Rehab | 8 | 2 | R-3 | KISH
3 | BWDB/Kish/HFMLIP/ PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 | 309.8 | 0 | 1 | KISH/PW-01 | Rehab | 8 | 3 | R-3 | KISH
4 | BWDB/Kish/HFMLIP/ PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 | 45.95 | 0 | 1 | KISH/PW-01 | Rehab | 8 | 4 | R-3 | KISH
5 | BWDB/Kish/HFMLIP/ PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 | 44.79 | 0 | 1 | KISH/PW-01 | Rehab | 2 | 5 | R-1 | KISH
6 | Package No-02 /ChandpurHaor | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 123.81 | 1 | 1 | KISH/PW-02 | 0 | 3 | 6 | N-1 | KISH
7 | Package No-02 /ChandpurHaor | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 | 31.9576 | 1 | 1 | KISH/PW-02 | 0 | 7 | 7 | N-2 | KISH
8 | Package No-02 /ChandpurHaor | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 | 93.4351 | 1 | 1 | KISH/PW-02 | 0 | 7 | 8 | N-3 | KISH
9 | Package No-02 /ChandpurHaor | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 | 52.1722 | 1 | 1 | KISH/PW-02 | 0 | 7 | 9 | N-4 | KISH
10 | Package No-02 /ChandpurHaor | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 | 16.201 | 1 | 1 | KISH/PW-02 | 0 | 7 | 10 | N-5 | KISH
11 | Package No-02 /ChandpurHaor | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 | 68.8599 | 1 | 1 | KISH/PW-02 | 0 | 7 | 11 | N-6 | KISH
12 | Package No-02 /ChandpurHaor | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 | 14.8109 | 1 | 1 | KISH/PW-02 | 0 | 11 | 12 | N-7 | KISH
13 | Package No.-03/ Nunnir Haor (Part-A) | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 | 180.84 | 1 | 1 | KISH/PW-03 | 0 | 3 | 13 | N-2 | KISH
14 | Package No.-03/ Nunnir Haor (Part-A) | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 | 236.03 | 1 | 1 | KISH/PW-03 | 0 | 11 | 14 | N-2 | KISH
15 | Package No.-03/ Nunnir Haor (Part-A) | Block Road | Km | 0 | 277.1 | 1 | 1 | KISH/PW-03 | 0 | 11 | 15 | N-2 | KISH
16 | Package No.-04/ Nunnir Haor (Part B+C) | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 | 97.3 | 1 | 1 | KISH/PW-04 | 0 | 3 | 16 | N-2 | KISH
17 | Package No.-04/ Nunnir Haor (Part B+C) | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 | 97.3 | 1 | 1 | KISH/PW-04 | 0 | 3 | 17 | N-2 | KISH
18 | Package No.-04/ Nunnir Haor (Part B+C) | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 | 254.37 | 1 | 1 | KISH/PW-04 | 0 | 3 | 18 | N-2 | KISH
19 | Package No.-04/ Nunnir Haor (Part B+C) | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 | 121.63 | 1 | 1 | KISH/PW-04 | 0 | 11 | 19 | N-2 | KISH
20 | Package No.-04/ Nunnir Haor (Part B+C) | Block Road | Km | 1 | 143.39 | 1 | 1 | KISH/PW-04 | 0 | 11 | 20 | N-2 | KISH
21 | Package No.-05/ NunnirHaor (Part-A& C) | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 | 190.22 | 1 | 1 | KISH/PW-05 | 0 | 3 | 21 | N-2 | KISH
22 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 | 35.282 | 1 | 1 | KISH/PW-05 | 0 | 11 | 22 | N-2 | KISH
23 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 | 4.0969 | 1 | 1 | KISH/PW-05 | 0 | 11 | 23 | N-2 | KISH
24 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 | 8.7693 | 0 | 1 | KISH/PW-05 | 0 | 11 | 24 | N-2 | KISH
25 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 | 156.8227 | 1 | 1 | KISH/PW-05 | 0 | 11 | 25 | N-2 | KISH
26 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 | 28.9482 | 1 | 1 | KISH/PW-05 | 0 | 11 | 26 | N-2 | KISH
27 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 | 17.8983 | 1 | 1 | KISH/PW-05 | 0 | 11 | 27 | N-2 | KISH
28 | Package No.-05/ NunnirHaor (Part-A& C) | Block Road | Km | 12.214 | 325.54 | 1 | 1 | KISH/PW-05 | 0 | 11 | 28 | N-2 | KISH
29 | Package No.-06/ NunnirHaor (Part-A) | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 | 227.8819 | 1 | 1 | KISH/PW-06 | 0 | 3 | 29 | N-2 | KISH
30 | Package No.-06/ NunnirHaor (Part-A) | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4 | 41.55 | 1 | 1 | KISH/PW-06 | 0 | 7 | 30 | N-2 | KISH
31 | Package No.-06/ NunnirHaor (Part-A) | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.43 | 69.7 | 1 | 1 | KISH/PW-06 | 0 | 7 | 31 | N-2 | KISH
32 | Package No.-06/ NunnirHaor (Part-A) | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 0.9 | 23.7 | 1 | 1 | KISH/PW-06 | 0 | 7 | 32 | N-2 | KISH
33 | Package No.-06/ NunnirHaor (Part-A) | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.5 | 10.04 | 1 | 1 | KISH/PW-06 | 0 | 7 | 33 | N-2 | KISH
34 | Package No.-06/ NunnirHaor (Part-A) | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 7.07 | 356.51 | 1 | 1 | KISH/PW-06 | 0 | 7 | 34 | N-2 | KISH
35 | Package No.-06/ NunnirHaor (Part-A) | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 | 120.16 | 1 | 1 | KISH/PW-06 | 0 | 7 | 35 | N-2 | KISH
36 | Package No.-07/ Boro Haor | Hazir Khal | Km | 1.73 | 20.5494 | 0 | 0 | KISH/PW-07 | 0 | 7 | 36 | N-3 | KISH
37 | Package No.-07/ Boro Haor | Karpasha Khal | Km | 1.615 | 26.0781 | 2.16 | 2.16 | KISH/PW-07 | 0 | 7 | 37 | N-3 | KISH
38 | Package No.-07/ Boro Haor | Dampara Khal | Km | 3.6 | 46.8873 | 0.4 | 0.4 | KISH/PW-07 | 0 | 7 | 38 | N-3 | KISH
39 | Package No.-07/ Boro Haor | Baniajan | Km | 6.854 | 130.1184 | 1 | 1 | KISH/PW-07 | 0 | 7 | 39 | N-3 | KISH
40 | Package No.-07/ Boro Haor | Suti Khal | Km | 6.1 | 120.3313 | 1 | 1 | KISH/PW-07 | 0 | 7 | 40 | N-3 | KISH
41 | Package No.-07/ Boro Haor | Digha Nadi | Km | 5.7 | 424.0032 | 0.65 | 1 | KISH/PW-07 | 0 | 7 | 41 | N-3 | KISH
42 | Package No.-07/ Boro Haor | Old Singua | Km | 10.86 | 197.6384 | 0 | 0 | KISH/PW-07 | 0 | 7 | 42 | N-3 | KISH
43 | Package No.-07/ Boro Haor | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 | 35.33 | 0.08 | 0.2 | KISH/PW-07 | 0 | 11 | 43 | N-3 | KISH
44 | Package No.-07/ Boro Haor | Block Road | Km | 0 | 55.74 | 0 | 1 | KISH/PW-07 | 0 | 11 | 44 | N-3 | KISH
45 | Package No.PW-09/Kish/ Boro Haor | Causeway 6.0m wide-1 at Dampara | Nos | 1 | 210.83 | 1 | 1 | KISH/PW-09 | 0 | 5 | 45 | N-3 | KISH
46 | Package No.PW-09/Kish/ Boro Haor | Causeway 4.0m wide-1 at Karpasha | Nos | 1 | 176.64 | 1 | 1 | KISH/PW-09 | 0 | 5 | 46 | N-3 | KISH
47 | Package No.PW-09/Kish/ Boro Haor | Mohorkona Box Outlet | Nos | 1 | 66.64 | 1 | 1 | KISH/PW-09 | 0 | 4 | 47 | N-3 | KISH
48 | Package No.PW-09/Kish/ Boro Haor | Causeway 6.0m wide-1 at Samar Bari | Nos | 1 | 241.26 | 1 | 1 | KISH/PW-09 | 0 | 5 | 48 | N-3 | KISH
49 | Package No.: PW-10/ Noapara Haor | Causeway 6.0m wide-1 | Nos | 1 | 137.35 | 0 | 0.65 | KISH/PW-10 | 0 | 3 | 49 | N-4 | KISH
50 | Package No.: PW-10/ Noapara Haor | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 | 128.67 | 0.45 | 1 | KISH/PW-10 | 0 | 3 | 50 | N-4 | KISH
51 | Package No.: PW-10/ Noapara Haor | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 | 274.06 | 0.64 | 1 | KISH/PW-10 | 0 | 11 | 51 | N-4 | KISH
52 | Package No.: PW-10/ Noapara Haor | Block Road | Km | 0 | 343.88 | 1 | 1 | KISH/PW-10 | 0 | 11 | 52 | N-4 | KISH
53 | Package No.-11/ Noapara Haor | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 | 274.49 | 0.95 | 1 | KISH/PW-11 | 0 | 3 | 53 | N-4 | KISH
54 | Package No.-11/ Noapara Haor | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 | 557.63 | 0.5 | 1 | KISH/PW-11 | 0 | 11 | 54 | N-4 | KISH
55 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 | 253.8935 | 1 | 1 | KISH/PW-12 | 0 | 3 | 55 | N-4 | KISH
56 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 | 277.0365 | 1 | 1 | KISH/PW-12 | 0 | 3 | 56 | N-4 | KISH
57 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 | 18.397 | 0 | 0 | KISH/PW-12 | 0 | 7 | 57 | N-4 | KISH
58 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 | 4.398 | 1 | 1 | KISH/PW-12 | 0 | 7 | 58 | N-4 | KISH
59 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 | 99.257 | 1 | 1 | KISH/PW-12 | 0 | 7 | 59 | N-4 | KISH
60 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 | 110.6945 | 1 | 1 | KISH/PW-12 | 0 | 7 | 60 | N-4 | KISH
61 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 | 167.984 | 1 | 1 | KISH/PW-12 | 0 | 7 | 61 | N-4 | KISH
62 | Package No.-13/ Naogaon Haor (Part-A) | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 | 224.08 | 0.95 | 1 | KISH/PW-13 | 0 | 3 | 62 | N-5 | KISH
63 | Package No.-13/ Naogaon Haor (Part-A) | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 | 196.52 | 0.95 | 1 | KISH/PW-13 | 0 | 3 | 63 | N-5 | KISH
64 | Package No.-13/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 | 489.176 | 0.4 | 1 | KISH/PW-13 | 0 | 11 | 64 | N-5 | KISH
65 | Package No.-13/ Naogaon Haor (Part-A) | Block Road | Km | 1 | 70.98 | 0.4 | 1 | KISH/PW-13 | 0 | 11 | 65 | N-5 | KISH
66 | Package No.-14/ Naogaon Haor (Part-A) | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 | 263.7 | 0.95 | 1 | KISH/PW-14 | 0 | 3 | 66 | N-5 | KISH
67 | Package No.-14/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 | 485.98 | 0.86 | 1 | KISH/PW-14 | 0 | 11 | 67 | N-5 | KISH
68 | Package No.-14/ Naogaon Haor (Part-A) | Block Road | Km | 0.5 | 133.96 | 0 | 1 | KISH/PW-14 | 0 | 11 | 68 | N-5 | KISH
69 | Package No.-15/ Naogaon Haor- Part-B | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 | 166.9 | 0 | 0 | KISH/PW-15 | 0 | 3 | 69 | N-5 | KISH
70 | Package No.-15/ Naogaon Haor- Part-B | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 | 616.92 | 1 | 1 | KISH/PW-15 | 0 | 11 | 70 | N-5 | KISH
71 | Package No.-16/ NaogaonHaor-Part-B | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 | 267.88 | 0.85 | 1 | KISH/PW-16 | 0 | 3 | 71 | N-5 | KISH
72 | Package No.-16/ NaogaonHaor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 | 343.32 | 1 | 1 | KISH/PW-16 | 0 | 11 | 72 | N-5 | KISH
73 | Package No.-16/ NaogaonHaor-Part-B | Block Road | Km | 0 | 167.97 | 1 | 1 | KISH/PW-16 | 0 | 11 | 73 | N-5 | KISH
74 | Package No.-17/ Naogaon Haor-Part-B | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 | 348.66 | 1 | 1 | KISH/PW-17 | 0 | 3 | 74 | N-5 | KISH
75 | Package No.-17/ Naogaon Haor-Part-B | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 | 217.5324 | 1 | 1 | KISH/PW-17 | 0 | 3 | 75 | N-5 | KISH
76 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-1 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 76 | N-5 | KISH
77 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-2 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 77 | N-5 | KISH
78 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-3 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 78 | N-5 | KISH
79 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-4 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 79 | N-5 | KISH
80 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-5 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 80 | N-5 | KISH
81 | Package No.-17/ Naogaon Haor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 | 460.54 | 1 | 1 | KISH/PW-17 | 0 | 11 | 81 | N-5 | KISH
82 | Package No.-17/ Naogaon Haor-Part-B | Block Road | Km | 0 | 89.5 | 1 | 1 | KISH/PW-17 | 0 | 11 | 82 | N-5 | 0
83 | Package No.-17/ Naogaon Haor-Part-B | Irrigation Pipe Inlet-1 | Nos | 25 | 274.47 | 1 | 1 | KISH/PW-17 | 0 | 1 | 83 | N-5 | KISH
84 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 | 159.8606 | 0 | 1 | KISH/PW-18 | 0 | 5 | 84 | 0 | KISH
85 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 | 161.4295 | 0.8 | 1 | KISH/PW-18 | 0 | 5 | 85 | 0 | KISH
86 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 | 186.8205 | 1 | 1 | KISH/PW-18 | 0 | 5 | 86 | 0 | KISH
87 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 | 265.5873 | 0.8 | 1 | KISH/PW-18 | 0 | 5 | 87 | 0 | KISH
88 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 | 101.2011 | 0 | 0 | KISH/PW-18 | 0 | 7 | 88 | 0 | KISH
89 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 | 35.7041 | 1 | 1 | KISH/PW-18 | 0 | 7 | 89 | 0 | KISH
90 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 | 17.1427 | 1 | 1 | KISH/PW-18 | 0 | 7 | 90 | 0 | KISH
91 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 | 59.4674 | 1 | 1 | KISH/PW-18 | 0 | 7 | 91 | 0 | KISH
92 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 | 141.516 | 0 | 1 | KISH/PW-18 | 0 | 7 | 92 | 0 | KISH
93 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 | 187.0328 | 0 | 1 | KISH/PW-18 | 0 | 7 | 93 | 0 | KISH
94 | BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 | 472.9622 | 0.25 | 1 | KISH/PW-19 | 0 | 7 | 94 | N-5 | KISH
95 | BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 | 374.9638 | 0.4 | 1 | KISH/PW-19 | 0 | 7 | 95 | N-5 | KISH
96 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chitra Khal 4m wide | Nos | 1 | 136.31 | 1 | 1 | KISH/PW-20 | New | 5 | 96 | 0 | KISH
97 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Nabinpur Khal 4m Wide | Nos | 1 | 193.69 | 1 | 1 | KISH/PW-20 | New | 5 | 97 | 0 | KISH
98 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Dipjuri Khal 4m CW | Nos | 1 | 185.03 | 1 | 1 | KISH/PW-20 | New | 5 | 98 | 0 | KISH
99 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Sudhikhal 4m wide CW | Nos | 1 | 136.66 | 1 | 1 | KISH/PW-20 | New | 5 | 99 | 0 | KISH
100 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chhagalia khal sluice | Nos | 1 | 41.0186 | 1 | 1 | KISH/PW-20 | New | 3 | 100 | 0 | KISH
101 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Near nasir sluice | Nos | 1 | 42.7991 | 1 | 1 | KISH/PW-20 | New | 3 | 101 | 0 | KISH
102 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Shingpur khal sluice | Nos | 1 | 41.9704 | 1 | 1 | KISH/PW-20 | New | 3 | 102 | 0 | KISH
103 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Gharu khal sluice | Nos | 1 | 41.9704 | 0.75 | 1 | KISH/PW-20 | New | 3 | 103 | 0 | KISH
104 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Irrigation Pipe Inlet 600mm dia | Nos | 36 | 334.27 | 0.57 | 0.57 | KISH/PW-20 | New | 1 | 104 | 0 | KISH
105 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 | 321.3991 | 0.48 | 1 | KISH/PW-21 | New | 3 | 105 | N-6 | KISH
106 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 | 156.6821 | 0.45 | 1 | KISH/PW-21 | New | 3 | 106 | N-6 | KISH
107 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 | 120.5564 | 0 | 1 | KISH/PW-21 | New | 12 | 107 | N-6 | KISH
108 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 | 329.1074 | 0 | 1 | KISH/PW-21 | New | 11 | 108 | N-6 | KISH
109 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 | 235.9924 | 0.8 | 0.8 | KISH/PW-22 | 0 | 11 | 109 | N-6 | KISH
110 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 | 18.1492 | 0 | 1 | KISH/PW-22 | 0 | 7 | 110 | N-6 | KISH
111 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 | 28.0679 | 1 | 1 | KISH/PW-22 | 0 | 7 | 111 | N-6 | KISH
112 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 | 5.8814 | 0 | 1 | KISH/PW-22 | 0 | 7 | 112 | N-6 | KISH
113 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 | 8.1389 | 0 | 1 | KISH/PW-22 | 0 | 7 | 113 | N-6 | KISH
114 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 | 84.8797 | 0.16 | 1 | KISH/PW-22 | 0 | 7 | 114 | N-6 | KISH
115 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 | 11.9047 | 0 | 1 | KISH/PW-22 | 0 | 7 | 115 | N-6 | KISH
116 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 | 2.4463 | 0 | 1 | KISH/PW-22 | 0 | 7 | 116 | N-6 | KISH
117 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 | 14.6073 | 1 | 1 | KISH/PW-22 | 0 | 7 | 117 | N-6 | KISH
118 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 | 4.4592 | 0 | 1 | KISH/PW-22 | 0 | 7 | 118 | N-6 | KISH
119 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 | 195.2169 | 0.15 | 1 | KISH/PW-22 | 0 | 5 | 119 | N-6 | KISH
120 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 | 0 | 4 | 120 | N-6 | KISH
121 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 | 0 | 4 | 121 | N-6 | KISH
122 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 | 0 | 4 | 122 | N-6 | KISH
123 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 | 107.4208 | 0.8 | 1 | KISH/PW-23 | New | 11 | 123 | N-7 | KISH
124 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 | 295.5262 | 0.85 | 1 | KISH/PW-23 | New | 3 | 124 | N-7 | KISH
125 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 | 227.0604 | 0.95 | 1 | KISH/PW-23 | New | 3 | 125 | N-7 | KISH
126 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 | 28.5772 | 0 | 0.3 | KISH/PW-23 | New | 7 | 126 | N-7 | KISH
127 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 | 3.8604 | 1 | 1 | KISH/PW-23 | New | 7 | 127 | N-7 | KISH
128 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 | 38.9293 | 1 | 1 | KISH/PW-23 | New | 4 | 128 | N-7 | KISH
129 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Irrigation Pipe Inlet 600mm dia | Nos | 4 | 62.862 | 1 | 1 | KISH/PW-23 | New | 1 | 129 | N-7 | KISH
130 | Package No.-24/ Dakshiner Haor. | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 | 1149.1962 | 1 | 1 | KISH/PW-24 | New | 11 | 130 | N-8 | KISH
131 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Regulator 5-Vent-1 | Nos | 1 | 405.9371 | 0.65 | 1 | KISH/PW-25 | New | 3 | 131 | N-8 | KISH
132 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 | 320.0346 | 0.88 | 0.88 | KISH/PW-25 | New | 7 | 132 | N-8 | KISH
133 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Km | 1.65 | 54.4035 | 0.36 | 1 | KISH/PW-25 | New | 7 | 133 | N-8 | KISH
134 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 | 346.4138 | 0 | 0 | KISH/PW-25 | New | 5 | 134 | N-8 | KISH
135 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 | 288.0795 | 0 | 0 | KISH/PW-25 | New | 5 | 135 | N-8 | KISH
136 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 | 189.5297 | 0.65 | 1 | KISH/PW-25 | New | 5 | 136 | N-8 | KISH
137 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Box Sluice-1 | Nos | 1 | 41.8221 | 0 | 0 | KISH/PW-25 | New | 4 | 137 | N-8 | KISH
138 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Irrigation Pipe Inlet 600mm dia | Nos | 15 | 118.5673 | 0.86 | 1 | KISH/PW-25 | New | 1 | 138 | N-8 | KISH
139 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 | 22.7161 | 1 | 1 | KISH/PW-26 | New | 11 | 139 | N-9 | KISH
140 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 | 71.5264 | 1 | 1 | KISH/PW-26 | New | 7 | 140 | N-9 | KISH
141 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 | 12.7224 | 1 | 1 | KISH/PW-26 | New | 7 | 141 | N-9 | KISH
142 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 | 16.3878 | 1 | 1 | KISH/PW-26 | New | 7 | 142 | N-9 | KISH
143 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 | 367.3183 | 1 | 1 | KISH/PW-26 | New | 7 | 143 | N-9 | KISH
144 | BWDB/Kish/HFMLIP/ PW-27 | phuleshwari | Nos | 1 | 156.62 | 0 | 1 | KISH/PW-27 | New | 3 | 144 | N-9 | KISH
145 | BWDB/Kish/HFMLIP/ PW-27 | Kalna | Nos | 1 | 148 | 0 | 1 | KISH/PW-27 | New | 3 | 145 | N-9 | KISH
146 | BWDB/Kish/HFMLIP/ PW-27 | RCC Box Drainage | Nos | 1 | 41.88 | 0 | 1 | KISH/PW-27 | New | 4 | 146 | N-9 | KISH
147 | BWDB/Kish/HFMLIP/ PW-27 | Causeway | Nos | 1 | 140.87 | 0 | 1 | KISH/PW-27 | New | 5 | 147 | N-9 | KISH
148 | BWDB/Kish/HFMLIP/ PW-27 | Causeway & Drainage | Nos | 1 | 407.31 | 0 | 1 | KISH/PW-27 | New | 5 | 148 | N-9 | KISH
149 | BWDB/Kish/HFMLIP/ PW-28 | WMG Building | Nos | 11 | 347.64 | 0.17 | 0.54 | KISH/PW-28/Lot-01 | New | 15 | 149 | N-9 | KISH

## Package_Name
| sl | Package_No | Payment_30_06_2020
0 | 1 | KISH/PW-01 | 51.09
1 | 2 | KISH/PW-02 | 347.71
2 | 3 | KISH/PW-03 | 625.93
3 | 4 | KISH/PW-04 | 714.69
4 | 5 | KISH/PW-05 | 575.15
5 | 6 | KISH/PW-06 | 837.25
6 | 7 | KISH/PW-07 | 565.07
7 | 8 | KISH/PW-08 | 0
8 | 9 | KISH/PW-09 | 712.33
9 | 10 | KISH/PW-10 | 409.68
10 | 11 | KISH/PW-11 | 522.86
11 | 12 | KISH/PW-12 | 705.59
12 | 13 | KISH/PW-13 | 647.2
13 | 14 | KISH/PW-14 | 806.89
14 | 15 | KISH/PW-15 | 333.94
15 | 16 | KISH/PW-16 | 721.62
16 | 17 | KISH/PW-17 | 1451.95
17 | 18 | KISH/PW-18 | 711.02
18 | 19 | KISH/PW-19 | 331.35
19 | 20 | KISH/PW-20 | 501.12
20 | 21 | KISH/PW-21 | 268.24
21 | 22 | KISH/PW-22 | 281.05
22 | 23 | KISH/PW-23 | 720.33
23 | 24 | KISH/PW-24 | 890.42
24 | 25 | KISH/PW-25 | 749.37
25 | 26 | KISH/PW-26 | 501.12
26 | 27 | KISH/PW-27 | 0
27 | 28 | KISH/PW-28/Lot-01 | 61.6
28 | 29 | KISH/PW-28/Lot-02 | 0
29 | 30 | KISH/PW-28/Lot-03 | 0
30 | 31 | KISH/PW-28/Lot-04 | 74.41
31 | 32 | KISH/PW-29 | 0
32 | 33 | KISH/PW-30 | 0
33 | 34 | KISH/PW-31 | 0
34 | 35 | KISH/PW-32 | 0
35 | 36 | KISH/PW-33 | 0
36 | 37 | KISH/PW-34 | 0
37 | 38 | KISH/PW-35 | 0
38 | 39 | KISH/PW-36 | 0
39 | 40 | KISH/PW-37 | 0
40 | 41 | KISH/PW-38 | 0
41 | 42 | HOBI/PW-01 | 938.57
42 | 43 | HOBI/PW-02 | 1079.52
43 | 44 | HOBI/PW-03 | 0
44 | 45 | HOBI/PW-04 | 655.94
45 | 46 | HOBI/PW-05 | 307.8
46 | 47 | HOBI/PW-06 | 1094.31
47 | 48 | HOBI/PW-07 | 667.67
48 | 49 | NETR/PW-01 | 817.97
49 | 50 | NETR/PW-02 | 475.85
50 | 51 | NETR/PW-03 | 712.73
51 | 52 | NETR/PW-04 | 844.17
52 | 53 | NETR/PW-05 | 635.34
53 | 54 | NETR/PW-06 | 375.82
54 | 55 | NETR/PW-07 | 567.71
55 | 56 | NETR/PW-08 | 134.16
56 | 57 | SUNM/PW-01 | 913.55
57 | 58 | SUNM/PW-02 | 926.3
58 | 59 | SUNM/PW-03 | 511.73
59 | 60 | SUNM/PW-04 | 1521.41
60 | 61 | SUNM/PW-05 | 1061.82
61 | 62 | SUNM/PW-06 | 1268.067
62 | 63 | SUNM/PW-07 | 0

## Value_of_Work_Done
| Package | Structure Code | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | VDW_30_06_2020 | VDW_30_06_2021 | Work_Done_20_21 | Payment_30_06_2020
0 | KISH/PW-01 | 8 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 | 40.94 | 1 | 1 | 40.94 | 40.94 | 0 | 0
1 | KISH/PW-01 | 8 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 | 35.88 | 1 | 1 | 35.88 | 35.88 | 0 | 0
2 | KISH/PW-01 | 8 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 | 19.18 | 0 | 1 | 0 | 19.18 | 19.18 | 0
3 | KISH/PW-01 | 8 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 | 309.8 | 0 | 1 | 0 | 309.8 | 309.8 | 0
4 | KISH/PW-01 | 8 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 | 45.95 | 0 | 1 | 0 | 45.95 | 45.95 | 0
5 | KISH/PW-01 | 2 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 | 44.79 | 0 | 1 | 0 | 44.79 | 44.79 | 0
6 | KISH/PW-02 | 3 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 123.81 | 1 | 1 | 123.81 | 123.81 | 0 | 0
7 | KISH/PW-02 | 7 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 | 31.9576 | 1 | 1 | 31.9576 | 31.9576 | 0 | 0
8 | KISH/PW-02 | 7 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 | 93.4351 | 1 | 1 | 93.4351 | 93.4351 | 0 | 0
9 | KISH/PW-02 | 7 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 | 52.1722 | 1 | 1 | 52.1722 | 52.1722 | 0 | 0
10 | KISH/PW-02 | 7 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 | 16.201 | 1 | 1 | 16.201 | 16.201 | 0 | 0
11 | KISH/PW-02 | 7 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 | 68.8599 | 1 | 1 | 68.8599 | 68.8599 | 0 | 0
12 | KISH/PW-02 | 11 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 | 14.8109 | 1 | 1 | 14.8109 | 14.8109 | 0 | 0
13 | KISH/PW-03 | 3 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 | 180.84 | 1 | 1 | 180.84 | 180.84 | 0 | 0
14 | KISH/PW-03 | 11 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 | 236.03 | 1 | 1 | 236.03 | 236.03 | 0 | 0
15 | KISH/PW-03 | 11 | Block Road | Km | 0 | 277.1 | 1 | 1 | 277.1 | 277.1 | 0 | 0
16 | KISH/PW-04 | 3 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 | 97.3 | 1 | 1 | 97.3 | 97.3 | 0 | 0
17 | KISH/PW-04 | 3 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 | 97.3 | 1 | 1 | 97.3 | 97.3 | 0 | 0
18 | KISH/PW-04 | 3 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 | 254.37 | 1 | 1 | 254.37 | 254.37 | 0 | 0
19 | KISH/PW-04 | 11 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 | 121.63 | 1 | 1 | 121.63 | 121.63 | 0 | 0
20 | KISH/PW-04 | 11 | Block Road | Km | 1 | 143.39 | 1 | 1 | 143.39 | 143.39 | 0 | 0
21 | KISH/PW-05 | 3 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 | 190.22 | 1 | 1 | 190.22 | 190.22 | 0 | 0
22 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 | 35.282 | 1 | 1 | 35.282 | 35.282 | 0 | 0
23 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 | 4.0969 | 1 | 1 | 4.0969 | 4.0969 | 0 | 0
24 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 | 8.7693 | 0 | 1 | 0 | 8.7693 | 8.7693 | 0
25 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 | 156.8227 | 1 | 1 | 156.8227 | 156.8227 | 0 | 0
26 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 | 28.9482 | 1 | 1 | 28.9482 | 28.9482 | 0 | 0
27 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 | 17.8983 | 1 | 1 | 17.8983 | 17.8983 | 0 | 0
28 | KISH/PW-05 | 11 | Block Road | Km | 12.214 | 325.54 | 1 | 1 | 325.54 | 325.54 | 0 | 0
29 | KISH/PW-06 | 3 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 | 227.8819 | 1 | 1 | 227.8819 | 227.8819 | 0 | 0
30 | KISH/PW-06 | 7 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4 | 41.55 | 1 | 1 | 41.55 | 41.55 | 0 | 0
31 | KISH/PW-06 | 7 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.43 | 69.7 | 1 | 1 | 69.7 | 69.7 | 0 | 0
32 | KISH/PW-06 | 7 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 0.9 | 23.7 | 1 | 1 | 23.7 | 23.7 | 0 | 0
33 | KISH/PW-06 | 7 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.5 | 10.04 | 1 | 1 | 10.04 | 10.04 | 0 | 0
34 | KISH/PW-06 | 7 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 7.07 | 356.51 | 1 | 1 | 356.51 | 356.51 | 0 | 0
35 | KISH/PW-06 | 7 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 | 120.16 | 1 | 1 | 120.16 | 120.16 | 0 | 0
36 | KISH/PW-07 | 7 | Hazir Khal | Km | 1.73 | 20.5494 | 0 | 0 | 0 | 0 | 0 | 0
37 | KISH/PW-07 | 7 | Karpasha Khal | Km | 1.615 | 26.0781 | 2.16 | 2.16 | 56.3287 | 56.3287 | 0 | 0
38 | KISH/PW-07 | 7 | Dampara Khal | Km | 3.6 | 46.8873 | 0.4 | 0.4 | 18.7549 | 18.7549 | 0 | 0
39 | KISH/PW-07 | 7 | Baniajan | Km | 6.854 | 130.1184 | 1 | 1 | 130.1184 | 130.1184 | 0 | 0
40 | KISH/PW-07 | 7 | Suti Khal | Km | 6.1 | 120.3313 | 1 | 1 | 120.3313 | 120.3313 | 0 | 0
41 | KISH/PW-07 | 7 | Digha Nadi | Km | 5.7 | 424.0032 | 0.65 | 1 | 275.6021 | 424.0032 | 148.4011 | 0
42 | KISH/PW-07 | 7 | Old Singua | Km | 10.86 | 197.6384 | 0 | 0 | 0 | 0 | 0 | 0
43 | KISH/PW-07 | 11 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 | 35.33 | 0.08 | 0.2 | 2.8264 | 7.066 | 4.2396 | 0
44 | KISH/PW-07 | 11 | Block Road | Km | 0 | 55.74 | 0 | 1 | 0 | 55.74 | 55.74 | 0
45 | KISH/PW-09 | 5 | Causeway 6.0m wide-1 at Dampara | Nos | 1 | 210.83 | 1 | 1 | 210.83 | 210.83 | 0 | 0
46 | KISH/PW-09 | 5 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 | 176.64 | 1 | 1 | 176.64 | 176.64 | 0 | 0
47 | KISH/PW-09 | 4 | Mohorkona Box Outlet | Nos | 1 | 66.64 | 1 | 1 | 66.64 | 66.64 | 0 | 0
48 | KISH/PW-09 | 5 | Causeway 6.0m wide-1 at Samar Bari | Nos | 1 | 241.26 | 1 | 1 | 241.26 | 241.26 | 0 | 0
49 | KISH/PW-10 | 3 | Causeway 6.0m wide-1 | Nos | 1 | 137.35 | 0 | 0.65 | 0 | 89.2775 | 89.2775 | 0
50 | KISH/PW-10 | 3 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 | 128.67 | 0.45 | 1 | 57.9015 | 128.67 | 70.7685 | 0
51 | KISH/PW-10 | 11 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 | 274.06 | 0.64 | 1 | 175.3984 | 274.06 | 98.6616 | 0
52 | KISH/PW-10 | 11 | Block Road | Km | 0 | 343.88 | 1 | 1 | 343.88 | 343.88 | 0 | 0
53 | KISH/PW-11 | 3 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 | 274.49 | 0.95 | 1 | 260.7655 | 274.49 | 13.7245 | 0
54 | KISH/PW-11 | 11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 | 557.63 | 0.5 | 1 | 278.815 | 557.63 | 278.815 | 0
55 | KISH/PW-12 | 3 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 | 253.8935 | 1 | 1 | 253.8935 | 253.8935 | 0 | 0
56 | KISH/PW-12 | 3 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 | 277.0365 | 1 | 1 | 277.0365 | 277.0365 | 0 | 0
57 | KISH/PW-12 | 7 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 | 18.397 | 0 | 0 | 0 | 0 | 0 | 0
58 | KISH/PW-12 | 7 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 | 4.398 | 1 | 1 | 4.398 | 4.398 | 0 | 0
59 | KISH/PW-12 | 7 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 | 99.257 | 1 | 1 | 99.257 | 99.257 | 0 | 0
60 | KISH/PW-12 | 7 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 | 110.6945 | 1 | 1 | 110.6945 | 110.6945 | 0 | 0
61 | KISH/PW-12 | 7 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 | 167.984 | 1 | 1 | 167.984 | 167.984 | 0 | 0
62 | KISH/PW-13 | 3 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 | 224.08 | 0.95 | 1 | 212.876 | 224.08 | 11.204 | 0
63 | KISH/PW-13 | 3 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 | 196.52 | 0.95 | 1 | 186.694 | 196.52 | 9.826 | 0
64 | KISH/PW-13 | 11 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 | 489.176 | 0.4 | 1 | 195.6704 | 489.176 | 293.5056 | 0
65 | KISH/PW-13 | 11 | Block Road | Km | 1 | 70.98 | 0.4 | 1 | 28.392 | 70.98 | 42.588 | 0
66 | KISH/PW-14 | 3 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 | 263.7 | 0.95 | 1 | 250.515 | 263.7 | 13.185 | 0
67 | KISH/PW-14 | 11 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 | 485.98 | 0.86 | 1 | 417.9428 | 485.98 | 68.0372 | 0
68 | KISH/PW-14 | 11 | Block Road | Km | 0.5 | 133.96 | 0 | 1 | 0 | 133.96 | 133.96 | 0
69 | KISH/PW-15 | 3 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 | 166.9 | 0 | 0 | 0 | 0 | 0 | 0
70 | KISH/PW-15 | 11 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 | 616.92 | 1 | 1 | 616.92 | 616.92 | 0 | 0
71 | KISH/PW-16 | 3 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 | 267.88 | 0.85 | 1 | 227.698 | 267.88 | 40.182 | 0
72 | KISH/PW-16 | 11 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 | 343.32 | 1 | 1 | 343.32 | 343.32 | 0 | 0
73 | KISH/PW-16 | 11 | Block Road | Km | 0 | 167.97 | 1 | 1 | 167.97 | 167.97 | 0 | 0
74 | KISH/PW-17 | 3 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 | 348.66 | 1 | 1 | 348.66 | 348.66 | 0 | 0
75 | KISH/PW-17 | 3 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 | 217.5324 | 1 | 1 | 217.5324 | 217.5324 | 0 | 0
76 | KISH/PW-17 | 4 | Box Drainage Outlet-1 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
77 | KISH/PW-17 | 4 | Box Drainage Outlet-2 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
78 | KISH/PW-17 | 4 | Box Drainage Outlet-3 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
79 | KISH/PW-17 | 4 | Box Drainage Outlet-4 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
80 | KISH/PW-17 | 4 | Box Drainage Outlet-5 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
81 | KISH/PW-17 | 11 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 | 460.54 | 1 | 1 | 460.54 | 460.54 | 0 | 0
82 | KISH/PW-17 | 11 | Block Road | Km | 0 | 89.5 | 1 | 1 | 89.5 | 89.5 | 0 | 0
83 | KISH/PW-17 | 1 | Irrigation Pipe Inlet-1 | Nos | 25 | 274.47 | 1 | 1 | 274.47 | 274.47 | 0 | 0
84 | KISH/PW-18 | 5 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 | 159.8606 | 0 | 1 | 0 | 159.8606 | 159.8606 | 0
85 | KISH/PW-18 | 5 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 | 161.4295 | 0.8 | 1 | 129.1436 | 161.4295 | 32.2859 | 0
86 | KISH/PW-18 | 5 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 | 186.8205 | 1 | 1 | 186.8205 | 186.8205 | 0 | 0
87 | KISH/PW-18 | 5 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 | 265.5873 | 0.8 | 1 | 212.4699 | 265.5873 | 53.1175 | 0
88 | KISH/PW-18 | 7 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 | 101.2011 | 0 | 0 | 0 | 0 | 0 | 0
89 | KISH/PW-18 | 7 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 | 35.7041 | 1 | 1 | 35.7041 | 35.7041 | 0 | 0
90 | KISH/PW-18 | 7 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 | 17.1427 | 1 | 1 | 17.1427 | 17.1427 | 0 | 0
91 | KISH/PW-18 | 7 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 | 59.4674 | 1 | 1 | 59.4674 | 59.4674 | 0 | 0
92 | KISH/PW-18 | 7 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 | 141.516 | 0 | 1 | 0 | 141.516 | 141.516 | 0
93 | KISH/PW-18 | 7 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 | 187.0328 | 0 | 1 | 0 | 187.0328 | 187.0328 | 0
94 | KISH/PW-19 | 7 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 | 472.9622 | 0.25 | 1 | 118.2406 | 472.9622 | 354.7217 | 0
95 | KISH/PW-19 | 7 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 | 374.9638 | 0.4 | 1 | 149.9855 | 374.9638 | 224.9783 | 0
96 | KISH/PW-20 | 5 | Chitra Khal 4m wide | Nos | 1 | 136.31 | 1 | 1 | 136.31 | 136.31 | 0 | 0
97 | KISH/PW-20 | 5 | Nabinpur Khal 4m Wide | Nos | 1 | 193.69 | 1 | 1 | 193.69 | 193.69 | 0 | 0
98 | KISH/PW-20 | 5 | Dipjuri Khal 4m CW | Nos | 1 | 185.03 | 1 | 1 | 185.03 | 185.03 | 0 | 0
99 | KISH/PW-20 | 5 | Sudhikhal 4m wide CW | Nos | 1 | 136.66 | 1 | 1 | 136.66 | 136.66 | 0 | 0
100 | KISH/PW-20 | 3 | Chhagalia khal sluice | Nos | 1 | 41.0186 | 1 | 1 | 41.0186 | 41.0186 | 0 | 0
101 | KISH/PW-20 | 3 | Near nasir sluice | Nos | 1 | 42.7991 | 1 | 1 | 42.7991 | 42.7991 | 0 | 0
102 | KISH/PW-20 | 3 | Shingpur khal sluice | Nos | 1 | 41.9704 | 1 | 1 | 41.9704 | 41.9704 | 0 | 0
103 | KISH/PW-20 | 3 | Gharu khal sluice | Nos | 1 | 41.9704 | 0.75 | 1 | 31.4778 | 41.9704 | 10.4926 | 0
104 | KISH/PW-20 | 1 | Irrigation Pipe Inlet 600mm dia | Nos | 36 | 334.27 | 0.57 | 0.57 | 190.5339 | 190.5339 | 0 | 0
105 | KISH/PW-21 | 3 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 | 321.3991 | 0.48 | 1 | 154.2716 | 321.3991 | 167.1275 | 0
106 | KISH/PW-21 | 3 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 | 156.6821 | 0.45 | 1 | 70.5069 | 156.6821 | 86.1751 | 0
107 | KISH/PW-21 | 12 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 | 120.5564 | 0 | 1 | 0 | 120.5564 | 120.5564 | 0
108 | KISH/PW-21 | 11 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 | 329.1074 | 0 | 1 | 0 | 329.1074 | 329.1074 | 0
109 | KISH/PW-22 | 11 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 | 235.9924 | 0.8 | 0.8 | 188.7939 | 188.7939 | 0 | 0
110 | KISH/PW-22 | 7 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 | 18.1492 | 0 | 1 | 0 | 18.1492 | 18.1492 | 0
111 | KISH/PW-22 | 7 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 | 28.0679 | 1 | 1 | 28.0679 | 28.0679 | 0 | 0
112 | KISH/PW-22 | 7 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 | 5.8814 | 0 | 1 | 0 | 5.8814 | 5.8814 | 0
113 | KISH/PW-22 | 7 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 | 8.1389 | 0 | 1 | 0 | 8.1389 | 8.1389 | 0
114 | KISH/PW-22 | 7 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 | 84.8797 | 0.16 | 1 | 13.5808 | 84.8797 | 71.299 | 0
115 | KISH/PW-22 | 7 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 | 11.9047 | 0 | 1 | 0 | 11.9047 | 11.9047 | 0
116 | KISH/PW-22 | 7 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 | 2.4463 | 0 | 1 | 0 | 2.4463 | 2.4463 | 0
117 | KISH/PW-22 | 7 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 | 14.6073 | 1 | 1 | 14.6073 | 14.6073 | 0 | 0
118 | KISH/PW-22 | 7 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 | 4.4592 | 0 | 1 | 0 | 4.4592 | 4.4592 | 0
119 | KISH/PW-22 | 5 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 | 195.2169 | 0.15 | 1 | 29.2825 | 195.2169 | 165.9344 | 0
120 | KISH/PW-22 | 4 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 | 36.662 | 0 | 1 | 0 | 36.662 | 36.662 | 0
121 | KISH/PW-22 | 4 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 | 36.662 | 0 | 1 | 0 | 36.662 | 36.662 | 0
122 | KISH/PW-22 | 4 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 | 36.662 | 0 | 1 | 0 | 36.662 | 36.662 | 0
123 | KISH/PW-23 | 11 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 | 107.4208 | 0.8 | 1 | 85.9367 | 107.4208 | 21.4842 | 0
124 | KISH/PW-23 | 3 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 | 295.5262 | 0.85 | 1 | 251.1973 | 295.5262 | 44.3289 | 0
125 | KISH/PW-23 | 3 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 | 227.0604 | 0.95 | 1 | 215.7073 | 227.0604 | 11.353 | 0
126 | KISH/PW-23 | 7 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 | 28.5772 | 0 | 0.3 | 0 | 8.5732 | 8.5732 | 0
127 | KISH/PW-23 | 7 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 | 3.8604 | 1 | 1 | 3.8604 | 3.8604 | 0 | 0
128 | KISH/PW-23 | 4 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 | 38.9293 | 1 | 1 | 38.9293 | 38.9293 | 0 | 0
129 | KISH/PW-23 | 1 | Irrigation Pipe Inlet 600mm dia | Nos | 4 | 62.862 | 1 | 1 | 62.862 | 62.862 | 0 | 0
130 | KISH/PW-24 | 11 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 | 1149.1962 | 1 | 1 | 1149.1962 | 1149.1962 | 0 | 0
131 | KISH/PW-25 | 3 | Regulator 5-Vent-1 | Nos | 1 | 405.9371 | 0.65 | 1 | 263.8591 | 405.9371 | 142.078 | 0
132 | KISH/PW-25 | 7 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 | 320.0346 | 0.88 | 0.88 | 281.6304 | 281.6304 | 0 | 0
133 | KISH/PW-25 | 7 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Km | 1.65 | 54.4035 | 0.36 | 1 | 19.5853 | 54.4035 | 34.8183 | 0
134 | KISH/PW-25 | 5 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 | 346.4138 | 0 | 0 | 0 | 0 | 0 | 0
135 | KISH/PW-25 | 5 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 | 288.0795 | 0 | 0 | 0 | 0 | 0 | 0
136 | KISH/PW-25 | 5 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 | 189.5297 | 0.65 | 1 | 123.1943 | 189.5297 | 66.3354 | 0
137 | KISH/PW-25 | 4 | Box Sluice-1 | Nos | 1 | 41.8221 | 0 | 0 | 0 | 0 | 0 | 0
138 | KISH/PW-25 | 1 | Irrigation Pipe Inlet 600mm dia | Nos | 15 | 118.5673 | 0.86 | 1 | 101.9679 | 118.5673 | 16.5994 | 0
139 | KISH/PW-26 | 11 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 | 22.7161 | 1 | 1 | 22.7161 | 22.7161 | 0 | 0
140 | KISH/PW-26 | 7 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 | 71.5264 | 1 | 1 | 71.5264 | 71.5264 | 0 | 0
141 | KISH/PW-26 | 7 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 | 12.7224 | 1 | 1 | 12.7224 | 12.7224 | 0 | 0
142 | KISH/PW-26 | 7 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 | 16.3878 | 1 | 1 | 16.3878 | 16.3878 | 0 | 0
143 | KISH/PW-26 | 7 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 | 367.3183 | 1 | 1 | 367.3183 | 367.3183 | 0 | 0
144 | KISH/PW-27 | 3 | phuleshwari | Nos | 1 | 156.62 | 0 | 1 | 0 | 156.62 | 156.62 | 0
145 | KISH/PW-27 | 3 | Kalna | Nos | 1 | 148 | 0 | 1 | 0 | 148 | 148 | 0
146 | KISH/PW-27 | 4 | RCC Box Drainage | Nos | 1 | 41.88 | 0 | 1 | 0 | 41.88 | 41.88 | 0
147 | KISH/PW-27 | 5 | Causeway | Nos | 1 | 140.87 | 0 | 1 | 0 | 140.87 | 140.87 | 0
148 | KISH/PW-27 | 5 | Causeway & Drainage | Nos | 1 | 407.31 | 0 | 1 | 0 | 407.31 | 407.31 | 0
149 | KISH/PW-28/Lot-01 | 15 | WMG Building | Nos | 11 | 347.64 | 0.17 | 0.54 | 59.0988 | 187.7256 | 128.6268 | 0

## Package_wise_payment
| Package_No | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | KISH/PW-01 | 76.82 | 496.54 | 51.09 | 445.45
1 | KISH/PW-02 | 401.2468 | 401.2468 | 347.71 | 53.5368
2 | KISH/PW-03 | 693.97 | 693.97 | 625.93 | 68.04
3 | KISH/PW-04 | 713.99 | 713.99 | 714.69 | -0.7
4 | KISH/PW-05 | 758.808 | 767.5773 | 575.15 | 192.4273
5 | KISH/PW-06 | 849.5419 | 849.5419 | 837.25 | 12.2919
6 | KISH/PW-07 | 603.9619 | 812.3426 | 565.07 | 247.2726
7 | KISH/PW-08 | 0 | 0 | 0 | 0
8 | KISH/PW-09 | 695.37 | 695.37 | 712.33 | -16.96
9 | KISH/PW-10 | 577.1799 | 835.8875 | 409.68 | 426.2075
10 | KISH/PW-11 | 539.5805 | 832.12 | 522.86 | 309.26
11 | KISH/PW-12 | 913.2634 | 913.2634 | 705.59 | 207.6734
12 | KISH/PW-13 | 623.6324 | 980.756 | 647.2 | 333.556
13 | KISH/PW-14 | 668.4578 | 883.64 | 806.89 | 76.75
14 | KISH/PW-15 | 616.92 | 616.92 | 333.94 | 282.98
15 | KISH/PW-16 | 738.988 | 779.17 | 721.62 | 57.55
16 | KISH/PW-17 | 1568.1457 | 1568.1457 | 1451.95 | 116.1957
17 | KISH/PW-18 | 640.7482 | 1214.5609 | 711.02 | 503.5409
18 | KISH/PW-19 | 268.2261 | 847.926 | 331.35 | 516.576
19 | KISH/PW-20 | 999.4897 | 1009.9823 | 501.12 | 508.8623
20 | KISH/PW-21 | 224.7785 | 927.7449 | 268.24 | 659.5049
21 | KISH/PW-22 | 274.3324 | 672.5314 | 281.05 | 391.4814
22 | KISH/PW-23 | 658.493 | 744.2322 | 720.33 | 23.9022
23 | KISH/PW-24 | 1149.1962 | 1149.1962 | 890.42 | 258.7762
24 | KISH/PW-25 | 790.2371 | 1050.0682 | 749.37 | 300.6982
25 | KISH/PW-26 | 490.671 | 490.671 | 501.12 | -10.449
26 | KISH/PW-27 | 0 | 894.68 | 0 | 894.68
27 | KISH/PW-28/Lot-01 | 59.0988 | 187.7256 | 61.6 | 126.1256
28 | KISH/PW-28/Lot-02 | 0 | 0 | 0 | 0
29 | KISH/PW-28/Lot-03 | 0 | 0 | 0 | 0
30 | KISH/PW-28/Lot-04 | 0 | 0 | 74.41 | -74.41
31 | KISH/PW-29 | 0 | 0 | 0 | 0
32 | KISH/PW-30 | 0 | 0 | 0 | 0
33 | KISH/PW-31 | 0 | 0 | 0 | 0
34 | KISH/PW-32 | 0 | 0 | 0 | 0
35 | KISH/PW-33 | 0 | 0 | 0 | 0
36 | KISH/PW-34 | 0 | 0 | 0 | 0
37 | KISH/PW-35 | 0 | 0 | 0 | 0
38 | KISH/PW-36 | 0 | 0 | 0 | 0
39 | KISH/PW-37 | 0 | 0 | 0 | 0
40 | KISH/PW-38 | 0 | 0 | 0 | 0
41 | HOBI/PW-01 | 0 | 0 | 938.57 | -938.57
42 | HOBI/PW-02 | 0 | 0 | 1079.52 | -1079.52
43 | HOBI/PW-03 | 0 | 0 | 0 | 0
44 | HOBI/PW-04 | 0 | 0 | 655.94 | -655.94
45 | HOBI/PW-05 | 0 | 0 | 307.8 | -307.8
46 | HOBI/PW-06 | 0 | 0 | 1094.31 | -1094.31
47 | HOBI/PW-07 | 0 | 0 | 667.67 | -667.67
48 | NETR/PW-01 | 0 | 0 | 817.97 | -817.97
49 | NETR/PW-02 | 0 | 0 | 475.85 | -475.85
50 | NETR/PW-03 | 0 | 0 | 712.73 | -712.73
51 | NETR/PW-04 | 0 | 0 | 844.17 | -844.17
52 | NETR/PW-05 | 0 | 0 | 635.34 | -635.34
53 | NETR/PW-06 | 0 | 0 | 375.82 | -375.82
54 | NETR/PW-07 | 0 | 0 | 567.71 | -567.71
55 | NETR/PW-08 | 0 | 0 | 134.16 | -134.16
56 | SUNM/PW-01 | 0 | 0 | 913.55 | -913.55
57 | SUNM/PW-02 | 0 | 0 | 926.3 | -926.3
58 | SUNM/PW-03 | 0 | 0 | 511.73 | -511.73
59 | SUNM/PW-04 | 0 | 0 | 1521.41 | -1521.41
60 | SUNM/PW-05 | 0 | 0 | 1061.82 | -1061.82
61 | SUNM/PW-06 | 0 | 0 | 1268.067 | -1268.067
62 | SUNM/PW-07 | 0 | 0 | 0 | 0

## Structure_Wise_payment
| Items | Code | DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Construction of Irrigation Inlet | 1 | Inlet | 629.8338 | 646.4332 | 291.81 | 354.6232
1 | Rehab Regulator Rehab Haor | 2 | Reg_Rehab_Rehab | 0 | 44.79 | 0 | 44.79
2 | Regulator | 3 | Reg_CW_Box | 4578.1023 | 5592.4449 | 6503.97 | -911.5251
3 | Box Drainage Outlet | 4 | Reg_CW_Box | 283.0126 | 434.8786 | 0 | 434.8786
4 | Causeway | 5 | Reg_CW_Box | 1961.3308 | 2987.0445 | 0 | 2987.0445
5 | Bridge | 6 | Reg_CW_Box | 0 | 0 | 0 | 0
6 | Khal_River Reexcavation(New Haor) | 7 | Khal_Riv_New | 3077.582 | 4299.902 | 2546.54 | 1753.362
7 | Khal_River Reexcavation(Rehab Haor) | 8 | Khal_Riv_Rehab | 76.82 | 451.75 | 51.09 | 400.66
8 | Embankment Rehablitation | 9 | Full_Emb_Rehab | 0 | 0 | 0 | 0
9 | Submersible Embankment Rehabilitation | 10 | Sub_Emb_Rehab | 0 | 0 | 0 | 0
10 | Submersible Embankment Construction | 11 | Sub_Emb_Const | 5929.3669 | 7264.2747 | 5833.04 | 1431.2347
11 | Rehab Regulator New Haor | 12 | Reg_Rehab_New | 0 | 120.5564 | 0 | 120.5564
12 | Thrashing Floor Construction | 14 | Thr_Fl_Cost | 0 | 0 | 0 | 0
13 | Construction of WMG | 15 | Wmg_Office | 59.0988 | 187.7256 | 0 | 187.7256
14 | M&E GATE Repair | 16 | Gate_Repair | 0 | 0 | 0 | 0

## DPP_Wise_payment
| DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Inlet | 629.8338 | 646.4332 | 291.81 | 354.6232
1 | Reg_Rehab_Rehab | 0 | 44.79 | 0 | 44.79
2 | Reg_CW_Box | 6822.4457 | 9014.3681 | 6503.97 | 2510.3981
3 | Khal_Riv_New | 3077.582 | 4299.902 | 2546.54 | 1753.362
4 | Khal_Riv_Rehab | 76.82 | 451.75 | 51.09 | 400.66
5 | Full_Emb_Rehab | 0 | 0 | 0 | 0
6 | Sub_Emb_Rehab | 0 | 0 | 0 | 0
7 | Sub_Emb_Const | 5929.3669 | 7264.2747 | 5833.04 | 1431.2347
8 | Reg_Rehab_New | 0 | 120.5564 | 0 | 120.5564
9 | Thr_Fl_Cost | 0 | 0 | 0 | 0
10 | Wmg_Office | 59.0988 | 187.7256 | 0 | 187.7256
11 | Gate_Repair | 0 | 0 | 0 | 0

## Physical_30_june_2020
| Package_No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Thrashing Floor Construction | Construction of WMG | M&E GATE Repair
0 | KISH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.371 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | KISH/PW-02 | 0 | 0 | 1 | 0 | 0 | 0 | 12.93 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0
2 | KISH/PW-03 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.383 | 0 | 0 | 0 | 0
3 | KISH/PW-04 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.471 | 0 | 0 | 0 | 0
4 | KISH/PW-05 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.838 | 0 | 0 | 0 | 0
5 | KISH/PW-06 | 0 | 0 | 1 | 0 | 0 | 0 | 19.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 21.5874 | 0 | 0 | 0 | 0.31032 | 0 | 0 | 0 | 0
7 | KISH/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | KISH/PW-09 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | KISH/PW-10 | 0 | 0 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.52 | 0 | 0 | 0 | 0
10 | KISH/PW-11 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.43 | 0 | 0 | 0 | 0
11 | KISH/PW-12 | 0 | 0 | 2 | 0 | 0 | 0 | 6.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | KISH/PW-13 | 0 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 0 | 0 | 0
13 | KISH/PW-14 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.534 | 0 | 0 | 0 | 0
14 | KISH/PW-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0
15 | KISH/PW-16 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
16 | KISH/PW-17 | 25 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
17 | KISH/PW-18 | 0 | 0 | 0 | 0 | 2.6 | 0 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | KISH/PW-20 | 20.52 | 0 | 3.75 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | KISH/PW-21 | 0 | 0 | 0.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | KISH/PW-22 | 0 | 0 | 0 | 0 | 0.15 | 0 | 2.864 | 0 | 0 | 0 | 8.3704 | 0 | 0 | 0 | 0
22 | KISH/PW-23 | 4 | 0 | 1.8 | 1 | 0 | 0 | 0.15 | 0 | 0 | 0 | 3.608 | 0 | 0 | 0 | 0
23 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.843 | 0 | 0 | 0 | 0
24 | KISH/PW-25 | 12.9 | 0 | 0.65 | 0 | 0.65 | 0 | 1.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0
26 | KISH/PW-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | KISH/PW-28/Lot-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.87 | 0
28 | KISH/PW-28/Lot-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | KISH/PW-28/Lot-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | KISH/PW-28/Lot-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | KISH/PW-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | KISH/PW-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | KISH/PW-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | KISH/PW-32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | KISH/PW-33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | KISH/PW-34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | KISH/PW-35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | KISH/PW-36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | KISH/PW-37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | KISH/PW-38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | HOBI/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | HOBI/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | HOBI/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | HOBI/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | HOBI/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | NETR/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | NETR/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | NETR/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | NETR/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | SUNM/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | SUNM/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | SUNM/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | SUNM/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | SUNM/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Physical_30_june_2021
| Package_No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Thrashing Floor Construction | Construction of WMG | M&E GATE Repair
0 | KISH/PW-01 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11.546 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | KISH/PW-02 | 0 | 0 | 1 | 0 | 0 | 0 | 12.93 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0
2 | KISH/PW-03 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.383 | 0 | 0 | 0 | 0
3 | KISH/PW-04 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.471 | 0 | 0 | 0 | 0
4 | KISH/PW-05 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.428 | 0 | 0 | 0 | 0
5 | KISH/PW-06 | 0 | 0 | 1 | 0 | 0 | 0 | 19.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5824 | 0 | 0 | 0 | 0.7758 | 0 | 0 | 0 | 0
7 | KISH/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | KISH/PW-09 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | KISH/PW-10 | 0 | 0 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.75 | 0 | 0 | 0 | 0
10 | KISH/PW-11 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.86 | 0 | 0 | 0 | 0
11 | KISH/PW-12 | 0 | 0 | 2 | 0 | 0 | 0 | 6.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | KISH/PW-13 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0
13 | KISH/PW-14 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.4 | 0 | 0 | 0 | 0
14 | KISH/PW-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0
15 | KISH/PW-16 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
16 | KISH/PW-17 | 25 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
17 | KISH/PW-18 | 0 | 0 | 0 | 0 | 4 | 0 | 18.645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 22.933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | KISH/PW-20 | 20.52 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | KISH/PW-21 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.494 | 5 | 0 | 0 | 0
21 | KISH/PW-22 | 0 | 0 | 0 | 3 | 1 | 0 | 11.623 | 0 | 0 | 0 | 8.3704 | 0 | 0 | 0 | 0
22 | KISH/PW-23 | 4 | 0 | 2 | 1 | 0 | 0 | 0.6825 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0
23 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.843 | 0 | 0 | 0 | 0
24 | KISH/PW-25 | 15 | 0 | 1 | 0 | 1 | 0 | 2.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0
26 | KISH/PW-27 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | KISH/PW-28/Lot-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94 | 0
28 | KISH/PW-28/Lot-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | KISH/PW-28/Lot-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | KISH/PW-28/Lot-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | KISH/PW-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | KISH/PW-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | KISH/PW-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | KISH/PW-32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | KISH/PW-33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | KISH/PW-34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | KISH/PW-35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | KISH/PW-36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | KISH/PW-37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | KISH/PW-38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | HOBI/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | HOBI/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | HOBI/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | HOBI/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | HOBI/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | NETR/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | NETR/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | NETR/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | NETR/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | SUNM/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | SUNM/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | SUNM/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | SUNM/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | SUNM/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Target_30_june_2021
| Package_No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Thrashing Floor Construction | Construction of WMG | M&E GATE Repair
0 | KISH/PW-01 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | KISH/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KISH/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | KISH/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | KISH/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59 | 0 | 0 | 0 | 0
5 | KISH/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 1.995 | 0 | 0 | 0 | 0.46548 | 0 | 0 | 0 | 0
7 | KISH/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | KISH/PW-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | KISH/PW-10 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.23 | 0 | 0 | 0 | 0
10 | KISH/PW-11 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.43 | 0 | 0 | 0 | 0
11 | KISH/PW-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | KISH/PW-13 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6 | 0 | 0 | 0 | 0
13 | KISH/PW-14 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.866 | 0 | 0 | 0 | 0
14 | KISH/PW-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | KISH/PW-16 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | KISH/PW-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | KISH/PW-18 | 0 | 0 | 0 | 0 | 1.4 | 0 | 13.895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | KISH/PW-20 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | KISH/PW-21 | 0 | 0 | 1.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.494 | 5 | 0 | 0 | 0
21 | KISH/PW-22 | 0 | 0 | 0 | 3 | 0.85 | 0 | 8.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | KISH/PW-23 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.5325 | 0 | 0 | 0 | 0.902 | 0 | 0 | 0 | 0
23 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | KISH/PW-25 | 2.1 | 0 | 0.35 | 0 | 0.35 | 0 | 1.056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | KISH/PW-27 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | KISH/PW-28/Lot-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.07 | 0
28 | KISH/PW-28/Lot-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | KISH/PW-28/Lot-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | KISH/PW-28/Lot-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | KISH/PW-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | KISH/PW-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | KISH/PW-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | KISH/PW-32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | KISH/PW-33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | KISH/PW-34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | KISH/PW-35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | KISH/PW-36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | KISH/PW-37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | KISH/PW-38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | HOBI/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | HOBI/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | HOBI/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | HOBI/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | HOBI/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | NETR/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | NETR/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | NETR/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | NETR/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | SUNM/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | SUNM/PW-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | SUNM/PW-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | SUNM/PW-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | SUNM/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.1 | 1 | 5.42 | 4 | 4.6 | 0 | 42.3703 | 8.175 | 0 | 0 | 30.5775 | 5 | 0 | 4.07 | 0