## Лист1
sl | Work Item | Code | Duration | Predecessor
1 | Land Lease | A | 7
2 | Labour Shed and Storage Construction | B | 15 | 1
3 | Casting Yard Preparation | Y | 7 | 1
4 | Equipment and Labour Mobilization | M | 7 | 2
5 | Material Consignment-1 | MC1 | 4 | 2
6 | CC Block Casting Batch No:1 | BC1 | 7 | 5
7 | CC Block Casting Batch No:2 | BC2 | 7 | 6
8 | Material Consignment-2 | MC2 | 4 | 6
9 | CC Block Casting Batch No:3 | BC3 | 7 | 8
10 | CC Block Casting Batch No:4 | BC4 | 7 | 9
11 | Material Consignment-3 | MC3 | 4 | 9
12 | CC Block Casting Batch No:5 | BC5 | 7 | 11
13 | CC Block Casting Batch No:6 | BC6 | 7 | 12
14 | Material Consignment-4 | MC4 | 4 | 12
15 | CC Block Casting Batch No:7 | BC7 | 7 | 14
16 | CC Block Casting Batch No:8 | BC8 | 7 | 15
17 | Material Consignment-5 | MC5 | 4 | 15
18 | CC Block Casting Batch No:9 | BC9 | 7 | 17
19 | CC Block Casting Batch No:10 | BC10 | 7 | 18
20 | Embakment Construction and Slope Prep | EMB1 | 15 | 14
21 | Sand Filter | SF1 | 10 | 20
22 | Khoa Filter | KF1 | 10 | 21
23 | Geotextile Filtter | GT1 | 10 | 22
24 | CC Block Placing | BP1 | 10 | 23
25 | Demobilization and Site Cleanup | DM | 7 | 24

## Labour Estimation
Labour for 500 CC Block
80-375 Labour, Unskilled | 0.0927 | 48.7895 | 45
80-425 Mason | 0.0062 | 3.2632 | 3
80-430 Mason, Head | 0.0011 | 0.57895
80-435 Mason, Helper | 0.0028 | 1.4737 | 2
80-500 Operator, Mixture Machine | 0.0019 | 1
80-755 Welder | 0.0019 | 1
50