## Type_A
| Type_A_211M_724_To_935 | Type_A_50M_965_TO_1015 | Type_A_40M_4500_TO_4570 | Type_A_40M_35020_TO_35100
Mobilization and Site Preparation
CC Block Manufacture(40X40X40) | 5012 | 1188 | 950 | 950
CC Block Manufacture(40X40X20) | 33338 | 7900 | 4151 | 4151
Embankment Construction | 6974 | 1653 | 330 | 330
Placing Sand Filter | 560 | 133 | 68 | 68
Placing Geotextile Filter | 6098 | 1445 | 770 | 770
Placing Pea Gravel Filter | 560 | 133 | 68 | 68
Placing CC Block | 1388 | 328 | 193 | 193
Ancilary Work for Site Completion
38350
| 0.064 | 0.064 | 0.064 | 0.064 | 263.5156 | 265 | 530
| 1387.584 | 328.832 | 193.632 | 193.632
| 16.4044 | 16.4044 | 16.4044 | 16.4044 |  |  |  | 313.25
| 8.2022 | 8.2022 | 8.2022 | 8.2022
40X40X40-cement | 1645 | 390 | 312 | 312
40x40X20-cement | 5469 | 1296 | 681 | 681
| 102.8125 | 24.375 | 19.5 | 19.5
| 341.8125 | 81 | 42.5625 | 42.5625
| 0.02848 | 0.02848 | 0.02848 | 0.02848
| 0.01424 | 0.01424 | 0.01424 | 0.01424
40X40X40-sand | 143 | 34 | 28 | 28
40x40X20-sand | 475 | 113 | 60 | 60
| 8.9375 | 2.125 | 1.75 | 1.75
| 29.6875 | 7.0625 | 3.75 | 3.75
| 0.062472 | 0.062472 | 0.062472 | 0.062472
| 0.031236 | 0.031236 | 0.031236 | 0.031236
40X40X40-stone chips-total | 314 | 75 | 60 | 60
40x40X20-stone chips-total | 1042 | 247 | 130 | 130
perday | 19.625 | 4.6875 | 3.75 | 3.75
perday | 65.125 | 15.4375 | 8.125 | 8.125
Mixture Machine 40X40X40 | 20 | 5 | 4 | 4
Mixture Machine 40X40X20 | 64 | 15 | 8 | 8
56
38350
Form Work 40X40X40/day | 320 | 74.25 | 59.375 | 59.375
Form Work 40X40X20/day | 2100 | 493.75 | 259.4375 | 259.4375

## Type B
| Type_B5_724M_0_TO_724 | work name | Type_B5_1165M_1015_TO_2180 |  | Type_B5_1150M_9200_TO_10350
Mobilization and Site Preparation
Embankment Construction | 3495 | Embankment Construction 3495 cum | 5623 | Embankment Construction 5623 cum | 5551 | Embankment Construction 5551 cum
Geotextile Filter | 11251 | Geotextile Filter 11251 sqm | 18105 | Geotextile Filter 18105 cum | 17871 | Geotextile Filter 17871 cum
Geo_Bags | 3388 | Geo_Bags 3388 sqm | 5451 | Geo_Bags 5451 cum | 5380 | Geo_Bags 5380 cum
Turfing | 9842 | Turfing 9842 sqm | 15836 | Turfing 15836 cum | 15632 | Turfing 15632 cum
Ancilary Work for Site Completion
For Type-B-5
[7 empty] | From km | 0 | to km. | 0.724 | = | 724
[7 empty] | From km | 1.015 | to km. | 2.18 | = | 1165
[7 empty] | From km | 9.2 | to km. | 10.35 | = | 1150

## Resctioning
| Rsec_850M_4600_TO_7800 |  | Rsec_3850M_25200_TO_38500
Mobilization and Site Preparation
Embankment Construction | 3366 | Embankment Construction 3366 cum | 15286 | Embankment Construction 15286 cum
Turfing | 11722 | Turfing 11722 sqm | 53230 | Turfing 53230 sqm
Ancilary Work for Site Completion
25