## Structure_Type
| Items | Initial | Code | Payment_30_06_2020 | DPP_Item
0 | Construction of Irrigation Inlet | IRRI_C | 1 | 291.81 | Inlet
1 | Rehab Regulator Rehab Haor | REG_R_REHAB | 2 | 0 | Reg_Rehab_Rehab
2 | Regulator | REG_C | 3 | 6503.97 | Reg_CW_Box
3 | Box Drainage Outlet | DROU_C | 4 | 0 | Reg_CW_Box
4 | Causeway | CW_C | 5 | 0 | Reg_CW_Box
5 | Bridge | BRI_C | 6 | 0 | Reg_CW_Box
6 | Khal_River Reexcavation(New Haor) | REX_KH_RIV_NEW | 7 | 2546.54 | Khal_Riv_New
7 | Khal_River Reexcavation(Rehab Haor) | REX_KH_RIV_REHAB | 8 | 51.09 | Khal_Riv_Rehab
8 | Embankment Rehablitation | EMB_R | 9 | 0 | Full_Emb_Rehab
9 | Submersible Embankment Rehabilitation | SEMB_R | 10 | 0 | Sub_Emb_Rehab
10 | Submersible Embankment Construction | SEMB_C | 11 | 5833.04 | Sub_Emb_Const
11 | Rehab Regulator New Haor | REG_R_NEW | 12 | 0 | Reg_Rehab_New
12 | Thrashing Floor Construction | THF_CONS | 14 | 0 | Thr_Fl_Cost
13 | Construction of WMG | WMG_OFF | 15 | 0 | Wmg_Office
14 | M&E GATE Repair | GATE_REP | 16 | 0 | Gate_Repair

## Projection_Info
| Package Name | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
0 | BWDB/Kish/HFMLIP/ PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 | 40.94 | 1 | 1 | KISH/PW-01 | Rehab | 8 | 0 | R-2 | KISH
1 | BWDB/Kish/HFMLIP/ PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 | 35.88 | 1 | 1 | KISH/PW-01 | Rehab | 8 | 0 | R-1 | KISH
2 | BWDB/Kish/HFMLIP/ PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 | 19.18 | 0 | 1 | KISH/PW-01 | Rehab | 8 | 0 | R-3 | KISH
3 | BWDB/Kish/HFMLIP/ PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 | 309.8 | 0 | 1 | KISH/PW-01 | Rehab | 8 | 0 | R-3 | KISH
4 | BWDB/Kish/HFMLIP/ PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 | 45.95 | 0 | 1 | KISH/PW-01 | Rehab | 8 | 0 | R-3 | KISH
5 | BWDB/Kish/HFMLIP/ PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 | 44.79 | 0 | 1 | KISH/PW-01 | Rehab | 2 | 0 | R-1 | KISH
6 | Package No-02 /ChandpurHaor | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 155.5114 | 1 | 1 | KISH/PW-02 | 0 | 3 | 0 | N-1 | KISH
7 | Package No-02 /ChandpurHaor | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 | 31.9576 | 1 | 1 | KISH/PW-02 | 0 | 7 | 0 | N-2 | KISH
8 | Package No-02 /ChandpurHaor | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 | 93.4351 | 1 | 1 | KISH/PW-02 | 0 | 7 | 0 | N-3 | KISH
9 | Package No-02 /ChandpurHaor | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 | 52.1722 | 1 | 1 | KISH/PW-02 | 0 | 7 | 0 | N-4 | KISH
10 | Package No-02 /ChandpurHaor | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 | 16.201 | 1 | 1 | KISH/PW-02 | 0 | 7 | 0 | N-5 | KISH
11 | Package No-02 /ChandpurHaor | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 | 68.8599 | 1 | 1 | KISH/PW-02 | 0 | 7 | 0 | N-6 | KISH
12 | Package No-02 /ChandpurHaor | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 | 14.8109 | 1 | 1 | KISH/PW-02 | 0 | 11 | 0 | N-7 | KISH
13 | Package No.-03/ Nunnir Haor (Part-A) | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 | 155.5114 | 1 | 1 | KISH/PW-03 | 0 | 3 | 0 | N-2 | KISH
14 | Package No.-03/ Nunnir Haor (Part-A) | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 | 247.1255 | 1 | 1 | KISH/PW-03 | 0 | 11 | 0 | N-2 | KISH
15 | Package No.-03/ Nunnir Haor (Part-A) | Block Road | Km | 0 | 286.8206 | 1 | 1 | KISH/PW-03 | 0 | 11 | 0 | N-2 | KISH
16 | Package No.-04/ Nunnir Haor (Part B+C) | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 | 97.9579 | 1 | 1 | KISH/PW-04 | 0 | 3 | 0 | N-2 | KISH
17 | Package No.-04/ Nunnir Haor (Part B+C) | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 | 97.9579 | 1 | 1 | KISH/PW-04 | 0 | 3 | 0 | N-2 | KISH
18 | Package No.-04/ Nunnir Haor (Part B+C) | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 | 257.73 | 1 | 1 | KISH/PW-04 | 0 | 3 | 0 | N-2 | KISH
19 | Package No.-04/ Nunnir Haor (Part B+C) | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 | 256.8713 | 1 | 1 | KISH/PW-04 | 0 | 11 | 0 | N-2 | KISH
20 | Package No.-05/ NunnirHaor (Part-A& C) | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 | 190.22 | 1 | 1 | KISH/PW-05 | 0 | 3 | 0 | N-2 | KISH
21 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 | 35.282 | 1 | 1 | KISH/PW-05 | 0 | 11 | 0 | N-2 | KISH
22 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 | 4.0969 | 1 | 1 | KISH/PW-05 | 0 | 11 | 0 | N-2 | KISH
23 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 | 8.7693 | 0 | 1 | KISH/PW-05 | 0 | 11 | 0 | N-2 | KISH
24 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 | 156.8227 | 1 | 1 | KISH/PW-05 | 0 | 11 | 0 | N-2 | KISH
25 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 | 28.9482 | 1 | 1 | KISH/PW-05 | 0 | 11 | 0 | N-2 | KISH
26 | Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 | 17.8983 | 1 | 1 | KISH/PW-05 | 0 | 11 | 0 | N-2 | KISH
27 | Package No.-05/ NunnirHaor (Part-A& C) | Block Road | Km | 12.214 | 325.54 | 1 | 1 | KISH/PW-05 | 0 | 11 | 0 | N-2 | KISH
28 | Package No.-06/ NunnirHaor (Part-A) | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 | 227.8819 | 1 | 1 | KISH/PW-06 | 0 | 3 | 0 | N-2 | KISH
29 | Package No.-06/ NunnirHaor (Part-A) | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 | 67.5613 | 1 | 1 | KISH/PW-06 | 0 | 7 | 0 | N-2 | KISH
30 | Package No.-06/ NunnirHaor (Part-A) | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 | 99.5765 | 1 | 1 | KISH/PW-06 | 0 | 7 | 0 | N-2 | KISH
31 | Package No.-06/ NunnirHaor (Part-A) | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 | 28.0877 | 1 | 1 | KISH/PW-06 | 0 | 7 | 0 | N-2 | KISH
32 | Package No.-06/ NunnirHaor (Part-A) | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 | 16.0154 | 1 | 1 | KISH/PW-06 | 0 | 7 | 0 | N-2 | KISH
33 | Package No.-06/ NunnirHaor (Part-A) | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 | 225.9517 | 1 | 1 | KISH/PW-06 | 0 | 7 | 0 | N-2 | KISH
34 | Package No.-06/ NunnirHaor (Part-A) | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 | 109.6136 | 1 | 1 | KISH/PW-06 | 0 | 7 | 0 | N-2 | KISH
35 | Package No.-07/ Boro Haor | Hazir Khal | Km | 1.73 | 20.5494 | 0 | 0 | KISH/PW-07 | 0 | 7 | 0 | N-3 | KISH
36 | Package No.-07/ Boro Haor | Karpasha Khal | Km | 1.615 | 26.0781 | 2.16 | 2.16 | KISH/PW-07 | 0 | 7 | 0 | N-3 | KISH
37 | Package No.-07/ Boro Haor | Dampara Khal | Km | 3.6 | 46.8873 | 0.4 | 0.4 | KISH/PW-07 | 0 | 7 | 0 | N-3 | KISH
38 | Package No.-07/ Boro Haor | Baniajan | Km | 6.854 | 130.1184 | 1 | 1 | KISH/PW-07 | 0 | 7 | 0 | N-3 | KISH
39 | Package No.-07/ Boro Haor | Suti Khal | Km | 6.1 | 120.3313 | 1 | 1 | KISH/PW-07 | 0 | 7 | 0 | N-3 | KISH
40 | Package No.-07/ Boro Haor | Digha Nadi | Km | 5.7 | 424.0032 | 0.65 | 1 | KISH/PW-07 | 0 | 7 | 0 | N-3 | KISH
41 | Package No.-07/ Boro Haor | Old Singua | Km | 10.86 | 197.6384 | 0 | 0 | KISH/PW-07 | 0 | 7 | 0 | N-3 | KISH
42 | Package No.-07/ Boro Haor | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 | 35.33 | 0.08 | 0.2 | KISH/PW-07 | 0 | 11 | 0 | N-3 | KISH
43 | Package No.-07/ Boro Haor | Block Road | Km | 0 | 55.74 | 0 | 1 | KISH/PW-07 | 0 | 11 | 0 | N-3 | KISH
44 | Package No.PW-09/Kish/ Boro Haor | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 | 185.76 | 1 | 1 | KISH/PW-09 | 0 | 3 | 0 | N-3 | KISH
45 | Package No.PW-09/Kish/ Boro Haor | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 | 211.88 | 1 | 1 | KISH/PW-09 | 0 | 3 | 0 | N-3 | KISH
46 | Package No.PW-09/Kish/ Boro Haor | Causeway 6.0m wide-1 at Dampara | Nos | 1 | 174.59 | 1 | 1 | KISH/PW-09 | 0 | 5 | 0 | N-3 | KISH
47 | Package No.PW-09/Kish/ Boro Haor | Causeway 4.0m wide-1 at Karpasha | Nos | 1 | 143.6138 | 1 | 1 | KISH/PW-09 | 0 | 5 | 0 | N-3 | KISH
48 | Package No.: PW-10/ Noapara Haor | Causeway 6.0m wide-1 | Nos | 1 | 137.35 | 0 | 0.65 | KISH/PW-10 | 0 | 3 | 0 | N-4 | KISH
49 | Package No.: PW-10/ Noapara Haor | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 | 128.67 | 0.45 | 1 | KISH/PW-10 | 0 | 3 | 0 | N-4 | KISH
50 | Package No.: PW-10/ Noapara Haor | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 | 274.06 | 0.64 | 1 | KISH/PW-10 | 0 | 11 | 0 | N-4 | KISH
51 | Package No.: PW-10/ Noapara Haor | Block Road | Km | 0 | 343.88 | 1 | 1 | KISH/PW-10 | 0 | 11 | 0 | N-4 | KISH
52 | Package No.-11/ Noapara Haor | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 | 274.49 | 0.95 | 1 | KISH/PW-11 | 0 | 3 | 0 | N-4 | KISH
53 | Package No.-11/ Noapara Haor | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 | 557.63 | 0.5 | 1 | KISH/PW-11 | 0 | 11 | 0 | N-4 | KISH
54 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 | 253.8935 | 1 | 1 | KISH/PW-12 | 0 | 3 | 0 | N-4 | KISH
55 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 | 277.0365 | 1 | 1 | KISH/PW-12 | 0 | 3 | 0 | N-4 | KISH
56 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 | 18.397 | 0 | 0 | KISH/PW-12 | 0 | 7 | 0 | N-4 | KISH
57 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 | 4.398 | 1 | 1 | KISH/PW-12 | 0 | 7 | 0 | N-4 | KISH
58 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 | 99.257 | 1 | 1 | KISH/PW-12 | 0 | 7 | 0 | N-4 | KISH
59 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 | 110.6945 | 1 | 1 | KISH/PW-12 | 0 | 7 | 0 | N-4 | KISH
60 | BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 | 167.984 | 1 | 1 | KISH/PW-12 | 0 | 7 | 0 | N-4 | KISH
61 | Package No.-13/ Naogaon Haor (Part-A) | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 | 232.96 | 0.95 | 1 | KISH/PW-13 | 0 | 3 | 0 | N-5 | KISH
62 | Package No.-13/ Naogaon Haor (Part-A) | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 | 193 | 0.95 | 1 | KISH/PW-13 | 0 | 3 | 0 | N-5 | KISH
63 | Package No.-13/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 | 576.67 | 0.4 | 1 | KISH/PW-13 | 0 | 11 | 0 | N-5 | KISH
64 | Package No.-14/ Naogaon Haor (Part-A) | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 | 176.58 | 0.95 | 1 | KISH/PW-14 | 0 | 3 | 0 | N-5 | KISH
65 | Package No.-14/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 | 680.42 | 0.86 | 1 | KISH/PW-14 | 0 | 11 | 0 | N-5 | KISH
66 | Package No.-15/ Naogaon Haor- Part-B | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 | 166.9 | 0 | 0 | KISH/PW-15 | 0 | 3 | 0 | N-5 | KISH
67 | Package No.-15/ Naogaon Haor- Part-B | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 | 616.92 | 1 | 1 | KISH/PW-15 | 0 | 11 | 0 | N-5 | KISH
68 | Package No.-16/ NaogaonHaor-Part-B | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 | 267.88 | 0.85 | 1 | KISH/PW-16 | 0 | 3 | 0 | N-5 | KISH
69 | Package No.-16/ NaogaonHaor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 | 343.32 | 1 | 1 | KISH/PW-16 | 0 | 11 | 0 | N-5 | KISH
70 | Package No.-16/ NaogaonHaor-Part-B | Block Road | Km | 0 | 167.97 | 1 | 1 | KISH/PW-16 | 0 | 11 | 0 | N-5 | KISH
71 | Package No.-17/ Naogaon Haor-Part-B | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 | 348.66 | 1 | 1 | KISH/PW-17 | 0 | 3 | 0 | N-5 | KISH
72 | Package No.-17/ Naogaon Haor-Part-B | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 | 217.5324 | 1 | 1 | KISH/PW-17 | 0 | 3 | 0 | N-5 | KISH
73 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-1 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 0 | N-5 | KISH
74 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-2 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 0 | N-5 | KISH
75 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-3 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 0 | N-5 | KISH
76 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-4 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 0 | N-5 | KISH
77 | Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-5 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 | 0 | 4 | 0 | N-5 | KISH
78 | Package No.-17/ Naogaon Haor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 | 460.54 | 1 | 1 | KISH/PW-17 | 0 | 11 | 0 | N-5 | KISH
79 | Package No.-17/ Naogaon Haor-Part-B | Block Road | Km | 0 | 89.5 | 1 | 1 | KISH/PW-17 | 0 | 11 | 0 | N-5 | 0
80 | Package No.-17/ Naogaon Haor-Part-B | Irrigation Pipe Inlet-1 | Nos | 25 | 274.47 | 1 | 1 | KISH/PW-17 | 0 | 1 | 0 | N-5 | KISH
81 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 | 159.8606 | 0 | 1 | KISH/PW-18 | 0 | 5 | 0 | 0 | KISH
82 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 | 161.4295 | 0.8 | 1 | KISH/PW-18 | 0 | 5 | 0 | 0 | KISH
83 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 | 186.8205 | 1 | 1 | KISH/PW-18 | 0 | 5 | 0 | 0 | KISH
84 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 | 265.5873 | 0.8 | 1 | KISH/PW-18 | 0 | 5 | 0 | 0 | KISH
85 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 | 101.2011 | 0 | 0 | KISH/PW-18 | 0 | 7 | 0 | 0 | KISH
86 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 | 35.7041 | 1 | 1 | KISH/PW-18 | 0 | 7 | 0 | 0 | KISH
87 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 | 17.1427 | 1 | 1 | KISH/PW-18 | 0 | 7 | 0 | 0 | KISH
88 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 | 59.4674 | 1 | 1 | KISH/PW-18 | 0 | 7 | 0 | 0 | KISH
89 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 | 141.516 | 0 | 1 | KISH/PW-18 | 0 | 7 | 0 | 0 | KISH
90 | BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 | 187.0328 | 0 | 1 | KISH/PW-18 | 0 | 7 | 0 | 0 | KISH
91 | BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 | 472.9622 | 0.19 | 1 | KISH/PW-19 | 0 | 7 | 0 | N-5 | KISH
92 | BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 | 374.9638 | 0.25 | 1 | KISH/PW-19 | 0 | 7 | 0 | N-5 | KISH
93 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chitra Khal 4m wide | Nos | 1 | 136.31 | 1 | 1 | KISH/PW-20 | New | 5 | 0 | 0 | KISH
94 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Nabinpur Khal 4m Wide | Nos | 1 | 193.69 | 1 | 1 | KISH/PW-20 | New | 5 | 0 | 0 | KISH
95 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Dipjuri Khal 4m CW | Nos | 1 | 185.03 | 1 | 1 | KISH/PW-20 | New | 5 | 0 | 0 | KISH
96 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Sudhikhal 4m wide CW | Nos | 1 | 136.66 | 1 | 1 | KISH/PW-20 | New | 5 | 0 | 0 | KISH
97 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chhagalia khal sluice | Nos | 1 | 41.0186 | 1 | 1 | KISH/PW-20 | New | 3 | 0 | 0 | KISH
98 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Near nasir sluice | Nos | 1 | 42.7991 | 1 | 1 | KISH/PW-20 | New | 3 | 0 | 0 | KISH
99 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Shingpur khal sluice | Nos | 1 | 41.9704 | 1 | 1 | KISH/PW-20 | New | 3 | 0 | 0 | KISH
100 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Gharu khal sluice | Nos | 1 | 41.9704 | 0.75 | 1 | KISH/PW-20 | New | 3 | 0 | 0 | KISH
101 | BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Irrigation Pipe Inlet 600mm dia | Nos | 36 | 334.27 | 0.57 | 0.57 | KISH/PW-20 | New | 1 | 0 | 0 | KISH
102 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 | 321.3991 | 0.48 | 1 | KISH/PW-21 | New | 3 | 0 | N-6 | KISH
103 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 | 156.6821 | 0.45 | 1 | KISH/PW-21 | New | 3 | 0 | N-6 | KISH
104 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 | 120.5564 | 0 | 1 | KISH/PW-21 | New | 12 | 0 | N-6 | KISH
105 | BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 | 329.1074 | 0 | 1 | KISH/PW-21 | New | 11 | 0 | N-6 | KISH
106 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 | 235.9924 | 0.8 | 0.8 | KISH/PW-22 | 0 | 11 | 0 | N-6 | KISH
107 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 | 18.1492 | 0 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
108 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 | 28.0679 | 1 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
109 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 | 5.8814 | 0 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
110 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 | 8.1389 | 0 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
111 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 | 84.8797 | 0.16 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
112 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 | 11.9047 | 0 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
113 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 | 2.4463 | 0 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
114 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 | 14.6073 | 1 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
115 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 | 4.4592 | 0 | 1 | KISH/PW-22 | 0 | 7 | 0 | N-6 | KISH
116 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 | 195.2169 | 0.15 | 1 | KISH/PW-22 | 0 | 5 | 0 | N-6 | KISH
117 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 | 0 | 4 | 0 | N-6 | KISH
118 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 | 0 | 4 | 0 | N-6 | KISH
119 | BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 | 0 | 4 | 0 | N-6 | KISH
120 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 | 107.4208 | 0.8 | 1 | KISH/PW-23 | New | 11 | 0 | N-7 | KISH
121 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 | 295.5262 | 0.85 | 1 | KISH/PW-23 | New | 3 | 0 | N-7 | KISH
122 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 | 227.0604 | 0.95 | 1 | KISH/PW-23 | New | 3 | 0 | N-7 | KISH
123 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 | 28.5772 | 0 | 0.3 | KISH/PW-23 | New | 7 | 0 | N-7 | KISH
124 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 | 3.8604 | 1 | 1 | KISH/PW-23 | New | 7 | 0 | N-7 | KISH
125 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 | 38.9293 | 1 | 1 | KISH/PW-23 | New | 4 | 0 | N-7 | KISH
126 | BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Irrigation Pipe Inlet 600mm dia | Nos | 4 | 62.862 | 1 | 1 | KISH/PW-23 | New | 1 | 0 | N-7 | KISH
127 | Package No.-24/ Dakshiner Haor. | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 | 1149.1962 | 1 | 1 | KISH/PW-24 | New | 11 | 0 | N-8 | KISH
128 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Regulator 5-Vent-1 | Nos | 1 | 405.9371 | 0.65 | 1 | KISH/PW-25 | New | 3 | 0 | N-8 | KISH
129 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 | 320.0346 | 0.88 | 0.88 | KISH/PW-25 | New | 7 | 0 | N-8 | KISH
130 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Km | 1.65 | 54.4035 | 0.36 | 1 | KISH/PW-25 | New | 7 | 0 | N-8 | KISH
131 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 | 346.4138 | 0 | 0 | KISH/PW-25 | New | 5 | 0 | N-8 | KISH
132 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 | 288.0795 | 0 | 0 | KISH/PW-25 | New | 5 | 0 | N-8 | KISH
133 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 | 189.5297 | 0.65 | 1 | KISH/PW-25 | New | 5 | 0 | N-8 | KISH
134 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Box Sluice-1 | Nos | 1 | 41.8221 | 0 | 0 | KISH/PW-25 | New | 4 | 0 | N-8 | KISH
135 | BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Irrigation Pipe Inlet 600mm dia | Nos | 15 | 118.5673 | 0.86 | 1 | KISH/PW-25 | New | 1 | 0 | N-8 | KISH
136 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 | 22.7161 | 0 | 0 | KISH/PW-26 | New | 11 | 0 | N-9 | KISH
137 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 | 71.5264 | 0 | 0 | KISH/PW-26 | New | 7 | 0 | N-9 | KISH
138 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 | 12.7224 | 0 | 0 | KISH/PW-26 | New | 7 | 0 | N-9 | KISH
139 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 | 16.3878 | 0 | 0 | KISH/PW-26 | New | 7 | 0 | N-9 | KISH
140 | BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 | 367.3183 | 0 | 0 | KISH/PW-26 | New | 7 | 0 | N-9 | KISH
141 | BWDB/Kish/HFMLIP/ PW-27 | phuleshwari | Nos | 1 | 156.62 | 0 | 1 | KISH/PW-27 | New | 3 | 0 | N-9 | KISH
142 | BWDB/Kish/HFMLIP/ PW-27 | Kalna | Nos | 1 | 148 | 0 | 1 | KISH/PW-27 | New | 3 | 0 | N-9 | KISH
143 | BWDB/Kish/HFMLIP/ PW-27 | RCC Box Drainage | Nos | 1 | 41.88 | 0 | 1 | KISH/PW-27 | New | 4 | 0 | N-9 | KISH
144 | BWDB/Kish/HFMLIP/ PW-27 | Causeway | Nos | 1 | 140.87 | 0 | 1 | KISH/PW-27 | New | 5 | 0 | N-9 | KISH
145 | BWDB/Kish/HFMLIP/ PW-27 | Causeway & Drainage | Nos | 1 | 407.31 | 0 | 1 | KISH/PW-27 | New | 5 | 0 | N-9 | KISH
146 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Resectioning of Full embankment from 0.000 to 41.771 | Km | 35.828 | 1132.4847 | 0.85 | 1 | NETR/PW-01 | Rehab | 9 | 0 | R-9 | NETR
147 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Resectioning of Full embankment from 0.911to 11.600 | km | 10.69 | 212.86 | 0.85 | 1 | NETR/PW-01 | Rehab | 9 | 0 | R-11 | NETR
148 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dhalia Khal | Km | 7.37 | 68.3113 | 0 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-9 | NETR
149 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Balai khal | Km | 5.896 | 107.2237 | 0.23 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-9 | NETR
150 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Anda Khal | Km | 7.192 | 215.6843 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
151 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dupikhali Khal part-1 | Km | 3.66 | 106.6825 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
152 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dupikhali Khal part-1 | Km | 5.057 | 112.0192 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
153 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dudhkura Khal | Km | 5.4 | 57.6844 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
154 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | kurikunia Khal | Km | 1.903 | 48.574 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
155 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dighjan Khal | Km | 4.32 | 102.8289 | 0.5 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
156 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Tutnir Khal | Km | 3.15 | 37.9263 | 0 | 0 | NETR/PW-02 | Rehab | 8 | 0 | R-11 | NETR
157 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Kamalpur Khal | Km | 2.98 | 91.9555 | 0.4 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-11 | NETR
158 | BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Resection of Full embankment in Kangsha River Sheme | km | 20.9 | 450.21 | 1 | 1 | NETR/PW-03 | Rehab | 9 | 0 | R-10 | NETR
159 | BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Resection of Submesible Singer Bill | km | 3.56 | 29.21 | 1 | 1 | NETR/PW-03 | Rehab | 10 | 0 | R-11 | NETR
160 | BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Reinstllation of 5-vent Regulator Dampara | No | 1 | 389.57 | 0.95 | 1 | NETR/PW-03 | Rehab | 2 | 0 | R-9 | NETR
161 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Piyan River from 0.075 to 5.00 | Km | 4.925 | 335.3397 | 0.78 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-12 | NETR
162 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Nayori Khal from 0.000 to 7.565 | Km | 7.565 | 158.059 | 1 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-12 | NETR
163 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Feni Khal from 0.000 to 1.903 | Km | 1.903 | 16.0636 | 0 | 0 | NETR/PW-04 | Rehab | 8 | 0 | R-13 | NETR
164 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Jhalokhali from 0.000 to 6.76 | Km | 6.76 | 282.4937 | 1 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-13 | NETR
165 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Putia Khal from 0.000 to 5.235 | Km | 5.235 | 313.3495 | 1 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-13 | NETR
166 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Resectioning of Submersible EMB from 44.600 to 48.650 | Km | 9.75 | 395.62 | 0.82 | 1 | NETR/PW-04 | Rehab | 10 | 0 | R-13 | NETR
167 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of Submesible Emb from Km 6.800 to 24.855 | Km | 3.071 | 57.25 | 0 | 1 | NETR/PW-05 | New | 10 | 0 | N-11 | NETR
168 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Chapri Regulator | Nos | 1 | 242.75 | 0.6 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
169 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Ukra Regulator | Nos | 1 | 286.86 | 0.85 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
170 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Ichamati Regulator | Nos | 1 | 182.66 | 0.85 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
171 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 4-Vent Ichamati Regulator | Nos | 1 | 419.66 | 0.6 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
172 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Narsua River from Km 0.000 to 6.225 | Km | 6.226 | 224.4496 | 1 | 1.1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
173 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Ukra Khal from Km 0.111 to 2.043 Km | Km | 1.933 | 118.7745 | 1 | 1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
174 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Chapri Khal from Km 0.280 to 2.590 Km | Km | 2.31 | 88.1515 | 1 | 1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
175 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Ichamati Khal from Km 0.072 to 1.250 Km | Km | 1.178 | 51.0575 | 1 | 1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
176 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Boilara Khal from Km 8.550 to 8.900 Km | Km | 0.35 | 28.0376 | 0 | 0 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
177 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of BoX drainage ountlet at Bhadera | Nos | 1 | 42.25 | 1 | 1 | NETR/PW-06 | New | 4 | 0 | N-11 | NETR
178 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of BoX drainage ountlet at Moheswar Khal | Nos | 1 | 42.25 | 1 | 1 | NETR/PW-06 | New | 4 | 0 | N-11 | NETR
179 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of Irrigation Inlet | Nos | 2 | 16.92 | 0 | 0 | NETR/PW-06 | New | 1 | 0 | N-11 | NETR
180 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehbilation of existing Regulator | Nos | 1 | 19.43 | 1 | 1 | NETR/PW-06 | New | 12 | 0 | N-11 | NETR
181 | BWDB/Netra/HFMLIP/PW-07 Ganesh Haor | Reexcavation of Kangsha river | Km | 15 | 654.8026 | 1 | 1 | NETR/PW-07 | New | 7 | 0 | N-12 | NETR
182 | BWDB/Netra/HFMLIP/PW-07 Ganesh Haor | Reexcavation of Gumai river | Km | 9 | 238.8741 | 1 | 0 | NETR/PW-07 | New | 7 | 0 | N-12 | NETR
183 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Agunia Regulator | No | 1 | 289.74 | 0.6 | 1 | NETR/PW-08 | New | 3 | 0 | N-14 | NETR
184 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Dharam Regulator | No | 1 | 239.88 | 0.25 | 1 | NETR/PW-08 | New | 3 | 0 | N-14 | NETR
185 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-1 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
186 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-2 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
187 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-3 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
188 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-4 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
189 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-5 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
190 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Inlet-1 | No | 1 | 12.18 | 0 | 1 | NETR/PW-08 | New | 1 | 0 | N-14 | NETR
191 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Inlet-2 | No | 1 | 12.18 | 0 | 1 | NETR/PW-08 | New | 1 | 0 | N-14 | NETR
192 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Inlet-3 | No | 1 | 12.18 | 0 | 1 | NETR/PW-08 | New | 1 | 0 | N-14 | NETR
193 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Resectioning of Embankment along the left bank of the Bashira River inbwt 2.420 to 9.760 | km | 7 | 151.385 | 1 | 1 | HOBI/PW-01 | Rehab | 10 | 0 | R-8 | HOBI
194 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | construction of new Embankment along the left bank of bitangal khal inbwt 10.000 to 17.000 | km | 7 | 151.385 | 1 | 1 | HOBI/PW-01 | Rehab | 10 | 0 | R-8 | HOBI
195 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Reexcavation of Bashira River 0.000 to 20.000 | km | 17.4 | 732.6 | 0.8 | 1 | HOBI/PW-01 | Rehab | 8 | 0 | R-8 | HOBI
196 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Reexcavation of Matikatakahl from 0.000 to Km 2.295 | km | 2.925 | 99.9 | 1 | 1 | HOBI/PW-01 | Rehab | 8 | 0 | R-8 | HOBI
197 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Construction of 2-vent Regulator | nos. | 1 | 208 | 0 | 1 | HOBI/PW-01 | Rehab | 3 | 0 | R-8 | HOBI
198 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Construction of 4.00m causeway | nos. | 1 | 178.13 | 1 | 1 | HOBI/PW-01 | Rehab | 5 | 0 | R-8 | HOBI
199 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Resctioning of Submersible Embankment from 0.000 to 26.000 at Left Bank of Kushiyara | Km | 7.23 | 274.56 | 1 | 1 | HOBI/PW-02 | Rehab | 10 | 0 | R-7 | HOBI
200 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of Retired Embankment in between 0.000 to 26.500 | Km | 6.894 | 225.46 | 1 | 1 | HOBI/PW-02 | Rehab | 10 | 0 | R-7 | HOBI
201 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Resctioning of Submersible Embankment from 0.000 to 16.02 at Right Bank of Khoai | Km | 16.02 | 318.42 | 1 | 1 | HOBI/PW-02 | Rehab | 10 | 0 | R-7 | HOBI
202 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of New Embankment from Km 22.850 to 31.210 | Km | 8.36 | 149.54 | 1 | 1 | HOBI/PW-02 | Rehab | 10 | 0 | R-7 | HOBI
203 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Kairdhala Khal from 0.000 to 1.6950 km | Km | 1.695 | 132.8661 | 0 | 0 | HOBI/PW-02 | Rehab | 8 | 0 | R-7 | HOBI
204 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Satmukha Khal from 0.000 to 1.790 km | Km | 1.79 | 53.0475 | 1 | 1 | HOBI/PW-02 | Rehab | 8 | 0 | R-7 | HOBI
205 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Singer Beel Khal from 0.000 to 2.720 km | Km | 2.72 | 29.975 | 1 | 1 | HOBI/PW-02 | Rehab | 8 | 0 | R-7 | HOBI
206 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of Dairar Khal Causeway 6-m width Causeway | nos. | 1 | 168.38 | 0.95 | 1 | HOBI/PW-02 | Rehab | 5 | 0 | R-7 | HOBI
207 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Ikrampur CW-6M | nos. | 1 | 168.38 | 0.1 | 1 | HOBI/PW-02 | 0 | 5 | 0 | R-7 | HOBI
208 | BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Submesible Embankment from 31.600 to 81.740 | km | 23.815 | 638.85 | 0.5 | 1 | HOBI/PW-04 | New | 11 | 0 | N-10 | HOBI
209 | BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Block road | km | 2 | 507.95 | 0.78 | 1 | HOBI/PW-04 | New | 11 | 0 | N-10 | HOBI
210 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Boranbil khal Regulator (1-vent) | nos. | 1 | 141.3235 | 0 | 0.75 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
211 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Chandakhali khal Regulator(1-vent) | nos. | 1 | 154.0746 | 0 | 0.75 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
212 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Chargaowdair khal Regulator(1-vent) | nos. | 1 | 151.0703 | 0.3 | 1 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
213 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Chhoto Katari khal Regulator(1-vent) | nos. | 1 | 143.8109 | 0.1 | 0.7 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
214 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Islampur khal Regulator (1-vent) | nos. | 1 | 155.6933 | 0.8 | 1 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
215 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Tetter Drepasionkhal Regulator(2-vent) | nos. | 1 | 216.7515 | 0 | 0.7 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
216 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Soaybeel khal Regulator (5-vent) | nos. | 1 | 353.8204 | 1 | 1 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
217 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Bibiyana 6.0m Causeway | nos. | 1 | 415.5317 | 1 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
218 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Old kushiyana 6.0m Causeway | nos. | 1 | 373.3459 | 0.85 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
219 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Ratna River 4.0m Causeway | nos. | 1 | 143.1604 | 1 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
220 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Rukway 4.0m Causeway | nos. | 1 | 165.1831 | 0.85 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
221 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX1 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
222 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX2 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
223 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX3 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
224 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX4 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
225 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX5 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
226 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX6 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
227 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX7 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
228 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX8 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
229 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX9 | nos. | 1 | 37.0833 | 0.4 | 0.4 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
230 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Irrigation Inlet | nos. | 15 | 150.7581 | 0.55 | 1 | HOBI/PW-06 | New | 1 | 0 | N-10 | HOBI
231 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chargaowdair khal | km | 3.036 | 45.4209 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
232 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chotokatari Khal | km | 3.264 | 61.408 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
233 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Salukadhar Khal | km | 2.428 | 67.6663 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
234 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Islampur khal | km | 0.634 | 25.7065 | 0 | 0 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
235 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Soyabeel Khal | km | 3.285 | 139.5951 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
236 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chatal Beel Khal | km | 5.2176 | 103.126 | 0 | 0 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
237 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Rajendrapur Khal | km | 4.327 | 115.1915 | 0.45 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
238 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Purohogun Khal | km | 2.428 | 65.549 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
239 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Sutki River | km | 4.5 | 145.977 | 0.57 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
240 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Ratna River | km | 7.51 | 137.4972 | 0.53 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
241 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Submersible Embankment between km10.600 to 49.426 total 33.849km | km | 33.849 | 867.33 | 0.58 | 1 | SUNM/PW-01 | New | 11 | 0 | N-14 | SUNM
242 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Dariabaz Khal | km | 1.48 | 18.8287 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
243 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Juriganga Khal | km | 1.438 | 32.0288 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
244 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Purukania Khal | km | 1.56 | 41.0489 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
245 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Muktakhai River | Km | 3.2 | 176.4745 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
246 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-1 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
247 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-2 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
248 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-3 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
249 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-4 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
250 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-5 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
251 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-6 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
252 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-7 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
253 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Irrigation Inlet | Nos | 9 | 10.66 | 0 | 1 | SUNM/PW-01 | New | 1 | 0 | 0 | SUNM
254 | BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Division-2) | Re-excavation of Piyan River from km 19.000 to km 55.575 total 36.575km | Km | 36.575 | 1193.75 | 0.8 | 1 | SUNM/PW-02 | New | 7 | 0 | N-14 | SUNM
255 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | 1 vent (1.50m X 1.80m)-1 | Nos | 1 | 183.3461 | 0.6 | 1 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
256 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 308.0018 | 0.6 | 1 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
257 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-1 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
258 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-2 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
259 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-3 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
260 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-4 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
261 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-5 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
262 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 6.0m wide-1 | Nos | 1 | 279.3507 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
263 | BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Beel (Division-1) | Construction of Submersible embankment-34.94km | Km | 34.94 | 1564.32 | 0.98 | 1 | SUNM/PW-04 | New | 11 | 0 | N-12 | SUNM
264 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Dahar 4vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 283.3851 | 0.5 | 1 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
265 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Deola 2 vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 267.8703 | 0.4 | 1 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
266 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Manani Causeway 6.0m wide-1 | Nos | 1 | 225.81 | 0 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
267 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Dahar Causeway 4.0m wide-1 | Nos | 1 | 301.6651 | 0.4 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
268 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Daharagang Causeway 4.0m wide-2 | Nos | 1 | 187.8663 | 0.8 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
269 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Chandrasona Causeway 4.0m wide-3 | Nos | 1 | 191.3901 | 0.8 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
270 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Khurma Khal | km | 7.18 | 36.0889 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
271 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Udani Khal | km | 3.828 | 54.377 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
272 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Deola Khal | km | 1.965 | 70.1082 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
273 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Shaitan Khal | km | 13.8 | 565.0549 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
274 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Banni Khal2 | km | 2.913 | 36.3507 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
275 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Rui Beel Khal | km | 3.414 | 62.7308 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
276 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dahar Gang | km | 6.832 | 176.7629 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
277 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Gobra Khal | km | 2.893 | 45.6733 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
278 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Banni Khal1 | km | 2.622 | 39.8891 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
279 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dagar Khal | km | 2.665 | 15.5116 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
280 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Rajpur Khal | km | 3.595 | 37.8562 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
281 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Kolma Khal | km | 2.204 | 17.6969 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
282 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Agunia khal | km | 7.611 | 157.1547 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
283 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Kakura Khal | km | 1.305 | 32.5728 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
284 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dharam Beel Khal | km | 1.105 | 37.7084 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
285 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Bararia Khal | km | 2.11 | 14.6001 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
286 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Const. of Box Drainage Outlet-1 | Nos | 1 | 45.13 | 0 | 1 | SUNM/PW-06 | New | 4 | 0 | N-12 | SUNM
287 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Irrigation Inlet | Nos | 12 | 131.38 | 0 | 1 | SUNM/PW-06 | New | 1 | 0 | N-12 | SUNM

## Package_Name
| sl | Package_No | Payment_30_06_2020
0 | 1 | KISH/PW-01 | 51.09
1 | 2 | KISH/PW-02 | 347.71
2 | 3 | KISH/PW-03 | 625.93
3 | 4 | KISH/PW-04 | 714.69
4 | 5 | KISH/PW-05 | 575.15
5 | 6 | KISH/PW-06 | 837.25
6 | 7 | KISH/PW-07 | 565.07
7 | 9 | KISH/PW-09 | 712.33
8 | 10 | KISH/PW-10 | 409.68
9 | 11 | KISH/PW-11 | 522.86
10 | 12 | KISH/PW-12 | 705.59
11 | 13 | KISH/PW-13 | 647.2
12 | 14 | KISH/PW-14 | 806.89
13 | 15 | KISH/PW-15 | 333.94
14 | 16 | KISH/PW-16 | 721.62
15 | 17 | KISH/PW-17 | 1451.95
16 | 18 | KISH/PW-18 | 711.02
17 | 19 | KISH/PW-19 | 331.35
18 | 20 | KISH/PW-20 | 501.12
19 | 21 | KISH/PW-21 | 268.24
20 | 22 | KISH/PW-22 | 281.05
21 | 23 | KISH/PW-23 | 720.33
22 | 24 | KISH/PW-24 | 890.42
23 | 25 | KISH/PW-25 | 749.37
24 | 26 | KISH/PW-26 | 501.12
25 | 27 | KISH/PW-27 | 0
26 | 39 | NETR/PW-01 | 817.97
27 | 40 | NETR/PW-02 | 475.85
28 | 41 | NETR/PW-03 | 712.73
29 | 42 | NETR/PW-04 | 844.17
30 | 43 | NETR/PW-05 | 635.34
31 | 44 | NETR/PW-06 | 375.82
32 | 45 | NETR/PW-07 | 567.71
33 | 46 | NETR/PW-08 | 134.16
34 | 47 | SUNM/PW-01 | 913.55
35 | 48 | SUNM/PW-02 | 926.3
36 | 49 | SUNM/PW-03 | 511.73
37 | 50 | SUNM/PW-04 | 1521.41
38 | 51 | SUNM/PW-05 | 1061.82
39 | 52 | SUNM/PW-06 | 1268.067
40 | 54 | HOBI/PW-01 | 938.27
41 | 55 | HOBI/PW-02 | 1079.52
42 | 57 | HOBI/PW-04 | 655.94
43 | 58 | HOBI/PW-05 | 307.8
44 | 59 | HOBI/PW-06 | 1094.31
45 | 60 | HOBI/PW-07 | 667.67

## Value_of_Work_Done
| Package | Structure Code | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | VDW_30_06_2020 | VDW_30_06_2021 | Work_Done_20_21 | Payment_30_06_2020
0 | KISH/PW-01 | 8 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 | 40.94 | 1 | 1 | 40.94 | 40.94 | 0 | 0
1 | KISH/PW-01 | 8 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 | 35.88 | 1 | 1 | 35.88 | 35.88 | 0 | 0
2 | KISH/PW-01 | 8 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 | 19.18 | 0 | 1 | 0 | 19.18 | 19.18 | 0
3 | KISH/PW-01 | 8 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 | 309.8 | 0 | 1 | 0 | 309.8 | 309.8 | 0
4 | KISH/PW-01 | 8 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 | 45.95 | 0 | 1 | 0 | 45.95 | 45.95 | 0
5 | KISH/PW-01 | 2 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 | 44.79 | 0 | 1 | 0 | 44.79 | 44.79 | 0
6 | KISH/PW-02 | 3 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 155.5114 | 1 | 1 | 155.5114 | 155.5114 | 0 | 0
7 | KISH/PW-02 | 7 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 | 31.9576 | 1 | 1 | 31.9576 | 31.9576 | 0 | 0
8 | KISH/PW-02 | 7 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 | 93.4351 | 1 | 1 | 93.4351 | 93.4351 | 0 | 0
9 | KISH/PW-02 | 7 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 | 52.1722 | 1 | 1 | 52.1722 | 52.1722 | 0 | 0
10 | KISH/PW-02 | 7 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 | 16.201 | 1 | 1 | 16.201 | 16.201 | 0 | 0
11 | KISH/PW-02 | 7 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 | 68.8599 | 1 | 1 | 68.8599 | 68.8599 | 0 | 0
12 | KISH/PW-02 | 11 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 | 14.8109 | 1 | 1 | 14.8109 | 14.8109 | 0 | 0
13 | KISH/PW-03 | 3 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 | 155.5114 | 1 | 1 | 155.5114 | 155.5114 | 0 | 0
14 | KISH/PW-03 | 11 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 | 247.1255 | 1 | 1 | 247.1255 | 247.1255 | 0 | 0
15 | KISH/PW-03 | 11 | Block Road | Km | 0 | 286.8206 | 1 | 1 | 286.8206 | 286.8206 | 0 | 0
16 | KISH/PW-04 | 3 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 | 97.9579 | 1 | 1 | 97.9579 | 97.9579 | 0 | 0
17 | KISH/PW-04 | 3 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 | 97.9579 | 1 | 1 | 97.9579 | 97.9579 | 0 | 0
18 | KISH/PW-04 | 3 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 | 257.73 | 1 | 1 | 257.73 | 257.73 | 0 | 0
19 | KISH/PW-04 | 11 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 | 256.8713 | 1 | 1 | 256.8713 | 256.8713 | 0 | 0
20 | KISH/PW-05 | 3 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 | 190.22 | 1 | 1 | 190.22 | 190.22 | 0 | 0
21 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 | 35.282 | 1 | 1 | 35.282 | 35.282 | 0 | 0
22 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 | 4.0969 | 1 | 1 | 4.0969 | 4.0969 | 0 | 0
23 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 | 8.7693 | 0 | 1 | 0 | 8.7693 | 8.7693 | 0
24 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 | 156.8227 | 1 | 1 | 156.8227 | 156.8227 | 0 | 0
25 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 | 28.9482 | 1 | 1 | 28.9482 | 28.9482 | 0 | 0
26 | KISH/PW-05 | 11 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 | 17.8983 | 1 | 1 | 17.8983 | 17.8983 | 0 | 0
27 | KISH/PW-05 | 11 | Block Road | Km | 12.214 | 325.54 | 1 | 1 | 325.54 | 325.54 | 0 | 0
28 | KISH/PW-06 | 3 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 | 227.8819 | 1 | 1 | 227.8819 | 227.8819 | 0 | 0
29 | KISH/PW-06 | 7 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 | 67.5613 | 1 | 1 | 67.5613 | 67.5613 | 0 | 0
30 | KISH/PW-06 | 7 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 | 99.5765 | 1 | 1 | 99.5765 | 99.5765 | 0 | 0
31 | KISH/PW-06 | 7 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 | 28.0877 | 1 | 1 | 28.0877 | 28.0877 | 0 | 0
32 | KISH/PW-06 | 7 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 | 16.0154 | 1 | 1 | 16.0154 | 16.0154 | 0 | 0
33 | KISH/PW-06 | 7 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 | 225.9517 | 1 | 1 | 225.9517 | 225.9517 | 0 | 0
34 | KISH/PW-06 | 7 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 | 109.6136 | 1 | 1 | 109.6136 | 109.6136 | 0 | 0
35 | KISH/PW-07 | 7 | Hazir Khal | Km | 1.73 | 20.5494 | 0 | 0 | 0 | 0 | 0 | 0
36 | KISH/PW-07 | 7 | Karpasha Khal | Km | 1.615 | 26.0781 | 2.16 | 2.16 | 56.3287 | 56.3287 | 0 | 0
37 | KISH/PW-07 | 7 | Dampara Khal | Km | 3.6 | 46.8873 | 0.4 | 0.4 | 18.7549 | 18.7549 | 0 | 0
38 | KISH/PW-07 | 7 | Baniajan | Km | 6.854 | 130.1184 | 1 | 1 | 130.1184 | 130.1184 | 0 | 0
39 | KISH/PW-07 | 7 | Suti Khal | Km | 6.1 | 120.3313 | 1 | 1 | 120.3313 | 120.3313 | 0 | 0
40 | KISH/PW-07 | 7 | Digha Nadi | Km | 5.7 | 424.0032 | 0.65 | 1 | 275.6021 | 424.0032 | 148.4011 | 0
41 | KISH/PW-07 | 7 | Old Singua | Km | 10.86 | 197.6384 | 0 | 0 | 0 | 0 | 0 | 0
42 | KISH/PW-07 | 11 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 | 35.33 | 0.08 | 0.2 | 2.8264 | 7.066 | 4.2396 | 0
43 | KISH/PW-07 | 11 | Block Road | Km | 0 | 55.74 | 0 | 1 | 0 | 55.74 | 55.74 | 0
44 | KISH/PW-09 | 3 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 | 185.76 | 1 | 1 | 185.76 | 185.76 | 0 | 0
45 | KISH/PW-09 | 3 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 | 211.88 | 1 | 1 | 211.88 | 211.88 | 0 | 0
46 | KISH/PW-09 | 5 | Causeway 6.0m wide-1 at Dampara | Nos | 1 | 174.59 | 1 | 1 | 174.59 | 174.59 | 0 | 0
47 | KISH/PW-09 | 5 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 | 143.6138 | 1 | 1 | 143.6138 | 143.6138 | 0 | 0
48 | KISH/PW-10 | 3 | Causeway 6.0m wide-1 | Nos | 1 | 137.35 | 0 | 0.65 | 0 | 89.2775 | 89.2775 | 0
49 | KISH/PW-10 | 3 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 | 128.67 | 0.45 | 1 | 57.9015 | 128.67 | 70.7685 | 0
50 | KISH/PW-10 | 11 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 | 274.06 | 0.64 | 1 | 175.3984 | 274.06 | 98.6616 | 0
51 | KISH/PW-10 | 11 | Block Road | Km | 0 | 343.88 | 1 | 1 | 343.88 | 343.88 | 0 | 0
52 | KISH/PW-11 | 3 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 | 274.49 | 0.95 | 1 | 260.7655 | 274.49 | 13.7245 | 0
53 | KISH/PW-11 | 11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 | 557.63 | 0.5 | 1 | 278.815 | 557.63 | 278.815 | 0
54 | KISH/PW-12 | 3 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 | 253.8935 | 1 | 1 | 253.8935 | 253.8935 | 0 | 0
55 | KISH/PW-12 | 3 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 | 277.0365 | 1 | 1 | 277.0365 | 277.0365 | 0 | 0
56 | KISH/PW-12 | 7 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 | 18.397 | 0 | 0 | 0 | 0 | 0 | 0
57 | KISH/PW-12 | 7 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 | 4.398 | 1 | 1 | 4.398 | 4.398 | 0 | 0
58 | KISH/PW-12 | 7 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 | 99.257 | 1 | 1 | 99.257 | 99.257 | 0 | 0
59 | KISH/PW-12 | 7 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 | 110.6945 | 1 | 1 | 110.6945 | 110.6945 | 0 | 0
60 | KISH/PW-12 | 7 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 | 167.984 | 1 | 1 | 167.984 | 167.984 | 0 | 0
61 | KISH/PW-13 | 3 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 | 232.96 | 0.95 | 1 | 221.312 | 232.96 | 11.648 | 0
62 | KISH/PW-13 | 3 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 | 193 | 0.95 | 1 | 183.35 | 193 | 9.65 | 0
63 | KISH/PW-13 | 11 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 | 576.67 | 0.4 | 1 | 230.668 | 576.67 | 346.002 | 0
64 | KISH/PW-14 | 3 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 | 176.58 | 0.95 | 1 | 167.751 | 176.58 | 8.829 | 0
65 | KISH/PW-14 | 11 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 | 680.42 | 0.86 | 1 | 585.1612 | 680.42 | 95.2588 | 0
66 | KISH/PW-15 | 3 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 | 166.9 | 0 | 0 | 0 | 0 | 0 | 0
67 | KISH/PW-15 | 11 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 | 616.92 | 1 | 1 | 616.92 | 616.92 | 0 | 0
68 | KISH/PW-16 | 3 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 | 267.88 | 0.85 | 1 | 227.698 | 267.88 | 40.182 | 0
69 | KISH/PW-16 | 11 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 | 343.32 | 1 | 1 | 343.32 | 343.32 | 0 | 0
70 | KISH/PW-16 | 11 | Block Road | Km | 0 | 167.97 | 1 | 1 | 167.97 | 167.97 | 0 | 0
71 | KISH/PW-17 | 3 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 | 348.66 | 1 | 1 | 348.66 | 348.66 | 0 | 0
72 | KISH/PW-17 | 3 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 | 217.5324 | 1 | 1 | 217.5324 | 217.5324 | 0 | 0
73 | KISH/PW-17 | 4 | Box Drainage Outlet-1 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
74 | KISH/PW-17 | 4 | Box Drainage Outlet-2 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
75 | KISH/PW-17 | 4 | Box Drainage Outlet-3 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
76 | KISH/PW-17 | 4 | Box Drainage Outlet-4 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
77 | KISH/PW-17 | 4 | Box Drainage Outlet-5 | Nos | 1 | 35.4887 | 1 | 1 | 35.4887 | 35.4887 | 0 | 0
78 | KISH/PW-17 | 11 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 | 460.54 | 1 | 1 | 460.54 | 460.54 | 0 | 0
79 | KISH/PW-17 | 11 | Block Road | Km | 0 | 89.5 | 1 | 1 | 89.5 | 89.5 | 0 | 0
80 | KISH/PW-17 | 1 | Irrigation Pipe Inlet-1 | Nos | 25 | 274.47 | 1 | 1 | 274.47 | 274.47 | 0 | 0
81 | KISH/PW-18 | 5 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 | 159.8606 | 0 | 1 | 0 | 159.8606 | 159.8606 | 0
82 | KISH/PW-18 | 5 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 | 161.4295 | 0.8 | 1 | 129.1436 | 161.4295 | 32.2859 | 0
83 | KISH/PW-18 | 5 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 | 186.8205 | 1 | 1 | 186.8205 | 186.8205 | 0 | 0
84 | KISH/PW-18 | 5 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 | 265.5873 | 0.8 | 1 | 212.4699 | 265.5873 | 53.1175 | 0
85 | KISH/PW-18 | 7 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 | 101.2011 | 0 | 0 | 0 | 0 | 0 | 0
86 | KISH/PW-18 | 7 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 | 35.7041 | 1 | 1 | 35.7041 | 35.7041 | 0 | 0
87 | KISH/PW-18 | 7 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 | 17.1427 | 1 | 1 | 17.1427 | 17.1427 | 0 | 0
88 | KISH/PW-18 | 7 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 | 59.4674 | 1 | 1 | 59.4674 | 59.4674 | 0 | 0
89 | KISH/PW-18 | 7 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 | 141.516 | 0 | 1 | 0 | 141.516 | 141.516 | 0
90 | KISH/PW-18 | 7 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 | 187.0328 | 0 | 1 | 0 | 187.0328 | 187.0328 | 0
91 | KISH/PW-19 | 7 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 | 472.9622 | 0.19 | 1 | 89.8628 | 472.9622 | 383.0994 | 0
92 | KISH/PW-19 | 7 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 | 374.9638 | 0.25 | 1 | 93.7409 | 374.9638 | 281.2228 | 0
93 | KISH/PW-20 | 5 | Chitra Khal 4m wide | Nos | 1 | 136.31 | 1 | 1 | 136.31 | 136.31 | 0 | 0
94 | KISH/PW-20 | 5 | Nabinpur Khal 4m Wide | Nos | 1 | 193.69 | 1 | 1 | 193.69 | 193.69 | 0 | 0
95 | KISH/PW-20 | 5 | Dipjuri Khal 4m CW | Nos | 1 | 185.03 | 1 | 1 | 185.03 | 185.03 | 0 | 0
96 | KISH/PW-20 | 5 | Sudhikhal 4m wide CW | Nos | 1 | 136.66 | 1 | 1 | 136.66 | 136.66 | 0 | 0
97 | KISH/PW-20 | 3 | Chhagalia khal sluice | Nos | 1 | 41.0186 | 1 | 1 | 41.0186 | 41.0186 | 0 | 0
98 | KISH/PW-20 | 3 | Near nasir sluice | Nos | 1 | 42.7991 | 1 | 1 | 42.7991 | 42.7991 | 0 | 0
99 | KISH/PW-20 | 3 | Shingpur khal sluice | Nos | 1 | 41.9704 | 1 | 1 | 41.9704 | 41.9704 | 0 | 0
100 | KISH/PW-20 | 3 | Gharu khal sluice | Nos | 1 | 41.9704 | 0.75 | 1 | 31.4778 | 41.9704 | 10.4926 | 0
101 | KISH/PW-20 | 1 | Irrigation Pipe Inlet 600mm dia | Nos | 36 | 334.27 | 0.57 | 0.57 | 190.5339 | 190.5339 | 0 | 0
102 | KISH/PW-21 | 3 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 | 321.3991 | 0.48 | 1 | 154.2716 | 321.3991 | 167.1275 | 0
103 | KISH/PW-21 | 3 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 | 156.6821 | 0.45 | 1 | 70.5069 | 156.6821 | 86.1751 | 0
104 | KISH/PW-21 | 12 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 | 120.5564 | 0 | 1 | 0 | 120.5564 | 120.5564 | 0
105 | KISH/PW-21 | 11 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 | 329.1074 | 0 | 1 | 0 | 329.1074 | 329.1074 | 0
106 | KISH/PW-22 | 11 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 | 235.9924 | 0.8 | 0.8 | 188.7939 | 188.7939 | 0 | 0
107 | KISH/PW-22 | 7 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 | 18.1492 | 0 | 1 | 0 | 18.1492 | 18.1492 | 0
108 | KISH/PW-22 | 7 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 | 28.0679 | 1 | 1 | 28.0679 | 28.0679 | 0 | 0
109 | KISH/PW-22 | 7 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 | 5.8814 | 0 | 1 | 0 | 5.8814 | 5.8814 | 0
110 | KISH/PW-22 | 7 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 | 8.1389 | 0 | 1 | 0 | 8.1389 | 8.1389 | 0
111 | KISH/PW-22 | 7 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 | 84.8797 | 0.16 | 1 | 13.5808 | 84.8797 | 71.299 | 0
112 | KISH/PW-22 | 7 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 | 11.9047 | 0 | 1 | 0 | 11.9047 | 11.9047 | 0
113 | KISH/PW-22 | 7 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 | 2.4463 | 0 | 1 | 0 | 2.4463 | 2.4463 | 0
114 | KISH/PW-22 | 7 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 | 14.6073 | 1 | 1 | 14.6073 | 14.6073 | 0 | 0
115 | KISH/PW-22 | 7 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 | 4.4592 | 0 | 1 | 0 | 4.4592 | 4.4592 | 0
116 | KISH/PW-22 | 5 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 | 195.2169 | 0.15 | 1 | 29.2825 | 195.2169 | 165.9344 | 0
117 | KISH/PW-22 | 4 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 | 36.662 | 0 | 1 | 0 | 36.662 | 36.662 | 0
118 | KISH/PW-22 | 4 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 | 36.662 | 0 | 1 | 0 | 36.662 | 36.662 | 0
119 | KISH/PW-22 | 4 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 | 36.662 | 0 | 1 | 0 | 36.662 | 36.662 | 0
120 | KISH/PW-23 | 11 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 | 107.4208 | 0.8 | 1 | 85.9367 | 107.4208 | 21.4842 | 0
121 | KISH/PW-23 | 3 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 | 295.5262 | 0.85 | 1 | 251.1973 | 295.5262 | 44.3289 | 0
122 | KISH/PW-23 | 3 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 | 227.0604 | 0.95 | 1 | 215.7073 | 227.0604 | 11.353 | 0
123 | KISH/PW-23 | 7 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 | 28.5772 | 0 | 0.3 | 0 | 8.5732 | 8.5732 | 0
124 | KISH/PW-23 | 7 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 | 3.8604 | 1 | 1 | 3.8604 | 3.8604 | 0 | 0
125 | KISH/PW-23 | 4 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 | 38.9293 | 1 | 1 | 38.9293 | 38.9293 | 0 | 0
126 | KISH/PW-23 | 1 | Irrigation Pipe Inlet 600mm dia | Nos | 4 | 62.862 | 1 | 1 | 62.862 | 62.862 | 0 | 0
127 | KISH/PW-24 | 11 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 | 1149.1962 | 1 | 1 | 1149.1962 | 1149.1962 | 0 | 0
128 | KISH/PW-25 | 3 | Regulator 5-Vent-1 | Nos | 1 | 405.9371 | 0.65 | 1 | 263.8591 | 405.9371 | 142.078 | 0
129 | KISH/PW-25 | 7 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 | 320.0346 | 0.88 | 0.88 | 281.6304 | 281.6304 | 0 | 0
130 | KISH/PW-25 | 7 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Km | 1.65 | 54.4035 | 0.36 | 1 | 19.5853 | 54.4035 | 34.8183 | 0
131 | KISH/PW-25 | 5 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 | 346.4138 | 0 | 0 | 0 | 0 | 0 | 0
132 | KISH/PW-25 | 5 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 | 288.0795 | 0 | 0 | 0 | 0 | 0 | 0
133 | KISH/PW-25 | 5 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 | 189.5297 | 0.65 | 1 | 123.1943 | 189.5297 | 66.3354 | 0
134 | KISH/PW-25 | 4 | Box Sluice-1 | Nos | 1 | 41.8221 | 0 | 0 | 0 | 0 | 0 | 0
135 | KISH/PW-25 | 1 | Irrigation Pipe Inlet 600mm dia | Nos | 15 | 118.5673 | 0.86 | 1 | 101.9679 | 118.5673 | 16.5994 | 0
136 | KISH/PW-26 | 11 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 | 22.7161 | 0 | 0 | 0 | 0 | 0 | 0
137 | KISH/PW-26 | 7 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 | 71.5264 | 0 | 0 | 0 | 0 | 0 | 0
138 | KISH/PW-26 | 7 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 | 12.7224 | 0 | 0 | 0 | 0 | 0 | 0
139 | KISH/PW-26 | 7 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 | 16.3878 | 0 | 0 | 0 | 0 | 0 | 0
140 | KISH/PW-26 | 7 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 | 367.3183 | 0 | 0 | 0 | 0 | 0 | 0
141 | KISH/PW-27 | 3 | phuleshwari | Nos | 1 | 156.62 | 0 | 1 | 0 | 156.62 | 156.62 | 0
142 | KISH/PW-27 | 3 | Kalna | Nos | 1 | 148 | 0 | 1 | 0 | 148 | 148 | 0
143 | KISH/PW-27 | 4 | RCC Box Drainage | Nos | 1 | 41.88 | 0 | 1 | 0 | 41.88 | 41.88 | 0
144 | KISH/PW-27 | 5 | Causeway | Nos | 1 | 140.87 | 0 | 1 | 0 | 140.87 | 140.87 | 0
145 | KISH/PW-27 | 5 | Causeway & Drainage | Nos | 1 | 407.31 | 0 | 1 | 0 | 407.31 | 407.31 | 0
146 | NETR/PW-01 | 9 | Resectioning of Full embankment from 0.000 to 41.771 | Km | 35.828 | 1132.4847 | 0.85 | 1 | 962.612 | 1132.4847 | 169.8727 | 0
147 | NETR/PW-01 | 9 | Resectioning of Full embankment from 0.911to 11.600 | km | 10.69 | 212.86 | 0.85 | 1 | 180.931 | 212.86 | 31.929 | 0
148 | NETR/PW-02 | 8 | Dhalia Khal | Km | 7.37 | 68.3113 | 0 | 1 | 0 | 68.3113 | 68.3113 | 0
149 | NETR/PW-02 | 8 | Balai khal | Km | 5.896 | 107.2237 | 0.23 | 1 | 24.6614 | 107.2237 | 82.5622 | 0
150 | NETR/PW-02 | 8 | Anda Khal | Km | 7.192 | 215.6843 | 1 | 1 | 215.6843 | 215.6843 | 0 | 0
151 | NETR/PW-02 | 8 | Dupikhali Khal part-1 | Km | 3.66 | 106.6825 | 1 | 1 | 106.6825 | 106.6825 | 0 | 0
152 | NETR/PW-02 | 8 | Dupikhali Khal part-1 | Km | 5.057 | 112.0192 | 1 | 1 | 112.0192 | 112.0192 | 0 | 0
153 | NETR/PW-02 | 8 | Dudhkura Khal | Km | 5.4 | 57.6844 | 1 | 1 | 57.6844 | 57.6844 | 0 | 0
154 | NETR/PW-02 | 8 | kurikunia Khal | Km | 1.903 | 48.574 | 1 | 1 | 48.574 | 48.574 | 0 | 0
155 | NETR/PW-02 | 8 | Dighjan Khal | Km | 4.32 | 102.8289 | 0.5 | 1 | 51.4145 | 102.8289 | 51.4145 | 0
156 | NETR/PW-02 | 8 | Tutnir Khal | Km | 3.15 | 37.9263 | 0 | 0 | 0 | 0 | 0 | 0
157 | NETR/PW-02 | 8 | Kamalpur Khal | Km | 2.98 | 91.9555 | 0.4 | 1 | 36.7822 | 91.9555 | 55.1733 | 0
158 | NETR/PW-03 | 9 | Resection of Full embankment in Kangsha River Sheme | km | 20.9 | 450.21 | 1 | 1 | 450.21 | 450.21 | 0 | 0
159 | NETR/PW-03 | 10 | Resection of Submesible Singer Bill | km | 3.56 | 29.21 | 1 | 1 | 29.21 | 29.21 | 0 | 0
160 | NETR/PW-03 | 2 | Reinstllation of 5-vent Regulator Dampara | No | 1 | 389.57 | 0.95 | 1 | 370.0915 | 389.57 | 19.4785 | 0
161 | NETR/PW-04 | 8 | Reexcavation of Piyan River from 0.075 to 5.00 | Km | 4.925 | 335.3397 | 0.78 | 1 | 261.565 | 335.3397 | 73.7747 | 0
162 | NETR/PW-04 | 8 | Reexcavation of Nayori Khal from 0.000 to 7.565 | Km | 7.565 | 158.059 | 1 | 1 | 158.059 | 158.059 | 0 | 0
163 | NETR/PW-04 | 8 | Reexcavation of Feni Khal from 0.000 to 1.903 | Km | 1.903 | 16.0636 | 0 | 0 | 0 | 0 | 0 | 0
164 | NETR/PW-04 | 8 | Reexcavation of Jhalokhali from 0.000 to 6.76 | Km | 6.76 | 282.4937 | 1 | 1 | 282.4937 | 282.4937 | 0 | 0
165 | NETR/PW-04 | 8 | Reexcavation of Putia Khal from 0.000 to 5.235 | Km | 5.235 | 313.3495 | 1 | 1 | 313.3495 | 313.3495 | 0 | 0
166 | NETR/PW-04 | 10 | Resectioning of Submersible EMB from 44.600 to 48.650 | Km | 9.75 | 395.62 | 0.82 | 1 | 324.4084 | 395.62 | 71.2116 | 0
167 | NETR/PW-05 | 10 | Const of Submesible Emb from Km 6.800 to 24.855 | Km | 3.071 | 57.25 | 0 | 1 | 0 | 57.25 | 57.25 | 0
168 | NETR/PW-05 | 3 | Const of 1-Vent Chapri Regulator | Nos | 1 | 242.75 | 0.6 | 1 | 145.65 | 242.75 | 97.1 | 0
169 | NETR/PW-05 | 3 | Const of 1-Vent Ukra Regulator | Nos | 1 | 286.86 | 0.85 | 1 | 243.831 | 286.86 | 43.029 | 0
170 | NETR/PW-05 | 3 | Const of 1-Vent Ichamati Regulator | Nos | 1 | 182.66 | 0.85 | 1 | 155.261 | 182.66 | 27.399 | 0
171 | NETR/PW-05 | 3 | Const of 4-Vent Ichamati Regulator | Nos | 1 | 419.66 | 0.6 | 1 | 251.796 | 419.66 | 167.864 | 0
172 | NETR/PW-06 | 7 | Reexcavation of Narsua River from Km 0.000 to 6.225 | Km | 6.226 | 224.4496 | 1 | 1.1 | 224.4496 | 246.8946 | 22.445 | 0
173 | NETR/PW-06 | 7 | Reexcavation of Ukra Khal from Km 0.111 to 2.043 Km | Km | 1.933 | 118.7745 | 1 | 1 | 118.7745 | 118.7745 | 0 | 0
174 | NETR/PW-06 | 7 | Reexcavation of Chapri Khal from Km 0.280 to 2.590 Km | Km | 2.31 | 88.1515 | 1 | 1 | 88.1515 | 88.1515 | 0 | 0
175 | NETR/PW-06 | 7 | Reexcavation of Ichamati Khal from Km 0.072 to 1.250 Km | Km | 1.178 | 51.0575 | 1 | 1 | 51.0575 | 51.0575 | 0 | 0
176 | NETR/PW-06 | 7 | Reexcavation of Boilara Khal from Km 8.550 to 8.900 Km | Km | 0.35 | 28.0376 | 0 | 0 | 0 | 0 | 0 | 0
177 | NETR/PW-06 | 4 | Const of BoX drainage ountlet at Bhadera | Nos | 1 | 42.25 | 1 | 1 | 42.25 | 42.25 | 0 | 0
178 | NETR/PW-06 | 4 | Const of BoX drainage ountlet at Moheswar Khal | Nos | 1 | 42.25 | 1 | 1 | 42.25 | 42.25 | 0 | 0
179 | NETR/PW-06 | 1 | Const of Irrigation Inlet | Nos | 2 | 16.92 | 0 | 0 | 0 | 0 | 0 | 0
180 | NETR/PW-06 | 12 | Rehbilation of existing Regulator | Nos | 1 | 19.43 | 1 | 1 | 19.43 | 19.43 | 0 | 0
181 | NETR/PW-07 | 7 | Reexcavation of Kangsha river | Km | 15 | 654.8026 | 1 | 1 | 654.8026 | 654.8026 | 0 | 0
182 | NETR/PW-07 | 7 | Reexcavation of Gumai river | Km | 9 | 238.8741 | 1 | 0 | 238.8741 | 0 | -238.8741 | 0
183 | NETR/PW-08 | 3 | Agunia Regulator | No | 1 | 289.74 | 0.6 | 1 | 173.844 | 289.74 | 115.896 | 0
184 | NETR/PW-08 | 3 | Dharam Regulator | No | 1 | 239.88 | 0.25 | 1 | 59.97 | 239.88 | 179.91 | 0
185 | NETR/PW-08 | 4 | Box-1 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
186 | NETR/PW-08 | 4 | Box-2 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
187 | NETR/PW-08 | 4 | Box-3 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
188 | NETR/PW-08 | 4 | Box-4 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
189 | NETR/PW-08 | 4 | Box-5 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
190 | NETR/PW-08 | 1 | Inlet-1 | No | 1 | 12.18 | 0 | 1 | 0 | 12.18 | 12.18 | 0
191 | NETR/PW-08 | 1 | Inlet-2 | No | 1 | 12.18 | 0 | 1 | 0 | 12.18 | 12.18 | 0
192 | NETR/PW-08 | 1 | Inlet-3 | No | 1 | 12.18 | 0 | 1 | 0 | 12.18 | 12.18 | 0
193 | HOBI/PW-01 | 10 | Resectioning of Embankment along the left bank of the Bashira River inbwt 2.420 to 9.760 | km | 7 | 151.385 | 1 | 1 | 151.385 | 151.385 | 0 | 0
194 | HOBI/PW-01 | 10 | construction of new Embankment along the left bank of bitangal khal inbwt 10.000 to 17.000 | km | 7 | 151.385 | 1 | 1 | 151.385 | 151.385 | 0 | 0
195 | HOBI/PW-01 | 8 | Reexcavation of Bashira River 0.000 to 20.000 | km | 17.4 | 732.6 | 0.8 | 1 | 586.08 | 732.6 | 146.52 | 0
196 | HOBI/PW-01 | 8 | Reexcavation of Matikatakahl from 0.000 to Km 2.295 | km | 2.925 | 99.9 | 1 | 1 | 99.9 | 99.9 | 0 | 0
197 | HOBI/PW-01 | 3 | Construction of 2-vent Regulator | nos. | 1 | 208 | 0 | 1 | 0 | 208 | 208 | 0
198 | HOBI/PW-01 | 5 | Construction of 4.00m causeway | nos. | 1 | 178.13 | 1 | 1 | 178.13 | 178.13 | 0 | 0
199 | HOBI/PW-02 | 10 | Resctioning of Submersible Embankment from 0.000 to 26.000 at Left Bank of Kushiyara | Km | 7.23 | 274.56 | 1 | 1 | 274.56 | 274.56 | 0 | 0
200 | HOBI/PW-02 | 10 | Construction of Retired Embankment in between 0.000 to 26.500 | Km | 6.894 | 225.46 | 1 | 1 | 225.46 | 225.46 | 0 | 0
201 | HOBI/PW-02 | 10 | Resctioning of Submersible Embankment from 0.000 to 16.02 at Right Bank of Khoai | Km | 16.02 | 318.42 | 1 | 1 | 318.42 | 318.42 | 0 | 0
202 | HOBI/PW-02 | 10 | Construction of New Embankment from Km 22.850 to 31.210 | Km | 8.36 | 149.54 | 1 | 1 | 149.54 | 149.54 | 0 | 0
203 | HOBI/PW-02 | 8 | Reexcavation of Kairdhala Khal from 0.000 to 1.6950 km | Km | 1.695 | 132.8661 | 0 | 0 | 0 | 0 | 0 | 0
204 | HOBI/PW-02 | 8 | Reexcavation of Satmukha Khal from 0.000 to 1.790 km | Km | 1.79 | 53.0475 | 1 | 1 | 53.0475 | 53.0475 | 0 | 0
205 | HOBI/PW-02 | 8 | Reexcavation of Singer Beel Khal from 0.000 to 2.720 km | Km | 2.72 | 29.975 | 1 | 1 | 29.975 | 29.975 | 0 | 0
206 | HOBI/PW-02 | 5 | Construction of Dairar Khal Causeway 6-m width Causeway | nos. | 1 | 168.38 | 0.95 | 1 | 159.961 | 168.38 | 8.419 | 0
207 | HOBI/PW-02 | 5 | Ikrampur CW-6M | nos. | 1 | 168.38 | 0.1 | 1 | 16.838 | 168.38 | 151.542 | 0
208 | HOBI/PW-04 | 11 | Submesible Embankment from 31.600 to 81.740 | km | 23.815 | 638.85 | 0.5 | 1 | 319.425 | 638.85 | 319.425 | 0
209 | HOBI/PW-04 | 11 | Block road | km | 2 | 507.95 | 0.78 | 1 | 396.201 | 507.95 | 111.749 | 0
210 | HOBI/PW-05 | 3 | Boranbil khal Regulator (1-vent) | nos. | 1 | 141.3235 | 0 | 0.75 | 0 | 105.9926 | 105.9926 | 0
211 | HOBI/PW-05 | 3 | Chandakhali khal Regulator(1-vent) | nos. | 1 | 154.0746 | 0 | 0.75 | 0 | 115.5559 | 115.5559 | 0
212 | HOBI/PW-05 | 3 | Chargaowdair khal Regulator(1-vent) | nos. | 1 | 151.0703 | 0.3 | 1 | 45.3211 | 151.0703 | 105.7492 | 0
213 | HOBI/PW-05 | 3 | Chhoto Katari khal Regulator(1-vent) | nos. | 1 | 143.8109 | 0.1 | 0.7 | 14.3811 | 100.6677 | 86.2866 | 0
214 | HOBI/PW-05 | 3 | Islampur khal Regulator (1-vent) | nos. | 1 | 155.6933 | 0.8 | 1 | 124.5546 | 155.6933 | 31.1387 | 0
215 | HOBI/PW-05 | 3 | Tetter Drepasionkhal Regulator(2-vent) | nos. | 1 | 216.7515 | 0 | 0.7 | 0 | 151.726 | 151.726 | 0
216 | HOBI/PW-05 | 3 | Soaybeel khal Regulator (5-vent) | nos. | 1 | 353.8204 | 1 | 1 | 353.8204 | 353.8204 | 0 | 0
217 | HOBI/PW-06 | 5 | Bibiyana 6.0m Causeway | nos. | 1 | 415.5317 | 1 | 1 | 415.5317 | 415.5317 | 0 | 0
218 | HOBI/PW-06 | 5 | Old kushiyana 6.0m Causeway | nos. | 1 | 373.3459 | 0.85 | 1 | 317.344 | 373.3459 | 56.0019 | 0
219 | HOBI/PW-06 | 5 | Ratna River 4.0m Causeway | nos. | 1 | 143.1604 | 1 | 1 | 143.1604 | 143.1604 | 0 | 0
220 | HOBI/PW-06 | 5 | Rukway 4.0m Causeway | nos. | 1 | 165.1831 | 0.85 | 1 | 140.4056 | 165.1831 | 24.7775 | 0
221 | HOBI/PW-06 | 4 | BoX1 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
222 | HOBI/PW-06 | 4 | BoX2 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
223 | HOBI/PW-06 | 4 | BoX3 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
224 | HOBI/PW-06 | 4 | BoX4 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
225 | HOBI/PW-06 | 4 | BoX5 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
226 | HOBI/PW-06 | 4 | BoX6 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
227 | HOBI/PW-06 | 4 | BoX7 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
228 | HOBI/PW-06 | 4 | BoX8 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
229 | HOBI/PW-06 | 4 | BoX9 | nos. | 1 | 37.0833 | 0.4 | 0.4 | 14.8333 | 14.8333 | 0 | 0
230 | HOBI/PW-06 | 1 | Irrigation Inlet | nos. | 15 | 150.7581 | 0.55 | 1 | 82.917 | 150.7581 | 67.8412 | 0
231 | HOBI/PW-07 | 7 | Chargaowdair khal | km | 3.036 | 45.4209 | 1 | 1 | 45.4209 | 45.4209 | 0 | 0
232 | HOBI/PW-07 | 7 | Chotokatari Khal | km | 3.264 | 61.408 | 1 | 1 | 61.408 | 61.408 | 0 | 0
233 | HOBI/PW-07 | 7 | Salukadhar Khal | km | 2.428 | 67.6663 | 1 | 1 | 67.6663 | 67.6663 | 0 | 0
234 | HOBI/PW-07 | 7 | Islampur khal | km | 0.634 | 25.7065 | 0 | 0 | 0 | 0 | 0 | 0
235 | HOBI/PW-07 | 7 | Soyabeel Khal | km | 3.285 | 139.5951 | 1 | 1 | 139.5951 | 139.5951 | 0 | 0
236 | HOBI/PW-07 | 7 | Chatal Beel Khal | km | 5.2176 | 103.126 | 0 | 0 | 0 | 0 | 0 | 0
237 | HOBI/PW-07 | 7 | Rajendrapur Khal | km | 4.327 | 115.1915 | 0.45 | 1 | 51.8362 | 115.1915 | 63.3553 | 0
238 | HOBI/PW-07 | 7 | Purohogun Khal | km | 2.428 | 65.549 | 1 | 1 | 65.549 | 65.549 | 0 | 0
239 | HOBI/PW-07 | 7 | Sutki River | km | 4.5 | 145.977 | 0.57 | 1 | 83.2069 | 145.977 | 62.7701 | 0
240 | HOBI/PW-07 | 7 | Ratna River | km | 7.51 | 137.4972 | 0.53 | 1 | 72.8735 | 137.4972 | 64.6237 | 0
241 | SUNM/PW-01 | 11 | Submersible Embankment between km10.600 to 49.426 total 33.849km | km | 33.849 | 867.33 | 0.58 | 1 | 503.0514 | 867.33 | 364.2786 | 0
242 | SUNM/PW-01 | 7 | Re-Excavation of Dariabaz Khal | km | 1.48 | 18.8287 | 0.84 | 1 | 15.8161 | 18.8287 | 3.0126 | 0
243 | SUNM/PW-01 | 7 | Re-Excavation of Juriganga Khal | km | 1.438 | 32.0288 | 0.84 | 1 | 26.9042 | 32.0288 | 5.1246 | 0
244 | SUNM/PW-01 | 7 | Re-Excavation of Purukania Khal | km | 1.56 | 41.0489 | 0.84 | 1 | 34.4811 | 41.0489 | 6.5678 | 0
245 | SUNM/PW-01 | 7 | Re-Excavation of Muktakhai River | Km | 3.2 | 176.4745 | 0.84 | 1 | 148.2386 | 176.4745 | 28.2359 | 0
246 | SUNM/PW-01 | 4 | Box Drainage Outlet-1 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
247 | SUNM/PW-01 | 4 | Box Drainage Outlet-2 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
248 | SUNM/PW-01 | 4 | Box Drainage Outlet-3 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
249 | SUNM/PW-01 | 4 | Box Drainage Outlet-4 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
250 | SUNM/PW-01 | 4 | Box Drainage Outlet-5 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
251 | SUNM/PW-01 | 4 | Box Drainage Outlet-6 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
252 | SUNM/PW-01 | 4 | Box Drainage Outlet-7 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
253 | SUNM/PW-01 | 1 | Irrigation Inlet | Nos | 9 | 10.66 | 0 | 1 | 0 | 10.66 | 10.66 | 0
254 | SUNM/PW-02 | 7 | Re-excavation of Piyan River from km 19.000 to km 55.575 total 36.575km | Km | 36.575 | 1193.75 | 0.8 | 1 | 955 | 1193.75 | 238.75 | 0
255 | SUNM/PW-03 | 3 | 1 vent (1.50m X 1.80m)-1 | Nos | 1 | 183.3461 | 0.6 | 1 | 110.0077 | 183.3461 | 73.3384 | 0
256 | SUNM/PW-03 | 3 | 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 308.0018 | 0.6 | 1 | 184.8011 | 308.0018 | 123.2007 | 0
257 | SUNM/PW-03 | 5 | Causeway 4.0m wide-1 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
258 | SUNM/PW-03 | 5 | Causeway 4.0m wide-2 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
259 | SUNM/PW-03 | 5 | Causeway 4.0m wide-3 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
260 | SUNM/PW-03 | 5 | Causeway 4.0m wide-4 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
261 | SUNM/PW-03 | 5 | Causeway 4.0m wide-5 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
262 | SUNM/PW-03 | 5 | Causeway 6.0m wide-1 | Nos | 1 | 279.3507 | 0.27 | 0.67 | 75.4247 | 187.165 | 111.7403 | 0
263 | SUNM/PW-04 | 11 | Construction of Submersible embankment-34.94km | Km | 34.94 | 1564.32 | 0.98 | 1 | 1533.0336 | 1564.32 | 31.2864 | 0
264 | SUNM/PW-05 | 3 | Dahar 4vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 283.3851 | 0.5 | 1 | 141.6926 | 283.3851 | 141.6926 | 0
265 | SUNM/PW-05 | 3 | Deola 2 vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 267.8703 | 0.4 | 1 | 107.1481 | 267.8703 | 160.7222 | 0
266 | SUNM/PW-05 | 5 | Manani Causeway 6.0m wide-1 | Nos | 1 | 225.81 | 0 | 1 | 0 | 225.81 | 225.81 | 0
267 | SUNM/PW-05 | 5 | Dahar Causeway 4.0m wide-1 | Nos | 1 | 301.6651 | 0.4 | 1 | 120.666 | 301.6651 | 180.9991 | 0
268 | SUNM/PW-05 | 5 | Daharagang Causeway 4.0m wide-2 | Nos | 1 | 187.8663 | 0.8 | 1 | 150.293 | 187.8663 | 37.5733 | 0
269 | SUNM/PW-05 | 5 | Chandrasona Causeway 4.0m wide-3 | Nos | 1 | 191.3901 | 0.8 | 1 | 153.1121 | 191.3901 | 38.278 | 0
270 | SUNM/PW-06 | 7 | Khurma Khal | km | 7.18 | 36.0889 | 1 | 1 | 36.0889 | 36.0889 | 0 | 0
271 | SUNM/PW-06 | 7 | Udani Khal | km | 3.828 | 54.377 | 1 | 1 | 54.377 | 54.377 | 0 | 0
272 | SUNM/PW-06 | 7 | Deola Khal | km | 1.965 | 70.1082 | 1 | 1 | 70.1082 | 70.1082 | 0 | 0
273 | SUNM/PW-06 | 7 | Shaitan Khal | km | 13.8 | 565.0549 | 1 | 1 | 565.0549 | 565.0549 | 0 | 0
274 | SUNM/PW-06 | 7 | Banni Khal2 | km | 2.913 | 36.3507 | 1 | 1 | 36.3507 | 36.3507 | 0 | 0
275 | SUNM/PW-06 | 7 | Rui Beel Khal | km | 3.414 | 62.7308 | 1 | 1 | 62.7308 | 62.7308 | 0 | 0
276 | SUNM/PW-06 | 7 | Dahar Gang | km | 6.832 | 176.7629 | 1 | 1 | 176.7629 | 176.7629 | 0 | 0
277 | SUNM/PW-06 | 7 | Gobra Khal | km | 2.893 | 45.6733 | 1 | 1 | 45.6733 | 45.6733 | 0 | 0
278 | SUNM/PW-06 | 7 | Banni Khal1 | km | 2.622 | 39.8891 | 1 | 1 | 39.8891 | 39.8891 | 0 | 0
279 | SUNM/PW-06 | 7 | Dagar Khal | km | 2.665 | 15.5116 | 1 | 1 | 15.5116 | 15.5116 | 0 | 0
280 | SUNM/PW-06 | 7 | Rajpur Khal | km | 3.595 | 37.8562 | 1 | 1 | 37.8562 | 37.8562 | 0 | 0
281 | SUNM/PW-06 | 7 | Kolma Khal | km | 2.204 | 17.6969 | 1 | 1 | 17.6969 | 17.6969 | 0 | 0
282 | SUNM/PW-06 | 7 | Agunia khal | km | 7.611 | 157.1547 | 1 | 1 | 157.1547 | 157.1547 | 0 | 0
283 | SUNM/PW-06 | 7 | Kakura Khal | km | 1.305 | 32.5728 | 1 | 1 | 32.5728 | 32.5728 | 0 | 0
284 | SUNM/PW-06 | 7 | Dharam Beel Khal | km | 1.105 | 37.7084 | 1 | 1 | 37.7084 | 37.7084 | 0 | 0
285 | SUNM/PW-06 | 7 | Bararia Khal | km | 2.11 | 14.6001 | 1 | 1 | 14.6001 | 14.6001 | 0 | 0
286 | SUNM/PW-06 | 4 | Const. of Box Drainage Outlet-1 | Nos | 1 | 45.13 | 0 | 1 | 0 | 45.13 | 45.13 | 0
287 | SUNM/PW-06 | 1 | Irrigation Inlet | Nos | 12 | 131.38 | 0 | 1 | 0 | 131.38 | 131.38 | 0

## Package_wise_payment
| Package_No | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | KISH/PW-01 | 76.82 | 496.54 | 51.09 | 445.45
1 | KISH/PW-02 | 432.9482 | 432.9482 | 347.71 | 85.2382
2 | KISH/PW-03 | 689.4575 | 689.4575 | 625.93 | 63.5275
3 | KISH/PW-04 | 710.5171 | 710.5171 | 714.69 | -4.1729
4 | KISH/PW-05 | 758.808 | 767.5773 | 575.15 | 192.4273
5 | KISH/PW-06 | 774.6882 | 774.6882 | 837.25 | -62.5618
6 | KISH/PW-07 | 603.9619 | 812.3426 | 565.07 | 247.2726
7 | KISH/PW-09 | 715.8438 | 715.8438 | 712.33 | 3.5138
8 | KISH/PW-10 | 577.1799 | 835.8875 | 409.68 | 426.2075
9 | KISH/PW-11 | 539.5805 | 832.12 | 522.86 | 309.26
10 | KISH/PW-12 | 913.2634 | 913.2634 | 705.59 | 207.6734
11 | KISH/PW-13 | 635.33 | 1002.63 | 647.2 | 355.43
12 | KISH/PW-14 | 752.9122 | 857 | 806.89 | 50.11
13 | KISH/PW-15 | 616.92 | 616.92 | 333.94 | 282.98
14 | KISH/PW-16 | 738.988 | 779.17 | 721.62 | 57.55
15 | KISH/PW-17 | 1568.1457 | 1568.1457 | 1451.95 | 116.1957
16 | KISH/PW-18 | 640.7482 | 1214.5609 | 711.02 | 503.5409
17 | KISH/PW-19 | 183.6038 | 847.926 | 331.35 | 516.576
18 | KISH/PW-20 | 999.4897 | 1009.9823 | 501.12 | 508.8623
19 | KISH/PW-21 | 224.7785 | 927.7449 | 268.24 | 659.5049
20 | KISH/PW-22 | 274.3324 | 672.5314 | 281.05 | 391.4814
21 | KISH/PW-23 | 658.493 | 744.2322 | 720.33 | 23.9022
22 | KISH/PW-24 | 1149.1962 | 1149.1962 | 890.42 | 258.7762
23 | KISH/PW-25 | 790.2371 | 1050.0682 | 749.37 | 300.6982
24 | KISH/PW-26 | 0 | 0 | 501.12 | -501.12
25 | KISH/PW-27 | 0 | 894.68 | 0 | 894.68
26 | NETR/PW-01 | 1143.543 | 1345.3447 | 817.97 | 527.3747
27 | NETR/PW-02 | 653.5026 | 910.9639 | 475.85 | 435.1139
28 | NETR/PW-03 | 849.5115 | 868.99 | 712.73 | 156.26
29 | NETR/PW-04 | 1339.8756 | 1484.8619 | 844.17 | 640.6919
30 | NETR/PW-05 | 796.538 | 1189.18 | 635.34 | 553.84
31 | NETR/PW-06 | 586.3632 | 608.8081 | 375.82 | 232.9881
32 | NETR/PW-07 | 893.6768 | 654.8026 | 567.71 | 87.0926
33 | NETR/PW-08 | 233.814 | 877.26 | 134.16 | 743.1
34 | SUNM/PW-01 | 898.9316 | 1462.001 | 913.55 | 548.451
35 | SUNM/PW-02 | 955 | 1193.75 | 926.3 | 267.45
36 | SUNM/PW-03 | 616.3195 | 1289.171 | 511.73 | 777.441
37 | SUNM/PW-04 | 1533.0336 | 1564.32 | 1521.41 | 42.91
38 | SUNM/PW-05 | 672.9118 | 1457.9869 | 1061.82 | 396.1669
39 | SUNM/PW-06 | 1400.1366 | 1576.6466 | 1268.067 | 308.5796
40 | HOBI/PW-01 | 1166.88 | 1521.4 | 938.27 | 583.13
41 | HOBI/PW-02 | 1227.8015 | 1387.7625 | 1079.52 | 308.2425
42 | HOBI/PW-04 | 715.626 | 1146.8 | 655.94 | 490.86
43 | HOBI/PW-05 | 538.0772 | 1134.5263 | 307.8 | 826.7263
44 | HOBI/PW-06 | 1366.3583 | 1559.4788 | 1094.31 | 465.1688
45 | HOBI/PW-07 | 587.556 | 778.3051 | 667.67 | 110.6351

## Structure_Wise_payment
| Items | Code | DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Construction of Irrigation Inlet | 1 | Inlet | 712.7508 | 975.7713 | 291.81 | 683.9613
1 | Rehab Regulator Rehab Haor | 2 | Reg_Rehab_Rehab | 370.0915 | 434.36 | 0 | 434.36
2 | Regulator | 3 | Reg_CW_Box | 7021.1975 | 9966.0532 | 6503.97 | 3462.0832
3 | Box Drainage Outlet | 4 | Reg_CW_Box | 738.3125 | 1436.0982 | 0 | 1436.0982
4 | Causeway | 5 | Reg_CW_Box | 3767.7573 | 5993.1839 | 0 | 5993.1839
5 | Bridge | 6 | Reg_CW_Box | 0 | 0 | 0 | 0
6 | Khal_River Reexcavation(New Haor) | 7 | Khal_Riv_New | 6994.3937 | 8557.3468 | 2546.54 | 6010.8068
7 | Khal_River Reexcavation(Rehab Haor) | 8 | Khal_Riv_Rehab | 2514.7922 | 3367.4783 | 51.09 | 3316.3883
8 | Embankment Rehablitation | 9 | Full_Emb_Rehab | 1593.753 | 1795.5547 | 0 | 1795.5547
9 | Submersible Embankment Rehabilitation | 10 | Sub_Emb_Rehab | 1624.3684 | 1752.83 | 0 | 1752.83
10 | Submersible Embankment Construction | 11 | Sub_Emb_Const | 8844.8532 | 10909.67 | 5833.04 | 5076.63
11 | Rehab Regulator New Haor | 12 | Reg_Rehab_New | 19.43 | 139.9864 | 0 | 139.9864
12 | Thrashing Floor Construction | 14 | Thr_Fl_Cost | 0 | 0 | 0 | 0
13 | Construction of WMG | 15 | Wmg_Office | 0 | 0 | 0 | 0
14 | M&E GATE Repair | 16 | Gate_Repair | 0 | 0 | 0 | 0

## DPP_Wise_payment
| DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Inlet | 712.75 | 975.77 | 291.81 | 683.96
1 | Reg_Rehab_Rehab | 370.09 | 434.36 | 0 | 434.36
2 | Reg_CW_Box | 11527.27 | 17395.34 | 6503.97 | 10891.37
3 | Khal_Riv_New | 6994.39 | 8557.35 | 2546.54 | 6010.81
4 | Khal_Riv_Rehab | 2514.79 | 3367.48 | 51.09 | 3316.39
5 | Full_Emb_Rehab | 1593.75 | 1795.55 | 0 | 1795.55
6 | Sub_Emb_Rehab | 1624.37 | 1752.83 | 0 | 1752.83
7 | Sub_Emb_Const | 8844.85 | 10909.67 | 5833.04 | 5076.63
8 | Reg_Rehab_New | 19.43 | 139.99 | 0 | 139.99
9 | Thr_Fl_Cost | 0 | 0 | 0 | 0
10 | Wmg_Office | 0 | 0 | 0 | 0
11 | Gate_Repair | 0 | 0 | 0 | 0

## Package_wise_str_value
| Package_No | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Total
0 | KISH/PW-01 | 0 | 44.79 | 0 | 0 | 0 | 0 | 0 | 451.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496.54
1 | KISH/PW-02 | 0 | 0 | 155.5114 | 0 | 0 | 0 | 262.6258 | 0 | 0 | 0 | 14.8109 | 0 | 0 | 0 | 0 | 0 | 432.9482
2 | KISH/PW-03 | 0 | 0 | 155.5114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533.9461 | 0 | 0 | 0 | 0 | 0 | 689.4575
3 | KISH/PW-04 | 0 | 0 | 453.6457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256.8713 | 0 | 0 | 0 | 0 | 0 | 710.5171
4 | KISH/PW-05 | 0 | 0 | 190.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577.3573 | 0 | 0 | 0 | 0 | 0 | 767.5773
5 | KISH/PW-06 | 0 | 0 | 227.8819 | 0 | 0 | 0 | 546.8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774.6882
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 965.6062 | 0 | 0 | 0 | 91.07 | 0 | 0 | 0 | 0 | 0 | 1056.6762
7 | KISH/PW-09 | 0 | 0 | 397.64 | 0 | 318.2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715.8438
8 | KISH/PW-10 | 0 | 0 | 266.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617.94 | 0 | 0 | 0 | 0 | 0 | 883.96
9 | KISH/PW-11 | 0 | 0 | 274.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557.63 | 0 | 0 | 0 | 0 | 0 | 832.12
10 | KISH/PW-12 | 0 | 0 | 530.93 | 0 | 0 | 0 | 400.7305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931.6604
11 | KISH/PW-13 | 0 | 0 | 425.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576.67 | 0 | 0 | 0 | 0 | 0 | 1002.63
12 | KISH/PW-14 | 0 | 0 | 176.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680.42 | 0 | 0 | 0 | 0 | 0 | 857
13 | KISH/PW-15 | 0 | 0 | 166.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616.92 | 0 | 0 | 0 | 0 | 0 | 783.82
14 | KISH/PW-16 | 0 | 0 | 267.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511.29 | 0 | 0 | 0 | 0 | 0 | 779.17
15 | KISH/PW-17 | 274.47 | 0 | 566.1924 | 177.4433 | 0 | 0 | 0 | 0 | 0 | 0 | 550.04 | 0 | 0 | 0 | 0 | 0 | 1568.1457
16 | KISH/PW-18 | 0 | 0 | 0 | 0 | 773.6979 | 0 | 542.0641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315.762
17 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 847.926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847.926
18 | KISH/PW-20 | 334.27 | 0 | 167.7584 | 0 | 651.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153.7184
19 | KISH/PW-21 | 0 | 0 | 478.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329.1074 | 120.5564 | 0 | 0 | 0 | 0 | 927.7449
20 | KISH/PW-22 | 0 | 0 | 0 | 109.986 | 195.2169 | 0 | 178.5346 | 0 | 0 | 0 | 235.9924 | 0 | 0 | 0 | 0 | 0 | 719.7299
21 | KISH/PW-23 | 62.862 | 0 | 522.5866 | 38.9293 | 0 | 0 | 32.4376 | 0 | 0 | 0 | 107.4208 | 0 | 0 | 0 | 0 | 0 | 764.2363
22 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149.1962 | 0 | 0 | 0 | 0 | 0 | 1149.1962
23 | KISH/PW-25 | 118.5673 | 0 | 405.9371 | 41.8221 | 824.0231 | 0 | 374.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1764.7878
24 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 467.9549 | 0 | 0 | 0 | 22.7161 | 0 | 0 | 0 | 0 | 0 | 490.671
25 | KISH/PW-27 | 0 | 0 | 304.62 | 41.88 | 548.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894.68
26 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1345.3447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1345.3447
27 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948.8902
28 | NETR/PW-03 | 0 | 389.57 | 0 | 0 | 0 | 0 | 0 | 0 | 450.21 | 29.21 | 0 | 0 | 0 | 0 | 0 | 0 | 868.99
29 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105.3055 | 0 | 395.62 | 0 | 0 | 0 | 0 | 0 | 0 | 1500.9255
30 | NETR/PW-05 | 0 | 0 | 1131.93 | 0 | 0 | 0 | 0 | 0 | 0 | 57.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1189.18
31 | NETR/PW-06 | 16.92 | 0 | 0 | 84.5 | 0 | 0 | 510.4707 | 0 | 0 | 0 | 0 | 19.43 | 0 | 0 | 0 | 0 | 631.3207
32 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 893.6768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 893.6768
33 | NETR/PW-08 | 36.54 | 0 | 529.62 | 311.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877.26
34 | SUNM/PW-01 | 10.66 | 0 | 0 | 315.63 | 0 | 0 | 268.381 | 0 | 0 | 0 | 867.33 | 0 | 0 | 0 | 0 | 0 | 1462.001
35 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 1193.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193.75
36 | SUNM/PW-03 | 0 | 0 | 491.348 | 0 | 1190.7806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1682.1286
37 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564.32 | 0 | 0 | 0 | 0 | 0 | 1564.32
38 | SUNM/PW-05 | 0 | 0 | 551.2554 | 0 | 906.7315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1457.9869
39 | SUNM/PW-06 | 131.38 | 0 | 0 | 45.13 | 0 | 0 | 1400.1366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576.6466
40 | HOBI/PW-01 | 0 | 0 | 208 | 0 | 178.13 | 0 | 0 | 832.5 | 0 | 302.77 | 0 | 0 | 0 | 0 | 0 | 0 | 1521.4
41 | HOBI/PW-02 | 0 | 0 | 0 | 0 | 336.76 | 0 | 0 | 215.8886 | 0 | 967.98 | 0 | 0 | 0 | 0 | 0 | 0 | 1520.6286
42 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146.8 | 0 | 0 | 0 | 0 | 0 | 1146.8
43 | HOBI/PW-05 | 0 | 0 | 1316.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316.5445
44 | HOBI/PW-06 | 150.7581 | 0 | 0 | 333.7495 | 1097.2211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581.7287
45 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 907.1377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907.1377

## Package_wise_str_df
Package_No | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | WMG_OFF
KISH/PW-01 | 0 | 0.0902 | 0 | 0 | 0.9098 | 0 | 0 | 0 | 0 | 0
KISH/PW-02 | 0 | 0 | 0.3592 | 0.6066 | 0 | 0 | 0 | 0.0342 | 0 | 0
KISH/PW-03 | 0 | 0 | 0.2256 | 0 | 0 | 0 | 0 | 0.7744 | 0 | 0
KISH/PW-04 | 0 | 0 | 0.6385 | 0 | 0 | 0 | 0 | 0.3615 | 0 | 0
KISH/PW-05 | 0 | 0 | 0.2478 | 0 | 0 | 0 | 0 | 0.7522 | 0 | 0
KISH/PW-06 | 0 | 0 | 0.2942 | 0.7058 | 0 | 0 | 0 | 0 | 0 | 0
KISH/PW-07 | 0 | 0 | 0 | 0.9138 | 0 | 0 | 0 | 0.0862 | 0 | 0
KISH/PW-09 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH/PW-10 | 0 | 0 | 0.3009 | 0 | 0 | 0 | 0 | 0.6991 | 0 | 0
KISH/PW-11 | 0 | 0 | 0.3299 | 0 | 0 | 0 | 0 | 0.6701 | 0 | 0
KISH/PW-12 | 0 | 0 | 0.5699 | 0.4301 | 0 | 0 | 0 | 0 | 0 | 0
KISH/PW-13 | 0 | 0 | 0.4248 | 0 | 0 | 0 | 0 | 0.5752 | 0 | 0
KISH/PW-14 | 0 | 0 | 0.206 | 0 | 0 | 0 | 0 | 0.794 | 0 | 0
KISH/PW-15 | 0 | 0 | 0.2129 | 0 | 0 | 0 | 0 | 0.7871 | 0 | 0
KISH/PW-16 | 0 | 0 | 0.3438 | 0 | 0 | 0 | 0 | 0.6562 | 0 | 0
KISH/PW-17 | 0.175 | 0 | 0.4743 | 0 | 0 | 0 | 0 | 0.3508 | 0 | 0
KISH/PW-18 | 0 | 0 | 0.588 | 0.412 | 0 | 0 | 0 | 0 | 0 | 0
KISH/PW-19 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
KISH/PW-20 | 0.2897 | 0 | 0.7103 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH/PW-21 | 0 | 0 | 0.5153 | 0 | 0 | 0 | 0 | 0.3547 | 0.1299 | 0
KISH/PW-22 | 0 | 0 | 0.424 | 0.2481 | 0 | 0 | 0 | 0.3279 | 0 | 0
KISH/PW-23 | 0.0823 | 0 | 0.7347 | 0.0424 | 0 | 0 | 0 | 0.1406 | 0 | 0
KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
KISH/PW-25 | 0.0672 | 0 | 0.7206 | 0.2122 | 0 | 0 | 0 | 0 | 0 | 0
KISH/PW-26 | 0 | 0 | 0 | 0.9537 | 0 | 0 | 0 | 0.0463 | 0 | 0
KISH/PW-27 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
NETR/PW-02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NETR/PW-03 | 0 | 0.4483 | 0 | 0 | 0 | 0.5181 | 0.0336 | 0 | 0 | 0
NETR/PW-04 | 0 | 0 | 0 | 0 | 0.7364 | 0 | 0.2636 | 0 | 0 | 0
NETR/PW-05 | 0 | 0 | 0.9519 | 0 | 0 | 0 | 0.0481 | 0 | 0 | 0
NETR/PW-06 | 0.0268 | 0 | 0.1338 | 0.8086 | 0 | 0 | 0 | 0 | 0.0308 | 0
NETR/PW-07 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
NETR/PW-08 | 0.0417 | 0 | 0.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM/PW-01 | 0.0073 | 0 | 0.2159 | 0.1836 | 0 | 0 | 0 | 0.5932 | 0 | 0
SUNM/PW-02 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SUNM/PW-03 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
SUNM/PW-05 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM/PW-06 | 0.0833 | 0 | 0.0286 | 0.888 | 0 | 0 | 0 | 0 | 0 | 0
HOBI/PW-01 | 0 | 0 | 0.2538 | 0 | 0.5472 | 0 | 0.199 | 0 | 0 | 0
HOBI/PW-02 | 0 | 0 | 0.2215 | 0 | 0.142 | 0 | 0.6366 | 0 | 0 | 0
HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HOBI/PW-05 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI/PW-06 | 0.0953 | 0 | 0.9047 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI/PW-07 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0