## Qstatus
SLNo | Package No | Structure/Works Name | Works Type | Start | Finish | Length | Vent | Current Status | Current Progress | LA Problems
1 | HOBI/PW-01 | Consruction of 4.00 m wide causeway | CASWCN | 0 | 0.001 | 1 | 0 | OG | 0
2 | HOBI/PW-01 | Re-excavation of Bashira River in between km 0.000 to 20.000=17.400 | EXRIVN | 0 | 20 | 17.399 | 0 | OG | 0.82
3 | HOBI/PW-01 | Resectioning of Submersible Embankment along the left bank of Bashira River in between km 2.420 to km 9.760=7.00 Km | SEMBRN | 2.42 | 9.76 | 7 | 0 | C | 1
4 | HOBI/PW-01 | Construction of New Embankment along the left bank of Bitangal khal in between km 10.000 to 17.000 =7.000 | SEMBCN | 10 | 17 | 17 | 0 | C | 1
5 | HOBI/PW-01 | Cnstruction of 2-Vent Regulator | REGCN | None | None | 1 | 2 | C
6 | HOBI/PW-01 | Re-excavation of Matikata Khal from km 0.000 to 2.295 | EXKHLN | 0 | 2.295 | 2.29 | 0 | C | 1
7 | HOBI/PW-02 | Singar Beel Khal from Km 0.000 to Km 2.720 | EXKHLR | 0 | 2.72 | 2.72 | 0 | C | 1
8 | HOBI/PW-02 | Satmukha Khal from Km 0.000 to Km 1.790 | EXKHLR | 0 | 1.79 | 1.79 | 0 | C | 1
9 | HOBI/PW-02 | 4m Causeway-1 | CASWCN | 0 | 0 | 1 | 0 | C | 1
10 | HOBI/PW-02 | Construction of New embankment from Km 22.850 to 32.210=8.360 Km | EMBRR | 22.85 | 31.21 | 8.36 | 0 | C | 1
11 | HOBI/PW-02 | Construction of new retired embankment between Km 0.000 to Km 26.500=6.894 km | EMBRR | 0 | 26.5 | 6.894 | 0 | C | 1
12 | HOBI/PW-02 | Resectiong of Submersible Embankment along left bank of Khoai River from Km 0.000 to Km 16.020=16.020 Km | SEMBRN | 0 | 16.02 | 16.02 | 0 | C | 1
13 | HOBI/PW-02 | Resectioning ofSubmesible Embankment along left bank of Kushiyara River in bnetween Km 0.000 to Km 26.000= 7.230 km | SEMBRN | 0 | 26 | 7.23 | 0 | OG | 0.66
14 | HOBI/PW-02 | Kairdhala Khal from Km 0.000to 1.695 | EXKHLR | 0 | 1.695 | 1.695 | 0 | P |  | evwZj
15 | HOBI/PW-04 | Submersible Embankment at Mokhar Haor in between km 31.600 to 81.749=23.815 | SEMBCN | 31.6 | 81.74 | 23.815 | None | OG | 0.44
16 | HOBI/PW-05 | 2-Vent Regulator at Km81.2 in Mokhar Haor Project | REGCN | 72.66 | 72.66 | 1 | 2 | OG
17 | HOBI/PW-05 | 4-Vent Regulator at Km7.61 in Mokhar Haor Project | REGCN | 81.2 | 81.2 | 1 | 4 | OG | 0.9
18 | HOBI/PW-05 | 1-Vent Regulator at Km35.97 in Mokhar Haor Project | REGCN | 33.69 | 33.69 | 1 | 1 | OG | 0.85
19 | HOBI/PW-05 | 1-Vent Regulator at Km46.9 in Mokhar Haor Project | REGCN | 35.97 | 35.97 | 1 | 1 | OG | 0.2
20 | HOBI/PW-05 | 1-Vent Regulator at Km51.58 in Mokhar Haor Project | REGCN | 46.9 | 46.9 | 1 | 1 | OG
21 | HOBI/PW-05 | 1-Vent Regulator at Km72.66 in Mokhar Haor Project | REGCN | 65.45 | 65.45 | 1 | 1 | OG
22 | HOBI/PW-05 | 1-Vent Regulator at Km65.45 in Mokhar Haor Project | REGCN | 51.58 | 51.58 | 1 | 1 | OG
23 | HOBI/PW-06 | 6m causeway at km 69.7 in Mokhar Haor Project | CASWCN | 69.7 | 69.7 | 1 | 6 | C | 1
24 | HOBI/PW-06 | Irrigation Inlet No-88 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
25 | HOBI/PW-06 | Irrigation Inlet No-89 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
26 | HOBI/PW-06 | Irrigation Inlet No-90 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
27 | HOBI/PW-06 | Irrigation Inlet No-93 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
28 | HOBI/PW-06 | Irrigation Inlet No-87 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
29 | HOBI/PW-06 | Irrigation Inlet No-92 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
30 | HOBI/PW-06 | Irrigation Inlet No-91 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
31 | HOBI/PW-06 | Irrigation Inlet No-94 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
32 | HOBI/PW-06 | Irrigation Inlet No-95 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
33 | HOBI/PW-06 | Irrigation Inlet No-96 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
34 | HOBI/PW-06 | Irrigation Inlet No-97 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
35 | HOBI/PW-06 | Irrigation Inlet No-98 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
36 | HOBI/PW-06 | Irrigation Inlet No-99 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
37 | HOBI/PW-06 | Irrigation Inlet No-100 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
38 | HOBI/PW-06 | Irrigation Inlet No-101 in Mokhar Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
39 | HOBI/PW-06 | Box Sluice at Km81.03 in Mokhar Haor Project | BOXSLCN | 81.03 | 81.03 | 1 | 0 | C | 1
40 | HOBI/PW-06 | Box Sluice at Km79.75 in Mokhar Haor Project | BOXSLCN | 79.75 | 79.75 | 1 | 0 | C | 1
41 | HOBI/PW-06 | Box Sluice at Km79.24 in Mokhar Haor Project | BOXSLCN | 79.24 | 79.24 | 1 | 0 | C | 1
42 | HOBI/PW-06 | Box Sluice at Km77.61 in Mokhar Haor Project | BOXSLCN | 77.61 | 77.61 | 1 | 0 | C | 1
43 | HOBI/PW-06 | Box Sluice at Km76.38 in Mokhar Haor Project | BOXSLCN | 76.38 | 76.38 | 1 | 0 | C | 1
44 | HOBI/PW-06 | Box Sluice at Km70.5 in Mokhar Haor Project | BOXSLCN | 70.5 | 70.5 | 1 | 0 | C | 1
45 | HOBI/PW-06 | Box Sluice at Km63.25 in Mokhar Haor Project | BOXSLCN | 63.25 | 63.25 | 1 | 0 | C | 1
46 | HOBI/PW-06 | Box Sluice at Km60.35 in Mokhar Haor Project | BOXSLCN | 60.35 | 60.35 | 1 | 0 | C | 1
47 | HOBI/PW-06 | Box Sluice at Km50.01 in Mokhar Haor Project | BOXSLCN | 50.01 | 50.01 | 1 | 0 | OG
48 | HOBI/PW-06 | 6m causeway at km 70.6 in Mokhar Haor Project | CASWCN | 70.6 | 70.6 | 1 | 6 | C | 1
49 | HOBI/PW-06 | 4m causeway at km 42.78 in Mokhar Haor Project | CASWCN | 42.78 | 42.78 | 1 | 4 | C | 1
50 | HOBI/PW-06 | 4m causeway at km 17.28 in Mokhar Haor Project | CASWCN | 17.28 | 17.28 | 1 | 4 | C | 1
51 | HOBI/PW-07 | Islampur Khal | EXKHLR | 0.157 | 0.791 | 0.634 | 0 | P |  | LGED
52 | HOBI/PW-07 | Rajendrapur Khal | EXKHLR | 0 | 4.327 | 4.327 | 0 | OG
53 | HOBI/PW-07 | Soay beel khal | EXKHLR | 0.094 | 3.379 | 3.285 | 0 | C | 1
54 | HOBI/PW-07 | Chatal beel Khal | EXKHLR | 0 | 5.217 | 5.217 | 0 | C |  | evwZj
55 | HOBI/PW-07 | Purohogun khal | EXKHLR | 0 | 2.428 | 2.428 | 0 | C | 1
56 | HOBI/PW-07 | Ratna River | EXRIVR | 0 | 10 | 8.614 | 0 | OG | 0.59
57 | HOBI/PW-07 | Sutki River | EXRIVR | 13.1 | 17.6 | 4.5 | 0 | OG | 0.32
58 | HOBI/PW-07 | Chargaowdair Khal | EXKHLR | 0.17 | 3.206 | 3.036 | 0 | C | 1
59 | HOBI/PW-07 | Chhotokatari Khal | EXKHLR | 0.184 | 3.448 | 3.264 | 0 | C | 1
60 | HOBI/PW-07 | Salukadar Khal | EXKHLR | 0 | 2.428 | 2.428 | 0 | C | 1
61 | KISH/PW-01 | Betal Doba from km1.315 to km 3.466 =2.151 km | EXRIVN | 1.315 | 3.446 | 2.151 | 0 | C | 1
62 | KISH/PW-01 | katakhali khal from km 0.000 to km 1.550=1.550 km | EXRIVN | 0 | 1.55 | 1.55 | 0 | OG
63 | KISH/PW-01 | Ganakkhali khal from km 0.000 to km 5.625=5.625 km | EXRIVN | 0 | 5.625 | 5.625 | 0 | OG
64 | KISH/PW-01 | Kali Khal from km 0.00 to km 1.00=1.000 km. | EXRIVR | 0 | 1 | 1 | None | OG
65 | KISH/PW-01 | Alalia-bahadia Khal from km 1.325 to km 2.545=1.220 km | EXRIVN | 1.325 | 2.545 | 1.22 | 0 | C | 1
66 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | EXKHLN | 0 | 2.225 | 2.225 | 0 | C | 1
67 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | EXKHLN | 0 | 2.79 | 2.79 | None | OG | 0.15 | Yes
68 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | EXKHLN | 0 | 1.38 | 460 | 0 | C | 1
69 | KISH/PW-02 | Construction of 2-vent Bata Khal Regulator at 12.09 km | REGCN | 12.09 | 12.09 | 1 | 2 | C | 1
70 | KISH/PW-02 | Submersible Embankment from 11.95 to 12.33=0.315 Km | SEMBCN | 11.95 | 12.23 | 0.315 | None | C | 1
71 | KISH/PW-02 | Diakul Khal from km 1.710 to m 4.690=2.980 | EXKHLN | 1.7 | 4.69 | 2.99 | 0 | C | 1
72 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | EXKHLN | 0.18 | 4.655 | 4.475 | 0 | C | 1
73 | KISH/PW-03 | Constriction of Kata Khali Khal Regulator 1-V (1.5m x 1.8m ) at km 23.846 (Part-A) | REGCN | 23.85 | 23.85 | 1 | 1 | OG | 0.98
74 | KISH/PW-03 | Submersible Embankment from 7.366 to 17.749 Part-A | SEMBCN | 7.369 | 17.749 | 10.383 | None | OG | 0.97
75 | KISH/PW-04 | Construction of Northern Depression Regulator 1-Vent (1.50mx1.80m) at km. 2.62 (Part- B) | REGCN | 2.62 | 2.62 | 1 | 1 | C | 1
76 | KISH/PW-04 | SamarbariKhal Regulator 4-Vent (1.50mx1.80m) at km. 0.78 (Part- C) | REGCN | 0.78 | 0.78 | 1 | 4 | C | 1
77 | KISH/PW-04 | Construction of Southern Depression Regulator 1-Vent (1.50mx1.80m) at km. 6.20 (Part- B) | REGCN | 6.2 | 6.2 | 1 | 1 | C | 1
78 | KISH/PW-04 | Submersible Embankment from 0.007 to 6.541 Part-B | SEMBCN | 0.007 | 6.541 | 6.534 | None | C | 1
79 | KISH/PW-05 | Construction of Kata Khal Regulator 3-Vent (1.50mx1.80m) at km. 15.30 | REGCN | 15.3 | 15.3 | 1 | 3 | C | 1
80 | KISH/PW-05 | Submersible Embankment from 0 to 19.377 Part-C | SEMBCN | 0 | 19.377 | 12.214 | None | OG | 0.05 | Yes
81 | KISH/PW-06 | Samarbari Khal | EXKHLN | 0 | 3.99 | 3.99 | 0 | C | 1
82 | KISH/PW-06 | Construction of Mahindra Khal Regulator (4V-1.5 x 1.80m) at km 12.18. | REGCN | 12.18 | 12.18 | 1 | 4 | C | 1
83 | KISH/PW-06 | Kata Khali Khal | EXKHLN | 0.2 | 4 | 3.8 | 0 | C | 1
84 | KISH/PW-06 | Mahinhandra Khal | EXKHLN | 1 | 1.9 | 0.9 | 0 | C | 1
85 | KISH/PW-06 | Kata Khal | EXKHLN | 0 | 0.6 | 0.6 | 0 | C | 1
86 | KISH/PW-06 | Kurigai Gang | EXRIVN | 0 | 8.38 | 8.38 | 0 | C | 1
87 | KISH/PW-06 | Beri Gang | EXRIVN | 0 | 3.56 | 3.56 | 0 | C | 1
88 | KISH/PW-07 | Baniajan Khal | EXKHLN | 0.16 | 7.06 | 6.9 | 0 | C | 1
89 | KISH/PW-07 | Diga Nadi | EXRIVN | 2.5 | 8.1 | 5.6 | 0 | OG | 0.9
90 | KISH/PW-07 | Suti Khal | EXKHLN | 0 | 6.1 | 6.1 | 0 | C | 1
91 | KISH/PW-07 | Dampara Khal | EXKHLN | 0.04 | 3.6 | 3.56 | 0 | OG | 0.6 | Yes
92 | KISH/PW-07 | Construction of Submersible embnakment In between km. 0.000to km. 56.949) =3.879 km. | SEMBCN | 0 | 56.949 | 3.879 | 0 | OG | 0.06 | Yes
93 | KISH/PW-07 | Karpasha Khal | EXKHLN | 0.1 | 1.615 | 1.515 | 0 | C | 1
94 | KISH/PW-07 | Hajirkhali Khal | EXKHLN | 0.175 | 1.81 | 1.635 | 0 | OG | 0.2 | Yes
95 | KISH/PW-07 | Old Singua River | EXRIVN | 7.3 | 14.4 | 7.1 | 0 | OG |  | Yes
96 | KISH/PW-09 | 4m Karpasha at km 27 in Boro Haor Project | CASWCN | 27 | 27 | 1 | 4 | C | 1
97 | KISH/PW-09 | 6m Dampara at km 33.3 in Boro Haor Project | CASWCN | 33.3 | 33.3 | 1 | 6 | C | 1
98 | KISH/PW-09 | 2- vent box drainage outlet of Mohorkona of Nunnir haor. | BOXSLCN | 7.74 | 7.74 | 1 | 0 | C | 1
99 | KISH/PW-09 | 6.0m Causeway at Samarbari of Nunnir Haor. | CASWCN | 0.78 | 0.78 | 1 | 6 | C | 1
100 | KISH/PW-10 | Submersible embankment in between km 0.020 to km 12.400=11.750 | SEMBCN | 0.02 | 12.4 | 11.75 | None | OG | 0.51 | Yes
101 | KISH/PW-10 | 6m Gazipur Causeway at Km 12.34 | CASWCN | 12.34 | 12.34 | 1 | 1 | OG | 0.1 | Yes
102 | KISH/PW-10 | 1-vent 1.50X1.80 Regulator at Jalalpur 22.64 km | REGCN | 22.64 | 22.64 | 1 | 4 | OG | 0.15 | Yes
103 | KISH/PW-11 | Construction of Submersible Embankment in between km 12.400 to km 23.260 | SEMBCN | 12.4 | 23.26 | 10.857 | None | OG | 0.65 | Yes
104 | KISH/PW-11 | 2-Vent Lalpur Khal Regulator at Km16.13 in Noapara Haor Project | REGCN | 16.13 | 16.13 | 1 | 2 | OG | 0.95
105 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | EXKHLN | 0.2 | 0.8 | 0.6 | 0 | C | 1
106 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km, | EXKHLN | 0.3 | 3.3 | 3 | 0 | C | 1
107 | KISH/PW-12 | Lalpurkhal km 0.410 to km 4.40 = 3.900 km, | EXKHLN | 0.41 | 4.4 | 3.99 | 0 | OG |  | Yes
108 | KISH/PW-12 | 3-Vent Naluar Khal Regulator at Km 4.77 in Noapara Haor Project | REGCN | 4.77 | 4.77 | 1 | 3 | C | 1
109 | KISH/PW-12 | 4-Vent Mohorkona Regulator at Km 1.64 in Noapara Haor Project | REGCN | 1.64 | 1.64 | 1 | 4 | OG | 0.96 | Yes
110 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | EXKHLN | 4 | 6.8 | 2.8 | 0 | C | 1
111 | KISH/PW-13 | Submersible Embankment from KM 0.00 0to KM 10.000 (Part-A)) | SEMBCN | 0 | 10 | 10 | 0 | OG | 0.6 | Yes
112 | KISH/PW-13 | 2-Vent Bera Khal Regulator at Km 4.07 in Naogaon Haor Project | REGCN | 4.07 | 4.07 | 1 | 2 | C | 1
113 | KISH/PW-13 | 3-Vent Pangair Dair Khal Regulator at Km 2.09 in Naogaon Haor Project | REGCN | 2.09 | 2.09 | 1 | 3 | OG | 0.92 | Yes
114 | KISH/PW-14 | Submergible Embankment from KM 10.000 to 28.900=16.900 KM (Part-A) | SEMBCN | 10 | 28.9 | 16.9 | 0 | OG | 0.9 | Yes
115 | KISH/PW-14 | 2-Vent Regulator Gokhra at Km 6.04 in Naogaon Haor Project | REGCN | 6.04 | 6.04 | 1 | 2 | OG | 0.96 | Yes
116 | KISH/PW-15 | 2-Vent Khayer Khal Regulator at Km 5.56 in Naogaon Haor Project | REGCN | 5.56 | 5.56 | 1 | 2 | P
117 | KISH/PW-15 | Submersible Embankment from 0.000 to 9.00-(Part-B) | SEMBCN | 0 | 9 | 36.104 | 0 | C | 1
118 | KISH/PW-16 | 2-Vent Markhali Khal Regulator at Km 33.8 in Naogaon Haor Project | REGCN | 33.8 | 33.8 | 1 | 3 | OG | 0.85 | Yes
119 | KISH/PW-16 | Submergible Embankment from KM 9.000 to KM 30.420=14.120 KM (Part-B) | SEMBCN | 9 | 30.42 | 14.12 | 0 | C | 1
120 | KISH/PW-17 | Box Sluice at Km6.65 in Naogaon Haor Project | BOXSLCN | 6.65 | 6.65 | 1 | 0 | OG | 0.5 | Yes
121 | KISH/PW-17 | Irrigation Inlet No-39 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
122 | KISH/PW-17 | Irrigation Inlet No-40 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
123 | KISH/PW-17 | Irrigation Inlet No-43 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
124 | KISH/PW-17 | Box Sluice at Km11.21 in Naogaon Haor Project | BOXSLCN | 11.21 | 11.21 | 1 | 0 | C | 1
125 | KISH/PW-17 | Box Sluice at Km18.24 in Naogaon Haor Project | BOXSLCN | 18.24 | 18.24 | 1 | 0 | C | 1
126 | KISH/PW-17 | 1-Vent Bagadia Khal Regulator at Km 14.52 in Naogaon Haor Project | REGCN | 14.52 | 14.52 | 1 | 2 | OG | 0.96
127 | KISH/PW-17 | 4-Vent Neora Khal Regulator at Km 44.230 in Naogaon Haor Project | REGCN | 44.15 | 44.15 | 1 | 4 | OG | 0.9
128 | KISH/PW-17 | Submersible Embankment from 30.420 to 44.200=13.170 KM-(Part-B) | SEMBCN | 30.42 | 44.2 | 13.17 | 0 | C | 1
129 | KISH/PW-17 | Irrigation Inlet No-41 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
130 | KISH/PW-17 | Irrigation Inlet No-61 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
131 | KISH/PW-17 | Box Sluice at Km13.7 in Naogaon Haor Project | BOXSLCN | 13.7 | 13.7 | 1 | 0 | C | 1
132 | KISH/PW-17 | Irrigation Inlet No-46 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
133 | KISH/PW-17 | Irrigation Inlet No-47 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
134 | KISH/PW-17 | Irrigation Inlet No-48 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
135 | KISH/PW-17 | Irrigation Inlet No-49 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
136 | KISH/PW-17 | Irrigation Inlet No-50 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
137 | KISH/PW-17 | Irrigation Inlet No-51 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
138 | KISH/PW-17 | Irrigation Inlet No-52 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
139 | KISH/PW-17 | Irrigation Inlet No-53 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
140 | KISH/PW-17 | Irrigation Inlet No-37 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
141 | KISH/PW-17 | Irrigation Inlet No-58 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
142 | KISH/PW-17 | Irrigation Inlet No-38 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
143 | KISH/PW-17 | Irrigation Inlet No-59 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
144 | KISH/PW-17 | Irrigation Inlet No-56 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
145 | KISH/PW-17 | Irrigation Inlet No-54 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
146 | KISH/PW-17 | Irrigation Inlet No-60 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
147 | KISH/PW-17 | Irrigation Inlet No-42 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
148 | KISH/PW-17 | Irrigation Inlet No-57 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
149 | KISH/PW-17 | Irrigation Inlet No-44 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
150 | KISH/PW-17 | Box Sluice at Km9.39 in Naogaon Haor Project | BOXSLCN | 9.39 | 9.39 | 1 | 0 | C | 1
151 | KISH/PW-17 | Irrigation Inlet No-45 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
152 | KISH/PW-17 | Irrigation Inlet No-55 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
153 | KISH/PW-18 | MarkhaliKhal 6.6 m causeway at km 39.07 in Naogaon Haor Project | CASWCN | 39.07 | 39.07 | 1 | 6 | OG | 0.7 | Yes
154 | KISH/PW-18 | NeoraKhal 4m causeway at km 44.2 in Naogaon Haor Project | CASWCN | 44.2 | 44.2 | 1 | 4 | OG | 0.85
155 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM | EXKHLN | 0.495 | 8.405 | 7.91 | 0 | C | 1
156 | KISH/PW-18 | MarkhaliKha l from KM 1.01 to KM 4.120=3.11 KM | EXKHLN | 1.01 | 4.12 | 3.11 | 0 | OG
157 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 | EXKHLN | 0 | 5.985 | 5.99 | 0 | C | 1
158 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | EXKHLN | 0.12 | 2.635 | 2.52 | 0 | C | 1
159 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM | EXKHLN | 0.185 | 0.91 | 0.73 | 0 | C | 1
160 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | EXKHLN | 0.52 | 2.03 | 1.51 | 0 | OG
161 | KISH/PW-18 | PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM | EXKHLN | 0.08 | 4.36 | 4.28 | 0 | OG
162 | KISH/PW-18 | DheuhalKhal 4m causeway at km 12.44 in Naogaon Haor Project | CASWCN | 12.44 | 12.44 | 1 | 4 | OG
163 | KISH/PW-18 | KhaiyarKhal 4m causeway at km 24.06 in Naogaon Haor Project | CASWCN | 24.06 | 24.06 | 1 | 4 | OG
164 | KISH/PW-19 | Re-excavation of Atoplal River from KM 0.000 to KM 7.113 | EXRIVN | 0 | 7.113 | 7.11 | 0 | OG | 0.35
165 | KISH/PW-19 | Re-excavation of Berachapra River from KM 0.000 to KM 15.820 | EXRIVN | 0 | 15.82 | 15.82 | 0 | OG | 0.22
166 | KISH/PW-20 | Construction of 4m Chhitra Khal causeway at km 21.77 in Nunnir Haor Project | CASWCN | 21.77 | 21.77 | 1 | 4 | C | 1
167 | KISH/PW-20 | 4m Nabinpur Khal Causeway at Km 23.380 | CASWCN | 23.38 | 23.28 | 1 | 4 | C | 1
168 | KISH/PW-20 | 4m Dipjurikhal Causeway at Km 27.000 | CASWCN | 27 | 27 | 1 | None | OG | 0.9 | Yes
169 | KISH/PW-20 | 4m Sudhikhal Causeway at Km 33.300 | CASWCN | 33.3 | 33.3 | 1 | 4 | OG | 0.9 | Yes
170 | KISH/PW-20 | Box Sluice near Nasir at 7.740 of Nunnir Haor Project | BOXSLCN | 7.74 | 7.74 | 1 | 0 | OG | 0.95
171 | KISH/PW-20 | Box Sluice Chagaliakhal at Km 10.480 | BOXSLCN | 10.48 | 10.48 | 1 | 0 | OG | 0.95
172 | KISH/PW-20 | Boxsluice Singhpurkhal at Km 11.170 in Noapa Haor | BOXSLCN | 11.17 | 11.17 | 1 | 0 | OG | 0.95
173 | KISH/PW-20 | Boxsluice Gorucharakhal at Km 10.000 in Noapara Haor | BOXSLCN | 10 | 10 | 1 | 0 | OG |  | Yes
174 | KISH/PW-20 | Irrigation Inlet No-32 in Noapara Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.86
175 | KISH/PW-20 | Irrigation Inlet No-33 in Noapara Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.22
176 | KISH/PW-21 | Construction of Kursi Khal Regulatior 2-vent 1.50m x 1.80m at km 16.10 | REGCN | 16.1 | 16.1 | 1 | 2 | OG | 0.6
177 | KISH/PW-21 | Construction of Chouganga Khal Regulatior 1-vent 1.50m x 1.80m at km 24.40 | REGCN | 24.4 | 24.4 | 1 | 1 | OG | 0.58
178 | KISH/PW-21 | Sub-Mergible Emabankment from km 2.565 to km 12.059=9.494 km | SEMBCN | 2.565 | 12.059 | 9.494 | 0 | OG |  | Yes
179 | KISH/PW-22 | Irrigation Inlet No-62 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
180 | KISH/PW-22 | Irrigation Inlet No-64 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
181 | KISH/PW-22 | Irrigation Inlet No-65 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
182 | KISH/PW-22 | Irrigation Inlet No-66 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
183 | KISH/PW-22 | Irrigation Inlet No-63 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
184 | KISH/PW-22 | Irrigation Inlet No-67 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
185 | KISH/PW-22 | Box Sluice at Km23.6 in Badla Haor Project | BOXSLCN | 23.6 | 23.6 | 1 | 0 | OG
186 | KISH/PW-22 | Box Sluice at Km22.3 in Badla Haor Project | BOXSLCN | 22.3 | 22.3 | 1 | 0 | OG
187 | KISH/PW-22 | Box Sluice at Km19.5 in Badla Haor Project | BOXSLCN | 19.5 | 19.5 | 1 | 0 | OG
188 | KISH/PW-22 | 4m Kalnakhal causeway at km 7.500 in Badla Haor Project | CASWCN | 7.5 | 7.5 | 1 | 4 | OG | 0.05 | Yes
189 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | EXKHLN | 0 | 0.439 | 0.439 | 0 | OG
190 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | EXKHLN | 0 | 1.7 | 1.7 | 0 | C | 1
191 | KISH/PW-22 | Chouganga Khal from km. 1.700 to 1.900 km | EXKHLN | 1.7 | 1.9 | 0.2 | 0 | OG
192 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | EXKHLN | 0 | 1.4 | 1.4 | 0 | OG
193 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | EXKHLN | 0 | 2.9 | 2.9 | 0 | OG | 0.35
194 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | EXKHLN | 0 | 0.584 | 0.584 | 0 | OG
195 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | EXKHLN | 0 | 1 | 1 | 0 | OG | 0.6
196 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | EXKHLN | 0 | 0.7 | 0.7 | 0 | c | 1
197 | KISH/PW-22 | Sajna Khal from km. 0.000 to km. 1.000 | EXKHLN | 0 | 1 | 1 | 0 | OG
198 | KISH/PW-22 | Submersible Embankment from 12.059 to 26.998 Total Length 10.463 | SEMBCN | 12.059 | 26.8 | 10.463 | 0 | OG | 0.77 | Yes
199 | KISH/PW-23 | Submersible Embankment from 2.469 to 6.979=4.510 | SEMBCN | 2.469 | 6.979 | 4.51 | 0 | C | 1
200 | KISH/PW-23 | Box Sluice Mogarkhal at Km2.74 in Chatal Haor Project | BOXSLCN | 2.74 | 2.74 | 1 | 0 | C | 1
201 | KISH/PW-23 | Re-excavation of Mogar Khal from Km 0.000 to 0.150 | EXKHLN | 0 | 0.15 | 0.15 | 0 | C | 1
202 | KISH/PW-23 | Re-excavation of Mozilla Khal from Km 0.000 to 1.775 | EXKHLN | 0 | 1.775 | 1.775 | 0 | OG | 0.45 | Yes
203 | KISH/PW-23 | 2-Vent NoaparakhaliKhal Regulator at Km 5.73 in Chatal Haor Project | REGCN | 5.73 | 5.73 | 1 | 2 | OG | 0.93
204 | KISH/PW-23 | 2-Vent Mozila Khal Regulator at Km 12.250 in Chatal Haor Project | REGCN | 12.25 | 12.25 | 1 | 2 | OG | 0.93
205 | KISH/PW-23 | Irrigation Inlet No-68 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
206 | KISH/PW-23 | Irrigation Inlet No-69 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
207 | KISH/PW-23 | Irrigation Inlet No-70 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
208 | KISH/PW-23 | Irrigation Inlet No-71 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | C | 1
209 | KISH/PW-24 | Submersible Embankment from Km 0.000 to Km 33.520 | SEMBCN | 0 | 33.52 | 19.843 | None | C | 1
210 | KISH/PW-25 | Irrigation Inlet No-73 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
211 | KISH/PW-25 | Irrigation Inlet No-75 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
212 | KISH/PW-25 | Irrigation Inlet No-76 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
213 | KISH/PW-25 | 5-Vent Regulator at Km 23.19 in Dakhshiner Haor Project | REGCN | 23.19 | 23.19 | 1 | 5 | OG | 0.85
214 | KISH/PW-25 | Shankirkhal from km 0.290 to km 8.885 = 8.595 km | EXKHLN | 0.41 | 8.995 | 8.585 | 0 | OG | 0.82
215 | KISH/PW-25 | Bantai river from km 0.000 to km 1.650 | EXRIVN | 0 | 1.65 | 1.65 | 0 | OG | 0.2
216 | KISH/PW-25 | 4m causeway at km 0.02 in Dakhshiner Haor Project | CASWCN | 0.02 | 0.02 | 1 | 4 | OG | 0.75
217 | KISH/PW-25 | 6m causeway at km 23.46 in Dakhshiner Haor Project | CASWCN | 23.46 | 23.46 | 1 | 6 | OG | .
218 | KISH/PW-25 | 6m causeway at km 12.38 in Dakhshiner Haor Project | CASWCN | 12.38 | 12.38 | 1 | 6 | OG
219 | KISH/PW-25 | Box Sluice at Km24.23 in Dakhshiner Haor Project | BOXSLCN | 24.23 | 24.23 | 1 | 0 | OG
220 | KISH/PW-25 | Irrigation Inlet No-72 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
221 | KISH/PW-25 | Irrigation Inlet No-86 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
222 | KISH/PW-25 | Irrigation Inlet No-85 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
223 | KISH/PW-25 | Irrigation Inlet No-84 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
224 | KISH/PW-25 | Irrigation Inlet No-83 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
225 | KISH/PW-25 | Irrigation Inlet No-82 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
226 | KISH/PW-25 | Irrigation Inlet No-81 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
227 | KISH/PW-25 | Irrigation Inlet No-80 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
228 | KISH/PW-25 | Irrigation Inlet No-79 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
229 | KISH/PW-25 | Irrigation Inlet No-78 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.8
230 | KISH/PW-25 | Irrigation Inlet No-77 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
231 | KISH/PW-25 | Irrigation Inlet No-74 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
232 | KISH/PW-26 | KalnaKhal from km 14.200 to km 17.200 = 1.140 km | EXKHLN | 14.2 | 17.2 | 1.14 | 0 | OG | 0.33 | Yes
233 | KISH/PW-26 | Phulesswari khal (New) from km 0.000 to km 4.715 = 4.715 km | EXKHLN | 0 | 4.715 | 4.715 | 0 | C | 1
234 | KISH/PW-26 | Phulesswari khal (Old) from km 3.250 to km 3.760 = 0.510 km | EXKHLN | 3.25 | 3.76 | 0.51 | 0 | C | 1
235 | KISH/PW-26 | Construction of Submersible Embankment in between Km 8.200 to 18.030=0.540 | SEMBCN | 8.2 | 18.03 | 0.54 | 0 | C | 1
236 | KISH/PW-26 | Suti Nadi from km 2.200 to km 17.700= 15.500 km | EXRIVN | 2.2 | 17.7 | 15.5 | 0 | C | 1
237 | KISH/PW-27 | Drainage box outlet at km | BOXSLCN | 0 | 0 | 1 | 0
238 | KISH/PW-27 | Drainage box outlet at km 17.74 | BOXSLCN | 17.74 | 17.74 | 1 | 0
239 | KISH/PW-27 | 4mchonati causeway | CASWCN | 9.84 | 9.84 | 1 | 4
240 | KISH/PW-27 | Constration of 1 vent (1.80m x 1.50 ) kalna regulatior at km 16.170 1 no. | REGCN | 16.17 | 16.17 | 1 | 1
241 | KISH/PW-27 | 6m Suti causeway | CASWCN | 17.71 | 17.71 | 1 | 6
242 | KISH/PW-27 | Constration of 1vent (1.80m x 1.50 m) Phulesgwari Regulator at km 8.241 | REGCN | 8.24 | 8.24 | 1 | 1
243 | NETR/PW-01 | Singer Beel full embankment scheme in between km 0.911 to km 11.60=10.69km, Volume- 87873.05 cum (Total length = 46.21km), | EMBRR | 0 | 11.6 | 10.69 | 0 | OG | 0.7
244 | NETR/PW-01 | Re-sectioning of full embankment of Dampara Water Management project in between km 0.00 to km 41.771= 35.828 km, Volume- 515681.07 cum | EMBRR | 0 | 41.771 | 35.828 | 0 | OG | 0.7
245 | NETR/PW-02 | DupikhaliKhal from km 0.00 to km.3.66=3.66 km, km 10.80 to km.15.857=5.057 km | EXKHLR | 0 | 10.8 | 5.057 | 0 | C | 1
246 | NETR/PW-02 | AndaKhal From km 0.055 to km.7.247=7.192 km | EXKHLR | 0.055 | 7.247 | 7.192 | 0 | C | 1
247 | NETR/PW-02 | DhalaiKhal in between km 0.00 to km 15.016=7.37 | EXKHLR | 0 | 15.016 | 7.37 | None | OG
248 | NETR/PW-02 | KurikuniaKhal from km 0.00 to km.1.903=1.903 km | EXKHLR | 0 | 1.903 | 1.903 | 0 | C | 1
249 | NETR/PW-02 | TutnirKhal in between km 0.00 to km.3.45=3.15km | EXKHLR | 0 | 3.45 | 3.15 | 0 | OG
250 | NETR/PW-02 | DighjanKhal From km 3.62 to km.7.94=4.32 km | EXKHLR | 3.62 | 7.94 | 4.32 | 0 | OG | 0.25
251 | NETR/PW-02 | DudkuraKhal From km 0.170 to km.5.570=5.40 km | EXKHLR | 0.17 | 5.57 | 5.4 | 0 | C | 1
252 | NETR/PW-02 | BaliaKhal from km 0.00 to km 5.896=5.896km | EXKHLR | 0 | 5.896 | 5.896 | None | OG | 0.3
253 | NETR/PW-02 | KamalpurKhal from km 0.00 to km.2.983=2.983km | EXKHLR | 0 | 2.983 | 0 | 0 | OG | 0.35
254 | NETR/PW-03 | Re-sectioning of submersible embankment (Singer bee-3.56km, volume-14852.987 cum), | SEMBRN | 0 | 0 | 3.56 | 0 | C | 1
255 | NETR/PW-03 | Re-Installation of Regulator 5Vent (1.8m x 1.5m)= 1 no (Dampara) | REGRR | 0 | 0 | 0 | 0 | OG | 0.3
256 | NETR/PW-03 | Re-sectioning of full embankment (Kangsha-20.90km, volume-297422.656 cum), | EMBRR | 0 | 0 | 20.9 | 0 | C | 1
257 | NETR/PW-04 | Naiyori Khal from km 0.00 to km 7.565 5.27 km | EXRIVR | 0 | 7.056 | 7.065 | 0 | C | 1
258 | NETR/PW-04 | Re-excavation of Piyan River from km 0.075 to km 5.00 4.925 km | EXRIVR | 0.075 | 5 | 4.925 | 0 | OG | 0.5
259 | NETR/PW-04 | Resectioning of Submersible Embankment in between 0.000 to 48.350 total 9.75 km | EMBRR | 0 | 48.35 | 9.75 | 0 | C | 1
260 | NETR/PW-04 | Putia khal From km.0.00 to km. 5.235 5.235 km | EXKHLR | 0 | 5.325 | 5.325 | 0 | C | 1
261 | NETR/PW-04 | Jhalokhali khal from km 0.00 to km 6.7 6.70 km | EXKHLR | 0 | 6.7 | 6.7 | 0 | C | 1
262 | NETR/PW-04 | Feni khal from km 0.00 to 1.903 1.93 km | EXKHLR | 0 | 1.903 | 1.903 | 0 | C | 1
263 | NETR/PW-05 | Construction of 1 vent 1.80 m x1.50 m Ichamati Regulator at km 29.670 | REGCN | 29.67 | 29.67 | 1 | 1 | OG | 0.65
264 | NETR/PW-05 | Construction of 4-vent Regulator over Boilara khal at km. 7.61 | REGCN | 7.61 | 7.61 | 1 | 4 | OG | 0.65
265 | NETR/PW-05 | Construction of submersible embankment of Ganesh Haor Sub-project in between Km 6.8 to km 24.855 Total Length 3.071 km | SEMBCN | 6.8 | 24.855 | 3.071 | 0 |  |  | GjvKvevmx PvB bv
266 | NETR/PW-05 | Construction of 1 vent 1.80 m x1.50 m Chapri Regulator at km 27.270 | REGCN | 27.27 | 27.27 | 1 | 1 | C | 1
267 | NETR/PW-05 | Construction of 1 vent 1.80 m x1.50 m Ukra Regulator at km 18.02 | REGCN | 18.02 | 18.02 | 1 | 1 | C | 1
268 | NETR/PW-06 | Construction of Box Drainage Outlet Box Sluice at Km15.16 in Ganesh Haor Project | BOXSLCN | 15.16 | 15.16 | 1 | 0 | C | 1
269 | NETR/PW-06 | Rehabilitation of Existing 4 vent regulator at KM 20.11over the Nasir khal | REGRN | 20.11 | 20.11 | 1 | 0 | C | 1
270 | NETR/PW-06 | Boilara khal From km. 8.550 to km.8.900 =0.35 | EXKHLN | 8.55 | 8.99 | 0.35 | 0 | C | 1
271 | NETR/PW-06 | Ichamati khal from km 0.072 to km 1.250 1.178 | EXKHLN | 0.072 | 1.25 | 1.178 | 0 | C | 1
272 | NETR/PW-06 | Chapri khal from km 0.280 to 2.590=2.310 km | EXKHLN | 0.28 | 2.59 | 2.31 | 0 | C | 1
273 | NETR/PW-06 | Ukhra Khal from km 0.110 to km 2.043=1.933 km, | EXKHLN | 0.11 | 2.043 | 1.933 | 0 | C | 1
274 | NETR/PW-06 | Narsua River from km 0.00 to km 6.225=6.226 km | EXRIVN | 0 | 6.225 | 6.225 | 0 | C | 1
275 | NETR/PW-06 | Construction of Box Drainage Outlet of Box Sluice at Km24.58 in Ganesh Haor Project | BOXSLCN | 24.58 | 24.58 | 1 | 0 | C | 1
276 | NETR/PW-06 | Construction of Irrigation Inlet at Km 0.60 | IRINCN | 0 | 0 | 1 | 0 | C | 1
277 | NETR/PW-06 | Construction of Irrigation Inlet at Km 7.8 | IRINCN | 0 | 0 | 1 | 0 | C | 1
278 | NETR/PW-07 | Gunai river From km.0.00 to km.9.00 = km.9.00 (Total=24.00km) | EXRIVR | 0 | 9 | 9 | 0 | C | 1
279 | NETR/PW-07 | Lower Kangsha river from km 54.42 to km 69.42= km15.00. | EXRIVR | 54.42 | 69.32 | 15 | 0 | C | 1
280 | NETR/PW-08 | Box Sluice at Km7.8 in Dharmapasha Rui Beel Project | BOXSLCN | 7.8 | 7.8 | 1 | 0 | OG
281 | NETR/PW-08 | Agunia Regulator 2-vent -1.5m x 1.8m at km 47.31 | REGCN | 47.31 | 47.31 | 0 | 2 | OG | 0.6
282 | NETR/PW-08 | Irrigation Inlet No-113 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0 | OG
283 | NETR/PW-08 | Irrigation Inlet No-105 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0 | OG
284 | NETR/PW-08 | Box Sluice at Km48.05 in Dharmapasha Rui Beel Project | BOXSLCN | 48.05 | 48.05 | 1 | 0 | OG
285 | NETR/PW-08 | Box Sluice at Km43.13 in Dharmapasha Rui Beel Project | BOXSLCN | 43.13 | 43.13 | 1 | 0 | OG
286 | NETR/PW-08 | Box Sluice at Km40.66 in Dharmapasha Rui Beel Project | BOXSLCN | 40.66 | 40.66 | 1 | 0 | OG
287 | NETR/PW-08 | Dharam Beel Regulator 2-vent- 1.5m x 1.8m at km 54.42 = 2 nos. | REGCN | 54.42 | 54.42 | 0 | 2 | OG
288 | NETR/PW-08 | Box Sluice at Km33.08 in Dharmapasha Rui Beel Project | BOXSLCN | 33.08 | 33.08 | 1 | 0 | OG
289 | NETR/PW-08 | Irrigation Inlet No-116 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0 | OG
290 | SUNM/PW-01 | Dariabaz Khal | EXKHLN | 0 | 1.5 | 1.5 | 0 | C | 1
291 | SUNM/PW-01 | Irrigation Inlet No-123 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
292 | SUNM/PW-01 | Irrigation Inlet No-128 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
293 | SUNM/PW-01 | Irrigation Inlet No-129 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
294 | SUNM/PW-01 | Irrigation Inlet No-127 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
295 | SUNM/PW-01 | Irrigation Inlet No-130 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
296 | SUNM/PW-01 | Irrigation Inlet No-131 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
297 | SUNM/PW-01 | Irrigation Inlet No-126 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
298 | SUNM/PW-01 | Irrigation Inlet No-125 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
299 | SUNM/PW-01 | Irrigation Inlet No-124 in Dhakua Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG
300 | SUNM/PW-01 | Box Sluice No-7 at Km14.72 in Dhakua Haor Project | BOXSLCN | 0 | 0 | 1 | 0 | OG | 0.8
301 | SUNM/PW-01 | Submersible Embankment in between 10.600 to 49.426 total 33.849 km | SEMBCN | 10.6 | 49.426 | 33.849 | 0 | OG | 0.58
302 | SUNM/PW-01 | Box Sluice No-6 at Km14.72 in Dhakua Haor Project | BOXSLCN | 14.72 | 14.72 | 1 | 0 | OG | 0.8
303 | SUNM/PW-01 | Box Sluice No-5 at Km19.93 in Dhakua Haor Project | BOXSLCN | 19.93 | 19.93 | 1 | 0 | OG
304 | SUNM/PW-01 | Box Sluice No-4 at Km28.2 in Dhakua Haor Project | BOXSLCN | 28.2 | 28.2 | 1 | 0 | OG | 0.25
305 | SUNM/PW-01 | Box Sluice No-3 at Km50.74 in Dhakua Haor Project | BOXSLCN | 50.74 | 50.74 | 1 | 0 | OG
306 | SUNM/PW-01 | Box Sluice No-2 at Km53.78 in Dhakua Haor Project | BOXSLCN | 53.78 | 53.78 | 1 | 0 | OG | 0.8
307 | SUNM/PW-01 | Box Sluice No-1 at Km55.4 in Dhakua Haor Project | BOXSLCN | 55.4 | 55.4 | 1 | 0 | OG | 0.8
308 | SUNM/PW-01 | Muktakhai Khal | EXKHLN | 0 | 3.2 | 3.2 | None | C | 1
309 | SUNM/PW-01 | Juringa Khal | EXKHLN | 0 | 1.5 | 1.5 | 0 | OG | 0.15
310 | SUNM/PW-01 | Puknarai Khal | EXKHLN | 0 | 1.56 | 1.56 | 0 | OG | 0.32
311 | SUNM/PW-02 | Re-excavation of Piyan River from Km 19.000 to 55.575 total 36.575 | EXRIVN | 19 | 55.575 | None | None | OG | 0.7
312 | SUNM/PW-03 | 4m causeway at km 16.33 in Dhakua Haor Project No-3 | CASWCN | 0 | 0 | 1 | 4 | OG | 0.85
313 | SUNM/PW-03 | 1-Vent Regulator at Km26.45 in Dhakua Haor Project No-1 | REGCN | 25.72 | 25.72 | 1 | 1 | OG | 0.8
314 | SUNM/PW-03 | 2-Vent Regulator at Km27.51 in Dhakua Haor Project | REGCN | 26.45 | 26.45 | 1 | 2 | OG | 0.25
315 | SUNM/PW-03 | 6m causeway at km 18.56 in Dhakua Haor Project | CASWCN | 18.56 | 18.56 | 1 | 6 | OG | 0.1
316 | SUNM/PW-03 | 4m causeway at km 16.33 in Dhakua Haor Project No-1 | CASWCN | 16.33 | 16.33 | 1 | 4 | OG | 0.85
317 | SUNM/PW-03 | 4m causeway at km 16.33 in Dhakua Haor Project No-2 | CASWCN | 0 | 0 | 1 | 4 | OG
318 | SUNM/PW-03 | 4m causeway at km 16.33 in Dhakua Haor Project No-4 | CASWCN | 0 | 0 | 1 | 4 | OG
319 | SUNM/PW-03 | 4m causeway at km 16.33 in Dhakua Haor Project No-5 | CASWCN | 0 | 0 | 1 | 4 | OG
320 | SUNM/PW-04 | Submersible Embankment -34.94 km | SEMBCN | 0 | 71.71 | 42.05 | None | OG | 0.75 | Yes
321 | SUNM/PW-05 | Manai 6m causeway at km 38.74 in Dharmapasha Rui Beel Project | CASWCN | 38.74 | 38.74 | 1 | 6 | OG | 0.3
322 | SUNM/PW-05 | Dahar 4m causeway at km 27.77 in Dharmapasha Rui Beel Project | CASWCN | 27.77 | 27.77 | 1 | 4 | OG | 0.6
323 | SUNM/PW-05 | Dharagang 4m causeway at km 26.98 in Dharmapasha Rui Beel Project | CASWCN | 26.98 | 26.98 | 1 | 4 | OG | 0.8
324 | SUNM/PW-05 | Chandrasona Thal 4m causeway at km 22.27 in Dharmapasha Rui Beel Project | CASWCN | 22.27 | 22.27 | 1 | 4 | OG | 0.9
325 | SUNM/PW-05 | Dahar 4-Vent Regulator at Km2.07 in Dharmapasha Rui Beel Project | REGCN | 54.42 | 54.42 | 1 | 4 | OG | 0.7
326 | SUNM/PW-05 | Deola 2-Vent Regulator at Km54.42 in Dharmapasha Rui Beel Project | REGCN | 47.31 | 47.31 | 1 | 2 | OG | 0.6
327 | SUNM/PW-06 | Irrigation Inlet No-118 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0 |  |  | Yes
328 | SUNM/PW-06 | Irrigation Inlet No-117 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0 |  |  | Yes
329 | SUNM/PW-06 | Irrigation Inlet No-106 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0 |  |  | Yes
330 | SUNM/PW-06 | Irrigation Inlet No-104 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0 |  |  | Yes
331 | SUNM/PW-06 | Dharam khal | EXKHLN | 0 | 1.1 | 1.1 | 0 | C | 1
332 | SUNM/PW-06 | Islam Beel Khal | EXKHLN | 0 | 4.5 | 4.5 | 0 | C | 1
333 | SUNM/PW-06 | Khurma Khal | EXKHLN | 0 | 9 | 9 | 0 | C | 1
334 | SUNM/PW-06 | Undani Khal | EXKHLN | 0 | 4 | 4 | 0 | OG | 0.9 | Yes
335 | SUNM/PW-06 | Rui Beel Khal | EXKHLN | 0 | 3.5 | 3.5 | 0 | C | 1
336 | SUNM/PW-06 | Saitan Khal | EXKHLN | 0 | 3 | 3 | 0 | OG | 0.95 | Yes
337 | SUNM/PW-06 | Gobra Khal | EXKHLN | 0 | 3 | 3 | 0 | C | 1
338 | SUNM/PW-06 | Banni Link Khal | EXKHLN | 0 | 1.5 | 1.5 | 0 | OG | 0.1
339 | SUNM/PW-06 | Banni Khal-1 | EXKHLN | 0 | 2.6 | 2.6 | 0 | C | 1
340 | SUNM/PW-06 | Banni Khal-2 | EXKHLN | 0 | 2.9 | 2.9 | 0 | C | 1
341 | SUNM/PW-06 | Bir Khal | EXKHLN | 0 | 2.4 | 2.4 | 0
342 | SUNM/PW-06 | Irrigation Inlet No-107 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
343 | SUNM/PW-06 | Irrigation Inlet No-108 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
344 | SUNM/PW-06 | Irrigation Inlet No-109 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
345 | SUNM/PW-06 | Irrigation Inlet No-110 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
346 | SUNM/PW-06 | Irrigation Inlet No-111 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
347 | SUNM/PW-06 | Irrigation Inlet No-112 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
348 | SUNM/PW-06 | Irrigation Inlet No-114 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
349 | SUNM/PW-06 | Irrigation Inlet No-115 in Dharmapasha Rui Beel Project | IRINCN | 0 | 0 | 1 | 0
350 | SUNM/PW-06 | Box Sluice at Km1.75 in Dharmapasha Rui Beel Project No-1 | BOXSLCN | 1.75 | 1.75 | 1 | 0 |  |  | Yes
351 | SUNM/PW-06 | Dahar Gang | EXRIVN | 0 | 7 | 7 | 0 | C | 1
352 | SUNM/PW-06 | Kolma Khal | EXKHLN | 3.6 | 7 | 3.4 | 0 | C | 1
353 | SUNM/PW-06 | Dagar Khal | EXKHLN | 1.2 | 3.2 | 2 | 0 | C | 1
354 | SUNM/PW-06 | Agunia Khal | EXKHLN | 0 | 8 | 8 | 0 | C | 1
355 | SUNM/PW-06 | Rajapur Khal | EXKHLN | 0 | 2.8 | 2.8 | 0 | C | 1
356 | SUNM/PW-06 | Baraia Khal | EXKHLN | 0 | 2.7 | 2.7 | 0 | C | 1