## Resource_List
Code | Name | Unit
101 | Mixture Machine | Nos
102 | Excavator | Nos
103 | Compaction Ruller | Nos
104 | Form Work | Nos
201 | Cement | Bag
202 | Sand 1.5 FM | cum
203 | Stone Chips | cum
204 | Geotextile Filter | sqm
205 | Filter Sand | cum
206 | Peagravel | cum
207 | CC Block | Nos
301 | Labor | m-day
401 | Labor payment | BDT Lac

## Resources_Consumption
Code | Name | Unit | NS101 | 40-190-05 | 40-190-15 | 40-190-35 | 40-190-40 | 40-190-50 | NS105 | 16-240 | 40-550-10 | 40-500-40 | 40-530-30 | NS106 | NS102 | 16-510 | 40-450 | 16-470 | 40-380-20 | 48-100 | 40-670-30
101 | Mixture Machine | Nos | 0 | 0.0037037 | 0.0061728 | 0.0031546 | 0.0015798 | 0.0013333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Excavator | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0033 | 0 | 0 | 0 | 0 | 0 | 0.0033 | 0.0033 | 0.0033 | 0.0033 | 0 | 0
103 | Compaction Roller | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0013158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Form Work | Nos | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | Cement | Bag | 0 | 0.38448 | 0.6408 | 0.32809 | 0.16404 | 0.13841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21
202 | Sand 1.5 FM | cum | 0 | 0.033375 | 0.055625 | 0.02848 | 0.01424 | 0.012015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031
203 | Stone Chips | cum | 0 | 0.073209 | 0.12202 | 0.062472 | 0.031236 | 0.026355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | Filter Sand | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | Geotextile Filter | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | Peagravel | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | CC Block | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | Geobag | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
209 | Turfing Sod | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
211 | Gunnybag | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | Sheet Pile | mton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | MS Rod | Kg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | Labor | m-day | 0.7 | 0.11111 | 0.18519 | 0.094637 | 0.047393 | 0.04 | 0.4 | 0.1 | 0.18 | 0.018 | 0.18 | 0.0057143 | 0.7 | 0.1 | 0.1 | 0.1 | 0.016327 | 0.02 | 0.06
401 | Labor payment | BDT Thousand | 210 | 33 | 56 | 29 | 14 | 12 | 120 | 60 | 54 | 5.4 | 54 | 1.72 | 210 | 60 | 60 | 60 | 5 | 6 | 18

## WBS3
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | -1 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9

## Main
Name | Start | Finish | Allocation_Sheet_Name | Site Name
T_A_44M_M480_TO_M524 | 1 | 87 | T_A_44M_M480_TO_M524 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M480 to M524=44M under HFMLIP
T_A_35M_M1210_TO_M1245 | 1 | 87 | T_A_35M_M1210_TO_M1245 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M1210 to M1245=35M under HFMLIP
T_A_37M_M8760_TO_M8797 | 1 | 87 | T_A_37M_M8760_TO_M8797 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M8760 to M8797=37M under HFMLIP
T_A_200M_M10100_TO_M10300 | 1 | 87 | T_A_200M_M10100_TO_M10300 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M10100 to M10300=200M under HFMLIP
T_A_110M_M12330_TO_M12440 | 1 | 87 | T_A_110M_M12330_TO_M12440 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M12330 to M12440=110M under HFMLIP
T_A_72M_M12712_TO_M12784 | 1 | 87 | T_A_72M_M12712_TO_M12784 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M12712 to M12784=72M under HFMLIP
T_A_133M_M21600_TO_M21733 | 1 | 87 | T_A_133M_M21600_TO_M21733 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M21600 to M21733=133M under HFMLIP
T_A_105M_M22375_TO_M22480 | 1 | 87 | T_A_105M_M22375_TO_M22480 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M2735 to M22480=105M under HFMLIP
T_A_100M_M25170_TO_M525270 | 1 | 87 | T_A_100M_M25170_TO_M525270 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M25170 to M25720=100M under HFMLIP
T_A_180M_M25720_TO_M25900 | 1 | 87 | T_A_180M_M25720_TO_M25900 | Type A slope protection work of theDakshiner Haor Submergible Embankment from M25720 to M25900=180M under HFMLIP
T_A_78M_M25925_TO_M26003 | 1 | 87 | T_A_78M_M25925_TO_M26003 | Type A slope protection work of the Dakshiner Haor Submergible Embankment from M25925 to M26003=78M under HFMLIP
T_B5_425M_M9175_TO_M9600 | 1 | 87 | T_B5_425M_M9175_TO_M9600 | Type B5 slope protection work of the Dakshiner Haorr Submergible Embankment from M9175 to M9600=425M under HFMLIP
T_B5_167M_M9785_TO_M9952 | 1 | 87 | T_B5_167M_M9785_TO_M9952 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M9785 to M9952=167M under HFMLIP
T_B5_100M_M10300_TO_M10400 |  |  | T_B5_100M_M10300_TO_M10400 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M10300 to M10400=100M under HFMLIP
T_B5_255M_M12075_TO_M12330 |  |  | T_B5_255M_M12075_TO_M12330 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M12075 to M12330=255M under HFMLIP
T_B5_150M_M24950_TO_M25100 |  |  | T_B5_150M_M24950_TO_M25100 | Type B5 slope protection work of the Dakshiner Haor Submergible Embankment from M24950 to M25100=150M under HFMLIP
FF_15M_5560M |  |  | FF_15M_5560M | Construction of 15M Flood Fuse on Submersible Embankment M5560 of Noagaon Haor under HFMLIP

## T_A_44M_M480_TO_M524
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 3 | 1 | Nos | 1496 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 3 | 1 | Nos | 3603 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 581 | 16-240
6 | Placing Sand Filter | 4 | 4,5 | Cum | 61 | 40-550-10
7 | Placing Geotextile Filter | 4 | 4,5 | sqm | 686 | 40-500-40
8 | Placing Pea Gravel Filter | 4 | 4,5 | Cum | 69 | 40-530-30
9 | Placing CC Block | 4 | 4,5 | Nos | 5099 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_35M_M1210_TO_M1245
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 1190 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 5 | 1 | Nos | 2866 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 462 | 16-240
6 | Placing Sand Filter | 4 | 4,5 | Cum | 49 | 40-550-10
7 | Placing Geotextile Filter | 4 | 4,5 | sqm | 546 | 40-500-40
8 | Placing Pea Gravel Filter | 4 | 4,5 | Cum | 55 | 40-530-30
9 | Placing CC Block | 4 | 4,5 | Nos | 4056 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_37M_M8760_TO_M8797
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 1258 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 5 | 1 | Nos | 3030 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 489 | 16-240
6 | Placing Sand Filter | 4 | 4,5 | Cum | 52 | 40-550-10
7 | Placing Geotextile Filter | 4 | 4,5 | sqm | 577 | 40-500-40
8 | Placing Pea Gravel Filter | 4 | 4,5 | Cum | 58 | 40-530-30
9 | Placing CC Block | 4 | 4,5 | Nos | 4288 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_200M_M10100_TO_M10300
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 13 | 1 | Nos | 6800 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 13 | 1 | Nos | 16376 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 15 | 1 | Cum | 2640 | 16-240
6 | Placing Sand Filter | 17 | 4,5 | Cum | 276 | 40-550-10
7 | Placing Geotextile Filter | 17 | 4,5 | sqm | 3118 | 40-500-40
8 | Placing Pea Gravel Filter | 17 | 4,5 | Cum | 312 | 40-530-30
9 | Placing CC Block | 17 | 4,5 | Nos | 23176 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_110M_M12330_TO_M12440
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 14 | 1 | Nos | 3740 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 14 | 1 | Nos | 9007 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 30 | 1 | Cum | 4172 | 16-240
6 | Placing Sand Filter | 10 | 4,5 | Cum | 438 | 40-550-10
7 | Placing Geotextile Filter | 10 | 4,5 | sqm | 4927 | 40-500-40
8 | Placing Pea Gravel Filter | 10 | 4,5 | Cum | 494 | 40-530-30
9 | Placing CC Block | 10 | 4,5 | Nos | 12747 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_72M_M12712_TO_M12784
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 4 | 1 | Nos | 2448 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 10 | 1 | Nos | 5896 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 15 | 1 | Cum | 951 | 16-240
6 | Placing Sand Filter | 6 | 4,5 | Cum | 100 | 40-550-10
7 | Placing Geotextile Filter | 6 | 4,5 | sqm | 1123 | 40-500-40
8 | Placing Pea Gravel Filter | 6 | 4,5 | Cum | 113 | 40-530-30
9 | Placing CC Block | 6 | 4,5 | Nos | 8344 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_133M_M21600_TO_M21733
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 7 | 1 | Nos | 4522 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 17 | 1 | Nos | 10890 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 21 | 1 | Cum | 1756 | 16-240
6 | Placing Sand Filter | 12 | 4,5 | Cum | 184 | 40-550-10
7 | Placing Geotextile Filter | 12 | 4,5 | sqm | 2074 | 40-500-40
8 | Placing Pea Gravel Filter | 12 | 4,5 | Cum | 208 | 40-530-30
9 | Placing CC Block | 12 | 4,5 | Nos | 15412 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_105M_M22375_TO_M22480
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 5 | 1 | Nos | 3570 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 14 | 1 | Nos | 8598 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 21 | 1 | Cum | 1386 | 16-240
6 | Placing Sand Filter | 10 | 4,5 | Cum | 145 | 40-550-10
7 | Placing Geotextile Filter | 10 | 4,5 | sqm | 1637 | 40-500-40
8 | Placing Pea Gravel Filter | 10 | 4,5 | Cum | 164 | 40-530-30
9 | Placing CC Block | 10 | 4,5 | Nos | 12168 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_100M_M25170_TO_M525270
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 14 | 1 | Nos | 3400 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 14 | 1 | Nos | 8188 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 30 | 1 | Cum | 1320 | 16-240
6 | Placing Sand Filter | 10 | 4,5 | Cum | 138 | 40-550-10
7 | Placing Geotextile Filter | 10 | 4,5 | sqm | 1559 | 40-500-40
8 | Placing Pea Gravel Filter | 10 | 4,5 | Cum | 156 | 40-530-30
9 | Placing CC Block | 10 | 4,5 | Nos | 11588 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_180M_M25720_TO_M25900
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 9 | 1 | Nos | 6120 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 24 | 1 | Nos | 14739 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 40 | 1 | Cum | 5413 | 16-240
6 | Placing Sand Filter | 17 | 4,5 | Cum | 567 | 40-550-10
7 | Placing Geotextile Filter | 17 | 4,5 | sqm | 6393 | 40-500-40
8 | Placing Pea Gravel Filter | 17 | 4,5 | Cum | 641 | 40-530-30
9 | Placing CC Block | 17 | 4,5 | Nos | 20859 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_78M_M25925_TO_M26003
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 4 | 1 | Nos | 2652 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 10 | 1 | Nos | 6387 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 15 | 1 | Cum | 1030 | 16-240
6 | Placing Sand Filter | 6 | 4,5 | Cum | 108 | 40-550-10
7 | Placing Geotextile Filter | 6 | 4,5 | sqm | 1217 | 40-500-40
8 | Placing Pea Gravel Filter | 6 | 4,5 | Cum | 122 | 40-530-30
9 | Placing CC Block | 6 | 4,5 | Nos | 9039 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_B5_425M_M9175_TO_M9600
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 6197 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 6881 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 5861 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_167M_M9785_TO_M9952
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 2436 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 2704 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 2303 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_100M_M10300_TO_M10400
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 1458 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 1619 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 1379 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_255M_M12075_TO_M12330
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 3718 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 4129 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 3517 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_150M_M24950_TO_M25100
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 2187 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 2429 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 2069 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## FF_15M_5560M
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1798 | 40-190-15
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 7312 | 40-190-05
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781 | 40-190-35
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917 | 40-190-40
6 | Curing | 21 | 2,3,4,5 | percent | 100 | NS105
7 | Ring Bundh construction | 5 | 1 | Cum | 2052 | 40-450
8 | Excavation | 4 | 1 | Cum | 1598 | 16-510
9 | Embankment Construction | 15 | 7 | Cum | 4479 | 16-240
10 | Placing Sand Filter | 9 | 9 | Cum | 460 | 40-550-10
11 | Placing Geotextile Filter | 9 | 9 | sqm | 3117 | 40-500-40
12 | Placing Pea Gravel Filter | 9 | 9 | Cum | 613 | 40-530-30
13 | Geo Bag Placing(175) Kg | 9 | 9 | Nos | 4047 | 40-380-20
14 | Placing CC Block | 9 | 9 | Nos | 14808 | NS106
15 | Ring Bundh Removal | 5 | 14 | percent | 1641 | 16-470
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100 | NS102

## Equipment Production Rate
CC Bock | L | B | H | Relative Size wrt 30X30X30 | Standard Production Rate | Block/machine |  | code
50X50X50 | 50 | 50 | 50 | 4.6296 | 750 | 162 | 0.0061728 | 40-190-15
50X50X30 | 50 | 50 | 30 | 2.7778 | 750 | 270 | 0.0037037 | 40-190-05
40X40X40 | 40 | 40 | 40 | 2.3704 | 750 | 317 | 0.0031546 | 40-190-35
40X40X20 | 40 | 40 | 20 | 1.1852 | 750 | 633 | 0.0015798 | 40-190-40
30X30X30 | 30 | 30 | 30 | 1 | 750 | 750 | 0.0013333 | 40-190-50
|  |  |  | Equipment |  | Daily Prod(8hrs)
|  |  |  | Excavator |  | 300
|  |  |  | Roller |  | 760 | 0.0013158
|  |  |  | Mixuture Machie |  | 17
CC Block Placing
Block Size | L | B | H | Realtive Area | Standard Prod/Day | Daily Production
50X50X30 | 50 | 50 | 30 | 1.5625 | 1400 | 896
50X50X20 | 50 | 50 | 30 | 1.5625 | 1400 | 896
40X40X40 | 40 | 40 | 40 | 1 | 1400 | 1400
40X40X20 | 40 | 40 | 20 | 1 | 1400 | 1400
30X30X30 | 30 | 30 | 30 | 0.5625 | 1400 | 2489
175 kg geobag |  |  |  | 245/day by group 20 incld bed prep

## Block Placing Production Rate
1 Group | 20 Labour
Dayliy Placing Including Bed Preparation for 40X40X20 CC Block | 1400 | Nos
unit area of block | 0.16 | sqm
Bed Area | 224 | sqm
Sand Filter 100mm thick | 22.4 | cum
Geo Textile Filter | 224 | sqm
Gravel Filter | 22.4 | cum

## Project_name
Name
Submersible Embankment Slope Protection Work at Kishoregonj PW-34