## imed_df
| code | rindex | Unnamed: 2 | Dpp_alloc_total | Dpp_alloc_gob | Dpp_alloc_rpa | Dpp_alloc_dpa | Upto_last_fy_total | Upto_last_fy_gob | Upto_last_fy_rpa | Upto_last_fy_dpa | Target_curr_fy_total | Target_curr_fy_gob | Target_curr_fy_rpa | Target_curr_fy_dpa | Achiv_up_cur_month_total | Achiv_up_cur_month_gob | Achiv_up_cur_month_rpa | Achiv_up_cur_month_dpa | Achiv_up_prev_month_total | Achiv_up_prev_month_gob | Achiv_up_prev_month_rpa | Achiv_up_prev_month_dpa | fund_release | phy_upto_lastyr | phy_target | phy_curmonth
0 | REV_1 | 5 | 0 | 160 | 160 | 0 | 0 | 37.62 | 37.62 | 0 | 0 | 14.5 | 14.5 | 0 | 0 | 9.1504 | 9.1504 | 6e-05 | 0 | 7.7941 | 7.794 | 6e-05 | 0 | 3.6 | 0 | 0 | 0
1 | REV_2 | 6 | 1 | 100 | 100 | 0 | 0 | 58.54 | 58.54 | 0 | 0 | 15 | 15 | 0 | 0 | 7.4155 | 7.4154 | 4e-05 | 0 | 6.0105 | 6.0105 | 4e-05 | 0 | 3.75 | 0 | 0 | 0
2 | REV_3 | 7 | 2 | 245 | 245 | 0 | 0 | 116.67 | 116.67 | 0 | 0 | 34.25 | 34.25 | 0 | 0 | 19.958 | 19.9579 | 5e-05 | 0 | 19.958 | 19.9579 | 5e-05 | 0 | 8.56 | 0 | 0 | 0
3 | REV_4 | 8 | 3 | 2596.27 | 2596.27 | 0 | 0 | 1603.18 | 1603.18 | 0 | 0 | 359.08 | 359.08 | 0 | 0 | 79.1395 | 79.1394 | 6e-05 | 0 | 75.7693 | 75.7692 | 6e-05 | 0 | 89.77 | 0.012 | 0.004 | 0.003
4 | REV_5 | 9 | 4 | 75 | 75 | 0 | 0 | 2.18 | 2.18 | 0 | 0 | 0.9 | 0.9 | 0 | 0 | 0.25787 | 0.25763 | 0.00024 | 0 | 0.19261 | 0.19237 | 0.00024 | 0 | 0.23 | 0 | 0 | 0
5 | REV_6 | 10 | 5 | 15 | 15 | 0 | 0 | 11.92 | 11.92 | 0 | 0 | 1 | 1 | 0 | 0 | 0.14254 | 0.14244 | 0.0001 | 0 | 0.14254 | 0.14244 | 0.0001 | 0 | 0.25 | 0 | 0 | 0
6 | REV_7 | 11 | 6 | 25 | 25 | 0 | 0 | 9.85 | 9.85 | 0 | 0 | 3.95 | 3.95 | 0 | 0 | 2.3183 | 2.3181 | 0.00023 | 0 | 2.11 | 2.1098 | 0.00023 | 0 | 0.99 | 0 | 0 | 0
7 | REV_8 | 12 | 7 | 350 | 350 | 0 | 0 | 82.11 | 82.11 | 0 | 0 | 26 | 26 | 0 | 0 | 17.2041 | 17.2039 | 0.00027 | 0 | 13.0761 | 13.0759 | 0.00027 | 0 | 6.5 | 0 | 0 | 0
8 | REV_9 | 13 | 8 | 3 | 3 | 0 | 0 | 1.16 | 1.16 | 0 | 0 | 0.15 | 0.15 | 0 | 0 | 0.41293 | 0.41278 | 0.00015 | 0 | 0.00763 | 0.00748 | 0.00015 | 0 | 0.04 | 0 | 0 | 0
9 | REV_10 | 14 | 9 | 35 | 35 | 0 | 0 | 34.16 | 34.16 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0.41745 | 0.41729 | 0.00016 | 0 | 0.41745 | 0.41729 | 0.00016 | 0 | 0.13 | 0 | 0 | 0
10 | REV_11 | 15 | 10 | 150 | 150 | 0 | 0 | 49.91 | 49.91 | 0 | 0 | 20 | 20 | 0 | 0 | 11.3156 | 11.3154 | 0.00017 | 0 | 10.9563 | 10.9561 | 0.00017 | 0 | 5 | 0 | 0 | 0
11 | REV_12 | 16 | 11 | 2 | 2 | 0 | 0 | 0.28 | 0.28 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0.03306 | 0.03288 | 0.00018 | 0 | 0.03021 | 0.03003 | 0.00018 | 0 | 0.05 | 0 | 0 | 0
12 | REV_13 | 17 | 12 | 238.54 | 0 | 238.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00019 | 0 | 0.00019 | 0 | 0.00019 | 0 | 0.00019 | 0 | 0 | 0 | 0 | 0
13 | REV_14 | 18 | 13 | 4253.43 | 510.41 | 3743.02 | 0 | 2226.33 | 138.35 | 2087.98 | 0 | 1119.97 | 119.97 | 1000 | 0 | 331.6581 | 33.977 | 297.681 | 0 | 244.22 | 25.0844 | 219.1356 | 0 | 30 | 0.03 | 0.01 | 0.004
14 | REV_15 | 19 | 14 | 15 | 15 | 0 | 0 | 10.96 | 10.96 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 2.1093 | 2.1091 | 0.00023 | 0 | 2.1093 | 2.1091 | 0.00023 | 0 | 0.88 | 0 | 0 | 0
15 | REV_16 | 20 | 15 | 25 | 25 | 0 | 0 | 3.74 | 3.74 | 0 | 0 | 3 | 3 | 0 | 0 | 0.00024 | 0 | 0.00024 | 0 | 0.00024 | 0 | 0.00024 | 0 | 0.75 | 0 | 0 | 0
16 | REV_17 | 21 | 16 | 7901.4 | 0 | 0 | 7901.4 | 5168.01 | 0 | 0 | 5168.01 | 500 | 0 | 0 | 500 | 262.3802 | 0 | 0.00025 | 262.38 | 262.3802 | 0 | 0.00025 | 262.38 | 0 | 0.03 | 0.01 | 0.005
17 | REV_18 | 22 | 17 | 45 | 45 | 0 | 0 | 15.32 | 15.32 | 0 | 0 | 7 | 7 | 0 | 0 | 2.2024 | 2.2016 | 0.00081 | 0 | 2.2024 | 2.2016 | 0.00081 | 0 | 1.75 | 0 | 0 | 0
18 | REV_19 | 23 | 18 | 162 | 162 | 0 | 0 | 85.02 | 85.02 | 0 | 0 | 50 | 50 | 0 | 0 | 6.0209 | 6.0206 | 0.00029 | 0 | 3.0339 | 3.0336 | 0.00029 | 0 | 12.5 | 0 | 0 | 0
19 | REV_20 | 24 | 19 | 50 | 50 | 0 | 0 | 20.47 | 20.47 | 0 | 0 | 10 | 10 | 0 | 0 | 6.1407 | 6.1404 | 0.0003 | 0 | 5.9984 | 5.9981 | 0.0003 | 0 | 2.5 | 0 | 0 | 0
20 | REV_21 | 25 | 20 | 1700 | 1700 | 0 | 0 | 875.46 | 875.46 | 0 | 0 | 300 | 300 | 0 | 0 | 205.6571 | 205.6568 | 0.00031 | 0 | 192.178 | 192.1777 | 0.00031 | 0 | 75 | 0.018 | 0.006 | 0.0045
21 | REV_22 | 26 | 21 | 627.5 | 308.5 | 319 | 0 | 211.96 | 127.76 | 84.2 | 0 | 91 | 41 | 50 | 0 | 40.1124 | 10.648 | 29.4644 | 0 | 38.9147 | 9.4503 | 29.4644 | 0 | 10.25 | 0 | 0 | 0
22 | CAP_1 | 29 | 22 | 770.75 | 770.75 | 0 | 0 | 657.12 | 657.12 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 0.00085 | 0 | 0.00085 | 0 | 0.00085 | 0 | 0.00085 | 0 | 0 | 0.01 | 0.01 | 0
23 | CAP_2 | 30 | 23 | 100 | 100 | 0 | 0 | 61.29 | 61.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00044 | 0 | 0.00044 | 0 | 0.00044 | 0 | 0.00044 | 0 | 0 | 0 | 0 | 0
24 | CAP_3 | 31 | 24 | 13.97 | 13.97 | 0 | 0 | 9.74 | 9.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00091 | 0 | 0.00091 | 0 | 0.00091 | 0 | 0.00091 | 0 | 0 | 0 | 0 | 0
25 | CAP_4 | 32 | 25 | 76.5 | 76.5 | 0 | 0 | 31.8 | 31.8 | 0 | 0 | 5 | 5 | 0 | 0 | 0.00144 | 0 | 0.00144 | 0 | 0.00144 | 0 | 0.00144 | 0 | 5 | 0 | 0 | 0
26 | CAP_5 | 33 | 26 | 40 | 40 | 0 | 0 | 33.63 | 33.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00206 | 0 | 0.00206 | 0 | 0.00206 | 0 | 0.00206 | 0 | 0 | 0 | 0 | 0
27 | CAP_6 | 34 | 27 | 65 | 65 | 0 | 0 | 55.05 | 55.05 | 0 | 0 | 4 | 4 | 0 | 0 | 0.00109 | 0 | 0.00109 | 0 | 0.00109 | 0 | 0.00109 | 0 | 4 | 0 | 0 | 0
28 | CAP_7 | 35 | 28 | 24000 | 24000 | 0 | 0 | 14323.6 | 14323.6 | 0 | 0 | 2049.42 | 2049.42 | 0 | 0 | 0.00056 | 0 | 0.00056 | 0 | 0.00056 | 0 | 0.00056 | 0 | 0 | 0.08 | 0.03 | 0
29 | CAP_8 | 36 | 29 | 53364.5 | 6579.74 | 46784.76 | 0 | 19763.62 | 2667.86 | 17095.76 | 0 | 20285.98 | 2835.98 | 17450 | 0 | 2346.8043 | 369.7313 | 1977.0731 | 0 | 909.5167 | 190.0703 | 719.4464 | 0 | 1238.5 | 0.36 | 0.19 | 0.0705
30 | C | 42 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | D | 43 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## cum_gob
| Ecode | Description | Imedcode | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Q1 | Q2 | Q3 | Q4
0 | 3111302 | Conveyance Allowance | REV_1 | 0 | 0.0465 | 0.0965 | 0.1465 | 0.1975 | 0.2475 | 0.2975 | 0.3475 | 0.3975 | 0.3975 | 0.4475 | 0.5 | 0.0965 | 0.2475 | 0.3975 | 0.5
1 | 3111327 | Overtime Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 3111338 | Other Allowance | REV_1 | 0 | 0 | 0 | 3.6215 | 4.8475 | 6.1902 | 7.4965 | 8.8029 | 10.1092 | 10.1092 | 12.7219 | 14.0003 | 0 | 6.1902 | 10.1092 | 14.0003
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 0 | 0 | 0.91434 | 2.117 | 3.1763 | 4.5304 | 6.0105 | 7.4154 | 8.4351 | 8.4351 | 8.4351 | 14.8301 | 0.91434 | 4.5304 | 8.4351 | 14.8301
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 0 | 5.7014 | 8.5521 | 11.4028 | 14.2535 | 17.1072 | 19.9579 | 19.9579 | 26.5145 | 26.5145 | 26.5145 | 36.3494 | 8.5521 | 17.1072 | 26.5145 | 36.3494
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 0 | 8.5226 | 15.2081 | 21.542 | 28.4169 | 71.4953 | 75.7692 | 79.1394 | 87.4454 | 97.075 | 99.6715 | 175.0337 | 15.2081 | 71.4953 | 87.4454 | 175.0337
6 | 3211119 | Postage | REV_5 | 0 | 0.01438 | 0.03163 | 0.04744 | 0.06584 | 0.12173 | 0.13869 | 0.20395 | 0.28365 | 0.35162 | 0.41579 | 0.4848 | 0.03163 | 0.12173 | 0.28365 | 0.4848
7 | 3211120 | Telephones/Telegram/Teleprinter | REV_5 | 0 | 0 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.07148 | 0.03178 | 0.03178 | 0.03178 | 0.07148
8 | 3211117 | Telex/Fax/Internet | REV_5 | 0 | 0 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.09855 | 0.0219 | 0.0219 | 0.0219 | 0.09855
9 | 3221104 | Registration Fee (Vehicles) | REV_6 | 0 | 0 | 0 | 0 | 0 | 0.06085 | 0.14244 | 0.14244 | 0.14244 | 0.1601 | 0.1601 | 0.22962 | 0 | 0.06085 | 0.14244 | 0.22962
10 | 3211115 | Water | REV_7 | 0 | 0.0282 | 0.09231 | 0.09231 | 0.09231 | 0.25741 | 0.25741 | 0.33681 | 0.39134 | 0.39134 | 0.44587 | 0.52767 | 0.09231 | 0.25741 | 0.39134 | 0.52767
11 | 3211113 | Electricity | REV_7 | 0 | 0.37257 | 1.0519 | 1.3562 | 1.3562 | 1.8524 | 1.8524 | 1.9813 | 2.0931 | 2.0931 | 2.2535 | 2.6779 | 1.0519 | 1.8524 | 2.0931 | 2.6779
12 | 3243102 | Gas & Fuel | REV_8 | 0 | 0 | 0.26648 | 0.40468 | 1.5321 | 1.8161 | 1.8161 | 2.4119 | 2.4119 | 2.4119 | 2.4119 | 3.7615 | 0.26648 | 1.8161 | 2.4119 | 3.7615
13 | 3243101 | Petrol and Lubricant | REV_8 | 0 | 1.295 | 2.9836 | 4.1673 | 5.1424 | 9.2166 | 11.2597 | 14.792 | 17.3147 | 18.6192 | 20.4662 | 24.4316 | 2.9836 | 9.2166 | 17.3147 | 24.4316
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00748 | 0.41278 | 0.83945 | 0.84693 | 0.84693 | 0.84693 | 0 | 0 | 0.83945 | 0.84693
15 | 3255102 | Printing & Binding | REV_10 | 0 | 0.14 | 0.15404 | 0.30029 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.48749 | 0.50007 | 0.15404 | 0.41729 | 0.41729 | 0.50007
16 | 3255104 | Stationery, Seals & Stamps | REV_11 | 0 | 0.49597 | 3.7906 | 3.8426 | 7.1743 | 10.608 | 10.9561 | 11.3154 | 14.4011 | 14.4313 | 17.5775 | 19.9498 | 3.7906 | 10.608 | 14.4011 | 19.9498
17 | 3211127 | Books & Periodicals | REV_12 | 0 | 0.00575 | 0.00794 | 0.02152 | 0.0274 | 0.03003 | 0.03003 | 0.03288 | 0.03562 | 0.03836 | 0.06574 | 0.19659 | 0.00794 | 0.03003 | 0.03562 | 0.19659
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 0 | 0 | 0 | 0.77343 | 2.1137 | 2.186 | 2.186 | 2.186 | 2.186 | 2.186 | 2.7169 | 3.2478 | 0 | 2.186 | 2.186 | 3.2478
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 0 | 0 | 0 | 3.6415 | 6.9852 | 12.0596 | 20.2616 | 27.6775 | 33.1536 | 33.1536 | 34.4556 | 35.7576 | 0 | 12.0596 | 33.1536 | 35.7576
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 0 | 0 | 0 | 0 | 0.60036 | 0.60036 | 2.6368 | 4.1136 | 4.5915 | 4.5915 | 7.9691 | 11.3466 | 0 | 0.60036 | 4.5915 | 11.3466
22 | 3211109 | Casual labour/Job worker | REV_15 | 0 | 0 | 0.368 | 0.368 | 0.8855 | 0.8855 | 2.1091 | 2.1091 | 2.4598 | 2.4598 | 2.4598 | 3.4857 | 0.368 | 0.8855 | 2.4598 | 3.4857
23 | 3256103 | Consumable Stores | REV_16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.461 | 2.461 | 2.461 | 2.5015 | 0 | 0 | 2.461 | 2.5015
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 0 | 0 | 0.69575 | 0.69575 | 0.69575 | 1.2753 | 2.2016 | 2.2016 | 2.7812 | 2.7812 | 2.7812 | 3.8162 | 0.69575 | 1.2753 | 2.7812 | 3.8162
26 | 3111332 | b) Interim Evaluation | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3111332 | c) Progress Monitoring | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3257104 | Survey | REV_19 | 0 | 0 | 0 | 3.0336 | 3.0336 | 3.0336 | 3.0336 | 6.0206 | 6.0206 | 6.0206 | 6.0206 | 30.3983 | 0 | 3.0336 | 6.0206 | 30.3983
29 | 3255101 | Computer Consumables | REV_20 | 0 | 0.14365 | 2.5503 | 5.7134 | 5.9981 | 5.9981 | 5.9981 | 6.1404 | 6.2116 | 6.2116 | 9.3871 | 9.9977 | 2.5503 | 5.9981 | 6.2116 | 9.9977
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 38.3871 | 63.9264 | 93.4543 | 119.0521 | 144.9222 | 170.7923 | 192.1777 | 205.6568 | 241.8001 | 280.3187 | 290.7046 | 346.3079 | 93.4543 | 170.7923 | 241.8001 | 346.3079
31 | 3258101 | Motor Vehicles | REV_22 | 0 | 0.08468 | 0.34066 | 0.82554 | 0.9865 | 1.7246 | 2.8009 | 3.6236 | 7.146 | 7.7558 | 8.4511 | 17.1877 | 0.34066 | 1.7246 | 7.146 | 17.1877
32 | 3258102 | Furnitures & Fixtures | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12734 | 0.12734 | 0.12734 | 1.2363 | 0 | 0 | 0.12734 | 1.2363
33 | 3258103 | Computers & office equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 2.0582 | 2.16 | 2.2887 | 2.6062 | 2.6062 | 2.6062 | 3.3195 | 0 | 2.0582 | 2.6062 | 3.3195
34 | 3258105 | Machineries & Equipments | REV_22 | 0 | 0.07642 | 0.08053 | 0.24553 | 0.28372 | 0.45443 | 0.46968 | 0.46968 | 0.46968 | 0.46968 | 0.46968 | 2.1105 | 0.08053 | 0.45443 | 0.46968 | 2.1105
35 | 3258107 | Office Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.953 | 0 | 0 | 0 | 4.953
37 | 3258105 | Engineering Equipments | REV_22 | 0 | 0.0565 | 0.24536 | 0.31106 | 0.31106 | 0.31106 | 0.31106 | 0.55744 | 0.55744 | 0.95164 | 1.2692 | 1.4334 | 0.24536 | 0.31106 | 0.55744 | 1.4334
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 0 | 0 | 0 | 0 | 0.2874 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 0 | 3.7086 | 3.7086 | 3.7086
39 | 3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37887 | 0 | 0 | 0 | 0.37887
40 | 3258107 | Others : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.488 | 0 | 0 | 0 | 1.488
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9957 | 0 | 0 | 0 | 4.9957
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 4112303 | Aircooler | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9876 | 0 | 0 | 0 | 2.9876
55 | 4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.81 | 15.16 | 15.16 | 20.5 | 0 | 0 | 11.81 | 20.5
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 15.3885 | 15.3885 | 15.3885 | 15.3885 | 15.3885 | 56.3785 | 0 | 0 | 15.3885 | 56.3785
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 15.4839 | 29.9743 | 209.6353 | 276.6453 | 318.0753 | 388.5453 | 516.1553 | 0 | 15.4839 | 276.6453 | 516.1553
59 | 4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 35.7527 | 35.7527 | 89.5427 | 209.8027 | 260.4027 | 357.6527 | 0 | 0 | 89.5427 | 357.6527
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5881 | 13.5881 | 13.5881 | 13.5881 | 25.1681 | 65.4181 | 0 | 0 | 13.5881 | 65.4181
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0735 | 8.0735 | 26.2035 | 26.2035 | 53.6035 | 67.5235 | 0 | 0 | 26.2035 | 67.5235
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.97 | 10.97 | 36.68 | 80.27 | 0 | 0 | 10.97 | 80.27
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.1 | 76.35 | 112.78 | 205.94 | 0 | 0 | 35.1 | 205.94
64 | 4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 87.2932 | 87.2932 | 87.2932 | 87.2932 | 87.2932 | 87.2932 | 0 | 0 | 87.2932 | 87.2932
65 | 4111201 | Construction of WMG Office | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.36 | 0 | 0 | 0 | 2.36
66 | 4111201 | O&M During Construction | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## cum_rpa
| Ecode | Description | Imedcode | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Q1 | Q2 | Q3 | Q4
0 | 3111302 | Conveyance Allowance | REV_1 | 0 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05 | 1e-05
1 | 3111327 | Overtime Allowance | REV_1 | 0 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 2e-05
2 | 3111338 | Other Allowance | REV_1 | 0 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05 | 3e-05
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 0 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05 | 4e-05
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 0 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05 | 5e-05
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 0 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05 | 6e-05
6 | 3211119 | Postage | REV_5 | 0 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05 | 7e-05
7 | 3211120 | Telephones/Telegram/Teleprinter | REV_5 | 0 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05 | 8e-05
8 | 3211117 | Telex/Fax/Internet | REV_5 | 0 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05 | 9e-05
9 | 3221104 | Registration Fee (Vehicles) | REV_6 | 0 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001 | 0.0001
10 | 3211115 | Water | REV_7 | 0 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011 | 0.00011
11 | 3211113 | Electricity | REV_7 | 0 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012 | 0.00012
12 | 3243102 | Gas & Fuel | REV_8 | 0 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013 | 0.00013
13 | 3243101 | Petrol and Lubricant | REV_8 | 0 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014 | 0.00014
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 0 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015 | 0.00015
15 | 3255102 | Printing & Binding | REV_10 | 0 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016 | 0.00016
16 | 3255104 | Stationery, Seals & Stamps | REV_11 | 0 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017 | 0.00017
17 | 3211127 | Books & Periodicals | REV_12 | 0 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018 | 0.00018
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 0 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0.00019
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 0 | 0.0002 | 0.0002 | 5.9295 | 14.5881 | 15.1109 | 15.1109 | 15.1109 | 15.1109 | 19.5009 | 19.5009 | 19.5009 | 0.0002 | 15.1109 | 15.1109 | 19.5009
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 0 | 0.00021 | 0.00021 | 25.6896 | 54.6332 | 105.8738 | 180.2909 | 247.3559 | 291.9069 | 303.6539 | 303.6539 | 303.6539 | 0.00021 | 105.8738 | 291.9069 | 303.6539
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 0 | 0.00022 | 0.00022 | 0.00022 | 7.5045 | 7.5045 | 23.7337 | 35.2142 | 38.6135 | 75.0082 | 75.0082 | 75.0082 | 0.00022 | 7.5045 | 38.6135 | 75.0082
22 | 3211109 | Casual labour/Job worker | REV_15 | 0 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023 | 0.00023
23 | 3256103 | Consumable Stores | REV_16 | 0 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024 | 0.00024
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 0 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 0 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026 | 0.00026
26 | 3111332 | b) Interim Evaluation | REV_18 | 0 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0.00027
27 | 3111332 | c) Progress Monitoring | REV_18 | 0 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0.00028
28 | 3257104 | Survey | REV_19 | 0 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029 | 0.00029
29 | 3255101 | Computer Consumables | REV_20 | 0 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 0 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031 | 0.00031
31 | 3258101 | Motor Vehicles | REV_22 | 0 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032 | 0.00032
32 | 3258102 | Furnitures & Fixtures | REV_22 | 0 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033 | 0.00033
33 | 3258103 | Computers & office equipments | REV_22 | 0 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034 | 0.00034
34 | 3258105 | Machineries & Equipments | REV_22 | 0 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035 | 0.00035
35 | 3258107 | Office Building : Repair & Maintenance | REV_22 | 0 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036 | 0.00036
36 | 3258106 | Residential Building : Repair & Maintenance | REV_22 | 0 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037 | 0.00037
37 | 3258105 | Engineering Equipments | REV_22 | 0 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038 | 0.00038
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 0 | 0.00039 | 0.00039 | 0.00039 | 1.961 | 29.4612 | 29.4612 | 29.4612 | 29.4612 | 29.4612 | 29.4612 | 29.4612 | 0.00039 | 29.4612 | 29.4612 | 29.4612
39 | 3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 0 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004
40 | 3258107 | Others : Repair & Maintenance | REV_22 | 0 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041 | 0.00041
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 0 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042 | 0.00042
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 0 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043 | 0.00043
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 0 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044 | 0.00044
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 0 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045 | 0.00045
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 0 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046 | 0.00046
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 0 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047 | 0.00047
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 0 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048 | 0.00048
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 0 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049 | 0.00049
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 0 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 0 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051 | 0.00051
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 0 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052 | 0.00052
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 0 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053 | 0.00053
53 | 4112314 | Furnitures & Fixtures | CAP_6 | 0 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054 | 0.00054
54 | 4112303 | Aircooler | CAP_6 | 0 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055 | 0.00055
55 | 4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 0 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056 | 0.00056
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 0 | 0.00057 | 0.00057 | 0.00057 | 0.00057 | 0.00057 | 0.00057 | 0.00057 | 82.6506 | 106.0706 | 106.0706 | 143.4506 | 0.00057 | 0.00057 | 82.6506 | 143.4506
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0.00058 | 0.00058 | 0.00058 | 0.00058 | 0.00058 | 107.7201 | 107.7201 | 107.7201 | 107.7201 | 107.7201 | 394.6201 | 0.00058 | 0.00058 | 107.7201 | 394.6201
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 0 | 0.00059 | 0.00059 | 0.00059 | 0.00059 | 108.3879 | 209.821 | 1467.4477 | 1936.5177 | 2226.5377 | 2719.5677 | 3612.8207 | 0.00059 | 108.3879 | 1936.5177 | 3612.8207
59 | 4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 0 | 0.0006 | 0.0006 | 0.0006 | 0.0006 | 0.0006 | 250.2694 | 250.2694 | 625.9194 | 1467.0294 | 1821.2194 | 2501.9434 | 0.0006 | 0.0006 | 625.9194 | 2501.9434
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0.00061 | 0.00061 | 0.00061 | 0.00061 | 0.00061 | 0.00061 | 0.00061 | 0.00061 | 0.00061 | 81.0706 | 362.6986 | 0.00061 | 0.00061 | 0.00061 | 362.6986
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0.00062 | 0.00062 | 0.00062 | 0.00062 | 0.00062 | 56.515 | 56.515 | 183.395 | 183.395 | 375.185 | 472.634 | 0.00062 | 0.00062 | 183.395 | 472.634
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0.00063 | 0.00063 | 0.00063 | 0.00063 | 0.00063 | 95.1171 | 95.1171 | 171.8771 | 171.8771 | 351.8571 | 3402.8071 | 0.00063 | 0.00063 | 171.8771 | 3402.8071
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 0 | 0.00064 | 0.00064 | 0.00064 | 0.00064 | 0.00064 | 0.00064 | 0.00064 | 245.7206 | 534.4966 | 789.4766 | 1441.6226 | 0.00064 | 0.00064 | 245.7206 | 1441.6226
64 | 4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 0 | 0.00065 | 0.00065 | 0.00065 | 0.00065 | 0.00065 | 0.00065 | 0.00065 | 0.00065 | 0.00065 | 0.00065 | 16.5466 | 0.00065 | 0.00065 | 0.00065 | 16.5466
65 | 4111201 | Construction of WMG Office | CAP_8 | 0 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066 | 0.00066
66 | 4111201 | O&M During Construction | CAP_8 | 0 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067 | 0.00067

## cum_dpa
| Ecode | Description | Imedcode | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Q1 | Q2 | Q3 | Q4
0 | 3111302 | Conveyance Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3111327 | Overtime Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 3111338 | Other Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 3211119 | Postage | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 3211120 | Telephones/Telegram/Teleprinter | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 3211117 | Telex/Fax/Internet | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 3221104 | Registration Fee (Vehicles) | REV_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 3211115 | Water | REV_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 3211113 | Electricity | REV_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3243102 | Gas & Fuel | REV_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3243101 | Petrol and Lubricant | REV_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3255102 | Printing & Binding | REV_10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 3255104 | Stationery, Seals & Stamps | REV_11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 3211127 | Books & Periodicals | REV_12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 3211109 | Casual labour/Job worker | REV_15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 3256103 | Consumable Stores | REV_16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 0 | 0 | 0 | 140.0596 | 262.38 | 262.38 | 262.38 | 262.38 | 262.38 | 262.38 | 390.325 | 445.7764 | 0 | 262.38 | 262.38 | 445.7764
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 3111332 | b) Interim Evaluation | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3111332 | c) Progress Monitoring | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3257104 | Survey | REV_19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 3255101 | Computer Consumables | REV_20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 3258101 | Motor Vehicles | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 3258102 | Furnitures & Fixtures | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 3258103 | Computers & office equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 3258105 | Machineries & Equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 3258107 | Office Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 3258105 | Engineering Equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 3258107 | Others : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 4112303 | Aircooler | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 4111201 | Construction of WMG Office | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 4111201 | O&M During Construction | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## quarterly
| Q1_F | Q2_F | Q3_F | Q4_F | Q1_Phy | Q2_Phy | Q3_Phy | Q4_Phy
0 | 0.09651 | 0.24751 | 0.39751 | 0.50001 | 0 | 0 | 0 | 0
1 | 2e-05 | 2e-05 | 2e-05 | 2e-05 | 0 | 0 | 0 | 0
2 | 3e-05 | 6.1902 | 10.1092 | 14.0003 | 0 | 0 | 0 | 0
3 | 0.91438 | 4.5304 | 8.4352 | 14.8301 | 0.0005 | 0.002 | 0.003 | 0.003
4 | 8.5521 | 17.1073 | 26.5146 | 36.3495 | 0 | 0 | 0 | 0
5 | 15.2082 | 71.4953 | 87.4454 | 175.0338 | 0 | 0 | 0 | 0
6 | 0.0317 | 0.1218 | 0.28372 | 0.48487 | 0 | 0 | 0 | 0
7 | 0.03186 | 0.03186 | 0.03186 | 0.07156 | 0 | 0 | 0 | 0
8 | 0.02199 | 0.02199 | 0.02199 | 0.09864 | 0 | 0 | 0 | 0
9 | 0.0001 | 0.06095 | 0.14254 | 0.22972 | 0 | 0 | 0 | 0
10 | 0.09242 | 0.25752 | 0.39145 | 0.52778 | 0 | 0 | 0 | 0
11 | 1.052 | 1.8525 | 2.0932 | 2.6781 | 0 | 0 | 0 | 0
12 | 0.26661 | 1.8163 | 2.412 | 3.7616 | 0 | 0 | 0 | 0
13 | 2.9837 | 9.2168 | 17.3148 | 24.4317 | 0 | 0.002 | 0.004 | 0.004
14 | 0.00015 | 0.00015 | 0.8396 | 0.84708 | 0 | 0 | 0 | 0
15 | 0.1542 | 0.41745 | 0.41745 | 0.50023 | 0 | 0 | 0 | 0
16 | 3.7907 | 10.6082 | 14.4013 | 19.95 | 0 | 0.003 | 0.005 | 0.005
17 | 0.00812 | 0.03021 | 0.0358 | 0.19677 | 0 | 0 | 0 | 0
18 | 0.00019 | 0.00019 | 0.00019 | 0.00019 | 0 | 0 | 0 | 0
19 | 0.0002 | 17.2969 | 17.2969 | 22.7487 | 0 | 0 | 0 | 0
20 | 0.00021 | 117.9334 | 325.0605 | 339.4116 | 0 | 0.0035 | 0.0045 | 0.0045
21 | 0.00022 | 8.1049 | 43.2049 | 86.3548 | 0 | 0 | 0 | 0
22 | 0.36823 | 0.88573 | 2.4601 | 3.4859 | 0 | 0 | 0 | 0
23 | 0.00024 | 0.00024 | 2.4612 | 2.5018 | 0 | 0 | 0 | 0
24 | 0.00025 | 262.3802 | 262.3802 | 445.7767 | 0 | 0 | 0 | 0
25 | 0.69601 | 1.2756 | 2.7815 | 3.8165 | 0 | 0 | 0 | 0
26 | 0.00027 | 0.00027 | 0.00027 | 0.00027 | 0 | 0 | 0 | 0
27 | 0.00028 | 0.00028 | 0.00028 | 0.00028 | 0 | 0 | 0 | 0
28 | 0.00029 | 3.0339 | 6.0209 | 30.3986 | 0 | 0 | 0 | 0
29 | 2.5507 | 5.9984 | 6.2119 | 9.998 | 0.015 | 0.0525 | 0.0705 | 0.0705
30 | 93.4546 | 170.7926 | 241.8004 | 346.3082 | 0 | 0 | 0 | 0
31 | 0.34098 | 1.7249 | 7.1463 | 17.188 | 0 | 0 | 0 | 0