## Structure_Type
| Items | Initial | Code | Payment_30_06_2020 | DPP_Item
0 | Construction of Irrigation Inlet | IRRI_C | 1 | 291.81 | Inlet
1 | Rehab Regulator Rehab Haor | REG_R_REHAB | 2 | 0 | Reg_Rehab_Rehab
2 | Regulator | REG_C | 3 | 6503.97 | Reg_CW_Box
3 | Box Drainage Outlet | DROU_C | 4 | 0 | Reg_CW_Box
4 | Causeway | CW_C | 5 | 0 | Reg_CW_Box
5 | Bridge | BRI_C | 6 | 0 | Reg_CW_Box
6 | Khal_River Reexcavation(New Haor) | REX_KH_RIV_NEW | 7 | 2546.54 | Khal_Riv_New
7 | Khal_River Reexcavation(Rehab Haor) | REX_KH_RIV_REHAB | 8 | 51.09 | Khal_Riv_Rehab
8 | Embankment Rehablitation | EMB_R | 9 | 0 | Full_Emb_Rehab
9 | Submersible Embankment Rehabilitation | SEMB_R | 10 | 0 | Sub_Emb_Rehab
10 | Submersible Embankment Construction | SEMB_C | 11 | 5833.04 | Sub_Emb_Const
11 | Rehab Regulator New Haor | REG_R_NEW | 12 | 0 | Reg_Rehab_New
12 | Thrashing Floor Construction | THF_CONS | 14 | 0 | Thr_Fl_Cost
13 | Construction of WMG | WMG_OFF | 15 | 0 | Wmg_Office
14 | M&E GATE Repair | GATE_REP | 16 | 0 | Gate_Repair

## Projection_Info
| Package Name | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
0 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Resectioning of Full embankment from 0.000 to 41.771 | Km | 35.828 | 1132.4847 | 0.85 | 1 | NETR/PW-01 | Rehab | 9 | 0 | R-9 | NETR
1 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Resectioning of Full embankment from 0.911to 11.600 | km | 10.69 | 212.86 | 0.85 | 1 | NETR/PW-01 | Rehab | 9 | 0 | R-11 | NETR
2 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dhalia Khal | Km | 7.37 | 68.3113 | 0 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-9 | NETR
3 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Balai khal | Km | 5.896 | 107.2237 | 0.23 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-9 | NETR
4 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Anda Khal | Km | 7.192 | 215.6843 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
5 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dupikhali Khal part-1 | Km | 3.66 | 106.6825 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
6 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dupikhali Khal part-1 | Km | 5.057 | 112.0192 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
7 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dudhkura Khal | Km | 5.4 | 57.6844 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
8 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | kurikunia Khal | Km | 1.903 | 48.574 | 1 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
9 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dighjan Khal | Km | 4.32 | 102.8289 | 0.5 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-10 | NETR
10 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Tutnir Khal | Km | 3.15 | 37.9263 | 0 | 0 | NETR/PW-02 | Rehab | 8 | 0 | R-11 | NETR
11 | BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Kamalpur Khal | Km | 2.98 | 91.9555 | 0.4 | 1 | NETR/PW-02 | Rehab | 8 | 0 | R-11 | NETR
12 | BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Resection of Full embankment in Kangsha River Sheme | km | 20.9 | 450.21 | 1 | 1 | NETR/PW-03 | Rehab | 9 | 0 | R-10 | NETR
13 | BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Resection of Submesible Singer Bill | km | 3.56 | 29.21 | 1 | 1 | NETR/PW-03 | Rehab | 10 | 0 | R-11 | NETR
14 | BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Reinstllation of 5-vent Regulator Dampara | No | 1 | 389.57 | 0.95 | 1 | NETR/PW-03 | Rehab | 2 | 0 | R-9 | NETR
15 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Piyan River from 0.075 to 5.00 | Km | 4.925 | 335.3397 | 0.78 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-12 | NETR
16 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Nayori Khal from 0.000 to 7.565 | Km | 7.565 | 158.059 | 1 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-12 | NETR
17 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Feni Khal from 0.000 to 1.903 | Km | 1.903 | 16.0636 | 0 | 0 | NETR/PW-04 | Rehab | 8 | 0 | R-13 | NETR
18 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Jhalokhali from 0.000 to 6.76 | Km | 6.76 | 282.4937 | 1 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-13 | NETR
19 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Putia Khal from 0.000 to 5.235 | Km | 5.235 | 313.3495 | 1 | 1 | NETR/PW-04 | Rehab | 8 | 0 | R-13 | NETR
20 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Resectioning of Submersible EMB from 44.600 to 48.650 | Km | 9.75 | 395.62 | 0.82 | 1 | NETR/PW-04 | Rehab | 10 | 0 | R-13 | NETR
21 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of Submesible Emb from Km 6.800 to 24.855 | Km | 3.071 | 57.25 | 0 | 1 | NETR/PW-05 | New | 10 | 0 | N-11 | NETR
22 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Chapri Regulator | Nos | 1 | 242.75 | 0.6 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
23 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Ukra Regulator | Nos | 1 | 286.86 | 0.85 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
24 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Ichamati Regulator | Nos | 1 | 182.66 | 0.85 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
25 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 4-Vent Ichamati Regulator | Nos | 1 | 419.66 | 0.6 | 1 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
26 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Narsua River from Km 0.000 to 6.225 | Km | 6.226 | 224.4496 | 1 | 1.1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
27 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Ukra Khal from Km 0.111 to 2.043 Km | Km | 1.933 | 118.7745 | 1 | 1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
28 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Chapri Khal from Km 0.280 to 2.590 Km | Km | 2.31 | 88.1515 | 1 | 1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
29 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Ichamati Khal from Km 0.072 to 1.250 Km | Km | 1.178 | 51.0575 | 1 | 1 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
30 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Boilara Khal from Km 8.550 to 8.900 Km | Km | 0.35 | 28.0376 | 0 | 0 | NETR/PW-06 | New | 7 | 0 | N-11 | NETR
31 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of BoX drainage ountlet at Bhadera | Nos | 1 | 42.25 | 1 | 1 | NETR/PW-06 | New | 4 | 0 | N-11 | NETR
32 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of BoX drainage ountlet at Moheswar Khal | Nos | 1 | 42.25 | 1 | 1 | NETR/PW-06 | New | 4 | 0 | N-11 | NETR
33 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of Irrigation Inlet | Nos | 2 | 16.92 | 0 | 0 | NETR/PW-06 | New | 1 | 0 | N-11 | NETR
34 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehbilation of existing Regulator | Nos | 1 | 19.43 | 1 | 1 | NETR/PW-06 | New | 12 | 0 | N-11 | NETR
35 | BWDB/Netra/HFMLIP/PW-07 Ganesh Haor | Reexcavation of Kangsha river | Km | 15 | 654.8026 | 1 | 1 | NETR/PW-07 | New | 7 | 0 | N-12 | NETR
36 | BWDB/Netra/HFMLIP/PW-07 Ganesh Haor | Reexcavation of Gumai river | Km | 9 | 238.8741 | 1 | 0 | NETR/PW-07 | New | 7 | 0 | N-12 | NETR
37 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Agunia Regulator | No | 1 | 289.74 | 0.6 | 1 | NETR/PW-08 | New | 3 | 0 | N-14 | NETR
38 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Dharam Regulator | No | 1 | 239.88 | 0.25 | 1 | NETR/PW-08 | New | 3 | 0 | N-14 | NETR
39 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-1 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
40 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-2 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
41 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-3 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
42 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-4 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
43 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Box-5 | No | 1 | 62.22 | 0 | 1 | NETR/PW-08 | New | 4 | 0 | N-14 | NETR
44 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Inlet-1 | No | 1 | 12.18 | 0 | 1 | NETR/PW-08 | New | 1 | 0 | N-14 | NETR
45 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Inlet-2 | No | 1 | 12.18 | 0 | 1 | NETR/PW-08 | New | 1 | 0 | N-14 | NETR
46 | BWDB/Netra/HFMLIP/PW-08 Dharmapasha Rui Beel | Inlet-3 | No | 1 | 12.18 | 0 | 1 | NETR/PW-08 | New | 1 | 0 | N-14 | NETR

## Package_Name
| sl | Package_No | Payment_30_06_2020
0 | 1 | KISH/PW-01 | 51.09
1 | 2 | KISH/PW-02 | 347.71
2 | 3 | KISH/PW-03 | 625.93
3 | 4 | KISH/PW-04 | 714.69
4 | 5 | KISH/PW-05 | 575.15
5 | 6 | KISH/PW-06 | 837.25
6 | 7 | KISH/PW-07 | 565.07
7 | 8 | KISH/PW-08 | 0
8 | 9 | KISH/PW-09 | 712.33
9 | 10 | KISH/PW-10 | 409.68
10 | 11 | KISH/PW-11 | 522.86
11 | 12 | KISH/PW-12 | 705.59
12 | 13 | KISH/PW-13 | 647.2
13 | 14 | KISH/PW-14 | 806.89
14 | 15 | KISH/PW-15 | 333.94
15 | 16 | KISH/PW-16 | 721.62
16 | 17 | KISH/PW-17 | 1451.95
17 | 18 | KISH/PW-18 | 711.02
18 | 19 | KISH/PW-19 | 331.35
19 | 20 | KISH/PW-20 | 501.12
20 | 21 | KISH/PW-21 | 268.24
21 | 22 | KISH/PW-22 | 281.05
22 | 23 | KISH/PW-23 | 720.33
23 | 24 | KISH/PW-24 | 890.42
24 | 25 | KISH/PW-25 | 749.37
25 | 26 | KISH/PW-26 | 501.12
26 | 27 | KISH/PW-27 | 0
27 | 28 | KISH/PW-28 | 0
28 | 29 | KISH/PW-29 | 0
29 | 30 | KISH/PW-30 | 0
30 | 31 | KISH/PW-31 | 0
31 | 32 | KISH/PW-32 | 0
32 | 33 | KISH/PW-33 | 0
33 | 34 | KISH/PW-34 | 0
34 | 35 | KISH/PW-35 | 0
35 | 36 | KISH/PW-36 | 0
36 | 37 | KISH/PW-37 | 0
37 | 38 | KISH/PW-38 | 0
38 | 39 | NETR/PW-01 | 817.97
39 | 40 | NETR/PW-02 | 475.85
40 | 41 | NETR/PW-03 | 712.73
41 | 42 | NETR/PW-04 | 844.17
42 | 43 | NETR/PW-05 | 635.34
43 | 44 | NETR/PW-06 | 375.82
44 | 45 | NETR/PW-07 | 567.71
45 | 46 | NETR/PW-08 | 134.16

## Value_of_Work_Done
| Package | Structure Code | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | VDW_30_06_2020 | VDW_30_06_2021 | Work_Done_20_21 | Payment_30_06_2020
0 | NETR/PW-01 | 9 | Resectioning of Full embankment from 0.000 to 41.771 | Km | 35.828 | 1132.4847 | 0.85 | 1 | 962.612 | 1132.4847 | 169.8727 | 0
1 | NETR/PW-01 | 9 | Resectioning of Full embankment from 0.911to 11.600 | km | 10.69 | 212.86 | 0.85 | 1 | 180.931 | 212.86 | 31.929 | 0
2 | NETR/PW-02 | 8 | Dhalia Khal | Km | 7.37 | 68.3113 | 0 | 1 | 0 | 68.3113 | 68.3113 | 0
3 | NETR/PW-02 | 8 | Balai khal | Km | 5.896 | 107.2237 | 0.23 | 1 | 24.6614 | 107.2237 | 82.5622 | 0
4 | NETR/PW-02 | 8 | Anda Khal | Km | 7.192 | 215.6843 | 1 | 1 | 215.6843 | 215.6843 | 0 | 0
5 | NETR/PW-02 | 8 | Dupikhali Khal part-1 | Km | 3.66 | 106.6825 | 1 | 1 | 106.6825 | 106.6825 | 0 | 0
6 | NETR/PW-02 | 8 | Dupikhali Khal part-1 | Km | 5.057 | 112.0192 | 1 | 1 | 112.0192 | 112.0192 | 0 | 0
7 | NETR/PW-02 | 8 | Dudhkura Khal | Km | 5.4 | 57.6844 | 1 | 1 | 57.6844 | 57.6844 | 0 | 0
8 | NETR/PW-02 | 8 | kurikunia Khal | Km | 1.903 | 48.574 | 1 | 1 | 48.574 | 48.574 | 0 | 0
9 | NETR/PW-02 | 8 | Dighjan Khal | Km | 4.32 | 102.8289 | 0.5 | 1 | 51.4145 | 102.8289 | 51.4145 | 0
10 | NETR/PW-02 | 8 | Tutnir Khal | Km | 3.15 | 37.9263 | 0 | 0 | 0 | 0 | 0 | 0
11 | NETR/PW-02 | 8 | Kamalpur Khal | Km | 2.98 | 91.9555 | 0.4 | 1 | 36.7822 | 91.9555 | 55.1733 | 0
12 | NETR/PW-03 | 9 | Resection of Full embankment in Kangsha River Sheme | km | 20.9 | 450.21 | 1 | 1 | 450.21 | 450.21 | 0 | 0
13 | NETR/PW-03 | 10 | Resection of Submesible Singer Bill | km | 3.56 | 29.21 | 1 | 1 | 29.21 | 29.21 | 0 | 0
14 | NETR/PW-03 | 2 | Reinstllation of 5-vent Regulator Dampara | No | 1 | 389.57 | 0.95 | 1 | 370.0915 | 389.57 | 19.4785 | 0
15 | NETR/PW-04 | 8 | Reexcavation of Piyan River from 0.075 to 5.00 | Km | 4.925 | 335.3397 | 0.78 | 1 | 261.565 | 335.3397 | 73.7747 | 0
16 | NETR/PW-04 | 8 | Reexcavation of Nayori Khal from 0.000 to 7.565 | Km | 7.565 | 158.059 | 1 | 1 | 158.059 | 158.059 | 0 | 0
17 | NETR/PW-04 | 8 | Reexcavation of Feni Khal from 0.000 to 1.903 | Km | 1.903 | 16.0636 | 0 | 0 | 0 | 0 | 0 | 0
18 | NETR/PW-04 | 8 | Reexcavation of Jhalokhali from 0.000 to 6.76 | Km | 6.76 | 282.4937 | 1 | 1 | 282.4937 | 282.4937 | 0 | 0
19 | NETR/PW-04 | 8 | Reexcavation of Putia Khal from 0.000 to 5.235 | Km | 5.235 | 313.3495 | 1 | 1 | 313.3495 | 313.3495 | 0 | 0
20 | NETR/PW-04 | 10 | Resectioning of Submersible EMB from 44.600 to 48.650 | Km | 9.75 | 395.62 | 0.82 | 1 | 324.4084 | 395.62 | 71.2116 | 0
21 | NETR/PW-05 | 10 | Const of Submesible Emb from Km 6.800 to 24.855 | Km | 3.071 | 57.25 | 0 | 1 | 0 | 57.25 | 57.25 | 0
22 | NETR/PW-05 | 3 | Const of 1-Vent Chapri Regulator | Nos | 1 | 242.75 | 0.6 | 1 | 145.65 | 242.75 | 97.1 | 0
23 | NETR/PW-05 | 3 | Const of 1-Vent Ukra Regulator | Nos | 1 | 286.86 | 0.85 | 1 | 243.831 | 286.86 | 43.029 | 0
24 | NETR/PW-05 | 3 | Const of 1-Vent Ichamati Regulator | Nos | 1 | 182.66 | 0.85 | 1 | 155.261 | 182.66 | 27.399 | 0
25 | NETR/PW-05 | 3 | Const of 4-Vent Ichamati Regulator | Nos | 1 | 419.66 | 0.6 | 1 | 251.796 | 419.66 | 167.864 | 0
26 | NETR/PW-06 | 7 | Reexcavation of Narsua River from Km 0.000 to 6.225 | Km | 6.226 | 224.4496 | 1 | 1.1 | 224.4496 | 246.8946 | 22.445 | 0
27 | NETR/PW-06 | 7 | Reexcavation of Ukra Khal from Km 0.111 to 2.043 Km | Km | 1.933 | 118.7745 | 1 | 1 | 118.7745 | 118.7745 | 0 | 0
28 | NETR/PW-06 | 7 | Reexcavation of Chapri Khal from Km 0.280 to 2.590 Km | Km | 2.31 | 88.1515 | 1 | 1 | 88.1515 | 88.1515 | 0 | 0
29 | NETR/PW-06 | 7 | Reexcavation of Ichamati Khal from Km 0.072 to 1.250 Km | Km | 1.178 | 51.0575 | 1 | 1 | 51.0575 | 51.0575 | 0 | 0
30 | NETR/PW-06 | 7 | Reexcavation of Boilara Khal from Km 8.550 to 8.900 Km | Km | 0.35 | 28.0376 | 0 | 0 | 0 | 0 | 0 | 0
31 | NETR/PW-06 | 4 | Const of BoX drainage ountlet at Bhadera | Nos | 1 | 42.25 | 1 | 1 | 42.25 | 42.25 | 0 | 0
32 | NETR/PW-06 | 4 | Const of BoX drainage ountlet at Moheswar Khal | Nos | 1 | 42.25 | 1 | 1 | 42.25 | 42.25 | 0 | 0
33 | NETR/PW-06 | 1 | Const of Irrigation Inlet | Nos | 2 | 16.92 | 0 | 0 | 0 | 0 | 0 | 0
34 | NETR/PW-06 | 12 | Rehbilation of existing Regulator | Nos | 1 | 19.43 | 1 | 1 | 19.43 | 19.43 | 0 | 0
35 | NETR/PW-07 | 7 | Reexcavation of Kangsha river | Km | 15 | 654.8026 | 1 | 1 | 654.8026 | 654.8026 | 0 | 0
36 | NETR/PW-07 | 7 | Reexcavation of Gumai river | Km | 9 | 238.8741 | 1 | 0 | 238.8741 | 0 | -238.8741 | 0
37 | NETR/PW-08 | 3 | Agunia Regulator | No | 1 | 289.74 | 0.6 | 1 | 173.844 | 289.74 | 115.896 | 0
38 | NETR/PW-08 | 3 | Dharam Regulator | No | 1 | 239.88 | 0.25 | 1 | 59.97 | 239.88 | 179.91 | 0
39 | NETR/PW-08 | 4 | Box-1 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
40 | NETR/PW-08 | 4 | Box-2 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
41 | NETR/PW-08 | 4 | Box-3 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
42 | NETR/PW-08 | 4 | Box-4 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
43 | NETR/PW-08 | 4 | Box-5 | No | 1 | 62.22 | 0 | 1 | 0 | 62.22 | 62.22 | 0
44 | NETR/PW-08 | 1 | Inlet-1 | No | 1 | 12.18 | 0 | 1 | 0 | 12.18 | 12.18 | 0
45 | NETR/PW-08 | 1 | Inlet-2 | No | 1 | 12.18 | 0 | 1 | 0 | 12.18 | 12.18 | 0
46 | NETR/PW-08 | 1 | Inlet-3 | No | 1 | 12.18 | 0 | 1 | 0 | 12.18 | 12.18 | 0

## Package_wise_payment
| Package_No | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | KISH/PW-01 | 0 | 0 | 51.09 | -51.09
1 | KISH/PW-02 | 0 | 0 | 347.71 | -347.71
2 | KISH/PW-03 | 0 | 0 | 625.93 | -625.93
3 | KISH/PW-04 | 0 | 0 | 714.69 | -714.69
4 | KISH/PW-05 | 0 | 0 | 575.15 | -575.15
5 | KISH/PW-06 | 0 | 0 | 837.25 | -837.25
6 | KISH/PW-07 | 0 | 0 | 565.07 | -565.07
7 | KISH/PW-08 | 0 | 0 | 0 | 0
8 | KISH/PW-09 | 0 | 0 | 712.33 | -712.33
9 | KISH/PW-10 | 0 | 0 | 409.68 | -409.68
10 | KISH/PW-11 | 0 | 0 | 522.86 | -522.86
11 | KISH/PW-12 | 0 | 0 | 705.59 | -705.59
12 | KISH/PW-13 | 0 | 0 | 647.2 | -647.2
13 | KISH/PW-14 | 0 | 0 | 806.89 | -806.89
14 | KISH/PW-15 | 0 | 0 | 333.94 | -333.94
15 | KISH/PW-16 | 0 | 0 | 721.62 | -721.62
16 | KISH/PW-17 | 0 | 0 | 1451.95 | -1451.95
17 | KISH/PW-18 | 0 | 0 | 711.02 | -711.02
18 | KISH/PW-19 | 0 | 0 | 331.35 | -331.35
19 | KISH/PW-20 | 0 | 0 | 501.12 | -501.12
20 | KISH/PW-21 | 0 | 0 | 268.24 | -268.24
21 | KISH/PW-22 | 0 | 0 | 281.05 | -281.05
22 | KISH/PW-23 | 0 | 0 | 720.33 | -720.33
23 | KISH/PW-24 | 0 | 0 | 890.42 | -890.42
24 | KISH/PW-25 | 0 | 0 | 749.37 | -749.37
25 | KISH/PW-26 | 0 | 0 | 501.12 | -501.12
26 | KISH/PW-27 | 0 | 0 | 0 | 0
27 | KISH/PW-28 | 0 | 0 | 0 | 0
28 | KISH/PW-29 | 0 | 0 | 0 | 0
29 | KISH/PW-30 | 0 | 0 | 0 | 0
30 | KISH/PW-31 | 0 | 0 | 0 | 0
31 | KISH/PW-32 | 0 | 0 | 0 | 0
32 | KISH/PW-33 | 0 | 0 | 0 | 0
33 | KISH/PW-34 | 0 | 0 | 0 | 0
34 | KISH/PW-35 | 0 | 0 | 0 | 0
35 | KISH/PW-36 | 0 | 0 | 0 | 0
36 | KISH/PW-37 | 0 | 0 | 0 | 0
37 | KISH/PW-38 | 0 | 0 | 0 | 0
38 | NETR/PW-01 | 1143.543 | 1345.3447 | 817.97 | 527.3747
39 | NETR/PW-02 | 653.5026 | 910.9639 | 475.85 | 435.1139
40 | NETR/PW-03 | 849.5115 | 868.99 | 712.73 | 156.26
41 | NETR/PW-04 | 1339.8756 | 1484.8619 | 844.17 | 640.6919
42 | NETR/PW-05 | 796.538 | 1189.18 | 635.34 | 553.84
43 | NETR/PW-06 | 586.3632 | 608.8081 | 375.82 | 232.9881
44 | NETR/PW-07 | 893.6768 | 654.8026 | 567.71 | 87.0926
45 | NETR/PW-08 | 233.814 | 877.26 | 134.16 | 743.1

## Structure_Wise_payment
| Items | Code | DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Construction of Irrigation Inlet | 1 | Inlet | 0 | 36.54 | 291.81 | -255.27
1 | Rehab Regulator Rehab Haor | 2 | Reg_Rehab_Rehab | 370.0915 | 389.57 | 0 | 389.57
2 | Regulator | 3 | Reg_CW_Box | 1030.352 | 1661.55 | 6503.97 | -4842.42
3 | Box Drainage Outlet | 4 | Reg_CW_Box | 84.5 | 395.6 | 0 | 395.6
4 | Causeway | 5 | Reg_CW_Box | 0 | 0 | 0 | 0
5 | Bridge | 6 | Reg_CW_Box | 0 | 0 | 0 | 0
6 | Khal_River Reexcavation(New Haor) | 7 | Khal_Riv_New | 1376.1099 | 1159.6807 | 2546.54 | -1386.8593
7 | Khal_River Reexcavation(Rehab Haor) | 8 | Khal_Riv_Rehab | 1668.9698 | 2000.2058 | 51.09 | 1949.1158
8 | Embankment Rehablitation | 9 | Full_Emb_Rehab | 1593.753 | 1795.5547 | 0 | 1795.5547
9 | Submersible Embankment Rehabilitation | 10 | Sub_Emb_Rehab | 353.6184 | 482.08 | 0 | 482.08
10 | Submersible Embankment Construction | 11 | Sub_Emb_Const | 0 | 0 | 5833.04 | -5833.04
11 | Rehab Regulator New Haor | 12 | Reg_Rehab_New | 19.43 | 19.43 | 0 | 19.43
12 | Thrashing Floor Construction | 14 | Thr_Fl_Cost | 0 | 0 | 0 | 0
13 | Construction of WMG | 15 | Wmg_Office | 0 | 0 | 0 | 0
14 | M&E GATE Repair | 16 | Gate_Repair | 0 | 0 | 0 | 0

## DPP_Wise_payment
| DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Inlet | 0 | 36.54 | 0 | 36.54
1 | Reg_Rehab_Rehab | 370.0915 | 389.57 | 310.37 | 79.2
2 | Reg_CW_Box | 1114.852 | 2057.15 | 814.57 | 1242.58
3 | Khal_Riv_New | 1376.1099 | 1159.6807 | 886.28 | 273.4007
4 | Khal_Riv_Rehab | 1668.9698 | 2000.2058 | 1101.76 | 898.4458
5 | Full_Emb_Rehab | 1593.753 | 1795.5547 | 1438.59 | 356.9647
6 | Sub_Emb_Rehab | 353.6184 | 482.08 | 0 | 482.08
7 | Sub_Emb_Const | 0 | 0 | 0 | 0
8 | Reg_Rehab_New | 19.43 | 19.43 | 12.48 | 6.95
9 | Thr_Fl_Cost | 0 | 0 | 0 | 0
10 | Wmg_Office | 0 | 0 | 0 | 0
11 | Gate_Repair | 0 | 0 | 0 | 0