## Regulator
রেগুলেটর নির্মানের ধারাবাহিক বিবরনী
Sl No. | Continuation of items
1 | Location fixup and bill board ¯’vcb
2 | Site Preparation Kiv
3 | Office/ Contractor's shed wbg©vb Kiv
4 | BM Pillar ¯’vcb
5 | bKkv †gvZv‡eK Layout fixup Kiv
6 | Foundation trenches Lbb
7 | Ring bundh wbg©vb
8 | Pizeo meter ¯’vcb
9 | Shoring Gi slpoe protection
10 | Bailing out Gi cÖ‡qvRb n‡j pump ¯’vcb
11 | Sump Well ¯’vcb
12 | Sheet pile mn Ab¨vb¨ gvjvgvj mieivn
13 | Sheet pile Cutting
14 | bKkv †gvZv‡eK Sheet pile Gi layout fixup Kiv
15 | Painting of Sheet pile
16 | Driving sheet pile
17 | Sand filling under bed
18 | Khoa filter under bed
19 | Pholythene ¯’vcb
20 | Lean concrete work
21 | Hessain cloth ¯’vcb
22 | bKkv †gvZv‡eK M.S Reinforcement ¯’vcb
23 | Form work KvR
24 | Gate Gi Horizontal & vertical Channel ¯’vcb
25 | PVC water sloper ¯’vcb
26 | R.C.C KvR
27 | G.I pipe ¯’vcb
28 | C.C block supply
29 | Diversion khal Lbb
30 | Cement morter gauge wbg©vb
31 | Back filling of sand and earth
32 | Ring bundth removing
33 | Approach embankment wbg©vb
34 | Loose appron G sand, khoa filter, Geo filter ¯’vcb
35 | Loose appron G C.C block ¯’vcb
36 | Gate mieivn I ¯’vcb
37 | Fall boad ¯’vcb
38 | Fine Dressing Close turfing Kiv
39 | Name Plate ¯’vcb
40 | Site handed over

## Causeway
KRI‡q নির্মানের ধারাবাহিক বিবরনী
Sl No. | Continuation of items
1 | Location fixup and bill board ¯’vcb
2 | Site Preparation Kiv
3 | Office/ Contractor's shed wbg©vb Kiv
4 | BM Pillar ¯’vcb
5 | bKkv †gvZv‡eK Layout fixup Kiv
6 | Foundation trenches Lbb
7 | Ring bundh wbg©vb
8 | Pizeo meter ¯’vcb
9 | Shoring Gi slpoe protection
10 | Bailing out Gi cÖ‡qvRb n‡j pump ¯’vcb
11 | Sump Well ¯’vcb
12 | Sheet pile mn Ab¨vb¨ gvjvgvj mieivn
13 | Sheet pile Cutting
14 | bKkv †gvZv‡eK Sheet pile Gi layout fixup Kiv
15 | Painting of Sheet pile
16 | Driving sheet pile
17 | Sand filling under bed
18 | Khoa filter under bed
19 | Pholythene ¯’vcb
20 | Lean concrete work
21 | Hessain cloth ¯’vcb
22 | bKkv †gvZv‡eK M.S Reinforcement ¯’vcb
23 | Form work KvR
24 | R.C.C KvR
25 | G.I pipe ¯’vcb
26 | C.C block supply
27 | Diversion khal Lbb
28 | Cement morter gauge wbg©vb
29 | Back filling of sand and earth
30 | Ring bundth removing
31 | Approach embankment wbg©vb
32 | Loose appron G sand, khoa filter, Geo filter ¯’vcb
33 | Loose appron G C.C block ¯’vcb
34 | Fine Dressing Close turfing Kiv
35 | Name Plate ¯’vcb
36 | Site handed over

## Box outlet
e· †Wª‡bR AvDU‡jU wbg©v‡Yi avivevwnK weeiYx
Sl No. | Continuation of items
1 | Location fixup and bill board ¯’vcb
2 | Site Preparation Kiv
3 | Office/ Contractor's shed wbg©vb Kiv
4 | BM Pillar ¯’vcb
5 | bKkv †gvZv‡eK Layout fixup Kiv
6 | Foundation trenches Lbb
7 | Ring bundh wbg©vb
8 | Shoring Gi slpoe protection
9 | Bailing out Gi cÖ‡qvRb n‡j pump ¯’vcb
10 | Sand filling under bed
11 | Pholythene ¯’vcb
12 | Lean concrete work
13 | bKkv †gvZv‡eK M.S Reinforcement ¯’vcb
14 | Form work KvR
15 | R.C.C KvR
16 | C.C block supply
17 | Diversion khal Lbb
18 | Back filling of sand and earth
19 | Ring bundth removing
20 | Approach embankment wbg©vb
21 | Loose appron G sand, khoa filter, Geo filter ¯’vcb
22 | Loose appron G C.C block ¯’vcb
23 | Fine Dressing Close turfing Kiv
24 | Name Plate ¯’vcb
25 | Site handed over