## Revised_2nd
8.0 Economic code wise comparison of cost summary between the 1st Revised DPP and proposed 2nd Revised DPP | [27 empty] | (BDT in Lakh)
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3111327 | Overtime Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111338 | Other Allowance |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Supplies and Services
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | 1 Item | 100 | 100 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 1 Item | 2596.27 | 2596.27 |  | 0 | 0 |  |  |  | 1 Item | 2596.27 | 2596.27 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3211119 | Postage |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3211115 | Water |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3211113 | Electricity |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3243102 | Gas & Fuel |  | 1 Item | 200 | 200 |  | 0 | 0 |  |  |  | 1 Item | 100 | 100 |  | 0 | 0 |  |  |  |  | -100 | -100 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 200 | 200 |  | 0 | 0 |  |  |  |  | 50 | 50 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255102 | Printing & Binding |  | 1 Item | 35 | 35 |  | 0 | 0 |  |  |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | -30 | -30 |  | 0 | 0
| 3211127 | Books & Periodicals |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 1 Item | 238.54 | 0 |  | 238.54 | 0 |  |  |  | 1 Item | 238.54 | 238.54 |  | 0 | 0 |  |  |  |  | 0 | 238.54 |  | -238.54 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 1 Item | 398.41 | 47.81 |  | 350.6 | 0 |  |  |  | 1 Item | 536.58 | 64.39 |  | 472.19 | 0 |  |  |  |  | 138.17 | 16.58 |  | 121.59 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 1 Item | 2533.34 | 304 |  | 2229.34 | 0 |  |  |  | 1 Item | 3139.8 | 375.07 |  | 2764.73 | 0 |  |  |  |  | 606.46 | 71.07 |  | 535.39 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1 Item | 1321.68 | 158.6 |  | 1163.08 | 0 |  |  |  | 1 Item | 1321.68 | 158.6 |  | 1163.08 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3211109 | Casual labour/Job worker |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 22 | 22 |  | 0 | 0 |  |  |  |  | 7 | 7 |  | 0 | 0
| 3256103 | Consumable Stores |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 71+234 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM | 56+532 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM |  | 0 | 0 |  | 0 | 0
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 30 | 30 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3257104 | Survey |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255101 | Computer Consumables |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  | 1 Item | 60 | 60 |  | 0 | 0 |  |  |  |  | 10 | 10 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Repair, Maintenance & Rehabilitation
| 3258101 | Motor Vehicles |  | L.S. | 100 | 100 |  | 0 | 0 |  |  |  | L.S. | 125 | 125 |  | 0 | 0 |  |  |  |  | 25 | 25 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258103 | Computers & office equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -15 | -15 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3258105 | Engineering Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) |  | 104 | 362.5 | 43.5 |  | 319 | 0 |  |  |  | 86 | 294.34 | 41.2076 |  | 253.1324 | 0 |  |  |  |  | -68.16 | -2.2924 |  | -65.8676 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  | L.S. | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
Sub-total : (a) Revenue Component: |  |  |  |  | 18774.14 | 6572.18 |  | 4300.56 | 7901.4 |  |  |  |  | 19382.61 | 6828.0776 |  | 4653.1324 | 7901.4 |  |  |  |  | 608.47 | 255.8976 |  | 352.5724 | 0
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos | 35 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos | 45 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos | 6 | 100 | 100 |  | 0 | 0 |  |  | Nos | 5 | 90 | 90 |  | 0 | 0 |  |  | Nos |  | -10 | -10 |  | 0 | 0
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos | 7 | 5 | 5 |  | 0 | 0 |  |  | Nos | 2 | 1 | 1 |  | 0 | 0 |  |  | Nos |  | -4 | -4 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos | 6 | 6 | 6 |  | 0 | 0 |  |  | Nos | 3 | 3 | 3 |  | 0 | 0 |  |  | Nos |  | -3 | -3 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos | 30 | 19.5 | 19.5 |  | 0 | 0 |  |  | Nos | 37 | 24.5 | 24.5 |  | 0 | 0 |  |  | Nos |  | 5 | 5 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 11 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos | 11 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos | 11 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos | 17 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | LS | 50 | 50 |  | 0 | 0 |  |  |  | LS | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 4112303 | Aircooler | Nos | 15 | 15 | 15 |  | 0 | 0 |  |  | Nos | 15 | 15 | 15 | 1054.22 | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Ori |  |  | Pro |  | Diff
| 4141101 | Land Acquisition ( 470 hectare) | ha | 470 | 24000 | 24000 |  | 0 | 0 |  |  | ha | 470 | 23151.71 | 23151.71 |  | 0 | 0 |  |  | ha |  | -848.29 | -848.29 |  | 0 | 0 |  |  |  | #REF! | #REF! | #REF! | 50 | 371 | 421 | #REF!
Construction and Works:
|  | Irrigation Infrastructures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos | 131 | 1261 | 151.32 |  | 1109.68 | 0 |  |  | Nos | 127 | 1213.55 | 169.897 |  | 1043.653 | 0 |  |  | Nos |  | -47.45 | 18.577 |  | -66.027 | 0
|  | Drainage Structures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos | 7(2+5) | 1515 | 181.8 |  | 1333.2 | 0 |  |  | Nos | 5 | 1276.62 | 178.7268 |  | 1097.8932 | 0 |  |  | Nos |  | -238.38 | -3.0732 |  | -235.3068 | 0 |  |  | #DIV/0! | 978.5 | 18871.5 | 19850 | 3398 | 24917 | 28315 | 8465
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos | 137(57+35+14) | 20311 | 2437.32 |  | 17873.68 | 0 |  |  | Nos | 114 | 17903.94 | 2506.5516 |  | 15397.3884 | 0 |  |  | Nos |  | -2407.06 | 69.2316 |  | -2476.2916 | 0 |  |  | #DIV/0! | 131 | 2528 | 2659 | 455 | 3337 | 3792 | 1133
| 4111307 | Re-excavation of Khal/River (New Haors) | Km | 318 | 9729 | 1167.48 |  | 8561.52 | 0 |  |  | Km | 342.584 | 10091.78 | 1412.8492 |  | 8678.9308 | 0 |  |  | Km |  | 362.78 | 245.3692 |  | 117.4108 | 0 |  |  | #REF!
|  | Others | [27 empty] | #DIV/0! | 18 | 360 | 378 | 65 | 475.36 | 540.36 | 162.36
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | Km | 143 | 2515 | 301.8 |  | 2213.2 | 0 |  |  | Km | 108.974 | 3145.78 | 440.4092 |  | 2705.3708 | 0 |  |  | Km |  | 630.78 | 138.6092 |  | 492.1708 | 0 |  |  | #DIV/0! | 3 | 60 | 63 | 11 | 80 | 91 | 28
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | Km | 84.31 | 2550 | 306 |  | 2244 | 0 |  |  | Km | 67.11 | 1684.96 | 235.8944 |  | 1449.0656 | 0 |  |  | Km |  | -865.04 | -70.1056 |  | -794.9344 | 0 |  |  | #DIV/0! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | Km | 87.03 | 1785 | 214.2 |  | 1570.8 | 0 |  |  | Km | 57.912 | 1568.07 | 219.5298 |  | 1348.5402 | 0 |  |  | Km |  | -216.93 | 5.3298 |  | -222.2598 | 0 |  |  | #DIV/0!
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 255.067 | 17374.5 | 5375.6976 |  | 11998.8024 | 0 |  |  | Km |  | 5422 | 3941.3976 |  | 1480.6024 | 0 |  |  | #REF!
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos | 8 | 166 | 19.92 |  | 146.08 | 0 |  |  | Nos | 7 | 154.12 | 21.5768 |  | 132.5432 | 0 |  |  | Nos |  | -11.88 | 1.6568 |  | -13.5368 | 0 |  |  | #REF! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
| 4111201 | Threshing Floor Construction | Nos |  | 0 | 0 |  | 0 | 0 |  |  | Nos | 20 | 900 | 126 |  | 774 | 0 |  |  | Nos |  | 900 | 126 |  | 774 | 0
| 4111201 | Construction of WMG Office | Nos | 60 | 1380 | 165.6 |  | 1214.4 | 0 |  |  | Nos | 60 | 2100 | 294 |  | 1806 | 0 |  |  | Nos |  | 720 | 128.4 |  | 591.6 | 0 |  |  |  | 726.6 | 14031.95 | 14758.55 | 2526 | 18527 | 21053 | 6294.45
| 4111201 | O&M During Construction | Iten | L.S | 200 | 200 |  | 0 | 0 |  |  | Iten | 2 | 600 | 600 |  | 0 | 0 |  |  | Iten |  | 400 | 400 |  | 0 | 0 |  |  |  | #REF! | #REF! | #REF! | 6889 | 50521.36 | 57410.36 | #REF!
Sub-total : (b) Capital Component: |  |  |  |  | 78430.72 | 31645.96 |  | 46784.76 | 0 |  |  |  |  | 82219.25 | 35787.0624 |  | 46432.1876 | 0 |  |  |  |  | 3788.53 | 4141.1024 |  | -352.5724 | 0
Total Cost (a+b) : |  |  |  |  | 97204.86 | 38218.14 |  | 51085.32 | 7901.4 |  |  |  |  | 101601.86 | 42615.14 |  | 51085.32 | 7901.4 |  |  |  |  | 4397 | 4397 |  | -8.0718e-12 | 0
| 0 | (c) Physical Contingency ( Lump sum): | Item | L.S. | 258 | 100 |  | 158 | 0 |  |  | Item | L.S. | 258 | 100 |  | 158 | 0 |  |  | Item |  | 0 | 0 |  | 0 | 0
| 0 | (d) Price Contingency (Lump sum): | Item | L.S. | 402.14 | 100.76 |  | 301.38 | 0 |  |  | Item | L.S. | 402.14 | 100.76 |  | 301.38 | 0 |  |  | Item |  | 0 | 0 |  | 0 | 0
|  | Grand Total : (a)+(b)+(c)+(d): |  |  | 97865 | 38418.9 |  | 51544.7 | 7901.4 |  |  |  |  | 102262 | 42815.9 |  | 51544.7 | 7901.4 |  |  |  |  | 4397 | 4397 |  | -8.0718e-12 | 0
* DOSA, CONTASA, SAFE, IMPREST etc.
|  |  |  | c+d | 53527 | 6423.24 |  | 47103.76 | [5 empty] | 57707.66 | 11022.34 |  | 46685.32 |  |  | 0 |  |  | 4180.66 | 4599.1 |  | -418.44
|  |  |  | Phy.Works | 53727 | 6623.24 |  | 47103.76 |  |  |  |  | Phy.Works | 57407.66 | 11496.34 |  | 45911.32 |  |  | 0 |  | Phy.Works | 3680.66 | 4873.1 |  | -1192.44
|  |  |  | c+d+works |  | 13046.48 |  | 94207.52 | [6 empty] | 22518.68 |  | 92596.64 |  |  | 0
|  |  |  | other |  | 25372.42 |  | 3981.56 | [8 empty] | 4400
[8 empty] | 98189.08 | [8 empty] | 96996.64
[9 empty] | Reh | [7 empty] | Reh | 0
[9 empty] | New | [7 empty] | New | #REF!
[5 empty] | 4253.43 | [8 empty] | 4998.06 |  |  | 4400 | 0
#REF!
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 254.207 | 16526.21 | 4527.399 |  | 11998.811 | 0 |  |  | Km | -9.033 | 4573.71 | 3093.099 |  | 1480.611 | 0

## 9.Detil Phasing
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2019 (Year 1 to Year-5) † | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-21 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | Part | 1.01 | 1.01 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 3111327 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 3111338 | Other Allowance |  |  | 36.61 | 36.61 |  | 0 | 0 |  |  |  |  | Part | 14 | 14 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 58.54 | 58.54 |  | 0 | 0 |  |  |  |  | Part | 15 | 15 |  | 0 | 0 |  |  |  |  | Part | 28.8052 | 28.8052 |  | 0 | 0 |  |  |  |  | Part | 17.6548 | 17.6548 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 116.67 | 116.67 |  | 0 | 0 |  |  |  |  | Part | 34.25 | 34.25 |  | 0 | 0 |  |  |  |  | Part | 58.3296 | 58.3296 |  | 0 | 0 |  |  |  |  | Part | 35.7504 | 35.7504 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1603.18 | 1603.18 |  | 0 | 0 |  |  |  |  | Part | 359.08 | 359.08 |  | 0 | 0 |  |  |  |  | Part | 367.7258 | 367.7258 |  | 0 | 0 |  |  |  |  | Part | 266.2842 | 266.2842 |  | 0 | 0
| 3211119 | Postage |  | Part | 0.77 | 0.77 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.1634 | 2.1634 |  | 0 | 0 |  |  |  |  | Part | 1.5666 | 1.5666 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | Part | 0.97 | 0.97 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 2.3363 | 2.3363 |  | 0 | 0 |  |  |  |  | Part | 1.4937 | 1.4937 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | Part | 0.44 | 0.44 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 2.4416 | 2.4416 |  | 0 | 0 |  |  |  |  | Part | 1.9184 | 1.9184 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | Part | 11.92 | 11.92 |  | 0 | 0 | [5 empty] | 1 | 1 |  | 0 | 0 | [5 empty] | 4.4604 | 4.4604 |  | 0 | 0 | [5 empty] | 2.6196 | 2.6196 |  | 0 | 0
| 3211115 | Water |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 0.45 | 0.45 |  | 0 | 0 |  |  |  |  | Part | 2.0984 | 2.0984 |  | 0 | 0 |  |  |  |  | Part | 1.3416 | 1.3416 |  | 0 | 0
| 3211113 | Electricity |  | Part | 8.74 | 8.74 |  | 0 | 0 |  |  |  |  | Part | 3.5 | 3.5 |  | 0 | 0 |  |  |  |  | Part | 4.268 | 4.268 |  | 0 | 0 |  |  |  |  | Part | 3.492 | 3.492 |  | 0 | 0
| 3243102 | Gas & Fuel |  | Part | 17.52 | 17.52 |  | 0 | 0 |  |  |  |  | Part | 6 | 6 |  | 0 | 0 |  |  |  |  | Part | 46.6528 | 46.6528 |  | 0 | 0 |  |  |  |  | Part | 29.8272 | 29.8272 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | Part | 64.59 | 64.59 |  | 0 | 0 |  |  |  |  | Part | 20 | 20 |  | 0 | 0 |  |  |  |  | Part | 65.7837 | 65.7837 |  | 0 | 0 |  |  |  |  | Part | 49.6263 | 49.6263 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | Part | 1.16 | 1.16 |  | 0 | 0 |  |  |  |  | Part | 0.15 | 0.15 |  | 0 | 0 |  |  |  |  | Part | 0.9295 | 0.9295 |  | 0 | 0 | [5 empty] | 0.7605 | 0.7605 |  | 0 | 0
| 3255102 | Printing & Binding |  | Part | 34.16 | 34.16 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 9.3574 | 9.3574 |  | 0 | 0 |  |  |  |  | Part | 5.9826 | 5.9826 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | Part | 49.91 | 49.91 |  | 0 | 0 |  |  |  |  | Part | 20 | 20 |  | 0 | 0 |  |  |  |  | Part | 31.5567 | 31.5567 |  | 0 | 0 |  |  |  |  | Part | 18.5333 | 18.5333 |  | 0 | 0
| 3211127 | Books & Periodicals |  | Part | 0.28 | 0.28 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 238.54 | 0 |  | 238.54 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 301.5 | 22.54 |  | 278.96 | 0 |  |  |  |  | Part | 196.17 | 21.0294 |  | 175.1406 | 0 |  |  |  |  | Part | 23.346 | 2.5027 |  | 20.8433 | 0 |  |  |  |  | Part | 15.564 | 1.6685 |  | 13.8955 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1346.63 | 80.34 |  | 1266.29 | 0 |  |  |  |  | Part | 677.14 | 72.5894 |  | 604.5506 | 0 |  |  |  |  | Part | 703.0989 | 75.3722 |  | 627.7267 | 0 |  |  |  |  | Part | 412.9311 | 44.2662 |  | 368.6649 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 578.2 | 35.47 |  | 542.73 | 0 |  |  |  |  | Part | 246.66 | 26.442 |  | 220.218 | 0 |  |  |  |  | Part | 273.251 | 29.2925 |  | 243.9585 | 0 |  |  |  |  | Part | 223.569 | 23.9666 |  | 199.6024 | 0
| 3211109 | Casual labour/Job worker |  | Part | 10.96 | 10.96 |  | 0 | 0 |  |  |  |  | Part | 3.5 | 3.5 |  | 0 | 0 |  |  |  |  | Part | 4.6748 | 4.6748 |  | 0 | 0 |  |  |  |  | Part | 2.8652 | 2.8652 |  | 0 | 0
| 3256103 | Consumable Stores |  | Part | 3.74 | 3.74 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5168.01 | 0 |  | 0 | 5168.01 |  |  |  | MM | Part | 500 | 0 |  | 0 | 500 |  |  |  | MM | Part | 1362.3679 | 0 |  | 0 | 1362.3679 |  |  |  | MM | Part | 871.0221 | 0 |  | 0 | 871.0221
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 12.73 | 12.73 |  | 0 | 0 |  |  |  |  | Part | 5 | 5 |  | 0 | 0 |  |  |  |  | Part | 7.1166 | 7.1166 |  | 0 | 0 |  |  |  |  | Part | 5.1534 | 5.1534 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  |  | 1.29 | 1.29 |  | 0 | 0 |  |  |  |  | Part | 1 | 1 |  | 0 | 0 | [5 empty] | 7.71 | 7.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  |  | 1.3 | 1.3 |  | 0 | 0 |  |  |  |  | Part | 1 | 1 |  | 0 | 0 |  |  |  |  | Part | 4.774 | 4.774 |  | 0 | 0 |  |  |  |  | Part | 2.926 | 2.926 |  | 0 | 0
| 3257104 | Survey |  | Part | 85.02 | 85.02 |  | 0 | 0 |  |  |  |  | Part | 50 | 50 |  | 0 | 0 |  |  |  |  | Part | 15.3786 | 15.3786 |  | 0 | 0 |  |  |  |  | Part | 11.6014 | 11.6014 |  | 0 | 0
| 3255101 | Computer Consumables |  | Part | 20.47 | 20.47 |  | 0 | 0 |  |  |  |  | Part | 10 | 10 |  | 0 | 0 |  |  |  |  | Part | 16.2415 | 16.2415 |  | 0 | 0 |  |  |  |  | Part | 13.2885 | 13.2885 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 875.46 | 875.46 |  | 0 | 0 |  |  |  |  | Part | 300 | 300 |  | 0 | 0 |  |  |  |  | Part | 298.9878 | 298.9878 |  | 0 | 0 |  |  |  |  | Part | 225.5522 | 225.5522 |  | 0 | 0
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | Part | 61.4 | 61.4 |  | 0 | 0 |  |  |  |  | Part | 15 | 15 |  | 0 | 0 |  |  |  |  | Part | 26.73 | 26.73 |  | 0 | 0 |  |  |  |  | Part | 21.87 | 21.87 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | Part | 3.2 | 3.2 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 2.88 | 2.88 |  | 0 | 0 |  |  |  |  | Part | 1.92 | 1.92 |  | 0 | 0
| 3258103 | Computers & office equipments |  | Part | 5.34 | 5.34 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | Part | 1.22 | 1.22 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  |  | 14.53 | 14.53 |  | 0 | 0 |  |  |  |  | Part | 5 | 5 |  | 0 | 0 |  |  |  |  | Part | 11.8726 | 11.8726 |  | 0 | 0 |  |  |  |  | Part | 8.5974 | 8.5974 |  | 0 | 0
| 3258105 | Engineering Equipments |  | Part | 1.39 | 1.39 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
|  | Drainage Structures : | [12 empty] | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 95.03 | 10.83 |  | 84.2 | 0 |  |  |  | Nos. | Part | 58.25 | 8.5744 |  | 49.6756 | 0 |  |  |  | Nos. | Part | 88.8678 | 13.0813 |  | 75.7865 | 0 | [5 empty] | 52.1922 | 7.6827 |  | 44.5095 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.39 | 2.39 |  | 0 | 0 |  |  |  | Nos. | Part | 0.75 | 0.75 |  | 0 | 0 |  |  |  | Nos. | Part | 1.1346 | 1.1346 |  | 0 | 0 |  |  |  | Nos. | Part | 0.7254 | 0.7254 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  |  | 7.48 | 7.48 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 16.5312 | 16.5312 |  | 0 | 0 |  |  |  |  | Part | 12.9888 | 12.9888 |  | 0 | 0
(a) Sub-total Revenue Component: |  |  |  |  | 10624.85 | 3284.66 |  | 2172.18 | 5168.01 | [5 empty] | 2560 | 1010.4152 |  | 1049.5848 | 500 | [5 empty] | 3818.2052 | 1248.9823 |  | 1206.855 | 1362.3679 | [5 empty] | 2379.5548 | 881.8604 |  | 626.6723 | 871.0221
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 18.03 | 18.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 28.71 | 28.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.95 | 8.95 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 2 nos. | 0.796 | 0.796 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.18 | 20.18 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) |  |  | 2.13 | 2.13 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 9.49 | 9.49 | 70 | 0 | 0 | [5 empty] | 5 | 5 |  | 0 | 0 | [5 empty] | 35.51 | 35.51 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 | 72 | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 5.03 | 5.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 | 73 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 3.87 | 3.87 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 | 74 | 0 | 0 |  |  |  | No. | 1 no. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.3 | 1.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 | 75 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.17 | 1.17 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | Part | 45.32 | 45.32 | 76 | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9016 | 2.9016 |  | 0 | 0 |  |  |  |  | Part | 1.7784 | 1.7784 |  | 0 | 0
| 4112303 | Aircooler | Nos. | 4 nos. | 9.73 | 9.73 | 77 | 0 | 0 |  |  |  | Nos. | 6 nos. | 4 | 4 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.7747 | 0.7747 |  | 0 | 0 | [5 empty] | 0.4953 | 0.4953 |  | 0 | 0
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) |  |  | 14323.6 | 14323.6 | 79 | 0 | 0 |  |  |  | ha. | Part | 2049.42 | 2049.42 |  | 0 | 0 |  |  |  | ha. | Part | 6778.69 | 6778.69 |  | 0 | 0 |  |  |  | ha. |  | 0 | 0 |  | 0 | 0
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) |  |  | 116.72 | 16.34 | 82 | 100.38 | 0 | [5 empty] | 490.33 | 68.6462 |  | 421.6838 | 0 |  |  |  | Nos. | 131 | 333.575 | 46.7005 |  | 286.8745 | 0 | [5 empty] | 272.925 | 38.2095 |  | 234.7155 | 0
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 | 84 | 0 | 0 |  |  |  | No. | Part | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 778.7382 | 109.0233 |  | 669.7149 | 0 | [5 empty] | 497.8818 | 69.7035 |  | 428.1783 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 6143.66 | 889.49 | 85 | 5254.17 | 0 |  |  |  | Nos. | Part | 8105.58 | 1134.7812 |  | 6970.7988 | 0 |  |  |  | Nos. | Part | 2229.367 | 312.1114 |  | 1917.2556 | 0 |  |  |  | Nos. | Part | 1425.333 | 199.5466 |  | 1225.7864 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) |  |  | 6011.48 | 791.08 | 86 | 5220.4 | 0 |  |  |  | Km. | Part | 3936.68 | 551.1352 |  | 3385.5448 | 0 |  |  |  | Km. | Part | 83.2996 | 11.6619 |  | 71.6377 | 0 |  |  |  | Km. | Part | 60.3204 | 8.4449 |  | 51.8755 | 0
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) |  |  | 455.04 | 64.36 | 88 | 390.68 | 0 |  |  |  | Km. | Part | 900.73 | 126.1022 |  | 774.6278 | 0 |  |  |  | Km. | Part | 1020.3057 | 142.8428 |  | 877.4629 | 0 | [5 empty] | 769.7043 | 107.7586 |  | 661.9457 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) |  |  | 452.46 | 63.49 | 89 | 388.97 | 0 |  |  |  | Km. | Part | 913.26 | 127.8564 |  | 785.4036 | 0 |  |  |  | Km. | Part | 181.9668 | 25.4754 |  | 156.4914 | 0 | [5 empty] | 137.2732 | 19.2182 |  | 118.055 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) |  |  | 341.85 | 48.84 | 90 | 293.01 | 0 |  |  |  | Km. | Part | 657.55 | 92.057 |  | 565.493 | 0 |  |  |  | Km. | Part | 358.2621 | 50.1567 |  | 308.1054 | 0 | [5 empty] | 210.4079 | 29.4571 |  | 180.9508 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  |  | 6127.06 | 779.02 | 91 | 5348.04 | 0 |  |  |  | Km. | Part | 4650.77 | 651.1078 |  | 3999.6622 | 0 |  |  |  | Km. | Part | 4023.9687 | 563.3556 |  | 3460.6131 | 0 |  |  |  | Km. |  | 2572.7013 | 360.1782 |  | 2212.5231 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 | 92 | 63.49 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 |  |  |  | Nos. |  | 50.1332 | 7.0186 |  | 43.1146 | 0 |  |  |  | Nos. |  | 30.7268 | 4.3018 |  | 26.425 | 0
| 4111201 | Threshing Floor Construction |  |  | 0 | 0 | 93 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 549 | 76.86 |  | 472.14 | 0 | [5 empty] | 351 | 49.14 |  | 301.86 | 0
| 4111201 | Construction of WMG Office |  |  | 42.09 | 5.47 | 94 | 36.62 | 0 |  |  |  | Nos. | Part | 348.14 | 48.7396 |  | 299.4004 | 0 |  |  |  | Nos. |  | 1008.7643 | 141.227 |  | 867.5373 | 0 |  |  |  | Nos. |  | 701.0057 | 98.1408 |  | 602.8649 | 0
| 4111201 | O&M During Construction |  |  | 0 | 0 | 95 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 342 | 47.88 |  | 294.12 | 0 | [5 empty] | 258 | 36.12 |  | 221.88 | 0
(b)Sub-total Capital Component: |  |  |  |  | 34935.856 | 17840.096 |  | 17095.76 | 0 | [5 empty] | 22157.06 | 4954.4456 |  | 17202.6144 | 0 | [5 empty] | 17835.3669 | 8410.2996 |  | 9425.0673 | 0 | [5 empty] | 7289.5531 | 1022.4928 |  | 6267.0603 | 0
Total Cost (a+b) : |  |  |  |  | 45560.706 | 21124.756 |  | 19267.94 | 5168.01 | [5 empty] | 24717.06 | 5964.8608 |  | 18252.1992 | 500 | [5 empty] | 21653.5721 | 9659.2819 |  | 10631.9223 | 1362.3679 | [5 empty] | 9669.1079 | 1904.3532 |  | 6893.7326 | 871.0221
| 0 | (c) Physical Contingency ( Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 162.54 | 162.54 |  | 0 | 0 | [5 empty] | 95.46 | 95.46 |  | 0 | 0
| 0 | (d) Price Contingency (Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 221.177 | 221.177 |  | 0 | 0 | [5 empty] | 180.963 | 180.963 |  | 0 | 0
Grand Total (a+b+c+d) : |  |  |  | 16% | 45560.706 | 21124.756 |  | 19267.94 | 5168.01 | [5 empty] | 24717.06 | 5964.8608 |  | 18252.1992 | 500 | [5 empty] | 22037.2891 | 10042.9989 |  | 10631.9223 | 1362.3679 | [5 empty] | 9945.5309 | 2180.7762 |  | 6893.7326 | 871.0221
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17

## Annex-II
Year wise Financial and Physical Target Plan | [16 empty] | Annexure-II | [11 empty] | Annexure-II
Name of the Project : Haor Flood Management and Livelihood Improvement Project.(BWDB Part)
Name of agency/Division/Ministry: Bangladesh Water Development Board / Ministry of Water Resources
Economic Code | Economic Sub-Code (In detail) | Sub Code Description (In detail) | Total Physical & Financial Target |  |  |  |  | FY: 2014-15 (Year-1) |  |  | FY: 2015-16 (Year-2) |  |  | FY: 2016-17 (Year-3) |  |  | FY: 2017-18 (Year-4) |  |  | FY: 2018-19 (Year-5) |  |  | FY: 2019-20 (Year-6) |  |  | FY: 2020-21 (Year-7) |  |  | FY: 2021-22 (Year-8)
|  |  | Unit | Unit Cost | Quantity | Total Cost (Taka in Lac) | Weight | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical
[9 empty] | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.3 | 6 | 0.0003 | 0.13 | 2.6 | 0.00013 | 0.28 | 5.6 | 0.00028 | 0.3 | 6 | 0.0003 | 0.5 | 10 | 0.0005 | 2.0242 | 40.484 | 0.0020242 | 1.4658 | 29.316 | 0.0014658 | 100 | 0.005 | 10
| 3111327 | Overtime Allowance | Item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 63 | 0.0063 | 3.7 | 37 | 0.0037 | 100 | 0.01 | 11
| 3111338 | Other Allowance | Item | 140 | 1 Item | 140 | 0.00137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 17.8571 | 0.024464 | 11.61 | 8.2929 | 0.011361 | 14 | 10 | 0.0137 | 53.634 | 38.31 | 0.052485 | 35.756 | 25.54 | 0.03499 | 100 | 0.137 | 12
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | Item | 120 | 1 Item | 120 | 0.00117 | 0.991 | 0.82583 | 0.00096623 | 11.909 | 9.9242 | 0.011611 | 14.98 | 12.4833 | 0.014606 | 17.96 | 14.9667 | 0.017511 | 12.7 | 10.5833 | 0.012382 | 15 | 12.5 | 0.014625 | 28.8052 | 24.0043 | 0.028085 | 17.6548 | 14.7123 | 0.017213 | 100 | 0.11603 | 14
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | Months | 245 | 1 Item | 245 | 0.0024 | 0 | 0 | 0 | 16.25 | 6.6327 | 0.015918 | 31.35 | 12.7959 | 0.03071 | 34.86 | 14.2286 | 0.034149 | 34.21 | 13.9633 | 0.033512 | 34.25 | 13.9796 | 0.033551 | 58.3296 | 23.808 | 0.057139 | 35.7504 | 14.592 | 0.035021 | 100 | 0.24 | 15 | 245 | 100
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | Item | 2596.27 | 1 Item | 2596.27 | 0.02539 | 223.746 | 8.618 | 0.21881 | 464.654 | 17.897 | 0.4544 | 327.7 | 12.622 | 0.32047 | 337.33 | 12.9929 | 0.32989 | 249.75 | 9.6196 | 0.24424 | 359.08 | 13.8306 | 0.35116 | 367.7258 | 14.1636 | 0.35961 | 266.2842 | 10.2564 | 0.26041 | 100 | 2.3202 | 16
| 3211119 | Postage | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.05 | 1 | 5e-05 | 0.13 | 2.6 | 0.00013 | 0.22 | 4.4 | 0.00022 | 0.37 | 7.4 | 0.00037 | 0.5 | 10 | 0.0005 | 2.1634 | 43.268 | 0.0021634 | 1.5666 | 31.332 | 0.0015666 | 100 | 0.005 | 17
| 3211120 | Telephones/Telegram/Teleprinter | Item | 5 | 1 Item | 5 | 5e-05 | 0.21 | 4.2 | 0.00021 | 0.24 | 4.8 | 0.00024 | 0.29 | 5.8 | 0.00029 | 0.15 | 3 | 0.00015 | 0.08 | 1.6 | 8e-05 | 0.2 | 4 | 0.0002 | 2.3363 | 46.726 | 0.0023363 | 1.4937 | 29.874 | 0.0014937 | 100 | 0.00479 | 18
| 3211117 | Telex/Fax/Internet | Item | 5 | 1 Item | 5 | 5e-05 | 0.249 | 4.98 | 0.000249 | 0.001 | 0.02 | 1e-06 | 0.09 | 1.8 | 9e-05 | 0.05 | 1 | 5e-05 | 0.05 | 1 | 5e-05 | 0.2 | 4 | 0.0002 | 2.4416 | 48.832 | 0.0024416 | 1.9184 | 38.368 | 0.0019184 | 100 | 0.004751 | 19
| 3221104 | Registration Fee (Vehicles) | Item | 20 | 1 Item | 20 | 0.0002 | 1.1 | 5.5 | 0.0011 | 8.37 | 41.85 | 0.00837 | 0.08 | 0.4 | 8e-05 | 0 | 0 | 0 | 2.37 | 11.85 | 0.00237 | 1 | 5 | 0.001 | 4.4604 | 22.302 | 0.0044604 | 2.6196 | 13.098 | 0.0026196 | 100 | 0.0189 | 20
| 3211115 | Water | Item | 5 | 1 Item | 5 | 5e-05 | 0 | 0 | 0 | 0.11 | 2.2 | 0.00011 | 0.23 | 4.6 | 0.00023 | 0.37 | 7.4 | 0.00037 | 0.4 | 8 | 0.0004 | 0.45 | 9 | 0.00045 | 2.0984 | 41.968 | 0.0020984 | 1.3416 | 26.832 | 0.0013416 | 100 | 0.005 | 21
| 3211113 | Electricity | Item | 20 | 1 Item | 20 | 0.0002 | 0.187 | 0.935 | 0.000187 | 1.683 | 8.415 | 0.001683 | 1.78 | 8.9 | 0.00178 | 2.31 | 11.55 | 0.00231 | 2.78 | 13.9 | 0.00278 | 3.5 | 17.5 | 0.0035 | 4.268 | 21.34 | 0.004268 | 3.492 | 17.46 | 0.003492 | 100 | 0.019813 | 22
| 3243102 | Gas & Fuel | Item | 100 | 1 Item | 100 | 0.00098 | 0.938 | 0.938 | 0.00091924 | 3.692 | 3.692 | 0.0036182 | 3 | 3 | 0.00294 | 4 | 4 | 0.00392 | 5.89 | 5.89 | 0.0057722 | 6 | 6 | 0.00588 | 46.6528 | 46.6528 | 0.04572 | 29.8272 | 29.8272 | 0.029231 | 100 | 0.097081 | 23
| 3243101 | Petrol and Lubricant | Item | 200 | 1 Item | 200 | 0.00196 | 0.625 | 0.3125 | 0.0006125 | 6.995 | 3.4975 | 0.0068551 | 18.97 | 9.485 | 0.018591 | 18 | 9 | 0.01764 | 20 | 10 | 0.0196 | 20 | 10 | 0.0196 | 65.7837 | 32.8918 | 0.064468 | 49.6263 | 24.8132 | 0.048634 | 100 | 0.19539 | 24
| 3221108 | Insurance/Bank Charges (including Vehicles) | Item | 3 | 1 Item | 3 | 3e-05 | 0.081 | 2.7 | 8.1e-05 | 0.749 | 24.9667 | 0.000749 | 0.01 | 0.33333 | 1e-05 | 0.22 | 7.3333 | 0.00022 | 0.1 | 3.3333 | 0.0001 | 0.15 | 5 | 0.00015 | 0.9295 | 30.9833 | 0.0009295 | 0.7605 | 25.35 | 0.0007605 | 100 | 0.002919 | 25
| 3255102 | Printing & Binding | Item | 50 | 1 Item | 50 | 0.00049 | 0.196 | 0.392 | 0.00019208 | 6.994 | 13.988 | 0.0068541 | 16.99 | 33.98 | 0.01665 | 6 | 12 | 0.00588 | 3.98 | 7.96 | 0.0039004 | 0.5 | 1 | 0.00049 | 9.3574 | 18.7148 | 0.0091703 | 5.9826 | 11.9652 | 0.0058629 | 100 | 0.048808 | 26
| 3255104 | Stationery, Seals & Stamps | Item | 120 | 1 Item | 120 | 0.00117 | 0.968 | 0.80667 | 0.0009438 | 6.972 | 5.81 | 0.0067977 | 11.2 | 9.3333 | 0.01092 | 12.79 | 10.6583 | 0.01247 | 17.98 | 14.9833 | 0.017531 | 20 | 16.6667 | 0.0195 | 31.5567 | 26.2972 | 0.030768 | 18.5333 | 15.4444 | 0.01807 | 100 | 0.11606 | 27
| 3211127 | Books & Periodicals | Item | 2 | 1 Item | 2 | 2e-05 | 0 | 0 | 0 | 0.1 | 5 | 0.0001 | 0.03 | 1.5 | 3e-05 | 0.05 | 2.5 | 5e-05 | 0.1 | 5 | 0.0001 | 0.2 | 10 | 0.0002 | 0.8816 | 44.08 | 0.0008816 | 0.6384 | 31.92 | 0.0006384 | 100 | 0.002 | 28
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | Item | 238.54 | 1 Item | 238.54 | 0.00233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.54 | 100 | 0.233 | 0 | 0 | 0 | 100 | 0.233 | 30
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 536.58 | 1 Item | 536.58 | 0.00525 | 0 | 0 | 0 | 9.22 | 1.7183 | 0.009021 | 29.86 | 5.5649 | 0.029216 | 86.55 | 16.1299 | 0.084682 | 175.87 | 32.7761 | 0.17207 | 196.17 | 36.5593 | 0.19194 | 23.346 | 4.3509 | 0.022842 | 15.564 | 2.9006 | 0.015228 | 100 | 0.525 | 31
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 3139.8 | 1 Item | 3139.8 | 0.0307 | 0 | 0 | 0 | 0 | 0 | 0 | 199.49 | 6.3536 | 0.19506 | 524.89 | 16.7173 | 0.51322 | 622.25 | 19.8181 | 0.60842 | 677.14 | 21.5663 | 0.66209 | 703.0989 | 22.3931 | 0.68747 | 412.9311 | 13.1515 | 0.40375 | 100 | 3.07 | 32
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1321.68 | 1 Item | 1321.68 | 0.01292 | 0 | 0 | 0 | 0 | 0 | 0 | 119.7 | 9.0567 | 0.11701 | 224.29 | 16.9701 | 0.21925 | 234.21 | 17.7206 | 0.22895 | 246.66 | 18.6626 | 0.24112 | 273.251 | 20.6745 | 0.26711 | 223.569 | 16.9155 | 0.21855 | 100 | 1.292 | 33
| 3211109 | Casual labour/Job worker | MM | 22 | 1 Item | 22 | 0.00022 | 0.25 | 1.1364 | 0.00025 | 2.11 | 9.5909 | 0.00211 | 2.35 | 10.6818 | 0.00235 | 2 | 9.0909 | 0.002 | 4.25 | 19.3182 | 0.00425 | 3.5 | 15.9091 | 0.0035 | 4.6748 | 21.2491 | 0.0046748 | 2.8652 | 13.0236 | 0.0028652 | 100 | 0.02175 | 34
| 3256103 | Consumable Stores |  | 15 | 1 Item | 15 | 0.00015 | 0 | 0 | 0 | 0.99 | 6.6 | 0.00099 | 0.75 | 5 | 0.00075 | 1 | 6.6667 | 0.001 | 1 | 6.6667 | 0.001 | 3 | 20 | 0.003 | 4.7908 | 31.9387 | 0.0047908 | 3.4692 | 23.128 | 0.0034692 | 100 | 0.015 | 35
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 0 | 56+532 | 7901.4 | 0.07727 | 849.675 | 10.7535 | 0.83092 | 1819.425 | 23.0266 | 1.7793 | 1123.15 | 14.2146 | 1.0984 | 689.33 | 8.7242 | 0.67412 | 686.43 | 8.6874 | 0.67128 | 500 | 6.328 | 0.48896 | 1362.3679 | 17.2421 | 1.3323 | 871.0221 | 11.0236 | 0.8518 | 100 | 6.8961 | 36
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | item | 30 | 1 Item | 30 | 0.00029 | 0.4 | 1.3333 | 0.00038667 | 1.33 | 4.4333 | 0.0012857 | 1.5 | 5 | 0.00145 | 4.5 | 15 | 0.00435 | 5 | 16.6667 | 0.0048333 | 5 | 16.6667 | 0.0048333 | 7.1166 | 23.722 | 0.0068794 | 5.1534 | 17.178 | 0.0049816 | 100 | 0.028613 | 37
| 3111332 | b) Interim Evaluation | item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27 | 2.7 | 0.00027 | 0.25 | 2.5 | 0.00025 | 0.77 | 7.7 | 0.00077 | 1 | 10 | 0.001 | 7.71 | 77.1 | 0.00771 | 0 | 0 | 0 | 100 | 0.01 | 38
| 3111332 | c) Progress Monitoring | item | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 3 | 0.0003 | 0.25 | 2.5 | 0.00025 | 0.75 | 7.5 | 0.00075 | 1 | 10 | 0.001 | 4.774 | 47.74 | 0.004774 | 2.926 | 29.26 | 0.002926 | 100 | 0.01 | 39
| 3257104 | Survey | item | 162 | 1 Item | 162 | 0.00158 | 0 | 0 | 0 | 7.62 | 4.7037 | 0.0074319 | 17.47 | 10.784 | 0.017039 | 30 | 18.5185 | 0.029259 | 29.93 | 18.4753 | 0.029191 | 50 | 30.8642 | 0.048765 | 15.3786 | 9.493 | 0.014999 | 11.6014 | 7.1614 | 0.011315 | 100 | 0.158 | 40
| 3255101 | Computer Consumables | item | 60 | 1 Item | 60 | 0.00059 | 0.491 | 0.81833 | 0.00048282 | 1.499 | 2.4983 | 0.001474 | 4.5 | 7.5 | 0.004425 | 6.48 | 10.8 | 0.006372 | 7.5 | 12.5 | 0.007375 | 10 | 16.6667 | 0.0098333 | 16.2415 | 27.0692 | 0.015971 | 13.2885 | 22.1475 | 0.013067 | 100 | 0.058517 | 41
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | item | 1700 | 1 Item | 1700 | 0.01662 | 0 | 0 | 0 | 84.32 | 4.96 | 0.082435 | 227.97 | 13.41 | 0.22287 | 263.24 | 15.4847 | 0.25736 | 299.93 | 17.6429 | 0.29323 | 300 | 17.6471 | 0.29329 | 298.9878 | 17.5875 | 0.2923 | 225.5522 | 13.2678 | 0.22051 | 100 | 1.662 | 42
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | 125 | L.S. | 125 | 0.00122 | 0.983 | 0.7864 | 0.00095941 | 5.967 | 4.7736 | 0.0058238 | 12 | 9.6 | 0.011712 | 21.99 | 17.592 | 0.021462 | 20.46 | 16.368 | 0.019969 | 15 | 12 | 0.01464 | 26.73 | 21.384 | 0.026088 | 21.87 | 17.496 | 0.021345 | 100 | 0.12104 | 44
| 3258102 | Furnitures & Fixtures |  | 10 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0.49 | 4.9 | 0.00049 | 0.74 | 7.4 | 0.00074 | 0.98 | 9.8 | 0.00098 | 0.99 | 9.9 | 0.00099 | 2 | 20 | 0.002 | 2.88 | 28.8 | 0.00288 | 1.92 | 19.2 | 0.00192 | 100 | 0.01 | 45
| 3258103 | Computers & office equipments |  | 15 | L.S. | 15 | 0.00015 | 0 | 0 | 0 | 0.5 | 3.3333 | 0.0005 | 0.85 | 5.6667 | 0.00085 | 2 | 13.3333 | 0.002 | 1.99 | 13.2667 | 0.00199 | 3 | 20 | 0.003 | 3.9294 | 26.196 | 0.0039294 | 2.7306 | 18.204 | 0.0027306 | 100 | 0.015 | 46
| 3258105 | Machineries & Equipments |  | 10 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0.21 | 2.1 | 0.00021 | 0.01 | 0.1 | 1e-05 | 0.5 | 5 | 0.0005 | 0.5 | 5 | 0.0005 | 2 | 20 | 0.002 | 4.1358 | 41.358 | 0.0041358 | 2.6442 | 26.442 | 0.0026442 | 100 | 0.01 | 47
| 3258107 | Office Building : Repair & Maintenance |  | 25 | L.S. | 25 | 0.00024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.98 | 39.92 | 0.0095808 | 10 | 40 | 0.0096 | 0 | 0 | 0 | 2.9618 | 11.8472 | 0.0028433 | 2.0582 | 8.2328 | 0.0019759 | 100 | 0.024 | 48
| 3258106 | Residential Building : Repair & Maintenance |  | 40 | L.S. | 40 | 0.00039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.95 | 22.375 | 0.0087262 | 5.58 | 13.95 | 0.0054405 | 5 | 12.5 | 0.004875 | 11.8726 | 29.6815 | 0.011576 | 8.5974 | 21.4935 | 0.0083825 | 100 | 0.039 | 49
| 3258105 | Engineering Equipments |  | 20 | L.S. | 20 | 0.0002 | 0 | 0 | 0 | 0.09 | 0.45 | 9e-05 | 0.3 | 1.5 | 0.0003 | 0.5 | 2.5 | 0.0005 | 0.5 | 2.5 | 0.0005 | 2 | 10 | 0.002 | 9.1355 | 45.6775 | 0.0091355 | 7.4745 | 37.3725 | 0.0074745 | 100 | 0.02 | 50
|  | Drainage Structures : | [31 empty] | 51
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | 294.34 | 86 | 294.34 | 0.00288 | 0 | 0 | 0 | 0 | 0 | 0 | 59.7 | 20.2827 | 0.058414 | 24.34 | 8.2693 | 0.023816 | 10.99 | 3.7338 | 0.010753 | 58.25 | 19.79 | 0.056995 | 88.8678 | 30.1922 | 0.086954 | 52.1922 | 17.7319 | 0.051068 | 100 | 0.288 | 52
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | 5 | L.S. | 5 | 5e-05 | 0 | 0 | 0 | 0.9 | 18 | 0.0009 | 0 | 0 | 0 | 0.75 | 15 | 0.00075 | 0.74 | 14.8 | 0.00074 | 0.75 | 15 | 0.00075 | 1.1346 | 22.692 | 0.0011346 | 0.7254 | 14.508 | 0.0007254 | 100 | 0.005 | 53
| 3258107 | Others : Repair & Maintenance |  | 40 | L.S. | 40 | 0.00039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 6.25 | 0.0024375 | 4.98 | 12.45 | 0.0048555 | 3 | 7.5 | 0.002925 | 16.5312 | 41.328 | 0.016118 | 12.9888 | 32.472 | 0.012664 | 100 | 0.039 | 54
(a)Sub-total Revenue Component: | [5 empty] | 19382.61 | 0.18957 | 1081.09 | 45.0359 | 1.0573 | 2463.74 |  | 2.4097 | 2227.87 |  | 2.1788 | 2364.86 |  | 2.3124 | 2487.29 |  | 2.4323 | 2560 |  | 2.5037 | 3818.2052 |  | 3.735 | 2379.5548 |  | 2.3278 |  |  | 55
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 70.25 | 10 | 702.5 | 0.00687 | 346.3 | 49.2954 | 0.33866 | 138.6 | 19.7295 | 0.13554 | 0 | 0 | 0 | 122 | 17.3665 | 0.11931 | 0 | 0 | 0 | 95.6 | 13.6085 | 0.093491 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.34834 | 59
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 1.52 | 45 | 68.25 | 0.00067 | 5.825 | 8.5348 | 0.0057183 | 26.315 | 38.5568 | 0.025833 | 10.08 | 14.7692 | 0.0098954 | 8 | 11.7216 | 0.0078535 | 0 | 0 | 0 | 0 | 0 | 0 | 18.03 | 26.4176 | 0.0177 | 0 | 0 | 0 | 100 | 0.061282 | 60
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 18 | 5 | 90 | 0.00088 | 0 | 0 | 0 | 0 | 0 | 0 | 40.29 | 44.7667 | 0.039395 | 21 | 23.3333 | 0.020533 | 0 | 0 | 0 | 0 | 0 | 0 | 28.71 | 31.9 | 0.028072 | 0 | 0 | 0 | 100 | 0.088 | 62
|  | Mechinary & Other Equipment | [30 empty] | 0 | 63
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 1.28 | 7 | 8.97 | 9e-05 | 3.726 | 41.5385 | 0.0037385 | 2.744 | 30.5909 | 0.0027532 | 2.48 | 27.6477 | 0.0024883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.777 | 0.0052415 | 64
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 0.5 | 2 | 1 | 1e-05 | 0.796 | 79.6 | 0.000796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.006 | -0.6 | -6e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | -6e-06 | 65
|  | Engineering Equipments | [31 empty] | 66
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Sets | 20.5 | 17 | 20.5 | 0.0002 | 0 | 0 | 0 | 5.55 | 27.0732 | 0.0054146 | 11.15 | 54.3902 | 0.010878 | 3.48 | 16.9756 | 0.0033951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.439 | 0.019688 | 67
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos. | 1 | 3 | 3 | 3e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.13 | 71 | 0.00213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0.00213 | 68
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | Nos. | 0 | L.S | 50 | 0.00049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.89 | 15.78 | 0.0077322 | 1.6 | 3.2 | 0.001568 | 5 | 10 | 0.0049 | 35.51 | 71.02 | 0.0348 | 0 | 0 | 0 | 100 | 0.049 | 69
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 0.66 | 37 | 24.5 | 0.00024 | 3.879 | 15.8327 | 0.0037998 | 7.141 | 29.1469 | 0.0069953 | 6.18 | 25.2245 | 0.0060539 | 2.27 | 9.2653 | 0.0022237 | 0 | 0 | 0 | 0 | 0 | 0 | 5.03 | 20.5306 | 0.0049273 | 0 | 0 | 0 | 100 | 0.0202 | 71
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 1.25 | 11 | 13.75 | 0.00013 | 3.744 | 27.2291 | 0.0035398 | 0 | 0 | 0 | 2.986 | 21.7164 | 0.0028231 | 3.15 | 22.9091 | 0.0029782 | 0 | 0 | 0 | 0 | 0 | 0 | 3.87 | 28.1455 | 0.0036589 | 0 | 0 | 0 | 100 | 0.0094602 | 72
| 4112202 | A3 Combo Printer 2 no ( PMO) | No. | 0.75 | 2 | 1.5 | 1e-05 | 0 | 0 | 0 | 0.2 | 13.3333 | 0.00013333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 86.6667 | 0.00086667 | 0 | 0 | 0 | 100 | 0.001 | 73
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 0.31 | 17 | 5.25 | 5e-05 | 2.97 | 56.5714 | 0.0028286 | 0.2 | 3.8095 | 0.00019048 | 0 | 0 | 0 | 0.91 | 17.3333 | 0.00086667 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 22.2857 | 0.0011143 | 0 | 0 | 0 | 100 | 0.0021714 | 74
| 4112314 | Furnitures & Fixtures | item | 50 | LS | 50 | 0.00049 | 7.96 | 15.92 | 0.0078008 | 8.44 | 16.88 | 0.0082712 | 8.99 | 17.98 | 0.0088102 | 9.96 | 19.92 | 0.0097608 | 9.97 | 19.94 | 0.0097706 | 0 | 0 | 0 | 2.9016 | 5.8032 | 0.0028436 | 1.7784 | 3.5568 | 0.0017428 | 100 | 0.041199 | 75
| 4112303 | Aircooler | Nos. | 1 | 15 | 15 | 0.00015 | 0 | 0 | 0 | 0 | 0 | 0 | 3.77 | 25.1333 | 0.00377 | 2 | 13.3333 | 0.002 | 3.96 | 26.4 | 0.00396 | 4 | 26.6667 | 0.004 | 0.7747 | 5.1647 | 0.0007747 | 0.4953 | 3.302 | 0.0004953 | 100 | 0.015 | 76
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | ha | 49.26 | 470 | 23151.71 | 0.2264 | 0 | 0 | 0 | 0 | 0 | 0 | 4649.65 | 20.0834 | 4.5469 | 5794.05 | 25.0264 | 5.666 | 3879.9 | 16.7586 | 3.7941 | 2049.42 | 8.8521 | 2.0041 | 6778.69 | 29.2794 | 6.6289 | 0 | 0 | 0 | 100 | 22.64 | 78
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos. | 9.56 | 127 | 1213.55 | 0.01187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 116.72 | 9.6181 | 0.11417 | 490.33 | 40.4046 | 0.4796 | 333.575 | 27.4875 | 0.32628 | 272.925 | 22.4898 | 0.26695 | 100 | 1.187 | 81
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos. | 255.32 | 5 | 1276.62 | 0.01248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778.7382 | 61 | 0.76128 | 497.8818 | 39 | 0.48672 | 100 | 1.248 | 83
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 157.05 | 114 | 17903.94 | 0.17508 | 0 | 0 | 0 | 0 | 0 | 0 | 293.15 | 1.6373 | 0.28667 | 2773.9 | 15.4932 | 2.7126 | 3076.61 | 17.184 | 3.0086 | 8105.58 | 45.2726 | 7.9263 | 2229.367 | 12.4518 | 2.1801 | 1425.333 | 7.961 | 1.3938 | 100 | 17.508 | 84
| 4111307 | Re-excavation of Khal/River (New Haors) | km | 29.46 | 342.584 | 10091.78 | 0.09869 | 0 | 0 | 0 | 0 | 0 | 0 | 349.16 | 3.4598 | 0.34145 | 840.8 | 8.3315 | 0.82224 | 4821.52 | 47.7767 | 4.7151 | 3936.68 | 39.0088 | 3.8498 | 83.2996 | 0.82542 | 0.081461 | 60.3204 | 0.59772 | 0.058989 | 100 | 9.869 | 85
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | km | 28.87 | 108.974 | 3145.78 | 0.03076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.04 | 14.4651 | 0.44495 | 900.73 | 28.633 | 0.88075 | 1020.3057 | 32.4341 | 0.99767 | 769.7043 | 24.4678 | 0.75263 | 100 | 3.076 | 87
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | km | 25.11 | 67.11 | 1684.96 | 0.01648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452.46 | 26.8529 | 0.44254 | 913.26 | 54.2007 | 0.89323 | 181.9668 | 10.7995 | 0.17798 | 137.2732 | 8.147 | 0.13426 | 100 | 1.648 | 88
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | km | 27.08 | 57.912 | 1568.07 | 0.01533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341.85 | 21.8007 | 0.3342 | 657.55 | 41.9337 | 0.64284 | 358.2621 | 22.8473 | 0.35025 | 210.4079 | 13.4183 | 0.2057 | 100 | 1.533 | 89
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | km | 0 | 255.067 | 17374.5 | 0.16986 | 0 | 0 | 0 | 0 | 0 | 0 | 336.91 | 1.9391 | 0.32938 | 3910 | 22.5042 | 3.8226 | 1880.15 | 10.8213 | 1.8381 | 4650.77 | 26.7678 | 4.5468 | 4023.9687 | 23.1602 | 3.934 | 2572.7013 | 14.8073 | 2.5152 | 100 | 16.986 | 90
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos. | 22.02 | 7 | 154.12 | 0.00151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 73.26 | 47.5344 | 0.071777 | 0 | 0 | 0 | 50.1332 | 32.5287 | 0.049118 | 30.7268 | 19.9369 | 0.030105 | 100 | 0.151 | 91
| 4111201 | Threshing Floor Construction | Nos. | 45 | 20 | 900 | 0.0088 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 549 |  |  | 351 |  |  |  |  | 92
| 4111201 | Construction of WMG Office | Nos. | 35 | 60 | 2100 | 0.02054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.09 | 2.0043 | 0.041168 | 348.14 | 16.5781 | 0.34051 | 1008.7643 | 48.0364 | 0.98667 | 701.0057 | 33.3812 | 0.68565 | 100 | 2.054 | 93
| 4111201 | O&M During Construction | item | 0 | 2 | 600 | 0.00587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 57 | 0.33459 | 258 | 43 | 0.25241 | 100 | 0.587 | 94
|  | (b) Sub-total Capital Component: |  |  |  | 82219.25 | 0.80398 | 375.2 |  | 0.36688 | 189.19 |  | 0.18513 | 5714.796 | 258.7477 | 5.5885 | 13501.54 |  | 13.2021 | 15155.124 |  | 14.82 | 22157.06 |  | 21.6663 | 17835.3669 |  | 16.903 | 7289.5531 |  | 6.7846 |  |  | 95
|  | Total Cost (a+b) : |  |  |  | 101601.86 | 0.99355 | 1456.29 |  | 1.4242 | 2652.93 |  | 2.5948 | 7942.666 | 258.7477 | 7.7673 | 15866.4 |  | 15.5146 | 17642.414 |  | 17.2523 | 24717.06 |  | 24.1701 | 21653.5721 |  | 20.6379 | 9669.1079 |  | 9.1125 |  |  | 96
| 0 | (c) Physical Contingency ( Lump sum): | item | 0 | L.S. | 258 | 0.00252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 162.54 | 63 | 0.15876 | 95.46 | 37 | 0.09324 | 100 | 0.252 | 97
| 0 | (d) Price Contingency (Lump sum): | item | 0 | L.S. | 402.14 | 0.00393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 221.177 | 55 | 0.21615 | 180.963 | 45 | 0.17685 | 100 | 0.393 | 98
|  | Grand Total (a+b+c+d) : |  |  |  | 102262 | 1 | 1456.29 |  | 1.4242 | 2652.93 |  | 2.5948 | 7942.666 |  | 7.7673 | 15866.4 |  | 15.5146 | 17642.414 |  | 17.2523 | 24717.06 |  | 24.1701 | 22037.2891 |  | 21.0129 | 9945.5309 |  | 9.3826 |  |  | 99 |  | 97.6944
# Weight of each item = |  | (Est. cost of each respective item)
(Total cost of all Physical items)
# Physical Percentage of item = |  | Quantity/number targeted in each year |  |  |  |  | x 100
Total quantity/number of respective item for whole project period
# Physical % of total Project = |  | Weight of each item x % of item
[10 empty] | 1.4241 |  |  | 2.5942 |  |  | 7.767 |  |  | 15.5154 |  |  | 17.2522 |  |  | 24.1703 |  |  | 21.5498 |  |  | 9.7255 |  | 99.9986

## Inves._Cost
Investment Cost
Name of the Project : |  |  | Haor Flood Management and Livelihood Improvement Project.(BWDB Part)(Revised)
Name of agency/Division/Ministry : |  |  | Bangladesh Water Development Board / Ministry of Water Resources
(In Lakh Taka)
Budget Head | Economic Code/ Sub Code | Code/Sub Code Description | Total Project Cost | Financial | [7 empty] | CF | Economic
|  |  |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8 |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | 5 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.902 | 0 | 0.2706 | 0.11726 | 0.25256 | 0.2706 | 0.451 | 1.8258 | 1.3222
| 3111327 | Overtime Allowance | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6826 | 3.3374
| 3111338 | Other Allowance | 140 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.902 | 0 | 0 | 0 | 22.55 | 10.4722 | 12.628 | 48.3779 | 32.2519
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 120 | 0.991 | 11.909 | 14.98 | 17.96 | 12.7 | 15 | 28.8052 | 17.6548 | 0.902 | 0.89388 | 10.7419 | 13.512 | 16.1999 | 11.4554 | 13.53 | 25.9823 | 15.9246
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.25 | 58.3296 | 35.7504 | 0.812 | 0 | 13.195 | 25.4562 | 28.3063 | 27.7785 | 27.811 | 47.3636 | 29.0293
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 | 223.746 | 464.654 | 327.7 | 337.33 | 249.75 | 359.08 | 367.7258 | 266.2842 | 0.812 | 181.6818 | 377.299 | 266.0924 | 273.912 | 202.797 | 291.573 | 298.5933 | 216.2228
| 3211119 | Postage | 5 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.5 | 2.1634 | 1.5666 | 0.812 | 0 | 0.0406 | 0.10556 | 0.17864 | 0.30044 | 0.406 | 1.7567 | 1.2721
| 3211120 | Telephones/Telegram/Teleprinter | 5 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.2 | 2.3363 | 1.4937 | 0.812 | 0.17052 | 0.19488 | 0.23548 | 0.1218 | 0.06496 | 0.1624 | 1.8971 | 1.2129
| 3211117 | Telex/Fax/Internet | 5 | 0.249 | 0.001 | 0.09 | 0.05 | 0.05 | 0.2 | 2.4416 | 1.9184 | 0.812 | 0.20219 | 0.000812 | 0.07308 | 0.0406 | 0.0406 | 0.1624 | 1.9826 | 1.5577
| 3221104 | Registration Fee (Vehicles) | 20 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 1 | 4.4604 | 2.6196 | 0.812 | 0.8932 | 6.7964 | 0.06496 | 0 | 1.9244 | 0.812 | 3.6218 | 2.1271
| 3211115 | Water | 5 | 0 | 0.11 | 0.23 | 0.37 | 0.4 | 0.45 | 2.0984 | 1.3416 | 0.812 | 0 | 0.08932 | 0.18676 | 0.30044 | 0.3248 | 0.3654 | 1.7039 | 1.0894
| 3211113 | Electricity | 20 | 0.187 | 1.683 | 1.78 | 2.31 | 2.78 | 3.5 | 4.268 | 3.492 | 0.812 | 0.15184 | 1.3666 | 1.4454 | 1.8757 | 2.2574 | 2.842 | 3.4656 | 2.8355
| 3243102 | Gas & Fuel | 100 | 0.938 | 3.692 | 3 | 4 | 5.89 | 6 | 46.6528 | 29.8272 | 0.812 | 0.76166 | 2.9979 | 2.436 | 3.248 | 4.7827 | 4.872 | 37.8821 | 24.2197
| 3243101 | Petrol and Lubricant | 200 | 0.625 | 6.995 | 18.97 | 18 | 20 | 20 | 65.7837 | 49.6263 | 0.72 | 0.45 | 5.0364 | 13.6584 | 12.96 | 14.4 | 14.4 | 47.3643 | 35.7309
| 3221108 | Insurance/Bank Charges (including Vehicles) | 3 | 0.081 | 0.749 | 0.01 | 0.22 | 0.1 | 0.15 | 0.9295 | 0.7605 | 0.902 | 0.073062 | 0.6756 | 0.00902 | 0.19844 | 0.0902 | 0.1353 | 0.83841 | 0.68597
| 3255102 | Printing & Binding | 50 | 0.196 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.3574 | 5.9826 | 0.812 | 0.15915 | 5.6791 | 13.7959 | 4.872 | 3.2318 | 0.406 | 7.5982 | 4.8579
| 3255104 | Stationery, Seals & Stamps | 120 | 0.968 | 6.972 | 11.2 | 12.79 | 17.98 | 20 | 31.5567 | 18.5333 | 0.812 | 0.78602 | 5.6613 | 9.0944 | 10.3855 | 14.5998 | 16.24 | 25.624 | 15.049
| 3211127 | Books & Periodicals | 2 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.812 | 0 | 0.0812 | 0.02436 | 0.0406 | 0.0812 | 0.1624 | 0.71586 | 0.51838
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 238.54 | 0 | 0 | 0 | 0 | 0 | 0 | 238.54 | 0 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 215.1631 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 536.58 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 196.17 | 23.346 | 15.564 | 0.902 | 0 | 8.3164 | 26.9337 | 78.0681 | 158.6347 | 176.9453 | 21.0581 | 14.0387 | 536.58 | 483.9952 | 0.902 | 483.9952
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 3139.8 | 0 | 0 | 199.49 | 524.89 | 622.25 | 677.14 | 703.0989 | 412.9311 | 0.902 | 0 | 0 | 179.94 | 473.4508 | 561.2695 | 610.7803 | 634.1952 | 372.4639 | 3139.8 | 2832.0996 | 0.902 | 2832.0996
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 1321.68 | 0 | 0 | 119.7 | 224.29 | 234.21 | 246.66 | 273.251 | 223.569 | 0.902 | 0 | 0 | 107.9694 | 202.3096 | 211.2574 | 222.4873 | 246.4724 | 201.6592 | 1321.68 | 1192.1554 | 0.902 | 1192.1554
| 3211109 | Casual labour/Job worker | 22 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.5 | 4.6748 | 2.8652 | 0.902 | 0.2255 | 1.9032 | 2.1197 | 1.804 | 3.8335 | 3.157 | 4.2167 | 2.5844
| 3256103 | Consumable Stores | 15 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.812 | 0 | 0.80388 | 0.609 | 0.812 | 0.812 | 2.436 | 3.8901 | 2.817 | 15 | 12.18 | 0.812 | 12.18
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 7901.4 | 849.675 | 1819.425 | 1123.15 | 689.33 | 686.43 | 500 | 1362.3679 | 871.0221 | 0.902 | 766.4068 | 1641.1213 | 1013.0813 | 621.7757 | 619.1599 | 451 | 1228.8558 | 785.6619 | 7901.4 | 7127.0628 | 0.902 | 7127.0628
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 30 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 5 | 7.1166 | 5.1534 | 0.902 | 0.3608 | 1.1997 | 1.353 | 4.059 | 4.51 | 4.51 | 6.4192 | 4.6484 | 30 | 27.06 | 0.902 | 27.06
| 3111332 | b) Interim Evaluation | 10 | 0 | 0 | 0.27 | 0.25 | 0.77 | 1 | 7.71 | 0 | 0.902 | 0 | 0 | 0.24354 | 0.2255 | 0.69454 | 0.902 | 6.9544 | 0
| 3111332 | c) Progress Monitoring | 10 | 0 | 0 | 0.3 | 0.25 | 0.75 | 1 | 4.774 | 2.926 | 0.902 | 0 | 0 | 0.2706 | 0.2255 | 0.6765 | 0.902 | 4.3061 | 2.6393
| 3257104 | Survey | 162 | 0 | 7.62 | 17.47 | 30 | 29.93 | 50 | 15.3786 | 11.6014 | 0.902 | 0 | 6.8732 | 15.7579 | 27.06 | 26.9969 | 45.1 | 13.8715 | 10.4645
| 3255101 | Computer Consumables | 60 | 0.491 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.2415 | 13.2885 | 0.902 | 0.44288 | 1.3521 | 4.059 | 5.845 | 6.765 | 9.02 | 14.6498 | 11.9862 | 60 | 54.12 | 0.902 | 54.12
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 | 0 | 84.32 | 227.97 | 263.24 | 299.93 | 300 | 298.9878 | 225.5522 | 0.86 | 0 | 72.5152 | 196.0542 | 226.3864 | 257.9398 | 258 | 257.1295 | 193.9749 |  | 1462 | 0.86
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles | 125 | 0.983 | 5.967 | 12 | 21.99 | 20.46 | 15 | 26.73 | 21.87 | 0.86 | 0.84538 | 5.1316 | 10.32 | 18.9114 | 17.5956 | 12.9 | 22.9878 | 18.8082
| 3258102 | Furnitures & Fixtures | 10 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 2 | 2.88 | 1.92 | 0.86 | 0 | 0.4214 | 0.6364 | 0.8428 | 0.8514 | 1.72 | 2.4768 | 1.6512
| 3258103 | Computers & office equipments | 15 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.86 | 0 | 0.43 | 0.731 | 1.72 | 1.7114 | 2.58 | 3.3793 | 2.3483
| 3258105 | Machineries & Equipments | 10 | 0 | 0.21 | 0.01 | 0.5 | 0.5 | 2 | 4.1358 | 2.6442 | 0.86 | 0 | 0.1806 | 0.0086 | 0.43 | 0.43 | 1.72 | 3.5568 | 2.274 | 10 | 8.6 | 0.86 | 8.6
| 3258107 | Office Building : Repair & Maintenance | 25 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.765 | 0 | 0 | 0 | 7.6347 | 7.65 | 0 | 2.2658 | 1.5745 | 25 | 19.125 | 0.765 | 19.125
| 3258106 | Residential Building : Repair & Maintenance | 40 | 0 | 0 | 0 | 8.95 | 5.58 | 5 | 11.8726 | 8.5974 | 0.765 | 0 | 0 | 0 | 6.8467 | 4.2687 | 3.825 | 9.0825 | 6.577 | 40 | 30.6 | 0.765 | 30.6
| 3258105 | Engineering Equipments | 20 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.86 | 0 | 0.0774 | 0.258 | 0.43 | 0.43 | 1.72 | 7.8565 | 6.4281
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 294.34 | 0 | 0 | 59.7 | 24.34 | 10.99 | 58.25 | 88.8678 | 52.1922 | 0.812 | 0 | 0 | 48.4764 | 19.7641 | 8.9239 | 47.299 | 72.1607 | 42.3801 | 294.34 | 239.0041 | 0.812 | 239.0041
| 3258128 | Water Transport : Repair of Speedboat(s) | 5 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.75 | 1.1346 | 0.7254 | 0.812 | 0 | 0.7308 | 0 | 0.609 | 0.60088 | 0.609 | 0.9213 | 0.58902 | 5 | 4.06 | 0.812 | 4.06
| 3258107 | Others : Repair & Maintenance | 40 | 0 | 0 | 0 | 2.5 | 4.98 | 3 | 16.5312 | 12.9888 | 0.902 | 0 | 0 | 0 | 2.255 | 4.492 | 2.706 | 14.9111 | 11.7159 | 40 | 36.08 | 0.902 | 36.08
| (a)Sub-total Revenue Component: |  | 19382.61 | 1081.09 | 2463.74 | 2227.87 | 2364.86 | 2487.29 | 2560 | 3818.2052 | 2379.5548 |  | 954.5047 | 2171.1836 | 1955.1289 | 2076.9077 | 2194.3755 | 2247.2778 | 3359.0567 | 2086.5295 | 19382.61 | 17044.9643 | 0 | 12066.142
(b) Capital Component:
Acquisition of Assets:
|  | Motor Vehicle : | [18 empty] | 0 | 0 | 0 | 0
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 | 346.3 | 138.6 | 0 | 122 | 0 | 95.6 | 0 | 0 | 0.68 | 235.484 | 94.248 | 0 | 82.96 | 0 | 65.008 | 0 | 0 | 702.5 | 477.7 | 0.68 | 477.7
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 68.25 | 5.825 | 26.315 | 10.08 | 8 | 0 | 0 | 18.03 | 0 | 0.68 | 3.961 | 17.8942 | 6.8544 | 5.44 | 0 | 0 | 12.2604 | 0 | 68.25 | 46.41 | 0.68 | 46.41
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 90 | 0 | 0 | 40.29 | 21 | 0 | 0 | 28.71 | 0 | 0.68 | 0 | 0 | 27.3972 | 14.28 | 0 | 0 | 19.5228 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 | 3.726 | 2.744 | 2.48 | 0 | 0 | 0 | 0 | 0 | 0.812 | 3.0255 | 2.2281 | 2.0138 | 0 | 0 | 0 | 0 | 0 | 8.95 | 7.2674 | 0.812 | 7.2674
| 4112316 | Fax -2 nos (PMO 2 Nos.). | 1 | 0.796 | 0 | 0 | 0 | -0.006 | 0 | 0 | 0 | 0.812 | 0.64635 | 0 | 0 | 0 | -0.004872 | 0 | 0 | 0 | 0.79 | 0.64148 | 0.812 | 0.64148
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 | 0 | 5.55 | 11.15 | 3.48 | 0 | 0 | 0 | 0 | 0.68 | 0 | 3.774 | 7.582 | 2.3664 | 0 | 0 | 0 | 0 | 20.18 | 13.7224 | 0.68 | 13.7224
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 3 | 0 | 0 | 0 | 2.13 | 0 | 0 | 0 | 0 | 0.68 | 0 | 0 | 0 | 1.4484 | 0 | 0 | 0 | 0 | 2.13 | 1.4484 | 0.68 | 1.4484
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 50 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 35.51 | 0 | 0.68 | 0 | 0 | 0 | 5.3652 | 1.088 | 3.4 | 24.1468 | 0 | 50 | 34 | 0.68 | 34
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 24.5 | 3.879 | 7.141 | 6.18 | 2.27 | 0 | 0 | 5.03 | 0 | 0.812 | 3.1497 | 5.7985 | 5.0182 | 1.8432 | 0 | 0 | 4.0844 | 0 | 24.5 | 19.894 | 0.812 | 19.894
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 3.87 | 0 | 0.812 | 3.0401 | 0 | 2.4246 | 2.5578 | 0 | 0 | 3.1424 | 0 | 13.75 | 11.165 | 0.812 | 11.165
| 4112202 | A3 Combo Printer 2 no ( PMO) | 1.5 | 0 | 0.2 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0.812 | 0 | 0.1624 | 0 | 0 | 0 | 0 | 1.0556 | 0 | 1.5 | 1.218 | 0.812 | 1.218
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 1.17 | 0 | 0.812 | 2.4116 | 0.1624 | 0 | 0.73892 | 0 | 0 | 0.95004 | 0
| 4112314 | Furnitures & Fixtures | 50 | 7.96 | 8.44 | 8.99 | 9.96 | 9.97 | 0 | 2.9016 | 1.7784 | 0.812 | 6.4635 | 6.8533 | 7.2999 | 8.0875 | 8.0956 | 0 | 2.3561 | 1.4441
| 4112303 | Aircooler | 15 | 0 | 0 | 3.77 | 2 | 3.96 | 4 | 0.7747 | 0.4953 | 0.812 | 0 | 0 | 3.0612 | 1.624 | 3.2155 | 3.248 | 0.62906 | 0.40218
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | 23151.71 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 2049.42 | 6778.69 | 0 | 0.902 | 0 | 0 | 4193.9843 | 5226.2331 | 3499.6698 | 1848.5768 | 6114.3784 | 0 | 23151.71 | 20882.8424 | 0.902 | 20882.8424
Construction and Works:
|  | Irrigation Infrastructurs : | [18 empty] | 0 | 0 | 0 | 0
| 4111306 | Construction of Irrigation Inlet (New Haors) | 1213.55 | 0 | 0 | 0 | 0 | 116.72 | 490.33 | 333.575 | 272.925 | 0.902 | 0 | 0 | 0 | 0 | 105.2814 | 442.2777 | 300.8847 | 246.1784 | 1310 | 996.91 | 0.761 | 996.91
|  | Drainage Structures : | [18 empty] | 0 | 0 | 0 | 0
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 1276.62 | 0 | 0 | 0 | 0 | 0 | 0 | 778.7382 | 497.8818 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 595.7347 | 380.8796 | 1276.62 | 976.6143 | 0.765 | 976.6143
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 17903.94 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 8105.58 | 2229.367 | 1425.333 | 0.765 | 0 | 0 | 224.2597 | 2122.0335 | 2353.6067 | 6200.7687 | 1705.4658 | 1090.3797 | 17903.94 | 13696.5141 | 0.765 | 13696.5141
| 4111307 | Re-excavation of Khal/River (New Haors) | 10091.78 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 3936.68 | 83.2996 | 60.3204 | 0.761 | 0 | 0 | 265.7108 | 639.8488 | 3669.1767 | 2995.8135 | 63.391 | 45.9038 | 10091.78 | 7679.8446 | 0.761 | 7679.8446
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 3145.78 | 0 | 0 | 0 | 0 | 455.04 | 900.73 | 1020.3057 | 769.7043 | 0.761 | 0 | 0 | 0 | 0 | 346.2854 | 685.4555 | 776.4526 | 585.745 | 3145.78 | 2393.9386 | 0.761 | 2393.9386
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 1684.96 | 0 | 0 | 0 | 0 | 452.46 | 913.26 | 181.9668 | 137.2732 | 0.761 | 0 | 0 | 0 | 0 | 344.3221 | 694.9909 | 138.4767 | 104.4649 | 1684.96 | 1282.2546 | 0.761 | 1282.2546
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 1568.07 | 0 | 0 | 0 | 0 | 341.85 | 657.55 | 358.2621 | 210.4079 | 0.761 | 0 | 0 | 0 | 0 | 260.1479 | 500.3955 | 272.6375 | 160.1204 | 1568.07 | 1193.3013 | 0.761 | 1193.3013
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 17374.5 | 0 | 0 | 336.91 | 3910 | 1880.15 | 4650.77 | 4023.9687 | 2572.7013 | 0.761 | 0 | 0 | 256.3885 | 2975.51 | 1430.7942 | 3539.236 | 3062.2402 | 1957.8257 | 17374.5 | 13221.9945 | 0.761 | 13221.9945
| 4111201 | Rehabilitation of Regulator (New Haors) | 154.12 | 0 | 0 | 0 | 0 | 73.26 | 0 | 50.1332 | 30.7268 | 0.761 | 0 | 0 | 0 | 0 | 55.7509 | 0 | 38.1514 | 23.3831 | 154.12 | 117.2853 | 0.761 | 117.2853
| 4111201 | Threshing Floor Construction | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 351 | 2.761 | 0 | 0 | 0 | 0 | 0 | 0 | 1515.789 | 969.111
| 4111201 | Construction of WMG Office | 2100 | 0 | 0 | 0 | 0 | 42.09 | 348.14 | 1008.7643 | 701.0057 | 0.765 | 0 | 0 | 0 | 0 | 32.1989 | 266.3271 | 771.7047 | 536.2694 | 2100 | 1606.5 | 0.765 | 1606.5
| 4111201 | O&M During Construction | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 258 | 0.761 | 0 | 0 | 0 | 0 | 0 | 0 | 260.262 | 196.338 | 600 | 456.6 | 0.761 | 456.6
|  | (b) Sub-total Capital Component: | 82219.25 | 375.2 | 189.19 | 5714.796 | 13501.54 | 15155.124 | 22157.06 | 17835.3669 | 7289.5531 |  | 258.1819 | 131.1209 | 5001.9946 | 11090.3369 | 12109.6281 | 17245.4977 | 15683.7162 | 6298.4452
|  | Total Cost (a+b) : | 101601.86 | 1456.29 | 2652.93 | 7942.666 | 15866.4 | 17642.414 | 24717.06 | 21653.5721 | 9669.1079 |  | 1212.6866 | 2302.3045 | 6957.1235 | 13167.2446 | 14304.0036 | 19492.7755 | 19042.7729 | 8384.9746
| 0 | (c) Physical Contingency ( Lump sum): | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 162.54 | 95.46 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3431 | 73.0269
| 0 | (d) Price Contingency (Lump sum): | 402.14 | 0 | 0 | 0 | 0 | 0 | 0 | 221.177 | 180.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total (a+b+c+d) : | 102262 | 1456.29 | 2652.93 | 7942.666 | 15866.4 | 17642.414 | 24717.06 | 22037.2891 | 9945.5309 |  | 1212.6866 | 2302.3045 | 6957.1235 | 13167.2446 | 14304.0036 | 19492.7755 | 19167.116 | 8458.0015 | 85061.2557 | 102260.58

## Crop. Pattern
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
PRE - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic | ML | Seed | Urea | TSP | MP
1. | Boro (L) | 47000 | 3.5 | 164500 | 10000 | 10050 | 16450 | 16532.25 | 5405000 | 1880000 | 9400000 | 7520000 | 4700000
2. | Boro (HYV) | 125000 | 4 | 500000 | 11000 | 11055 | 55000 | 55275 | 18750000 | 5000000 | 37500000 | 30000000 | 18750000
| Total : | 172000 | - | - | - | - | 71450 | 71807.25 | 24155000 | 6880000 | 46900000 | 37520000 | 23450000
|  | Cropping Intensity = |  | 110%
|  | Total Paddy Production = |  |  | 664500 | mt.
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
POST - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic
1. | Boro (HYV) | 280500 | 5.5 | 1542750 | 10000 | 10050 | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
| Total : | 280500 | - | - | - | - | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
|  | Cropping Intensity = |  | 179.357 | %
|  | Total Paddy Production = |  |  | 1542750 | mt.
|  | Incremental Paddy Production = |  |  | 878250 | mt.
Variable Cost of Cultivation
PRE - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 24155000 | 100 | 75 | 24155 | 18116.25
2. | Power Tiller | - | - | - | - | 6880 | 6205.76
3. | Seed/Seedlings
a) | Paddy | mt. | 6880 | 30000 | 27060 | 2064 | 1861.728
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
d) | Mustard | mt. | 0 | 50000 | 45100 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 46900 | 8000 | 12000 | 3752 | 5628
b) | T.S.P. | mt. | 37520 | 22000 | 33000 | 8254.4 | 12381.6
c) | M.P. | mt. | 23450 | 18000 | 27000 | 4221 | 6331.5
5. | Insecticide | - | - | - | - | 200 | 180.4
6. | Irrigation Cost | - | - | - | - | 500 | 750
| Total | - | - | - | - | 49526.4 | 50705.238
POST - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 43477500 | 100 | 75 | 43477.5 | 32608.125
2. | Power Tiller | - | - | - | - | 11220 | 10120.44
3. | Seed/Seedlings
a) | Paddy | mt. | 11220 | 30000 | 27060 | 3366 | 3036.132
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
c) | Onion | mt. | 0 | 50000 | 45100 | 0 | 0
d) | Jute | mt. | 0 | 50000 | 45100 | 0 | 0
e) | Vegetables | mt. | 0 | 20000 | 18040 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 84150 | 8000 | 12000 | 6732 | 10098
|  | mt. | 34.61 | 22000 | 19844 | 7.6142 | 6.868
b) | T.S.P. | mt. | 67320 | 22000 | 33000 | 14810.4 | 22215.6
|  | mt. | 34.61 | 200 | 180.4 | 0.06922 | 0.062436
c) | M.P. | mt. | 42075 | 18000 | 27000 | 7573.5 | 11360.25
|  |  | 0 | - | -
|  |  | 0 |  | 0 | 0 | 0
5. | Insecticide | - | - | - | - | 500 | 451
6. | Irrigation Cost | - | - | - | - | 1000 | 1500
| Total | - | - | - |  | 88687.0834 | 91396.4774
| Incremental Farm Labour = |  | 19322500 | mandays
FIXED COST
A. | PRE - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
B. | POST - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
SUMMARY OF BENEFIT
A. | POST - PROJECT CONDITION
|  |  |  | Financial |  |  | Economic
1. | Gross Production Value |  |  | 154275 |  |  | 155046.375
2. | Cost of cultivation
| i) Variable Cost |  |  | 88687.0834 |  |  | 91396.4774
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (A1-A2) |  |  | 65587.9166 |  |  | 63649.8976
B. | PRE - PROJECT CONDITION
1. | Gross Production Value |  |  | 71450 |  |  | 71807.25
2. | Cost of cultivation
| i) Variable Cost |  |  | 49526.4 |  |  | 50705.238
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (B1-B2) |  |  | 21923.6 |  |  | 21102.012
C. | Net Incremental Benefit from Agriculture (A3-B3) |  |  | 43664.3166 |  |  | 42547.8856

## FIRR
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.29 | 0 | 1456.29 | 0 | 0 | 0 | -1456.29
2 | 2652.93 | 0 | 2652.93 | 0 | 0 | 0 | -2652.93
3 | 7942.666 | 0 | 7942.666 | 0 | 0 | 0 | -7942.666
4 | 15866.4 | 0 | 15866.4 | 0 | 0 | 0 | -15866.4
5 | 17642.414 | 0 | 17642.414 | 0 | 0 | 0 | -17642.414
6 | 24717.06 | 0 | 24717.06 | 21832.1583 | 0 | 21832.1583 | -2884.9017
7 | 22037.2891 | 0 | 22037.2891 | 26198.5899 | 0 | 26198.5899 | 4161.3008
8 | 9945.5309 | 0 | 9945.5309 | 30565.0216 | 0 | 30565.0216 | 20619.4907
9 |  | 670 | 670 | 34931.4533 | 0 | 34931.4533 | 34261.4533
10 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
11 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
12 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
13 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
14 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
15 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
16 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
17 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
18 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
19 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
20 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
21 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
22 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
23 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
24 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
25 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
26 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
27 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
28 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
29 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
30 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
NPV @12% | 55670.5702 | 2068.6546 | 57739.2248 | 166922.8114 | 0 | 166922.8114 | 109183.5866
All calculations are based on project period of 30 years
FIRR base case |  |  | 32.42%
Benefit Cost Ratio |  |  | 2.891
NPV @12% |  |  | 109183.5866

## EIRR
Computation of Internal Rate of Return
(Economic)
(In Lakh Taka)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1212.6866 | 0 | 1212.6866 | 0 | 0 | 0 | -1212.6866
2 | 2302.3045 | 0 | 2302.3045 | 0 | 0 | 0 | -2302.3045
3 | 6957.1235 | 0 | 6957.1235 | 0 | 0 | 0 | -6957.1235
4 | 13167.2446 | 0 | 13167.2446 | 0 | 0 | 0 | -13167.2446
5 | 14304.0036 | 0 | 14304.0036 | 0 | 0 | 0 | -14304.0036
6 | 19492.7755 | 0 | 19492.7755 | 21273.9428 | 0 | 21273.9428 | 1781.1673
7 | 19167.116 | 0 | 19167.116 | 25528.7313 | 0 | 25528.7313 | 6361.6153
8 | 8458.0015 | 0 | 8458.0015 | 29783.5199 | 0 | 29783.5199 | 21325.5184
9 |  | 604.34 | 604.34 | 34038.3084 | 0 | 34038.3084 | 33433.9684
10 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
11 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
12 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
13 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
14 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
15 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
16 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
17 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
18 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
19 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
20 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
21 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
22 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
23 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
24 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
25 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
26 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
27 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
28 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
29 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
30 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
NPV @12% | 46316.5013 | 1865.9265 | 48182.4278 | 162654.8457 | 0 | 162654.8457 | 114472.418
All calculations are based on project period of 30 years
EIRR base case |  |  | 36.66%
Benefit Cost Ratio |  |  | 3.3758
NPV @12% |  |  | 110049.79

## Annex-IV
Annexure-IV
Revised Amortization Schedule
Name of Project |  | : Haor Flood Management & Livelihood Improvement Project (BWDB Part)
Total Investment |  | : BDT 102234.00 Lakh |  |  |  | 102234
Loan Portion |  | : BDT 59529.60 Lakh
Loan Period |  | : 40 Years Including 10 Uears grace Period
Trate of Investment |  | : 0.01% per annum
(Taka in Lac)
Year | Beginning Principal Amount | Yearly Fixed Amount to be Paid (Principal) | Yearly Interes to be Paid | Total Payment (Principal + Interest) | Ending Principal Balance |  |  | 2014-15
1 | 2 | 3 | 4 | 5= (3+4) | 6=(2-3) |  |  | GoB | RPA | DPA | Total
11 | 59529.6 | 1984.32 | 5.953 | 1990.273 | 57545.28 |  | Rev | 231.42 |  | 849.67 | 1081.09
12 | 57545.28 | 1984.32 | 5.7545 | 1990.0745 | 55560.96 |  | Cap | 375.2 |  |  | 375.2
13 | 55560.96 | 1984.32 | 5.5561 | 1989.8761 | 53576.64 |  | Total | 606.62 | 0 | 849.67 | 1456.29
14 | 53576.64 | 1984.32 | 5.3577 | 1989.6777 | 51592.32
15 | 51592.32 | 1984.32 | 5.1592 | 1989.4792 | 49608 |  |  | 2015-16
16 | 49608 | 1984.32 | 4.9608 | 1989.2808 | 47623.68 |  |  | GoB | RPA | DPA | Total
17 | 47623.68 | 1984.32 | 4.7624 | 1989.0824 | 45639.36 |  | Rev | 635.09 | 9.22 | 1849.43 | 2493.74
18 | 45639.36 | 1984.32 | 4.5639 | 1988.8839 | 43655.04 |  | Cap | 189.19 |  |  | 189.19
19 | 43655.04 | 1984.32 | 4.3655 | 1988.6855 | 41670.72 |  | Total | 824.28 | 9.22 | 1849.43 | 2682.93
20 | 41670.72 | 1984.32 | 4.1671 | 1988.4871 | 39686.4 |  | Cum | 1430.9 | 9.22 | 2699.1 | 4139.22
21 | 39686.4 | 1984.32 | 3.9686 | 1988.2886 | 37702.08
22 | 37702.08 | 1984.32 | 3.7702 | 1988.0902 | 35717.76
23 | 35717.76 | 1984.32 | 3.5718 | 1987.8918 | 33733.44 |  |  | 2016-17
24 | 33733.44 | 1984.32 | 3.3733 | 1987.6933 | 31749.12 |  |  | GoB | RPA | DPA | Total
25 | 31749.12 | 1984.32 | 3.1749 | 1987.4949 | 29764.8 |  | Rev | 703.95 | 401.59 | 1093.15 | 2198.69
26 | 29764.8 | 1984.32 | 2.9765 | 1987.2965 | 27780.48 |  | Cap | 4854.6 | 860.19 |  | 5714.79
27 | 27780.48 | 1984.32 | 2.778 | 1987.098 | 25796.16 |  | Total | 5558.55 | 1261.78 | 1093.15 | 7913.48
28 | 25796.16 | 1984.32 | 2.5796 | 1986.8996 | 23811.84 |  | Cum | 6989.45 | 1271 | 3792.25 | 12052.7
29 | 23811.84 | 1984.32 | 2.3812 | 1986.7012 | 21827.52
30 | 21827.52 | 1984.32 | 2.1828 | 1986.5028 | 19843.2 |  | ADP | 2017-18
31 | 19843.2 | 1984.32 | 1.9843 | 1986.3043 | 17858.88 |  |  | GoB | RPA | DPA | Total
32 | 17858.88 | 1984.32 | 1.7859 | 1986.1059 | 15874.56 |  | Rev | 700 | 800 | 800 | 2300
33 | 15874.56 | 1984.32 | 1.5875 | 1985.9075 | 13890.24 |  | Cap | 10300 | 7400 |  | 17700
34 | 13890.24 | 1984.32 | 1.389 | 1985.709 | 11905.92 |  | Total | 11000 | 8200 | 800 | 20000
35 | 11905.92 | 1984.32 | 1.1906 | 1985.5106 | 9921.6
36 | 9921.6 | 1984.32 | 0.99216 | 1985.3122 | 7937.28 |  |  | July2016-Mar17
37 | 7937.28 | 1984.32 | 0.79373 | 1985.1137 | 5952.96 |  |  | GoB | RPA | DPA | Total
38 | 5952.96 | 1984.32 | 0.5953 | 1984.9153 | 3968.64 |  | Rev | -166.51 | 790.78 | -1899.1 | -1274.83
39 | 3968.64 | 1984.32 | 0.39686 | 1984.7169 | 1984.32 |  | Cap | 9735.61 | 7400 | 0 | 17135.61
40 | 1984.32 | 1984.32 | 0.19843 | 1984.5184 | 6.8212e-12 |  | Total | 9569.1 | 8190.78 | -1899.1 | 15860.78
Total |  | 59529.6 | 92.2709 | 59621.8709
Apr2017-June17
[8 empty] | GoB | RPA | DPA | Total
[7 empty] | Rev | 870.46 | -389.19 | 2992.25 | 3473.52
[7 empty] | Cap | -4881.01 | -6539.81 | 0 | -11420.82
[7 empty] | Total | -4010.55 | -6929 | 2992.25 | -7947.3

## FIRR_Backup
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.29 | 0 | 1456.29 | 0 | 0 | 0 | -1456.29
2 | 2652.93 | 0 | 2652.93 | 0 | 0 | 0 | -2652.93
3 | 7942.666 | 0 | 7942.666 | 0 | 0 | 0 | -7942.666
4 | 15866.4 | 0 | 15866.4 | 0 | 0 | 0 | -15866.4
5 | 17642.414 | 0 | 17642.414 | 0 | 0 | 0 | -17642.414
6 | 24717.06 | 0 | 24717.06 | 21832.1583 | 0 | 21832.1583 | -2884.9017
7 | 18586.3447 | 0 | 18586.3447 | 26198.5899 | 0 | 26198.5899 | 7612.2452
8 | 12971.6853 | 0 | 12971.6853 | 30565.0216 | 0 | 30565.0216 | 17593.3363
9 |  | 670 | 670 | 34931.4533 | 0 | 34931.4533 | 34261.4533
10 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
11 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
12 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
13 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
14 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
15 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
16 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
17 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
18 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
19 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
20 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
21 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
22 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
23 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
24 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
25 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
26 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
27 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
28 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
29 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
30 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
NPV @12% | 55331.7512 | 2068.6546 | 57400.4058 | 166922.8114 | 0 | 166922.8114 | 109522.4056
All calculations are based on project period of 30 years
FIRR base case |  |  | 32.6%
Benefit Cost Ratio |  |  | 2.908
NPV @12% |  |  | 109522.4056

## Package_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [19 empty] | 2
KISH/PW-02 | [19 empty] | 3
KISH/PW-03 | [19 empty] | 4
KISH/PW-04 | [19 empty] | 5
KISH/PW-05 | [19 empty] | 6
KISH/PW-06 | [19 empty] | 7
KISH/PW-07 | [19 empty] | 8
KISH/PW-09 | [19 empty] | 9
KISH/PW-10 | [19 empty] | 10
KISH/PW-11 | [19 empty] | 11
KISH/PW-12 | [19 empty] | 12
KISH/PW-13 | [19 empty] | 13
KISH/PW-14 | [19 empty] | 14
KISH/PW-15 | [19 empty] | 15
KISH/PW-16 | [19 empty] | 16
KISH/PW-17 | [19 empty] | 17
KISH/PW-18 | [19 empty] | 18
KISH/PW-19 | [19 empty] | 19
KISH/PW-20 | [19 empty] | 20
KISH/PW-21 | [19 empty] | 21
KISH/PW-22 | [19 empty] | 22
KISH/PW-23 | [19 empty] | 23
KISH/PW-24 | [19 empty] | 24
KISH/PW-25 | [19 empty] | 25
KISH/PW-26 | [19 empty] | 26
KISH/PW-27 | [19 empty] | 27
KISH/PW-28 | [19 empty] | 28
KISH/PW-29 | [19 empty] | 29
KISH/PW-30 | [19 empty] | 30
KISH/PW-31 | [19 empty] | 31
KISH/PW-32 | [19 empty] | 32
KISH/PW-33 | [19 empty] | 33
HOBI/PW-01 | [19 empty] | 34
HOBI/PW-02 | [19 empty] | 35
HOBI/PW-04 | [19 empty] | 36
HOBI/PW-05 | [19 empty] | 37
HOBI/PW-06 | [19 empty] | 38
HOBI/PW-07 | [19 empty] | 39
HOBI/PW-08 | [19 empty] | 40
NETR/PW-01 | [19 empty] | 41
NETR/PW-02 | [19 empty] | 42
NETR/PW-03 | [19 empty] | 43
NETR/PW-04 | [19 empty] | 44
NETR/PW-05 | [19 empty] | 45
NETR/PW-06 | [19 empty] | 46
NETR/PW-07 | [19 empty] | 47
NETR/PW-08 | [19 empty] | 48
SUNM/PW-01 | [19 empty] | 49
SUNM/PW-02 | [19 empty] | 50
SUNM/PW-03 | [19 empty] | 51
SUNM/PW-04 | [19 empty] | 52
SUNM/PW-05 | [19 empty] | 53
SUNM/PW-06 | [19 empty] | 54
SUNM/PW-07 | [19 empty] | 55
BRAH/PW-01 | [19 empty] | 56
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Package_wise_cost
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [18 empty] | 0 | 2
KISH/PW-02 | [18 empty] | 0 | 3
KISH/PW-03 | [18 empty] | 0 | 4
KISH/PW-04 | [18 empty] | 0 | 5
KISH/PW-05 | [18 empty] | 0 | 6
KISH/PW-06 | [18 empty] | 0 | 7
KISH/PW-07 | [18 empty] | 0 | 8
KISH/PW-09 | [18 empty] | 0 | 9
KISH/PW-10 | [18 empty] | 0 | 10
KISH/PW-11 | [18 empty] | 0 | 11
KISH/PW-12 | [18 empty] | 0 | 12
KISH/PW-13 | [18 empty] | 0 | 13
KISH/PW-14 | [18 empty] | 0 | 14
KISH/PW-15 | [18 empty] | 0 | 15
KISH/PW-16 | [18 empty] | 0 | 16
KISH/PW-17 | [18 empty] | 0 | 17
KISH/PW-18 | [18 empty] | 0 | 18
KISH/PW-19 | [18 empty] | 0 | 19
KISH/PW-20 | [18 empty] | 0 | 20
KISH/PW-21 | [18 empty] | 0 | 21
KISH/PW-22 | [18 empty] | 0 | 22
KISH/PW-23 | [18 empty] | 0 | 23
KISH/PW-24 | [18 empty] | 0 | 24
KISH/PW-25 | [18 empty] | 0 | 25
KISH/PW-26 | [18 empty] | 0 | 26
KISH/PW-27 | [18 empty] | 0 | 27
KISH/PW-28 | [18 empty] | 0 | 28
KISH/PW-29 | [18 empty] | 0 | 29
KISH/PW-30 | [18 empty] | 0 | 30
KISH/PW-31 | [18 empty] | 0 | 31
KISH/PW-32 | [18 empty] | 0 | 32
KISH/PW-33 | [18 empty] | 0 | 33
HOBI/PW-01 | [18 empty] | 0 | 34
HOBI/PW-02 | [18 empty] | 0 | 35
HOBI/PW-04 | [18 empty] | 0 | 36
HOBI/PW-05 | [18 empty] | 0 | 37
HOBI/PW-06 | [18 empty] | 0 | 38
HOBI/PW-07 | [18 empty] | 0 | 39
HOBI/PW-08 | [18 empty] | 0 | 40
NETR/PW-01 | [18 empty] | 0 | 41
NETR/PW-02 | [18 empty] | 0 | 42
NETR/PW-03 | [18 empty] | 0 | 43
NETR/PW-04 | [18 empty] | 0 | 44
NETR/PW-05 | [18 empty] | 0 | 45
NETR/PW-06 | [18 empty] | 0 | 46
NETR/PW-07 | [18 empty] | 0 | 47
NETR/PW-08 | [18 empty] | 0 | 48
SUNM/PW-01 | [18 empty] | 0 | 49
SUNM/PW-02 | [18 empty] | 0 | 50
SUNM/PW-03 | [18 empty] | 0 | 51
SUNM/PW-04 | [18 empty] | 0 | 52
SUNM/PW-05 | [18 empty] | 0 | 53
SUNM/PW-06 | [18 empty] | 0 | 54
SUNM/PW-07 | [18 empty] | 0 | 55
BRAH/PW-01 | [18 empty] | 0 | 56
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Haor_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
Chandpur Haor Sub-Project | N-1 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
Nunnir Haor Sub-Project | N-2 | 15 | 0 | 6 | 3 | 2 | 0 | 20 | 0 | 0 | 0 | 29.418 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3
Boro Haor Sub-Project | N-3 | 7 | 0 | 0 | 0 | 4 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4
Noapara Haor Sub-Project | N-4 | 14 | 0 | 4 | 2 | 2 | 0 | 10.757 | 0 | 0 | 0 | 23.29 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
Naogaon Haor Sub-Project | N-5 | 25 | 0 | 6 | 5 | 3 | 0 | 48.968 | 0 | 0 | 0 | 70.395 | 0 | 0 | 20 | 0 | 0 | 0 |  | 6
Badla Haor Sub-Project | N-6 | 6 | 0 | 2 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 21 | 5 | 0 | 0 | 0 | 0 | 0 |  | 7
Chatal Haor Sub-Project | N-7 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8
Dakhshiner Haor Sub-Project | N-8 | 15 | 0 | 1 | 1 | 3 | 0 | 11 | 0 | 0 | 0 | 22.048 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
Suniar Haor Sub-Project | N-9 | 0 | 0 | 2 | 4 | 2 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10
Mokhar Haor Sub-Project | N-10 | 15 | 0 | 6 | 9 | 5 | 0 | 30.058 | 0 | 0 | 0 | 23.815 | 1 | 0 | 0 | 0 | 0 | 0 |  | 11
Ganesh Haor Sub-Project | N-11 | 2 | 0 | 3 | 2 | 0 | 0 | 11.97 | 0 | 0 | 0 | 3.071 | 1 | 0 | 0 | 0 | 0 | 0 |  | 12
Dharmapasha Rui Beel Sub-Project | N-12 | 15 | 0 | 4 | 6 | 4 | 0 | 87.983 | 0 | 0 | 0 | 38.465 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
Dhakua Haor Sub-Project | N-14 | 9 | 0 | 2 | 7 | 6 | 0 | 50.508 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 16
Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 17
Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 18
Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 19
Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 20
Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21
Aralia Khal Sub-Project | R-7 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3.312 | 0 | 26.952 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 22
Bashira River Re-excavation Sub-Project | R-8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
Dampara Water Management Scheme | R-9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13.27 | 35.52 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 24
Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.98 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 25
Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.133 | 10.69 | 3.56 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 26
Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.195 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 27
Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 28
Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 29
Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 30
All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2 |  | 31
Total |  | 127 | 5 | 39 | 43 | 32 | 0 | 342.584 | 108.974 | 67.11 | 57.912 | 254.207 | 7 | 0 | 20 | 60 | 86 | 2 | 0

## distribution_of_cost
Item | costcode | rindex | 1st Revised | 2nd revised | difference
Office Administration | 1 | 2 | 5403.27 | 5398.27 | -5
Fuel & Lubricant | 2 | 3 | 350 | 300 | -50
Training and Livelihood | 3 | 4 | 4491.97 | 5236.6 | 744.63
Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
Repair & Maintenance | 5 | 6 | 265 | 290 | 25
Vehicle & Equipments | 6 | 7 | 1066.22 | 1066.22 | 0
Land Acquisition | 7 | 8 | 24000 | 22000 | -2000
Civilworks | 8 | 9 | 53727 | 57459.36 | 3732.36
contingency | 9 | 10 | 660.14 | 660.14 | 0
Total |  |  | 97865 | 100311.99 | 2446.99