## Sheet1
Abstruct cost of estimate for slope protection work of submersible embankment around Naogaon Haor sub project (Part -B) from km. .200 to km 2.200=2000.00m, Including 2 nos 35.00 m length Flood Fuse at km. 29.618 & km.33.955 in C/W Haor Flood Management & Livelihood Improvement Project under Kishoregonj WD Division BWDB, Kishoregonj during the year 2019-20
Sl. No/ code no | Description of Items | Quantity | Unit | Rate | Amount Tk.
1 | 2 | 3 | 4 | 5 | 6
1/16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | 68 | No | 367.41 | 24983.88
2./16-220 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-220-10 . 300m to 1.00 km.(85% compaction) | 12789.65 | Cum | 429.88 | 5498014.742
3/16-240 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-240-10 : Equipment; ht: 0 to 4m; 85% comp. | 12789.65 | Cum | 157.7 | 2016927.805
4/16-180 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | 12789.65 | Cum | 16.97 | 217040.3605
5/40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550 . FM : FM : 1.0 to 1.5 | 1878 | Cum | 1267.96 | 2381228.88
6/40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric). 40-500-40 : Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm, EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N. | 41760 | Sqm | 250.13 | 10445428.8
7/40-520 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge (A) 40-520-20. :Well graded between 40mm to 20mm size. . | 1044 | Cum | 4564.59 | 4765431.96
| (B) 40-520-10. :. Well graded between 20mm to 5mm size. (Combination of sub-item 10 & 30 or 20 & 30 shall be used) | 1044 | Cum | 5028.49 | 5249743.56
8/40-150 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>=1.5) and Stone Chips (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm² including grading, washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. (A) 40-150-40. : Block Size: 40cmx40cmx20cm | 111506 | Nos | 446.54 | 49791889.24
| (B)40-150-50. : Block Size: 30cmx30cmx30cm | 19000 | Nos | 371.82 | 7064580
9/40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge. (A) 40-270 -10. Within 200 m. cum | 2040.6 | Cum | 1395.03 | 2846698.218
| (B)40-270 -10. 200 m to 500 m. | 2040.6 | Cum | 2185.1 | 4458915.06
10/28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. cum28-120 . With 25mm down graded picked jhama or 1st. class brick chips. 28-120-20.: With 25mm down graded stone chips | 120 | Cum | 12907.66 | 1548919.2
11. 40-670 | Protective work with sand cement (6:1 propotion) filled 3/4th in 75Kg gunny bags (sand F.M>=1.00) including supply of all materials and necessaary sewing, filling and placiing/dumping in position and mixing with mixture machine with desined water cement ratio & curing as per specification and direction of the Engineer-in-charge. 40-670-30 : Sand cement new gunny bag ( 75 Kg; sand cement 6:1; Fill vol = 0.031 cum) | 102877 | Nos | 256.67 | 26405439.59
|  |  |  | Total = | 122715241.2955