## Sheet1
Detail estimate for slope protection work of submersible embankment around Naogaon Haor( Part- A & B )sub project from km. 3.870 to km 4.070=200.00m, km 20.00 to km 21.900 =1900.00m, km. 21.900 to km 22.800 = 900.00m & km. 26.080 to km 26.180 =100.00m Total =3100.00M & low height Closer under under Bridge at km. 23.50 of Noagaon Haor Part -B length 125.00m in C/W Haor Flood Management & Livelihood Improvement Project under Kishoregonj WD Division BWDB, Kishoregonj during the year 2019-20
Sl No. Code no | Description of Items | [9 empty] | Quantity
1/16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge.
Erection bamboo profile
| From km | 3.87 | to km. | 4.07 | = | 200 | meter
| From km | 20 | to km. | 21.9 | = | 1900 | ,,
| From km | 21.9 | to km. | 22.8 | = | 900 | ,,
| From km | 23.65 | to km. | 24.15 | = | 500 | ,,
| From km | 24.5 | to km. | 25 | = | 500 | ,,
| From km | 26.08 | to km. | 26.18 | = | 100 | ,,
Noagaon Haor Part -B,
| From km | 39.13 | to km. | 39.21 | = | 80 | ,,
| From km | 23.437 | to km. | 23.562 | = | 125 | ,,
|  |  | Total = |  |  | 4305
| Erection @ | 30.00 m Interval = |  | ( | 4305 | ÷ | 30 | )+7 | = | 150.5 | 150.5
Nos
2 16-220 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-220-10 . 300m to 1.00 km.(85% compaction)
For Type - A
| From km | 21.9 | to km. | 22.8 | = | 900 | ,,
| Average GL. = |  | (3.10+3.40+3.20+3.31+3.37+3.38+3.93+3.78)/8= |  |  |  |  | 3.44m
| High of Filling = |  | 4.9 | - | 3.44 | = | 1.46 | m
| Quantity of earth = 900x( 1.46x3x2+4.3+4.3)/2x1.46 =11405.52 cum | [6 empty] | = | 11405.52 | Cum
| From km | 26.08 | to km. | 26.1 | = | 20 | meter
| From km | 26.16 | to km. | 26.18 | = | 20 | ,,
[5 empty] | Total | 40 | meter
Av. Gl = 3.99 m
| Filling hight = |  | 4.9 | - | 3.99 | = | 0.91 | m
| Volume of earth= |  | 40.00 x(0.91x3x2)+4.3+4.3 /2x0.91 = 255.892 cum |  |  |  |  | = | 255.892 | ,,
| From km | 26.1 | to km. | 26.16 | = | 60 | meter | (closer)
Av. Gl = 1.82 m
| Filling hight = |  | 4.9 | - | 1.82 | = | 3.08 | m
1st stage =El +1.82 m to +3.95 m= 2.13m height
| 1st stage = 1x60.00mx (29.78m+17.00m)/2 x2.13 m = 2989.24 cum | [6 empty] | = | 2989.24 | ,,
| 2nd stage = 1x60.00mx (13.00m+4.30m)/2 x1.45 m = 752.55 cum | [7 empty] | 752.55 | ,,
Noagaon Haor Part -B, Low height Closer under Bridge
from km. 23.437 to km 23.562 = 125.00m
Av. Gl = 3.90 m
| Filling hight = |  | 4.9 | - | 3.9 | = | 1 | m
| Volume of earth= |  | 125.00.00 x(1.00x3x2)+4.30+4.30 /2x1.00 = 912.50 cum= | [5 empty] | 912.5 | ,,
Naogaon Haor Part -B
For Type - A
| From km | 39.13 | to km. | 39.21 | = | 80 | meter
Av. Gl = (-) 2.50 m
| Filling hight = |  | 4.9 | - | -2.5 | = | 7.4
Volume of earth=
| 1st stage = |  | 80.00 x(56.70+41.70)/2x2.50 = 9840.00 cum
| 2nd stage = |  | 80.00 x(22.70+37.70)/2x 2.50 = 6040.00 cum
| 3rd stage = |  | 80.00 x(4.30+18.70)/2x 2.40 = 2208.00 cum
|  |  | Total Earth = |  |  | 18088 | cum | = | 18088 | ,,
For Type - B
| From km | 3.87 | to km. | 4.07 | = | 200 | ,,
| Average GL. = |  | (2.87+2.94+2.94+2.53+2.86)/5= |  |  |  | 2.83m
| High of Filling = |  | 4.9 | - | 2.83 | = | 2.07 | m
Volume of earth = 200x( 2.07x3x2+4.3+4.3)/2x2.07 = 4351.14 cum
|  | Earth required 20% of total Earth |  |  | = | 4351.14 x20% = 870.228 cum |  |  | 870.228 | ,,
| From km | 20 | to km. | 21.9 | = | 1900 | ,,
| Average GL. = |  | (3.38+3.22+3.67+3.66+3.61+3.40)/6 = 3.49 m
| High of Filling = |  | 4.9 | - | 3.49 | = | 1.41 | m
Volume of earth = 900x(1.41x3x2+4.3+4.3)/2x1.41 = 10824.57 cum
|  | Earth required 50% of total Earth |  |  | = | 10824.57 x50% = 5412.285 cum |  |  | 5412.285 | ,,
| From km | 23.65 | to km. | 24.15 | = | 500 | ,,
| From km | 24.5 | to km. | 25 | = | 500 | ,,
[5 empty] | Total= | 1000 | ,,
| High of Filling = |  | 4.9 | - | 4.1 | = | 0.8 | m
| Volume of earth = 1000.00x(0.80x3x2+4.3+4.3)/2x0.80 = 5360.00 cum | [7 empty] | 5360 | ,,
[6 empty] | Grand Total = |  |  | 46046.215 | ,,
| Carried earth = 50% of total Earth = |  |  |  | 46046.215 | x | 50% | = | 23023.1075 | ,, | 23023.1075
cum
3 16-240 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. cum16-240 . Embankment by Mech. 16-240-10 : Equipment; ht: 0 to 4m; 85% comp.
|  | Quantity Same as item no. 2 = |  |  |  | 23023.1075 |  |  |  |  | 23023.1075
cum
4 16-180 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement.
|  | Quantity Same as item no. 2 = |  |  |  | 23023.1075 |  |  |  |  | 23023.1075
cum
5. 40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. 40-550 . FM : FM : 1.0 to 1.5
For Type - A
| From km | 21.9 | to km. | 22.8 | = | 900 | Meter
Total slope length =[{√(1.46x3)²+(1.46)²}x2]+4.30=13.53 m
| Volume = | 1 | x | 900 | x | 13.52 | x | 0.1 | = | 1216.8
Cum
| From km | 26.08 | to km. | 26.1 | = | 20 | meter
| From km | 26.16 | to km. | 26.18 | = | 20 | ,,
[5 empty] | Total | 40 | meter
Total slope length =[{√(0.91x3)²+(0.91)²}x2]+4.30=10.05 m
| Volume = | 1 | x | 40 | x | 10.05 | x | 0.1 | = | 40.2
Cum
| From km | 26.1 | to km. | 26.16 | = | 60 | meter | (closer)
| Total slope length = |  | 2x(6.73+2.00+4.58)+4.30 = 30.92 m
| Volume = | 1 | x | 60 | x | 30.92 | x | 0.1 | = | 185.52
| Noagaon Haor Part -B, Low height Closer under Bridge | [8 empty] | Cum
from km. 23.437 to km 23.562 = 125.00m
Total slope length =[{√(1.00x3)²+(1.00)²}x2]+4.30=10.62 m
| Volume = | 1 | x | 125 | x | 10.62 | x | 0.1 | = | 132.75
| Noagaon Haor Part -B, (Closer) | [8 empty] | Cum
| From km | 39.13 | to km. | 39.21 | = | 80 | meter
1st Stage slope =[{√(2.50x3)²+(2.50)²}x2]+4.30+2.00+2.00= 19.82 m
2nd Stage slope =[{√(2.40x3)²+(2.40)²}x2]+4.30 = 19.48 m
[5 empty] | Total = |  | 43.30 m
| Volume = | 1 | x | 80 | x | 43.3 | x | 0.1 | = | 346.4
[10 empty] | 1921.67 | 1921.67
[10 empty] | Cum | Cum
6. 40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric). 40-500-40 : Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm, EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N.
For Type - A
| From km | 21.9 | to km. | 22.8 | = | 900 | Meter
| Slope length = |  | 13.53m+(2x1.05m)= 15.63 m
| Area = |  | 15.63 | x | 900 |  |  | = | 14067 | Sqm
| From km | 26.08 | to km. | 26.1 | = | 20 | meter
| From km | 26.16 | to km. | 26.18 | = | 20 | ,,
[5 empty] | Total | 40 | meter
| Slope length = |  | 10.05m+(2x1.05m)= 12.15 m
| Area = |  | 12.15 | x | 40 |  |  | = | 486 | Sqm
| From km | 26.1 | to km. | 26.16 | = | 60 | meter | (closer)
| Slope length = |  | 30.92m+(2x1.05m)= 33.02 m
| Area = |  | 33.02 | x | 60 |  |  | = | 1981.2 | Sqm
Noagaon Haor Part -B, Low height Closer under Bridge
from km. 23.437 to km 23.562 = 125.00m
| Slope length = |  | 10.62m+(2x1.05m)= 12.72 m
| Area = |  | 12.72 | x | 125 |  |  | = | 1590 | Sqm
Noagaon Haor Part -B, (Closer)
For Type - A
| From km | 39.13 | to km. | 39.21 | = | 80 | meter
1st Stage slope =[{√(2.50x3)²+(2.50)²}x2]+(2.00 x2.00 x2)+2.00= 25.80 m
2nd Stage slope =[{√(2.40x3)²+(2.40)²}x2]+4.30 = 19.48 m
[5 empty] | Total = |  | 45.28 m
| Area = |  | 45.2 | x | 80 |  |  | = | 3616 | Sqm
For Type - B
| From km | 3.87 | to km. | 4.07 | = | 200
Total slope length =[{√(2.07x3)²+(2.07)²}x2]+4.30+(2x1.05)=19.50 m
| Area = |  | 19.5 | x | 200 |  |  | = | 3900 | Sqm
| From km | 20 | to km. | 21.9 | = | 1900 | ,,
Total slope length =[{√(1.41x3)²+(1.41)²}x2]+4.30+(1.05x2)=15.32 m
| Area = |  | 15.32 | x | 1900 |  |  | = | 29108 | Sqm
| From km | 23.65 | to km. | 24.15 | = | 500 | ,,
| From km | 24.5 | to km. | 25 | = | 500 | ,,
[5 empty] | Total= | 1000 | ,,
Total slope length =[{√(0.80x3)²+(0.80)²}x2]+4.30+(2x1.05)=11.46 m
| Area = |  | 11.46 | x | 1000 |  |  | = | 11460 | Sqm
[7 empty] | Total = |  | 66208.2 | Sqm | 66208.2
Sqm
7. 40-520 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge (A) 40-520-20. :Well graded between 40mm to 20mm size. . Well graded between 20mm to 5mm size. (Combination of sub-item 10 & 30 or 20 & 30 shall be used)
For Type - A
| From km | 21.9 | to km. | 22.8 | = | 900 | Meter
Total slope length =[{√(1.46x3)²+(1.46)²}x2]+4.30+(2x1.05)=15.63 m
| Volume = | 1 | x | 900 | x | 15.63 | x | 0.1 | = | 1406.7
Cum
| From km | 26.08 | to km. | 26.1 | = | 20 | meter
| From km | 26.16 | to km. | 26.18 | = | 20 | ,,
[5 empty] | Total | 40 | meter
Total slope length =[{√(0.91x3)²+(0.91)²}x2]+4.30+(2x1.05)=12.15 m
| Volume = | 1 | x | 40 | x | 12.15 | x | 0.1 | = | 48.6
Cum
| From km | 26.1 | to km. | 26.16 | = | 60 | meter | (closer)
| Total slope length = |  | 2x(6.73+2.00+4.58)+4.30+(2x1.05) = 33.02 m
| Volume = | 1 | x | 60 | x | 33.02 | x | 0.1 | = | 198.12
| Noagaon Haor Part -B, Low height Closer under Bridge | [8 empty] | Cum
from km. 23.437 to km 23.562 = 125.00m
Total slope length =[{√(1.00x3)²+(1.00)²}x2]+4.30=10.62 m
| Volume = | 1 | x | 125 | x | 10.62 | x | 0.1 | = | 132.75
| Noagaon Haor Part -B, (Closer) | [8 empty] | ,,
| From km | 39.13 | to km. | 39.21 | = | 80 | meter
1st Stage slope =[{√(2.50x3)²+(2.50)²}x2]+(2.00 x2.00 x2)= 23.80 m
2nd Stage slope =[{√(2.40x3)²+(2.40)²}x2]+4.30 = 19.48 m
[5 empty] | Total = |  | 43.28 m
| Volume = | 1 | x | 80 | x | 43.28 | x | 0.1 | = | 346.24
,,
[7 empty] | Total Quantity= |  |  | 2132.41
| 40mm to 20mm size = 50% of total Quantity= |  |  |  |  | 2132.41 | x | 50% | = | 1066.205 | 1066.205
Cum
(B) 40-520-10. :. Well graded between 20mm to 5mm size. (Combination of sub-item 10 & 30 or 20 & 30 shall be used)
|  | Quantity same as itam no. 7 (A) = |  |  |  | 1066.205 |  |  |  |  | 1066.205
Cum
8. 40-150 | Manufacturing and supplying C.C. blocks in leanest mix. 1:3:6, with cement, sand (FM>=1.5) and Stone Chips (40mm down graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm² including grading, washing stone chips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. 40-150-40. : Block Size: 40cmx40cmx20cm
For Type - A
| From km | 21.9 | to km. | 22.8 | = | 900 | Meter
| Area = | 13.53 | x | 900 |  |  | = | 12177 | Sqm
| From km | 26.08 | to km. | 26.1 | = | 20 | meter
| From km | 26.16 | to km. | 26.18 | = | 20 | ,,
[5 empty] | Total | 40 | meter
| Area = | 10.05 | x | 40 |  |  | = | 402 | Sqm
| From km | 26.1 | to km. | 26.16 | = | 60 | m (Closer)
| Area = | 30.92 | x | 60 |  |  | = | 1855.2 | ,,
Noagaon Haor Part -B, Low height Closer under Bridge
| From km | 23.437 | to km. | 23.562 | = | 125 | meter
| Area = | 10.62 | x | 125 |  |  | = | 1327.5 | ,,
Noagaon Haor Part -B, (closer)
| From km | 39.13 | to km. | 39.21 | = | 80 | Meter
| Area = | 43.28 | x | 80 |  |  | = | 3462.4 | ,,
[7 empty] | Total = | 19224.1 | Sqm
| Area of each block = |  | 0.4 | x | 0.4 | = | 0.16 | Sqm
| Total nos of block = |  | 19224.1 | ÷ | 0.16 | = |  | 120150.625 | Nos
| Deduction 5% for gap = 90214 x 5% = |  |  |  |  | (-) |  | 6007.5313 | ,,
[7 empty] | Total = | 114143.0938 | ,,
For Type - B
| From km | 3.87 | to km. | 4.07 | = | 200 | Meter
| From km | 20 | to km. | 21.9 | = | 1900 | ,,
| From km | 23.65 | to km. | 24.15 | = | 500 | ,,
| From km | 24.5 | to km. | 25 | = | 500 | ,,
[5 empty] | Total = | 3100 | ,,
| Total nos of block =( |  | 3100 | ÷ | 2 | )+1 | = | 1551 | ,,
[5 empty] | Grand | Total nos of block = |  | 115694.0938 | Nos |  | 115694.0938
nos.
40-150-50. : Block Size: 30cmx30cmx30cm
For Type - A
| From km | 21.9 | to km. | 22.8 | = | 900 | Meter
| From km | 26.08 | to km. | 26.1 | = | 20 | ,,
| From km | 26.16 | to km. | 26.18 | = | 20 | ,,
| From km | 26.1 | to km. | 26.16 | = | 60 | ,,
Noagaon Haor Part -B, Low height Closer under Bridge
| From km | 23.437 | to km. | 23.562 | = | 125
For Type - B
| From km | 3.87 | to km. | 4.07 | = | 200 | ,,
| From km | 20 | to km. | 21.9 | = | 1900 | ,,
| From km | 23.65 | to km. | 24.15 | = | 500
| From km | 24.5 | to km. | 25 | = | 500
|  |  |  | Total | = | 4225 | Meter
| Nos of block = |  | 2 | x | 3 | 4225 | ÷ | 0.3 | = | 84500
Nos
| Deduction 5% for gap = |  |  | 84500 | x | 5% |  |  | = | 4225
[7 empty] | Sub Total = |  |  | 80275
| Dumping block | [8 empty] | Nos
Noagaon Haor Part -B, Closer
| From km | 39.14 | to km. | 39.2 | = | 60 | Meter
Dumping volume will be @ 5.50 cum per meter
| Volume of block = |  | 60 | x | 2 | x | 5.5 | = | 660
| Volume of Each Block = |  | 0.3 | x | 0.3 | x | 0.3 | = | 0.027
| Nos of block = |  |  |  | 660 | ÷ | 0.027 | = |  | 24444.4444
[7 empty] | Total |  | = | 104719.4444 | 104719.4444
[10 empty] | Nos | Nos
9. 40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge. (A) 40-270 -10. Within 200 m. cum
Block size 40cmx40cmx20cm :
|  | 115694.0938 | x | 0.4 | x | 0.4 | x | 0.2 | = | 3702.211
Cum
Block size 30cmx30cmx30cm :
|  | 80275 | x | 0.3 | x | 0.3 | x | 0.3 | = | 2167.425
Cum
[7 empty] | Total | = |  | 5869.636
Cum
| Within 200 meter = 50% of Total Quantity = |  |  |  |  | 5869.636 | x | 50% | = | 2934.818 | 2934.818
[10 empty] | Cum | cum
(B)40-270 -10. 200 m to 500 m.
|  | Quantity same as item no 9(A) |  |  |  | = | 2934.818 |  |  |  | 2934.818
Cum
10/40-300 | Dumping work of Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks over a uniform area from properly positioned flat-top pontoon/barge upto an accuracy of 10cm monitoring with Total Station. The dumping area to be determined by conducting bathymetric survey, furnishing topographic site plan, cross section, dumping alignment, providing location of benchmark and stake at batches of dumping activity, doing by a river survey team (including survey manager, hydrographic surveyor, Auto cad operator, etc) with total station etc. Sequential stacking of Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks on the pontoon/barge to be done by fork lift or manual labour, carrying the Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks to dumping area and dumping the block from the properly positioned barge by a pay loader/forklift, inducing the cost of mobilization & demobilization of equipment’s, all materials & charges etc. complete as per direction of engineer in charge, 40-300-10 . Within 200 m.
| Volume = | 24444.4444 | x | 0.3 | x | 0.3 | x | 0.3 | = | 660 | 660
[10 empty] | Cum | Cum
10. 40.380 | Supplying filling and placing of geo-textile bags of different sizes and capacity at project/work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordance with the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in rable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical specification, approved design and direction of Engineer in charge. [fill volume and weight will be measured after filling with dry sand]"
40-380-50 | Geo-bag; inner size:800mmx650mm, outer size:850mmx700mm,
geo-fabric th.=>3.0mm, Fill Vol: 0.0520cum; wt: 80kg
For Type - B
| From km | 3.87 | to km. | 4.07 | = | 200 | Meter
| From km | 20 | to km. | 21.9 | = | 1900 | ,,
| From km | 23.65 | to km. | 24.15 | = | 500 | ,,
| From km | 24.5 | to km. | 25 | = | 500 | ,,
|  |  |  | Total | = | 3100 | ,,
| Geo Bag | @ 2.00 | m c/c |  | =
| No. of bag=(( | 3100 | ÷ | 2 | )+1)x2 | = | 3102 | Nos |  |  | 3102
Nos
11. 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge. cum28-120 . With 25mm down graded picked jhama or 1st. class brick chips. 28-120-20.: With 25mm down graded stone chips
Total length
For Type - A
| From km | 21.9 | to km. | 22.8 | = | 900 | Meter
| From km | 26.08 | to km. | 26.1 | = | 20 | ,,
| From km | 26.16 | to km. | 26.18 | = | 20 | ,,
| From km | 26.1 | to km. | 26.16 | = | 60 | ,,
Noagaon Haor Part -B, Low height Closer
| From km | 23.437 | to km. | 23.562 | = | 125
|  |  |  | Total = |  | 1125 | Meter
Volume =
| 1125 | x | 4 | x | 0.3 | x | 0.2 | x | 0.5 | = | 135
Noagaon Haor Part -B, Closer
| From km | 39.13 | to km. | 39.21 | = | 80 | Meter
Volume =
| 80 | x | 8 | x | 0.3 | x | 0.2 | x | 0.5 | = | 19.2
154.2
Cum
12. 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only). as per direction of Engineer in charge.
Total length
For Type - B
| From km | 3.87 | to km. | 4.07 | = | 200
Total slope length =[{√(2.07x3)²+(2.07)²}x2]+4.30 =17.40 m
| Area | = | 200 | x | 17.4 | = | 3480 | Sqm
| From km | 20 | to km. | 21.9 | = | 1900 | ,,
Total slope length =[{√(1.41x3)²+(1.41)²}x2]+4.30 =13.22 m
| Area | = | 1900 | x | 13.22 | = | 25118 | Sqm
| From km | 23.65 | to km. | 24.15 | = | 500
| From km | 24.5 | to km. | 25 | = | 500
[5 empty] | = | 1000 | Meter
| Total slope length =[{√(0.80x3)²+(1.41)²}x2]+4.30 = |  |  |  |  | 9.36 | meter
| Area | = | 1000 | x | 9.36 | = | 9360 | Sqm |  |  | 37958
[6 empty] | Total= | 37958 | Sqm |  |  | Sqm