## Sheet1
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
| Monthly Implementation Progress Review meeting of ADP included Project of the year 2019-2020 |  |  |  |  | IMED 05/2003 (Revised)
Monthly Progress Report
Reporting Period: Feb/2020
| Name of the Ministry/Division/Organization |  |  | : Ministry of Water Resources /
Bangladesh Water Development Board (BWDB)
(In Lakh Taka)
| Name of the Project | Allocation for the year 2019-2020 |  |  | Taka released | Expenditure upto Reporting Period: Reporting Period: Feb/2020& % of allocation
|  | Total | Taka | Project Aid (RPA) |  | Total | Taka(GoB) | Project Aid (RPA)
a) Main Programme :
| “Haor Flood Management and Livelihood Improvement Project (BWDB part)” | 5168.01 | 25000.00 | 24500.00 (6000.00) | 1500.00 | 500.00 | 3350.86 | 3088.48 (784.25)
| Sub Total : | 5168.01 | 25000.00 | 24500.00 (6000.00) | 1500.00 | 500.00 | 3350.86 | 3088.48 (784.25)
b) Technical Assistance
Sub Total :
c) Organization's Self Financed Programme :
Sub Total :
d) Food Aided Programme :
4333.38
4603.73
Sub Total :
| Grand Total : | 5168.01 | 25000.00 | 24500.00 (6000.00) | 1500.00 | 500.00 | 3350.86 | 3088.48 (784.25)

## Sheet2
| Monthly Implementation Progress Review meeting of ADP included Project of the year 2019-2020 | [7 empty] | IMED 05/2003 (Revised)
Reporting Period: Feb/2020 | [8 empty] | Monthly Progress Report
Name of the Ministry/Division/Organization |  |  |  | : Ministry of Water Resources /
Bangladesh Water Development Board (BWDB)
1 | Name of the Project |  | : Haor Flood Management and Livelihood Improvement Project (BWDB part)
2 | Objectives of the Project |  | : The main objectives of the project are:
(a) Rehabilitating and constructing the flood management facilities and
(b) Implementing agriculture promotion activities.
3 | Implementation Period |  | : a) Original : July,2014 to June,2022
b) Revised :- July, 2014 to June, 2022
4 | Location of the Project |  | : Kishoreganj, Mymensingh, Netrokona, Sunamganj, Habiganj and Brahmanbaria District
5 | Source of Funding (with amount) |  |  | :JICA Loan (Loan No.. BD P-80) (Total-97865.00, PA-59446.10, GoB-38418.90)
6 | Estimated Cost |  |  | : |  |  |  |  | (In Lakh Taka)
[5 empty] | Total | Taka(GoB) | Project Aid (RPA) |  | Physical(% of Total Project)
a) i. Original |  |  |  | : | 99337.72 | 39891.62 | 59446.10(51544.70)
b) ii. Revised |  |  |  | : | 496.00 | 97204.86 | 89303.46(38218.14)
c) Cumulative Progress upto last
|  | Jun-19 |  | : | 7901.40 | 45560.70 | 40392.69(21124.75) |  | 150000%
d) Current year Revised allocation
and Physical Target |  |  |  | : | 5168.01 | 25000.00 | 24500.00(6000.00) |  | 54%
e) Progress of current month |  |  |  | : | 237.62 | 1553.83 | 1553.83(217.66) |  | 17.3% |  |  | -3686.78 | 2469.33 | 17643%
f) Progress upto the current | [11 empty] | 1298.44 | 1298.44
month of the year |  |  |  | : | 500.00 | 3350.86 | 3088.48(784.25) |  | 26%
g) Fund released upto the current | [11 empty] | 4420.69
month |  |  |  | : | [7 empty] | 4006.25
7 | Quarterly Financial |  |  | :
and Physical | [8 empty] | (In Lakh Taka)
|  |  | 1st Quarter |  |  | 2nd Quarter |  | 3rd Quarter |  | 4th Quarter |  |  | 500.00 | 3350.86 | 11329.88 | 10643.45
|  |  | Financial |  | Physical | Financial | Physical | Financial | Physical | Financial | Physical |  | 11562.02 | 2948.3 | 8884.19 | 8480.01
| a) Target : |  | 5000 |  | 3% | 7500 | 3% | 7500 | 6% | 5000 | 7% |  | -11062.02 | 402.56 | 2445.69 | 2163.44
| b) Achievement : |  | 130.62 |  | 1.55% | 582.82 | 4.75% | 374.68 | 2.40% | 514.37 |  |  | 1602.49 | 6313.62 | 11329.88 | 10643.45
[13 empty] | 11562.02 | 2948.3 | 8884.19 | 8480.01
[13 empty] | -9959.53 | 3365.32 | 2445.69 | 2163.44
[13 empty] | 6593 | 17643.22
[13 empty] | 11329.88 | -130.62
[13 empty] | 17922.88 | -582.82
-374.68
16555.1

## Sheet3
8 | Target and Achievement of the main Components of the Project: | [6 empty] | (In Lakh Taka)
Sl. No. | Work components as Per RDPP (With quantity) | Estimated Cost | Achievement upto last June |  | Revised Target of the current year |  | Progress upto the month of Reporting Period: Feb/2020 of the current year
|  |  | Financial | Physical (% of the component) | Financial | Physical (% of the component) | Financial | Physical (% of the component)
A. | Revenue Component
1 | Allowances | 0 | 0 | 360% | 0 | - | 0 | -
2 | Travel expences | 1 | 0 | 375% | 0 | - | 0 | -
3 | Office rent for PMO | 2 | 0 | 856% | 0 | - | 0 | -
4 | Misc. taxes | 3 | 0 | 8977% | 0 | 1.2% | 0 | 0.4%
5 | Postage, telephone, Internate, Fax, telex etc. | 4 | 0 | 23% | 0 | - | 0 | -
6 | Registration Fees (Vehicles) | 5 | 0 | 25% | 0 | - | 0 | -
7 | Water & Elecricity | 6 | 0 | 99% | 0 | - | 0 | -
8 | Gas & Fuel and Petrol & Lubricant | 7 | 0 | 650% | 0 | - | 0 | -
9 | Insurance/Bank Charges (incl.Veh.) | 8 | 0 | 4% | 0 | - | 0 | -
10 | Printing & Binding | 9 | 0 | 13% | 0 | - | 0 | - | 242.23
11 | Stationary | 10 | 0 | 500% | 0 | - | 0 | - | 860.03
12 | Books & periodical | 11 | 0 | 5% | 0 | - | 0 | - | 7478.2
13 | Overseas Training | 12 | 0 | - | 0 | - | 0 | - | 8580.46
14 | Local Training | 13 | 0 | 3000% | 0 | 3% | 0 | 1% | 11130.71
15 | Casual labour/Job worker | 14 | 0 | 88% | 0 | - | 0 | - | 2550.25
16 | Consumable Stores | 15 | 0 | 75% | 0 | - | 0 | - | 1
17 | Consultancy | 16 | 7901.4 | - | 5168.01 | 3% | 500 | 1% | 2.53
18 | Honorarium/Fees/ Remuneration | 17 | 0 | 175% | 0 | - | 0 | - | 2553.78
19 | Survey | 18 | 0 | 1250% | 0 | - | 0 | -
20 | Computer Consumables | 19 | 0 | 250% | 0 | - | 0 | -
21 | Other expenses, Out sourcing Staff Salary | 20 | 0 | 7500% | 0 | 1.8% | 0 | 0.6%
22 | Repair & Maintenance of Vehicles, furniture, computers & other structure | 21 | 0 | 1025% | 0 | - | 0 | -
| SubTotal A: | 231 | 7901.4 | 25250% | 5168.01 | 9% | 500 | 3%
B. | Capital Component
1 | Motor Vehicle | 22 | 0 | - | 0 | 1% | 0 | 1%
2 | Water Transport | 23 | 0 | - | 0 | - | 0 | -
3 | Machinary & other equipment | 24 | 0 | - | 0 | - | 0 | -
4 | Engineering equipment | 25 | 0 | 500% | 0 | - | 0 | -
5 | Computer & Accessories | 26 | 0 | - | 0 | - | 0 | -
6 | Furniture & fixture and Aircooler | 27 | 0 | 400% | 0 | - | 0
7 | Land acquisition | 28 | 0 | - | 0 | 8% | 0 | 3%
8 | Construction Works | 29 | 0 | 123850% | 0 | 36% | 0 | 19% | 11.6
| SubTotal B: | 204 | 0 | 124750% | 0 | 45% | 0 | 23% | 14
| Total A + B: | 435 | 7901.4 | 150000% | 5168.01 | 54% | 500 | 26%
Sl. No. | Work components as Per RDPP (With quantity) | Estimated Cost | Achievement upto last June |  | Revised Target of the current year |  | Progress upto the month of May/2018 of the current year
|  |  | Financial | Physical (% of the component) | Financial | Physical (% of the component) | Financial | Physical (% of the component)
C. | Physical Contingency | 30 | 0 |  | 0 | - | 0 | -
D. | Price Contingency | 31 | 0 |  | 0 | - | 0 | -
| Grand Total (A+B+C+D): | 496 | 7901.4 | 150000% | 5168.01 | 54% | 500 | 26% | 0
9. Reasons for the delay of | [8 empty] | 23000
Project implementation |  |  | : N/A | [5 empty] | 8287.4
14712.6
10. Existing problems of | [8 empty] | 3879.9
Implementation of the project |  |  |  | : N/A |  |  |  |  | 18592.5
1
2.53
18595.03
[6 empty] | Project Director |  |  | 23000
[6 empty] | Haor Flood Management and |  |  | -8287.4
[6 empty] | Livelihood Improvement Project. |  |  | 3879.9
[6 empty] | BWDB, Dhaka. |  |  | 3.53
18596.03