## Abstract (Embankment)
Abstract of cost of estimate for the construction of Sub mergible embankment from km.0.00 to km. 33.520 = 17.841 km in Dakshiner Haor Sub -Project in C/W Haor flood Management and Livelihood Improvement project Under Kishoreganj W.D Division,BWDB, Kishoreganj During the Financial year 2017-18 & 2018-19 . Package No. BWDB/Kish/HFMLIP/PW-24
Sl. No: | Item no & Code | Item Description | Qnty | Unit | Unit Rate (Tk) | Amount (Tk)
(A) Submergible Embankment Dakshiner Haor in between km 0.00 to 33.520 =17.841 km
1 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cmx38cm x75cm on cement concrete (1:2:4) base of size 50cmx50cmx7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement mortar on top (1:2), with inscription of "BWDB" with 25cm of the pillar below ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | 37 | each | 1095.51 | 40533.87
2 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | 1440 | each | 290.48 | 418291.2
3 | 16-650 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-650-10 : Embankment by Mech. Equipment; ht: 0 to 4m; 85% comp | 124143.024 | Cum | 126.32 | 15681746.7917
4 | 16-410 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) direction of Engineer in charge.Earth work bymanual labour in all kinds of soil for excavation/ re-excavation of pond/ tank in layers of 150mm includingbreaking clods, dressing, profiling etc. complete with all leads and lifts as per direction of Engineer in charge. 16-410-10 : 300m to 1.00 km.(85% compaction) | 41381.008 | Cum | 346.28 | 14329415.4502
5 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference ..., (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 : 0 m to 3 m height with 85% compaction. | 41381.008 | Cum | 182.93 | 7569827.7934
6 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3 m neglected) for all kinds of earth work. a) 2 nos lead | 20690.504 | 2 lead Cum | 29.14 | 602921.2866
|  | b) 1 no lead | 20690.504 | Pld Cum | 14.57 | 301460.6433
7 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turfgrows properly, maintaining etc. complete (measurement will be given onwell grown grass only). as per direction of Engineer in charge. | 132023.4 | Sqm | 26.17 | 3455052.378
8 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge. | 214092 | m | 4.47 | 956991.24
9 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | 165524.032 | cum | 14.27 | 2362027.9366
| Sub-Total Sub-mergiable Embankment |  |  |  |  | 45718268.5898
Block Road :
10 | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge. | 3612.8025 | Cum | 135.05 | 487908.9776
11 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by..drawing and direction of Engineer in charge (payment shall be made on compacted volume). | 1204.2675 | Cum | 733.12 | 882872.5896
12 | Approved Analysis Rate | Preparetion of Bed by cutting and filling including watering to bring moisture+-2% of OMC & compaction by appropiate machanical meands etc to attain minimum compaction 98% oc MDD (standard) to obtain a minimum soaked CBR 4& etc all complete as per direction of the Engineer in charge. | 8028.45 | Sqm | 11.39 | 91444.0455
13 | Analysis rate | Manufacturing and supplying of 30cm x 30cm x 30cm C.C Block inleanest mix. 1:2:4, with cement , sand(Fm>=1.5) and stone chips (40mm down graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing stone chips, mixing laying in forms, consolidation, curing for at lest 21 days, including preparation of platform, shuttering and stackiing in measureable stacks etc complete including supply of all materials (steel shutter to be used) as per direction of Engineer in Charge. Block size 30 x 30 x 30 cum | 80507.5125 | No | 340.002 | 27372715.265
14 | Analysis rate | Manufacturing and supplying of trapezoidal size 100cm x 65cm x(10-15)cm C.C. blocks in leanest mix. 1:2:4 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a minimum 28 days cylinder strength of 15.0 N/mm² including grading, washing stonechips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. Block size 30 x 30 x 30 cum | 5352.3 | No | 977.181 | 5230165.8663
15 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge. 24-310-10: proportion 1:2 | 8028.45 | Sqm | 162.47 | 1304382.2715
16 | 40-220-10 | Labour charge for protective work in laying sand cement blocks of different sizes including preparation of base, ramming of base etc. complete as per direction of the Engineer in charge: 40-220-20: Beyond 200m. | 2608.5772 | Cum | 2027.04 | 5287690.3528
17 | 36-150 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props. | 22.9456 | sqm | 909.69 | 20873.4251
18 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia | 108.6372 | kg | 77.34 | 8402.0015
19 | 76-115-10 | M.S Work for reinforcement with Standard deformed bar fy=276 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-115-10: 6mm dia . | 22.8142 | kg | 74.37 | 1696.6913
20 | 28-200-10 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: with stone chips . | 22.9456 | cum | 11674.49 | 267878.7198
21 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge | 18.841 | each | 47.91 | 902.6723
22 | 40-540 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >= 8.0 cm in position etc. complete as per direction of Engineer in charge. 40-450-20 : Length: >= 2.0 m to < 4.5 m. | 8922 | Nos | 131.55 | 1173689.1
23 | 40-550 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. 40-550-10 : >= 1.50 m to <= 2.0 m drive, on dry land. | 13382.25 | m | 132.94 | 1779036.315
24 | 40-560 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge. 40-560-10 : Double Walling | 35682 | m | 64.53 | 2302559.46
25 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah doubly woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. | 13380.75 | Sqm | 162.45 | 2173702.8375
26 | Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge. | 1 | SUM | 967050.85 | 967050.85
27 | Approved Analysis Rate | Peovide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | 150 | Day | 2497.86 | 374679
28 | Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | Sum | 112344.1 | 112344.1
29 | Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 4 nos. of tube well and sanitation facilities by installing 6 nos. of sanitary latrines for usage of labours, Officials and others for prevailing the hygenic and healthy environment at allover the working sithe as per direction of the engineer in charge. | 1 | SUM | 111148.95 | 111148.95
30 | Approved Analysis Rate | Mobilize, strengthen required land based consatruction equipment such as excavator, dump truck, chain dozer, vibro-compactor and plants such as gemetor for site electrification, digital camera for taking photographs and digital vedio camera for recording/Taking Photograph as sequences of works etc. for keeping records of the works by providing following information including transfer to site, complete for the purposes stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | Sum | 92026.55 | 92026.55
31 | Approved Analysis Rate | Operate, maintain of plant and equipment such as generator for site electrification for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge. | 1 | Sum | 110909.92 | 110909.92
| Sub-Total |  |  |  |  | 50154079.9609 | 95872348.5507
|  |  | Sub Total Embkt. |  |  | 95872348.5507

## Detailed(Embankment)
Detailed estimate for the construction of Sub mergible embankment from km.0.00 to km. 33.520 = 17.841 km in Dakshiner Haor Sub -Project in C/W Haor flood Management and Livelihood Improvement project Under Kishoreganj W.D Division,BWDB, Kishoreganj During the Financial year 2017-18 & 2018-19 . Package No. BWDB/Kish/HFMLIP/PW-24
Sl. No: | Item no & Code | Item Description | Measurement | [9 empty] | Quantity | Unit
(A) Submergible Embankment Dakshiner Haor in between km 0.00 to 33.520 =17.841 km
1 | 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cmx38cm x75cm on cement concrete (1:2:4) base of size 50cmx50cmx7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement mortar on top (1:2), with inscription of "BWDB" with 25cm of the pillar below ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | = | 17841 |  |  | / | 500 | + | 1 | = | 36.682 | 36.682 | Nos
2 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. |  | 50 m interval & Four (4)
Nos Each Section
|  |  | = | 17841 |  |  | / | 50 | + | 3 | = | 359.82
|  |  | = | 359.82 |  |  | x | 4 | = | 1439.28 |  | Nos | 1439.28 | Nos
3 | 16-650 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-650-10 : Embankment by Mech. Equipment; ht: 0 to 4m; 85% comp
Total Calculated Earth
|  |  | = | 206905.04 cum
(Attached Calculation)
Earth work by Mechanical Excavator
|  |  | = | 60 | % | of Total Earth
[5 empty] | = | 0.6 | x | 206905.04 |  |  | cum
[5 empty] | = | 124143.024 |  |  |  | cum |  |  | 124143.024 | cum
4 | 16-410 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) direction of Engineer in charge.Earth work bymanual labour in all kinds of soil for excavation/ re-excavation of pond/ tank in layers of 150mm includingbreaking clods, dressing, profiling etc. complete with all leads and lifts as per direction of Engineer in charge. 16-410-10 : 300m to 1.00 km.(85% compaction)
Total Calculated Earth
|  |  | = | 206905.04 cum
(Attached Calculation)
Earth work by carried earth
|  |  | = | 20 | % | of Total Earth
[5 empty] | = | 0.2 | x | 206905.04 |  |  | cum
[5 empty] | = | 41381.008 |  |  |  | cum |  |  | 41381.008 | cum
5 | 16-120-20 | Earth work by manual labour in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference ..., (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 16-120-10 : 0 m to 3 m height with 85% compaction.
Total Calculated Earth
|  |  | = | 206905.04 |  |  | cum
(Attached Calculation)
Earth work by manual labour
|  |  | = | 20 | % | of Total Earth
[5 empty] | = | 0.2 | x | 206905.04 |  |  | cum
[5 empty] | = | 41381.008 |  |  |  | cum |  |  | 41381.008 | cum
6 | 16-190 | Extra rate for every additional lead of 15m or part thereof beyond the initial lead of 30m upto a maximum of 19 leads (3 m neglected) for all kinds of earth work. | Lead Calculation for carried earth
for 50% of carried earth
|  |  | = | (0.5 |  | * top of borrow pit +0.50
|  |  |  | filling +dead lead-15 )/30.0 | [9 empty] | 2 lead Cum
|  |  | = | 1.9167 | ~ | 2 |  | Nos |  |  |  |  | 20690.504
|  |  | 1 no lead for 50% of carried earth | [9 empty] | 20690.504 | Pld Cum
7 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75mm thick, good quality durba or charkanta sods of size 200mm x 200mm, with all leads and lifts, including ramming, watering until the turfgrows properly, maintaining etc. complete (measurement will be given onwell grown grass only). as per direction of Engineer in charge.
Length of Embankment
|  |  | = | 17841 |  |  | m
Total Turf
[5 empty] | = | 17841 |  |  | x | 3.7 | x | 2
[5 empty] | = | 132023.4 |  |  |  | sqm |  |  | 132023.4 | sqm
8 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge.
6 Rows Each Side
|  |  | = | 6 | x | 2 | x | 17841
[7 empty] | = | 214092 |  |  | m |  | 214092 | m
9 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. |  | 80% of total earth volume
[5 empty] | = | 80 | % | 206905.04 |  |  | cum
[5 empty] | = | 165524.032 |  |  | cum
Submergible Block Road :
10 | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge. | Length of Block Road is 15% of
Submergible Embankment
|  |  | = | 15 | % | 17841 |  |  | m
[5 empty] | = | 2676.15 |  |  | m
|  |  | Volume Of Box Cutting | [9 empty] | 3612.8025 | cum
|  |  | = | 2676.15 |  |  | x | 3 | x | 0.45 | cum
[7 empty] | = | 3612.8025 |  |  | cum
11 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by..drawing and direction of Engineer in charge (payment shall be made on compacted volume).
Sand Filling,
|  |  | = | 2676.15 |  |  | x | 3 | x | 0.15 | cum
[5 empty] | = | 1204.2675 |  |  | cum |  |  |  | 1204.2675 | cum
12 | Approved Analysis Rate | Preparetion of Bed by cutting and filling including watering to bring moisture+-2% of OMC & compaction by appropiate machanical meands etc to attain minimum compaction 98% oc MDD (standard) to obtain a minimum soaked CBR 4& etc all complete as per direction of the Engineer in charge. | Subgrade Area,
|  |  | = | 2676.15 |  |  | x | 3 | sqm
[5 empty] | = | 8028.45 |  |  | sqm |  |  |  | 8028.45 | sqm
13 | Approved Analysis Rate | Manufacturing and supplying of 30cm x 30cm x 30cm C.C Block inleanest mix. 1:2:4, with cement , sand(Fm>=1.5) and stone chips (40mm down graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing stone chips, mixing laying in forms, consolidation, curing for at lest 21 days, including preparation of platform, shuttering and stackiing in measureable stacks etc complete including supply of all materials (steel shutter to be used) as per direction of Engineer in Charge. Block size 30cm x 30cm x 30 cm |  | length |  |  | = | 2676.15 |  |  | m
|  |  |  | Width |  |  | = | 2.85 |  |  | m
Block Size 30x 30x30 cm
Nos Of Block
[5 empty] | = | 2676.15 |  |  | x | 2.85
[6 empty] | 0.3 | x | 0.3 |  |  |  |  | 80507.5125 | nos
[5 empty] | = | 84744.75 |  |  | nos
Deduct 5% for joint
Actual nos Of block
[5 empty] | = | 80507.5125 |  |  | nos
14 | Analysis rate | Manufacturing and supplying of trapezoidal size 100cm x 65cm x(10-15)cm C.C. blocks in leanest mix. 1:2:4 with cement, sand (FM>=1.5) and Stone Chips (40mm down graded) to attain a minimum 28 days cylinder strength of 15.0 N/mm² including grading, washing stonechips, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. complete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge. Block size 100cm x 65cm x12.50cm |  | length |  |  | = | 2676.15 |  |  | m
Block Size 100x 65x 12.5 cm
|  |  | Nos Of Block |  |  |  | for both side
[5 empty] | = | 2676.15 |  |  | x | 2
[6 empty] | 1 | x | 1 |  |  |  |  | 5352.3 | nos
[5 empty] | = | 5352.3 |  |  | nos
15 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge. 24-310-10: proportion 1:2 |  | Flush pointing
[5 empty] | = | 2676.15 |  |  | x | 3
[5 empty] | = | 8028.45 |  |  | sqm |  |  |  | 8028.45 | sqm
16 | 40-220-10 | Labour charge for protective work in laying sand cement blocks of different sizes including preparation of base, ramming of base etc. complete as per direction of the Engineer in charge: 40-220-20: Beyond 200m. |  | Block Size 30x 30x30 cm
|  |  | = | 80507.5125 |  |  | x | 0.3 | x | 0.3 | x | 0.3
|  |  | = | 2173.7028 |  |  | cum
|  |  |  | edge block 100x 65x12.50 cm | [8 empty] | 2608.5772 | Cum
|  |  | = | 5352.3 |  |  | x | 1 | x | 0.65 | x | 0.125
|  |  | = | 434.8744 |  |  | cum
|  |  |  | Total |  |  | 2608.5772 |  |  | Cum
17 | 36-150 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M.S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. 36-150-10: Vertical and inclined walls, columns, piers with 60-80mm dia barrack bamboo props
Nos of post,
[5 empty] | = | 17841 |  |  | + | 1 | = | 18.841
1000
Suttering
[5 empty] | = | 22 | x | 0.25 | = | 0.78571 |  | m
7
|  |  | Area Of Suttering | [5 empty] | H=(m) |  | 1.55
[5 empty] | = | 18.841 | x | 0.78571 | x | 1.55
[5 empty] | = | 22.9456 |  | sqm |  |  |  |  | 22.9456 | sqm
18 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-120-10: 8mm dia to 30mm dia
D-10- 6Nos (Vertical)
[5 empty] | = | 18.841 | x | 6 | x | 1.55
[5 empty] | = | 175.2213 |  | m
[5 empty] | = | 175.2213 | x | 0.62
[5 empty] | = | 108.6372 |  | kg |  |  |  |  | 108.6372 | kg
19 | 76-115-10 | M.S Work for reinforcement with Standard deformed bar fy=276 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-115-10: 6mm dia .
D-6- 8Nos (Stirrups)
Each ring length=0.688 m
[5 empty] | = | 18.841 | x | 8 | x | 0.688
[5 empty] | = | 103.7009 |  | m
[5 empty] | = | 103.7009 | x | 0.22
[5 empty] | = | 22.8142 |  | kg |  |  |  |  | 22.8142 | kg
20 | 28-200-10 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. 28-200-10: with stone chips .
Volume of RCC
[5 empty] | = | 18.841 | X | 22 | X | 0.25 | X | 1.55
7
[5 empty] | = | 22.9456 |  | cum |  |  |  |  | 22.9456 | cum
21 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge
Nos OF Pillar,
[5 empty] | = | 17841 |  |  | + | 1
1000
[5 empty] | = | 18.841 | Nos | [5 empty] | 18.841 | Nos
22 | 40-540 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >= 8.0 cm in position etc. complete as per direction of Engineer in charge. 40-450-20 : Length: >= 2.0 m to < 4.5 m. | 50% of total Length,
[5 empty] | = | 17841 |  |  | x | 0.5
[5 empty] | = | 8920.5 |  |  | m
|  |  |  | Spacing, |  |  | = | 1 | m |  |  |  | 8921.5 | Nos
Nos of Bamboo pin,
[5 empty] | = | 8920.5 |  |  | + | 1 | = | 8921.5
[6 empty] | 1 | [5 empty] | Nos
23 | 40-550 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. 40-550-10 : >= 1.50 m to <= 2.0 m drive, on dry land. |  | driving barrack bamboo pins
|  |  |  | H | = | 1.5 |  | m
[5 empty] | = | 8921.5 |  |  | x | 1.5 |  |  | 13382.25 | m
[5 empty] | = | 13382.25 |  |  | m
24 | 40-560 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge. 40-560-10 : Double Walling |  | Two Line Both side of pins,
half split walling pieces
[5 empty] | = | 8920.5 |  |  | x | 2 | x | 2 | 35682 | m
[5 empty] | = | 35682 |  |  | m
25 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah doubly woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. |  | fixing single layer tarjah
|  |  |  | doubly woven |  |  |  |  | Width=(m) |  |  | 1.5
[5 empty] | = | 8920.5 |  |  | x | 1.5
[5 empty] | = | 13380.75 |  |  | sqm |  |  |  | 13380.75 | sqm
26 | Approved Analysis Rate | Preparetion of mobilization of the site for construction of submersoble embankment or other structural components in c/w``Haor Flood Management and Livelihood Improvement Project (BWDB part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office (40sqm), CI sheet labor sheds (200sqm), CI sheet stores (200 sqm), supply of wooden & cane seated furniture etc. as per specified and as per Contractor's method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
27 | Approved Analysis Rate | Peovide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge.
[5 empty] | = | 150 |  | days |  |  |  |  | 150 | days
28 | Approved Analysis Rate | Demobilization and clean-up of the site upon completion of the works, as per Technical Specification, Contractor's Method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
29 | Approved Analysis Rate | Providing and maintaining adequate portable water supply by installing 4 nos. of tube well and sanitation facilities by installing 6 nos. of sanitary latrines for usage of labours, Officials and others for prevailing the hygenic and healthy environment at allover the working sithe as per direction of the engineer in charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
30 | Approved Analysis Rate | Mobilize, strengthen required land based consatruction equipment such as excavator, dump truck, chain dozer, vibro-compactor and plants such as gemetor for site electrification, digital camera for taking photographs and digital vedio camera for recording/Taking Photograph as sequences of works etc. for keeping records of the works by providing following information including transfer to site, complete for the purposes stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item
31 | Approved Analysis Rate | Operate, maintain of plant and equipment such as generator for site electrification for the purpose stated in the technical specification and Contractor's Method Statement and as per direction of Engineer in Charge.
[6 empty] | 1 |  | item |  |  |  |  | 1 | item

## Sheet3
7 | 11750 | 12 | 141000