## Kishoregnj
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 |  |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 |  |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 |  |  |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 |  |  |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 |  |  |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 |  |  |  | Munshi Zahirul Islam
7 | KISH/PW-02 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 |  |  |  | Md. Amirul Islam
8 | KISH/PW-02 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 |  |  |  | Md. Amirul Islam
9 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 |  |  |  | Md. Amirul Islam
10 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 |  |  |  | Md. Amirul Islam
11 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 |  |  |  | Md. Amirul Islam
12 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 |  |  |  | Md. Amirul Islam
13 | KISH/PW-02 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 |  |  |  | Md. Amirul Islam
14 | KISH/PW-03 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 |  |  |  | Md.Abudl Latif
15 | KISH/PW-03 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 |  |  |  | Md.Abudl Latif
16 | KISH/PW-03 | Block Road | Km |  |  |  |  | Md.Abudl Latif
17 | KISH/PW-04 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
18 | KISH/PW-04 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
19 | KISH/PW-04 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 |  |  |  | Md. Amirul Islam
20 | KISH/PW-04 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 |  |  |  | Md. Amirul Islam
21 | KISH/PW-05 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 |  |  |  | Md.Abudl Latif
22 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 |  |  |  | Md.Abudl Latif
23 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 |  |  |  | Md.Abudl Latif
24 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 |  |  |  | Md.Abudl Latif
25 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 |  |  |  | Md.Abudl Latif
26 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 |  |  |  | Md.Abudl Latif
27 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 |  |  |  | Md.Abudl Latif
28 | KISH/PW-05 | Block Road | Km | 12.214 |  |  |  | Md.Abudl Latif
29 | KISH/PW-06 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 |  |  |  | Md.Abudl Latif
30 | KISH/PW-06 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 |  |  |  | Md.Abudl Latif
31 | KISH/PW-06 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 |  |  |  | Md.Abudl Latif
32 | KISH/PW-06 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 |  |  |  | Md.Abudl Latif
33 | KISH/PW-06 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 |  |  |  | Md.Abudl Latif
34 | KISH/PW-06 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 |  |  |  | Md.Abudl Latif
35 | KISH/PW-06 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 |  |  |  | Md.Abudl Latif
36 | KISH/PW-07 | Hazir Khal | Km | 1.73 |  |  |  | Md. Amirul Islam
37 | KISH/PW-07 | Karpasha Khal | Km | 1.615 |  |  |  | Md. Amirul Islam
38 | KISH/PW-07 | Dampara Khal | Km | 3.6 |  |  |  | Md. Amirul Islam
39 | KISH/PW-07 | Baniajan | Km | 6.854 |  |  |  | Md. Amirul Islam
40 | KISH/PW-07 | Suti Khal | Km | 6.1 |  |  |  | Md. Amirul Islam
41 | KISH/PW-07 | Digha Nadi | Km | 5.7 |  |  |  | Md. Amirul Islam
42 | KISH/PW-07 | Old Singua | Km | 10.86 |  |  |  | Md. Amirul Islam
43 | KISH/PW-07 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 |  |  |  | Md. Amirul Islam
44 | KISH/PW-07 | Block Road | Km |  |  |  |  | Md. Amirul Islam
45 | KISH/PW-09 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 |  |  |  | Md.Abudl Latif
46 | KISH/PW-09 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 |  |  |  | Md.Abudl Latif
47 | KISH/PW-09 | Causeway 6.0m wide-1 at Dampara | Nos | 1 |  |  |  | Md.Abudl Latif
48 | KISH/PW-09 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 |  |  |  | Md.Abudl Latif
49 | KISH/PW-10 | Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md. Amirul Islam
50 | KISH/PW-10 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 |  |  |  | Md. Amirul Islam
51 | KISH/PW-10 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 |  |  |  | Md. Amirul Islam
52 | KISH/PW-10 | Block Road | Km |  |  |  |  | Md. Amirul Islam
53 | KISH/PW-11 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 |  |  |  | Md. Amirul Islam
54 | KISH/PW-11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 |  |  |  | Md. Amirul Islam
55 | KISH/PW-12 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 |  |  |  | Md. Amirul Islam
56 | KISH/PW-12 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 |  |  |  | Md. Amirul Islam
57 | KISH/PW-12 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 |  |  |  | Md. Amirul Islam
58 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 |  |  |  | Md. Amirul Islam
59 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 |  |  |  | Md. Amirul Islam
60 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 |  |  |  | Md. Amirul Islam
61 | KISH/PW-12 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 |  |  |  | Md. Amirul Islam
62 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 |  |  |  | Munshi Zahirul Islam
63 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 |  |  |  | Munshi Zahirul Islam
64 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 |  |  |  | Munshi Zahirul Islam
65 | KISH/PW-14 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 |  |  |  | Munshi Zahirul Islam
66 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 |  |  |  | Munshi Zahirul Islam
67 | KISH/PW-15 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 |  |  |  | Md.Khalilur Rahman
68 | KISH/PW-15 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 |  |  |  | Md.Khalilur Rahman
69 | KISH/PW-16 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
70 | KISH/PW-16 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 |  |  |  | Md.Khalilur Rahman
71 | KISH/PW-16 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
72 | KISH/PW-17 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
73 | KISH/PW-17 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
74 | KISH/PW-17 | Box Drainage Outlet-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
75 | KISH/PW-17 | Box Drainage Outlet-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
76 | KISH/PW-17 | Box Drainage Outlet-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
77 | KISH/PW-17 | Box Drainage Outlet-4 | Nos | 1 |  |  |  | Md.Khalilur Rahman
78 | KISH/PW-17 | Box Drainage Outlet-5 | Nos | 1 |  |  |  | Md.Khalilur Rahman
79 | KISH/PW-17 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 |  |  |  | Md.Khalilur Rahman
80 | KISH/PW-17 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
81 | KISH/PW-17 | Irrigation Pipe Inlet-1 | Nos | 25 |  |  |  | Md.Khalilur Rahman
82 | KISH/PW-18 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 |  |  |  | Md.Khalilur Rahman
83 | KISH/PW-18 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 |  |  |  | Md.Khalilur Rahman
84 | KISH/PW-18 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 |  |  |  | Md.Khalilur Rahman
85 | KISH/PW-18 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 |  |  |  | Md.Khalilur Rahman
86 | KISH/PW-18 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 |  |  |  | Md.Khalilur Rahman
87 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 |  |  |  | Md.Khalilur Rahman
88 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 |  |  |  | Md.Khalilur Rahman
89 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 |  |  |  | Md.Khalilur Rahman
90 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 |  |  |  | Md.Khalilur Rahman
91 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 |  |  |  | Md.Khalilur Rahman
92 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 |  |  |  | Munshi Zahirul Islam
93 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 |  |  |  | Munshi Zahirul Islam
94 | KISH/PW-20 | Chitra Khal 4m wide | Nos | 1 |  |  |  | Md.Abudl Latif
95 | KISH/PW-20 | Nabinpur Khal 4m Wide | Nos | 1 |  |  |  | Md.Abudl Latif
96 | KISH/PW-20 | Dipjuri Khal 4m CW | Nos | 1 |  |  |  | Md.Abudl Latif
97 | KISH/PW-20 | Sudhikhal 4m wide CW | Nos | 1 |  |  |  | Md.Abudl Latif
98 | KISH/PW-20 | Chhagalia khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
99 | KISH/PW-20 | Near nasir sluice | Nos | 1 |  |  |  | Md.Abudl Latif
100 | KISH/PW-20 | Shingpur khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
101 | KISH/PW-20 | Gharu khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
102 | KISH/PW-20 | Irrigation Pipe Inlet 600mm dia | Nos | 36 |  |  |  | Md.Abudl Latif
103 | KISH/PW-21 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 |  |  |  | Md.Khalilur Rahman
104 | KISH/PW-21 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 |  |  |  | Md.Khalilur Rahman
105 | KISH/PW-21 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 |  |  |  | Md.Khalilur Rahman
106 | KISH/PW-21 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 |  |  |  | Md.Khalilur Rahman
107 | KISH/PW-22 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 |  |  |  | Md.Khalilur Rahman
108 | KISH/PW-22 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
109 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 |  |  |  | Md.Khalilur Rahman
110 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
111 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 |  |  |  | Md.Khalilur Rahman
112 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 |  |  |  | Md.Khalilur Rahman
113 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 |  |  |  | Md.Khalilur Rahman
114 | KISH/PW-22 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 |  |  |  | Md.Khalilur Rahman
115 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 |  |  |  | Md.Khalilur Rahman
116 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 |  |  |  | Md.Khalilur Rahman
117 | KISH/PW-22 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 |  |  |  | Md.Khalilur Rahman
118 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
119 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
120 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
121 | KISH/PW-23 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 |  |  |  | Anil Chandra Roy
122 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 |  |  |  | Anil Chandra Roy
123 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 |  |  |  | Anil Chandra Roy
124 | KISH/PW-23 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 |  |  |  | Anil Chandra Roy
125 | KISH/PW-23 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 |  |  |  | Anil Chandra Roy
126 | KISH/PW-23 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 |  |  |  | Anil Chandra Roy
127 | KISH/PW-23 | Irrigation Pipe Inlet 600mm dia | Nos | 4 |  |  |  | Anil Chandra Roy
128 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 |  |  |  | Munshi Zahirul Islam
129 | KISH/PW-25 | Regulator 5-Vent-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
130 | KISH/PW-25 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 |  |  |  | Md.Khalilur Rahman
131 | KISH/PW-25 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
132 | KISH/PW-25 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
133 | KISH/PW-25 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
134 | KISH/PW-25 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
135 | KISH/PW-25 | Box Sluice-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
136 | KISH/PW-25 | Irrigation Pipe Inlet 600mm dia | Nos | 15 |  |  |  | Md.Khalilur Rahman
137 | KISH/PW-26 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 |  |  |  | Anil Chandra Roy
138 | KISH/PW-26 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 |  |  |  | Anil Chandra Roy
139 | KISH/PW-26 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 |  |  |  | Anil Chandra Roy
140 | KISH/PW-26 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 |  |  |  | Anil Chandra Roy
141 | KISH/PW-26 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 |  |  |  | Anil Chandra Roy
142 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | Nos | 1 |  |  |  | Anil Chandra Roy
143 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | Nos | 1 |  |  |  | Anil Chandra Roy
144 | KISH/PW-27 | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | Nos | 1 |  |  |  | Anil Chandra Roy
145 | KISH/PW-27 | D 4.0 m width Chonati Causeway | Nos | 1 |  |  |  | Anil Chandra Roy
146 | KISH/PW-27 | R.C.C Box Drainage Outlet 900mm x 900mm | Nos | 1 |  |  |  | Anil Chandra Roy
Munshi Zahirul Islam
Md. Amirul Islam
Md.Abudl Latif
Anil Chandra Roy
Md.Khalilur Rahman

## Munshi
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 |  |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 |  |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 |  |  |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 |  |  |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 |  |  |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 |  |  |  | Munshi Zahirul Islam
62 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 |  |  |  | Munshi Zahirul Islam
63 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 |  |  |  | Munshi Zahirul Islam
64 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 |  |  |  | Munshi Zahirul Islam
65 | KISH/PW-14 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 |  |  |  | Munshi Zahirul Islam
66 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 |  |  |  | Munshi Zahirul Islam
92 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 |  |  |  | Munshi Zahirul Islam
93 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 |  |  |  | Munshi Zahirul Islam
128 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 |  |  |  | Munshi Zahirul Islam
Munshi Zahirul Islam
Md. Amirul Islam
Md.Abudl Latif
Anil Chandra Roy
Md.Khalilur Rahman

## Amirul
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
121 | KISH/PW-23 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 |  |  |  | Anil Chandra Roy
122 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 |  |  |  | Anil Chandra Roy
123 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 |  |  |  | Anil Chandra Roy
124 | KISH/PW-23 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 |  |  |  | Anil Chandra Roy
125 | KISH/PW-23 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 |  |  |  | Anil Chandra Roy
126 | KISH/PW-23 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 |  |  |  | Anil Chandra Roy
127 | KISH/PW-23 | Irrigation Pipe Inlet 600mm dia | Nos | 4 |  |  |  | Anil Chandra Roy
137 | KISH/PW-26 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 |  |  |  | Anil Chandra Roy
138 | KISH/PW-26 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 |  |  |  | Anil Chandra Roy
139 | KISH/PW-26 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 |  |  |  | Anil Chandra Roy
140 | KISH/PW-26 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 |  |  |  | Anil Chandra Roy
141 | KISH/PW-26 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 |  |  |  | Anil Chandra Roy
142 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | Nos | 1 |  |  |  | Anil Chandra Roy
143 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | Nos | 1 |  |  |  | Anil Chandra Roy
144 | KISH/PW-27 | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | Nos | 1 |  |  |  | Anil Chandra Roy
145 | KISH/PW-27 | D 4.0 m width Chonati Causeway | Nos | 1 |  |  |  | Anil Chandra Roy
146 | KISH/PW-27 | R.C.C Box Drainage Outlet 900mm x 900mm | Nos | 1 |  |  |  | Anil Chandra Roy
7 | KISH/PW-02 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 |  |  |  | Md. Amirul Islam
8 | KISH/PW-02 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 |  |  |  | Md. Amirul Islam
9 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 |  |  |  | Md. Amirul Islam
10 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 |  |  |  | Md. Amirul Islam
11 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 |  |  |  | Md. Amirul Islam
12 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 |  |  |  | Md. Amirul Islam
13 | KISH/PW-02 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 |  |  |  | Md. Amirul Islam
17 | KISH/PW-04 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
18 | KISH/PW-04 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
19 | KISH/PW-04 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 |  |  |  | Md. Amirul Islam
20 | KISH/PW-04 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 |  |  |  | Md. Amirul Islam
36 | KISH/PW-07 | Hazir Khal | Km | 1.73 |  |  |  | Md. Amirul Islam
37 | KISH/PW-07 | Karpasha Khal | Km | 1.615 |  |  |  | Md. Amirul Islam
38 | KISH/PW-07 | Dampara Khal | Km | 3.6 |  |  |  | Md. Amirul Islam
39 | KISH/PW-07 | Baniajan | Km | 6.854 |  |  |  | Md. Amirul Islam
40 | KISH/PW-07 | Suti Khal | Km | 6.1 |  |  |  | Md. Amirul Islam
41 | KISH/PW-07 | Digha Nadi | Km | 5.7 |  |  |  | Md. Amirul Islam
42 | KISH/PW-07 | Old Singua | Km | 10.86 |  |  |  | Md. Amirul Islam
43 | KISH/PW-07 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 |  |  |  | Md. Amirul Islam
44 | KISH/PW-07 | Block Road | Km |  |  |  |  | Md. Amirul Islam
49 | KISH/PW-10 | Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md. Amirul Islam
50 | KISH/PW-10 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 |  |  |  | Md. Amirul Islam
51 | KISH/PW-10 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 |  |  |  | Md. Amirul Islam
52 | KISH/PW-10 | Block Road | Km |  |  |  |  | Md. Amirul Islam
53 | KISH/PW-11 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 |  |  |  | Md. Amirul Islam
54 | KISH/PW-11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 |  |  |  | Md. Amirul Islam
55 | KISH/PW-12 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 |  |  |  | Md. Amirul Islam
56 | KISH/PW-12 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 |  |  |  | Md. Amirul Islam
57 | KISH/PW-12 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 |  |  |  | Md. Amirul Islam
58 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 |  |  |  | Md. Amirul Islam
59 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 |  |  |  | Md. Amirul Islam
60 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 |  |  |  | Md. Amirul Islam
61 | KISH/PW-12 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 |  |  |  | Md. Amirul Islam
14 | KISH/PW-03 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 |  |  |  | Md.Abudl Latif
15 | KISH/PW-03 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 |  |  |  | Md.Abudl Latif
16 | KISH/PW-03 | Block Road | Km |  |  |  |  | Md.Abudl Latif
21 | KISH/PW-05 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 |  |  |  | Md.Abudl Latif
22 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 |  |  |  | Md.Abudl Latif
23 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 |  |  |  | Md.Abudl Latif
24 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 |  |  |  | Md.Abudl Latif
25 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 |  |  |  | Md.Abudl Latif
26 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 |  |  |  | Md.Abudl Latif
27 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 |  |  |  | Md.Abudl Latif
28 | KISH/PW-05 | Block Road | Km | 12.214 |  |  |  | Md.Abudl Latif
29 | KISH/PW-06 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 |  |  |  | Md.Abudl Latif
30 | KISH/PW-06 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 |  |  |  | Md.Abudl Latif
31 | KISH/PW-06 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 |  |  |  | Md.Abudl Latif
32 | KISH/PW-06 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 |  |  |  | Md.Abudl Latif
33 | KISH/PW-06 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 |  |  |  | Md.Abudl Latif
34 | KISH/PW-06 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 |  |  |  | Md.Abudl Latif
35 | KISH/PW-06 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 |  |  |  | Md.Abudl Latif
45 | KISH/PW-09 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 |  |  |  | Md.Abudl Latif
46 | KISH/PW-09 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 |  |  |  | Md.Abudl Latif
47 | KISH/PW-09 | Causeway 6.0m wide-1 at Dampara | Nos | 1 |  |  |  | Md.Abudl Latif
48 | KISH/PW-09 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 |  |  |  | Md.Abudl Latif
94 | KISH/PW-20 | Chitra Khal 4m wide | Nos | 1 |  |  |  | Md.Abudl Latif
95 | KISH/PW-20 | Nabinpur Khal 4m Wide | Nos | 1 |  |  |  | Md.Abudl Latif
96 | KISH/PW-20 | Dipjuri Khal 4m CW | Nos | 1 |  |  |  | Md.Abudl Latif
97 | KISH/PW-20 | Sudhikhal 4m wide CW | Nos | 1 |  |  |  | Md.Abudl Latif
98 | KISH/PW-20 | Chhagalia khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
99 | KISH/PW-20 | Near nasir sluice | Nos | 1 |  |  |  | Md.Abudl Latif
100 | KISH/PW-20 | Shingpur khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
101 | KISH/PW-20 | Gharu khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
102 | KISH/PW-20 | Irrigation Pipe Inlet 600mm dia | Nos | 36 |  |  |  | Md.Abudl Latif
67 | KISH/PW-15 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 |  |  |  | Md.Khalilur Rahman
68 | KISH/PW-15 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 |  |  |  | Md.Khalilur Rahman
69 | KISH/PW-16 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
70 | KISH/PW-16 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 |  |  |  | Md.Khalilur Rahman
71 | KISH/PW-16 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
72 | KISH/PW-17 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
73 | KISH/PW-17 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
74 | KISH/PW-17 | Box Drainage Outlet-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
75 | KISH/PW-17 | Box Drainage Outlet-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
76 | KISH/PW-17 | Box Drainage Outlet-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
77 | KISH/PW-17 | Box Drainage Outlet-4 | Nos | 1 |  |  |  | Md.Khalilur Rahman
78 | KISH/PW-17 | Box Drainage Outlet-5 | Nos | 1 |  |  |  | Md.Khalilur Rahman
79 | KISH/PW-17 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 |  |  |  | Md.Khalilur Rahman
80 | KISH/PW-17 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
81 | KISH/PW-17 | Irrigation Pipe Inlet-1 | Nos | 25 |  |  |  | Md.Khalilur Rahman
82 | KISH/PW-18 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 |  |  |  | Md.Khalilur Rahman
83 | KISH/PW-18 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 |  |  |  | Md.Khalilur Rahman
84 | KISH/PW-18 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 |  |  |  | Md.Khalilur Rahman
85 | KISH/PW-18 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 |  |  |  | Md.Khalilur Rahman
86 | KISH/PW-18 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 |  |  |  | Md.Khalilur Rahman
87 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 |  |  |  | Md.Khalilur Rahman
88 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 |  |  |  | Md.Khalilur Rahman
89 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 |  |  |  | Md.Khalilur Rahman
90 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 |  |  |  | Md.Khalilur Rahman
91 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 |  |  |  | Md.Khalilur Rahman
103 | KISH/PW-21 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 |  |  |  | Md.Khalilur Rahman
104 | KISH/PW-21 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 |  |  |  | Md.Khalilur Rahman
105 | KISH/PW-21 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 |  |  |  | Md.Khalilur Rahman
106 | KISH/PW-21 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 |  |  |  | Md.Khalilur Rahman
107 | KISH/PW-22 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 |  |  |  | Md.Khalilur Rahman
108 | KISH/PW-22 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
109 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 |  |  |  | Md.Khalilur Rahman
110 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
111 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 |  |  |  | Md.Khalilur Rahman
112 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 |  |  |  | Md.Khalilur Rahman
113 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 |  |  |  | Md.Khalilur Rahman
114 | KISH/PW-22 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 |  |  |  | Md.Khalilur Rahman
115 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 |  |  |  | Md.Khalilur Rahman
116 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 |  |  |  | Md.Khalilur Rahman
117 | KISH/PW-22 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 |  |  |  | Md.Khalilur Rahman
118 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
119 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
120 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
129 | KISH/PW-25 | Regulator 5-Vent-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
130 | KISH/PW-25 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 |  |  |  | Md.Khalilur Rahman
131 | KISH/PW-25 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
132 | KISH/PW-25 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
133 | KISH/PW-25 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
134 | KISH/PW-25 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
135 | KISH/PW-25 | Box Sluice-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
136 | KISH/PW-25 | Irrigation Pipe Inlet 600mm dia | Nos | 15 |  |  |  | Md.Khalilur Rahman
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 |  |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 |  |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 |  |  |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 |  |  |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 |  |  |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 |  |  |  | Munshi Zahirul Islam
62 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 |  |  |  | Munshi Zahirul Islam
63 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 |  |  |  | Munshi Zahirul Islam
64 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 |  |  |  | Munshi Zahirul Islam
65 | KISH/PW-14 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 |  |  |  | Munshi Zahirul Islam
66 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 |  |  |  | Munshi Zahirul Islam
92 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 |  |  |  | Munshi Zahirul Islam
93 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 |  |  |  | Munshi Zahirul Islam
128 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 |  |  |  | Munshi Zahirul Islam
Munshi Zahirul Islam
Md. Amirul Islam
Md.Abudl Latif
Anil Chandra Roy
Md.Khalilur Rahman

## Latif
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
121 | KISH/PW-23 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 |  |  |  | Anil Chandra Roy
122 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 |  |  |  | Anil Chandra Roy
123 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 |  |  |  | Anil Chandra Roy
124 | KISH/PW-23 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 |  |  |  | Anil Chandra Roy
125 | KISH/PW-23 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 |  |  |  | Anil Chandra Roy
126 | KISH/PW-23 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 |  |  |  | Anil Chandra Roy
127 | KISH/PW-23 | Irrigation Pipe Inlet 600mm dia | Nos | 4 |  |  |  | Anil Chandra Roy
137 | KISH/PW-26 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 |  |  |  | Anil Chandra Roy
138 | KISH/PW-26 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 |  |  |  | Anil Chandra Roy
139 | KISH/PW-26 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 |  |  |  | Anil Chandra Roy
140 | KISH/PW-26 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 |  |  |  | Anil Chandra Roy
141 | KISH/PW-26 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 |  |  |  | Anil Chandra Roy
142 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | Nos | 1 |  |  |  | Anil Chandra Roy
143 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | Nos | 1 |  |  |  | Anil Chandra Roy
144 | KISH/PW-27 | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | Nos | 1 |  |  |  | Anil Chandra Roy
145 | KISH/PW-27 | D 4.0 m width Chonati Causeway | Nos | 1 |  |  |  | Anil Chandra Roy
146 | KISH/PW-27 | R.C.C Box Drainage Outlet 900mm x 900mm | Nos | 1 |  |  |  | Anil Chandra Roy
7 | KISH/PW-02 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 |  |  |  | Md. Amirul Islam
8 | KISH/PW-02 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 |  |  |  | Md. Amirul Islam
9 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 |  |  |  | Md. Amirul Islam
10 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 |  |  |  | Md. Amirul Islam
11 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 |  |  |  | Md. Amirul Islam
12 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 |  |  |  | Md. Amirul Islam
13 | KISH/PW-02 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 |  |  |  | Md. Amirul Islam
17 | KISH/PW-04 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
18 | KISH/PW-04 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
19 | KISH/PW-04 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 |  |  |  | Md. Amirul Islam
20 | KISH/PW-04 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 |  |  |  | Md. Amirul Islam
36 | KISH/PW-07 | Hazir Khal | Km | 1.73 |  |  |  | Md. Amirul Islam
37 | KISH/PW-07 | Karpasha Khal | Km | 1.615 |  |  |  | Md. Amirul Islam
38 | KISH/PW-07 | Dampara Khal | Km | 3.6 |  |  |  | Md. Amirul Islam
39 | KISH/PW-07 | Baniajan | Km | 6.854 |  |  |  | Md. Amirul Islam
40 | KISH/PW-07 | Suti Khal | Km | 6.1 |  |  |  | Md. Amirul Islam
41 | KISH/PW-07 | Digha Nadi | Km | 5.7 |  |  |  | Md. Amirul Islam
42 | KISH/PW-07 | Old Singua | Km | 10.86 |  |  |  | Md. Amirul Islam
43 | KISH/PW-07 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 |  |  |  | Md. Amirul Islam
44 | KISH/PW-07 | Block Road | Km |  |  |  |  | Md. Amirul Islam
49 | KISH/PW-10 | Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md. Amirul Islam
50 | KISH/PW-10 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 |  |  |  | Md. Amirul Islam
51 | KISH/PW-10 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 |  |  |  | Md. Amirul Islam
52 | KISH/PW-10 | Block Road | Km |  |  |  |  | Md. Amirul Islam
53 | KISH/PW-11 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 |  |  |  | Md. Amirul Islam
54 | KISH/PW-11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 |  |  |  | Md. Amirul Islam
55 | KISH/PW-12 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 |  |  |  | Md. Amirul Islam
56 | KISH/PW-12 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 |  |  |  | Md. Amirul Islam
57 | KISH/PW-12 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 |  |  |  | Md. Amirul Islam
58 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 |  |  |  | Md. Amirul Islam
59 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 |  |  |  | Md. Amirul Islam
60 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 |  |  |  | Md. Amirul Islam
61 | KISH/PW-12 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 |  |  |  | Md. Amirul Islam
14 | KISH/PW-03 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 |  |  |  | Md.Abudl Latif
15 | KISH/PW-03 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 |  |  |  | Md.Abudl Latif
16 | KISH/PW-03 | Block Road | Km |  |  |  |  | Md.Abudl Latif
21 | KISH/PW-05 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 |  |  |  | Md.Abudl Latif
22 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 |  |  |  | Md.Abudl Latif
23 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 |  |  |  | Md.Abudl Latif
24 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 |  |  |  | Md.Abudl Latif
25 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 |  |  |  | Md.Abudl Latif
26 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 |  |  |  | Md.Abudl Latif
27 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 |  |  |  | Md.Abudl Latif
28 | KISH/PW-05 | Block Road | Km | 12.214 |  |  |  | Md.Abudl Latif
29 | KISH/PW-06 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 |  |  |  | Md.Abudl Latif
30 | KISH/PW-06 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 |  |  |  | Md.Abudl Latif
31 | KISH/PW-06 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 |  |  |  | Md.Abudl Latif
32 | KISH/PW-06 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 |  |  |  | Md.Abudl Latif
33 | KISH/PW-06 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 |  |  |  | Md.Abudl Latif
34 | KISH/PW-06 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 |  |  |  | Md.Abudl Latif
35 | KISH/PW-06 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 |  |  |  | Md.Abudl Latif
45 | KISH/PW-09 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 |  |  |  | Md.Abudl Latif
46 | KISH/PW-09 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 |  |  |  | Md.Abudl Latif
47 | KISH/PW-09 | Causeway 6.0m wide-1 at Dampara | Nos | 1 |  |  |  | Md.Abudl Latif
48 | KISH/PW-09 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 |  |  |  | Md.Abudl Latif
94 | KISH/PW-20 | Chitra Khal 4m wide | Nos | 1 |  |  |  | Md.Abudl Latif
95 | KISH/PW-20 | Nabinpur Khal 4m Wide | Nos | 1 |  |  |  | Md.Abudl Latif
96 | KISH/PW-20 | Dipjuri Khal 4m CW | Nos | 1 |  |  |  | Md.Abudl Latif
97 | KISH/PW-20 | Sudhikhal 4m wide CW | Nos | 1 |  |  |  | Md.Abudl Latif
98 | KISH/PW-20 | Chhagalia khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
99 | KISH/PW-20 | Near nasir sluice | Nos | 1 |  |  |  | Md.Abudl Latif
100 | KISH/PW-20 | Shingpur khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
101 | KISH/PW-20 | Gharu khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
102 | KISH/PW-20 | Irrigation Pipe Inlet 600mm dia | Nos | 36 |  |  |  | Md.Abudl Latif
67 | KISH/PW-15 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 |  |  |  | Md.Khalilur Rahman
68 | KISH/PW-15 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 |  |  |  | Md.Khalilur Rahman
69 | KISH/PW-16 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
70 | KISH/PW-16 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 |  |  |  | Md.Khalilur Rahman
71 | KISH/PW-16 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
72 | KISH/PW-17 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
73 | KISH/PW-17 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
74 | KISH/PW-17 | Box Drainage Outlet-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
75 | KISH/PW-17 | Box Drainage Outlet-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
76 | KISH/PW-17 | Box Drainage Outlet-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
77 | KISH/PW-17 | Box Drainage Outlet-4 | Nos | 1 |  |  |  | Md.Khalilur Rahman
78 | KISH/PW-17 | Box Drainage Outlet-5 | Nos | 1 |  |  |  | Md.Khalilur Rahman
79 | KISH/PW-17 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 |  |  |  | Md.Khalilur Rahman
80 | KISH/PW-17 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
81 | KISH/PW-17 | Irrigation Pipe Inlet-1 | Nos | 25 |  |  |  | Md.Khalilur Rahman
82 | KISH/PW-18 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 |  |  |  | Md.Khalilur Rahman
83 | KISH/PW-18 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 |  |  |  | Md.Khalilur Rahman
84 | KISH/PW-18 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 |  |  |  | Md.Khalilur Rahman
85 | KISH/PW-18 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 |  |  |  | Md.Khalilur Rahman
86 | KISH/PW-18 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 |  |  |  | Md.Khalilur Rahman
87 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 |  |  |  | Md.Khalilur Rahman
88 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 |  |  |  | Md.Khalilur Rahman
89 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 |  |  |  | Md.Khalilur Rahman
90 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 |  |  |  | Md.Khalilur Rahman
91 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 |  |  |  | Md.Khalilur Rahman
103 | KISH/PW-21 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 |  |  |  | Md.Khalilur Rahman
104 | KISH/PW-21 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 |  |  |  | Md.Khalilur Rahman
105 | KISH/PW-21 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 |  |  |  | Md.Khalilur Rahman
106 | KISH/PW-21 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 |  |  |  | Md.Khalilur Rahman
107 | KISH/PW-22 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 |  |  |  | Md.Khalilur Rahman
108 | KISH/PW-22 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
109 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 |  |  |  | Md.Khalilur Rahman
110 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
111 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 |  |  |  | Md.Khalilur Rahman
112 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 |  |  |  | Md.Khalilur Rahman
113 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 |  |  |  | Md.Khalilur Rahman
114 | KISH/PW-22 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 |  |  |  | Md.Khalilur Rahman
115 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 |  |  |  | Md.Khalilur Rahman
116 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 |  |  |  | Md.Khalilur Rahman
117 | KISH/PW-22 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 |  |  |  | Md.Khalilur Rahman
118 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
119 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
120 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
129 | KISH/PW-25 | Regulator 5-Vent-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
130 | KISH/PW-25 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 |  |  |  | Md.Khalilur Rahman
131 | KISH/PW-25 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
132 | KISH/PW-25 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
133 | KISH/PW-25 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
134 | KISH/PW-25 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
135 | KISH/PW-25 | Box Sluice-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
136 | KISH/PW-25 | Irrigation Pipe Inlet 600mm dia | Nos | 15 |  |  |  | Md.Khalilur Rahman
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 |  |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 |  |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 |  |  |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 |  |  |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 |  |  |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 |  |  |  | Munshi Zahirul Islam
62 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 |  |  |  | Munshi Zahirul Islam
63 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 |  |  |  | Munshi Zahirul Islam
64 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 |  |  |  | Munshi Zahirul Islam
65 | KISH/PW-14 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 |  |  |  | Munshi Zahirul Islam
66 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 |  |  |  | Munshi Zahirul Islam
92 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 |  |  |  | Munshi Zahirul Islam
93 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 |  |  |  | Munshi Zahirul Islam
128 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 |  |  |  | Munshi Zahirul Islam
Munshi Zahirul Islam
Md. Amirul Islam
Md.Abudl Latif
Anil Chandra Roy
Md.Khalilur Rahman

## Anil
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
121 | KISH/PW-23 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 |  |  |  | Anil Chandra Roy
122 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 |  |  |  | Anil Chandra Roy
123 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 |  |  |  | Anil Chandra Roy
124 | KISH/PW-23 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 |  |  |  | Anil Chandra Roy
125 | KISH/PW-23 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 |  |  |  | Anil Chandra Roy
126 | KISH/PW-23 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 |  |  |  | Anil Chandra Roy
127 | KISH/PW-23 | Irrigation Pipe Inlet 600mm dia | Nos | 4 |  |  |  | Anil Chandra Roy
137 | KISH/PW-26 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 |  |  |  | Anil Chandra Roy
138 | KISH/PW-26 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 |  |  |  | Anil Chandra Roy
139 | KISH/PW-26 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 |  |  |  | Anil Chandra Roy
140 | KISH/PW-26 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 |  |  |  | Anil Chandra Roy
141 | KISH/PW-26 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 |  |  |  | Anil Chandra Roy
142 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | Nos | 1 |  |  |  | Anil Chandra Roy
143 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | Nos | 1 |  |  |  | Anil Chandra Roy
144 | KISH/PW-27 | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | Nos | 1 |  |  |  | Anil Chandra Roy
145 | KISH/PW-27 | D 4.0 m width Chonati Causeway | Nos | 1 |  |  |  | Anil Chandra Roy
146 | KISH/PW-27 | R.C.C Box Drainage Outlet 900mm x 900mm | Nos | 1 |  |  |  | Anil Chandra Roy
7 | KISH/PW-02 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 |  |  |  | Md. Amirul Islam
8 | KISH/PW-02 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 |  |  |  | Md. Amirul Islam
9 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 |  |  |  | Md. Amirul Islam
10 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 |  |  |  | Md. Amirul Islam
11 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 |  |  |  | Md. Amirul Islam
12 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 |  |  |  | Md. Amirul Islam
13 | KISH/PW-02 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 |  |  |  | Md. Amirul Islam
17 | KISH/PW-04 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
18 | KISH/PW-04 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
19 | KISH/PW-04 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 |  |  |  | Md. Amirul Islam
20 | KISH/PW-04 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 |  |  |  | Md. Amirul Islam
36 | KISH/PW-07 | Hazir Khal | Km | 1.73 |  |  |  | Md. Amirul Islam
37 | KISH/PW-07 | Karpasha Khal | Km | 1.615 |  |  |  | Md. Amirul Islam
38 | KISH/PW-07 | Dampara Khal | Km | 3.6 |  |  |  | Md. Amirul Islam
39 | KISH/PW-07 | Baniajan | Km | 6.854 |  |  |  | Md. Amirul Islam
40 | KISH/PW-07 | Suti Khal | Km | 6.1 |  |  |  | Md. Amirul Islam
41 | KISH/PW-07 | Digha Nadi | Km | 5.7 |  |  |  | Md. Amirul Islam
42 | KISH/PW-07 | Old Singua | Km | 10.86 |  |  |  | Md. Amirul Islam
43 | KISH/PW-07 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 |  |  |  | Md. Amirul Islam
44 | KISH/PW-07 | Block Road | Km |  |  |  |  | Md. Amirul Islam
49 | KISH/PW-10 | Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md. Amirul Islam
50 | KISH/PW-10 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 |  |  |  | Md. Amirul Islam
51 | KISH/PW-10 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 |  |  |  | Md. Amirul Islam
52 | KISH/PW-10 | Block Road | Km |  |  |  |  | Md. Amirul Islam
53 | KISH/PW-11 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 |  |  |  | Md. Amirul Islam
54 | KISH/PW-11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 |  |  |  | Md. Amirul Islam
55 | KISH/PW-12 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 |  |  |  | Md. Amirul Islam
56 | KISH/PW-12 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 |  |  |  | Md. Amirul Islam
57 | KISH/PW-12 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 |  |  |  | Md. Amirul Islam
58 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 |  |  |  | Md. Amirul Islam
59 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 |  |  |  | Md. Amirul Islam
60 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 |  |  |  | Md. Amirul Islam
61 | KISH/PW-12 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 |  |  |  | Md. Amirul Islam
14 | KISH/PW-03 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 |  |  |  | Md.Abudl Latif
15 | KISH/PW-03 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 |  |  |  | Md.Abudl Latif
16 | KISH/PW-03 | Block Road | Km |  |  |  |  | Md.Abudl Latif
21 | KISH/PW-05 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 |  |  |  | Md.Abudl Latif
22 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 |  |  |  | Md.Abudl Latif
23 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 |  |  |  | Md.Abudl Latif
24 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 |  |  |  | Md.Abudl Latif
25 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 |  |  |  | Md.Abudl Latif
26 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 |  |  |  | Md.Abudl Latif
27 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 |  |  |  | Md.Abudl Latif
28 | KISH/PW-05 | Block Road | Km | 12.214 |  |  |  | Md.Abudl Latif
29 | KISH/PW-06 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 |  |  |  | Md.Abudl Latif
30 | KISH/PW-06 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 |  |  |  | Md.Abudl Latif
31 | KISH/PW-06 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 |  |  |  | Md.Abudl Latif
32 | KISH/PW-06 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 |  |  |  | Md.Abudl Latif
33 | KISH/PW-06 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 |  |  |  | Md.Abudl Latif
34 | KISH/PW-06 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 |  |  |  | Md.Abudl Latif
35 | KISH/PW-06 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 |  |  |  | Md.Abudl Latif
45 | KISH/PW-09 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 |  |  |  | Md.Abudl Latif
46 | KISH/PW-09 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 |  |  |  | Md.Abudl Latif
47 | KISH/PW-09 | Causeway 6.0m wide-1 at Dampara | Nos | 1 |  |  |  | Md.Abudl Latif
48 | KISH/PW-09 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 |  |  |  | Md.Abudl Latif
94 | KISH/PW-20 | Chitra Khal 4m wide | Nos | 1 |  |  |  | Md.Abudl Latif
95 | KISH/PW-20 | Nabinpur Khal 4m Wide | Nos | 1 |  |  |  | Md.Abudl Latif
96 | KISH/PW-20 | Dipjuri Khal 4m CW | Nos | 1 |  |  |  | Md.Abudl Latif
97 | KISH/PW-20 | Sudhikhal 4m wide CW | Nos | 1 |  |  |  | Md.Abudl Latif
98 | KISH/PW-20 | Chhagalia khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
99 | KISH/PW-20 | Near nasir sluice | Nos | 1 |  |  |  | Md.Abudl Latif
100 | KISH/PW-20 | Shingpur khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
101 | KISH/PW-20 | Gharu khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
102 | KISH/PW-20 | Irrigation Pipe Inlet 600mm dia | Nos | 36 |  |  |  | Md.Abudl Latif
67 | KISH/PW-15 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 |  |  |  | Md.Khalilur Rahman
68 | KISH/PW-15 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 |  |  |  | Md.Khalilur Rahman
69 | KISH/PW-16 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
70 | KISH/PW-16 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 |  |  |  | Md.Khalilur Rahman
71 | KISH/PW-16 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
72 | KISH/PW-17 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
73 | KISH/PW-17 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
74 | KISH/PW-17 | Box Drainage Outlet-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
75 | KISH/PW-17 | Box Drainage Outlet-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
76 | KISH/PW-17 | Box Drainage Outlet-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
77 | KISH/PW-17 | Box Drainage Outlet-4 | Nos | 1 |  |  |  | Md.Khalilur Rahman
78 | KISH/PW-17 | Box Drainage Outlet-5 | Nos | 1 |  |  |  | Md.Khalilur Rahman
79 | KISH/PW-17 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 |  |  |  | Md.Khalilur Rahman
80 | KISH/PW-17 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
81 | KISH/PW-17 | Irrigation Pipe Inlet-1 | Nos | 25 |  |  |  | Md.Khalilur Rahman
82 | KISH/PW-18 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 |  |  |  | Md.Khalilur Rahman
83 | KISH/PW-18 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 |  |  |  | Md.Khalilur Rahman
84 | KISH/PW-18 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 |  |  |  | Md.Khalilur Rahman
85 | KISH/PW-18 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 |  |  |  | Md.Khalilur Rahman
86 | KISH/PW-18 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 |  |  |  | Md.Khalilur Rahman
87 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 |  |  |  | Md.Khalilur Rahman
88 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 |  |  |  | Md.Khalilur Rahman
89 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 |  |  |  | Md.Khalilur Rahman
90 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 |  |  |  | Md.Khalilur Rahman
91 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 |  |  |  | Md.Khalilur Rahman
103 | KISH/PW-21 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 |  |  |  | Md.Khalilur Rahman
104 | KISH/PW-21 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 |  |  |  | Md.Khalilur Rahman
105 | KISH/PW-21 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 |  |  |  | Md.Khalilur Rahman
106 | KISH/PW-21 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 |  |  |  | Md.Khalilur Rahman
107 | KISH/PW-22 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 |  |  |  | Md.Khalilur Rahman
108 | KISH/PW-22 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
109 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 |  |  |  | Md.Khalilur Rahman
110 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
111 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 |  |  |  | Md.Khalilur Rahman
112 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 |  |  |  | Md.Khalilur Rahman
113 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 |  |  |  | Md.Khalilur Rahman
114 | KISH/PW-22 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 |  |  |  | Md.Khalilur Rahman
115 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 |  |  |  | Md.Khalilur Rahman
116 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 |  |  |  | Md.Khalilur Rahman
117 | KISH/PW-22 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 |  |  |  | Md.Khalilur Rahman
118 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
119 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
120 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
129 | KISH/PW-25 | Regulator 5-Vent-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
130 | KISH/PW-25 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 |  |  |  | Md.Khalilur Rahman
131 | KISH/PW-25 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
132 | KISH/PW-25 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
133 | KISH/PW-25 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
134 | KISH/PW-25 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
135 | KISH/PW-25 | Box Sluice-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
136 | KISH/PW-25 | Irrigation Pipe Inlet 600mm dia | Nos | 15 |  |  |  | Md.Khalilur Rahman
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 |  |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 |  |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 |  |  |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 |  |  |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 |  |  |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 |  |  |  | Munshi Zahirul Islam
62 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 |  |  |  | Munshi Zahirul Islam
63 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 |  |  |  | Munshi Zahirul Islam
64 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 |  |  |  | Munshi Zahirul Islam
65 | KISH/PW-14 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 |  |  |  | Munshi Zahirul Islam
66 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 |  |  |  | Munshi Zahirul Islam
92 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 |  |  |  | Munshi Zahirul Islam
93 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 |  |  |  | Munshi Zahirul Islam
128 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 |  |  |  | Munshi Zahirul Islam
Munshi Zahirul Islam
Md. Amirul Islam
Md.Abudl Latif
Anil Chandra Roy
Md.Khalilur Rahman

## Khalil
SL | Package | Component | Unit | Qnty | Present Status | Detailed Progress | No of Equipment (Excavator/Dredeger) in case of Earth Work | FIELD INSPECTOR Name | FIELD INSPECTOR Signature | Remarks
121 | KISH/PW-23 | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 |  |  |  | Anil Chandra Roy
122 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 |  |  |  | Anil Chandra Roy
123 | KISH/PW-23 | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 |  |  |  | Anil Chandra Roy
124 | KISH/PW-23 | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 |  |  |  | Anil Chandra Roy
125 | KISH/PW-23 | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 |  |  |  | Anil Chandra Roy
126 | KISH/PW-23 | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 |  |  |  | Anil Chandra Roy
127 | KISH/PW-23 | Irrigation Pipe Inlet 600mm dia | Nos | 4 |  |  |  | Anil Chandra Roy
137 | KISH/PW-26 | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 |  |  |  | Anil Chandra Roy
138 | KISH/PW-26 | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 |  |  |  | Anil Chandra Roy
139 | KISH/PW-26 | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 |  |  |  | Anil Chandra Roy
140 | KISH/PW-26 | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 |  |  |  | Anil Chandra Roy
141 | KISH/PW-26 | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 |  |  |  | Anil Chandra Roy
142 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Phuleshwari Regulator | Nos | 1 |  |  |  | Anil Chandra Roy
143 | KISH/PW-27 | 1- vent 1.80 m x1.50 m Kalna Regulator at km 16.170 | Nos | 1 |  |  |  | Anil Chandra Roy
144 | KISH/PW-27 | 6.60m width Suti Causeway & 3-Drainage Box Outlet at km. 17.74 1 | Nos | 1 |  |  |  | Anil Chandra Roy
145 | KISH/PW-27 | D 4.0 m width Chonati Causeway | Nos | 1 |  |  |  | Anil Chandra Roy
146 | KISH/PW-27 | R.C.C Box Drainage Outlet 900mm x 900mm | Nos | 1 |  |  |  | Anil Chandra Roy
7 | KISH/PW-02 | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 |  |  |  | Md. Amirul Islam
8 | KISH/PW-02 | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 |  |  |  | Md. Amirul Islam
9 | KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 |  |  |  | Md. Amirul Islam
10 | KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 |  |  |  | Md. Amirul Islam
11 | KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 |  |  |  | Md. Amirul Islam
12 | KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 |  |  |  | Md. Amirul Islam
13 | KISH/PW-02 | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 |  |  |  | Md. Amirul Islam
17 | KISH/PW-04 | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
18 | KISH/PW-04 | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 |  |  |  | Md. Amirul Islam
19 | KISH/PW-04 | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 |  |  |  | Md. Amirul Islam
20 | KISH/PW-04 | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 |  |  |  | Md. Amirul Islam
36 | KISH/PW-07 | Hazir Khal | Km | 1.73 |  |  |  | Md. Amirul Islam
37 | KISH/PW-07 | Karpasha Khal | Km | 1.615 |  |  |  | Md. Amirul Islam
38 | KISH/PW-07 | Dampara Khal | Km | 3.6 |  |  |  | Md. Amirul Islam
39 | KISH/PW-07 | Baniajan | Km | 6.854 |  |  |  | Md. Amirul Islam
40 | KISH/PW-07 | Suti Khal | Km | 6.1 |  |  |  | Md. Amirul Islam
41 | KISH/PW-07 | Digha Nadi | Km | 5.7 |  |  |  | Md. Amirul Islam
42 | KISH/PW-07 | Old Singua | Km | 10.86 |  |  |  | Md. Amirul Islam
43 | KISH/PW-07 | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 |  |  |  | Md. Amirul Islam
44 | KISH/PW-07 | Block Road | Km |  |  |  |  | Md. Amirul Islam
49 | KISH/PW-10 | Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md. Amirul Islam
50 | KISH/PW-10 | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 |  |  |  | Md. Amirul Islam
51 | KISH/PW-10 | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 |  |  |  | Md. Amirul Islam
52 | KISH/PW-10 | Block Road | Km |  |  |  |  | Md. Amirul Islam
53 | KISH/PW-11 | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 |  |  |  | Md. Amirul Islam
54 | KISH/PW-11 | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 |  |  |  | Md. Amirul Islam
55 | KISH/PW-12 | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 |  |  |  | Md. Amirul Islam
56 | KISH/PW-12 | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 |  |  |  | Md. Amirul Islam
57 | KISH/PW-12 | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 |  |  |  | Md. Amirul Islam
58 | KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 |  |  |  | Md. Amirul Islam
59 | KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 |  |  |  | Md. Amirul Islam
60 | KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 |  |  |  | Md. Amirul Islam
61 | KISH/PW-12 | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 |  |  |  | Md. Amirul Islam
14 | KISH/PW-03 | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 |  |  |  | Md.Abudl Latif
15 | KISH/PW-03 | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 |  |  |  | Md.Abudl Latif
16 | KISH/PW-03 | Block Road | Km |  |  |  |  | Md.Abudl Latif
21 | KISH/PW-05 | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 |  |  |  | Md.Abudl Latif
22 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 |  |  |  | Md.Abudl Latif
23 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 |  |  |  | Md.Abudl Latif
24 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 |  |  |  | Md.Abudl Latif
25 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 |  |  |  | Md.Abudl Latif
26 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 |  |  |  | Md.Abudl Latif
27 | KISH/PW-05 | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 |  |  |  | Md.Abudl Latif
28 | KISH/PW-05 | Block Road | Km | 12.214 |  |  |  | Md.Abudl Latif
29 | KISH/PW-06 | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 |  |  |  | Md.Abudl Latif
30 | KISH/PW-06 | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4.5 |  |  |  | Md.Abudl Latif
31 | KISH/PW-06 | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.99 |  |  |  | Md.Abudl Latif
32 | KISH/PW-06 | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 1.9 |  |  |  | Md.Abudl Latif
33 | KISH/PW-06 | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.6 |  |  |  | Md.Abudl Latif
34 | KISH/PW-06 | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 8.4 |  |  |  | Md.Abudl Latif
35 | KISH/PW-06 | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 |  |  |  | Md.Abudl Latif
45 | KISH/PW-09 | Regulator 1-Vent (1.50mx1.80m)-1 at 35.20 km at Hazirkhali | Nos | 1 |  |  |  | Md.Abudl Latif
46 | KISH/PW-09 | Regulator 2-Vent (1.50mx1.80m)-1 at ) 23.40 km at Baniajanj | Nos | 1 |  |  |  | Md.Abudl Latif
47 | KISH/PW-09 | Causeway 6.0m wide-1 at Dampara | Nos | 1 |  |  |  | Md.Abudl Latif
48 | KISH/PW-09 | Causeway 4.0m wide-1 at Karpasha | Nos | 1 |  |  |  | Md.Abudl Latif
94 | KISH/PW-20 | Chitra Khal 4m wide | Nos | 1 |  |  |  | Md.Abudl Latif
95 | KISH/PW-20 | Nabinpur Khal 4m Wide | Nos | 1 |  |  |  | Md.Abudl Latif
96 | KISH/PW-20 | Dipjuri Khal 4m CW | Nos | 1 |  |  |  | Md.Abudl Latif
97 | KISH/PW-20 | Sudhikhal 4m wide CW | Nos | 1 |  |  |  | Md.Abudl Latif
98 | KISH/PW-20 | Chhagalia khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
99 | KISH/PW-20 | Near nasir sluice | Nos | 1 |  |  |  | Md.Abudl Latif
100 | KISH/PW-20 | Shingpur khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
101 | KISH/PW-20 | Gharu khal sluice | Nos | 1 |  |  |  | Md.Abudl Latif
102 | KISH/PW-20 | Irrigation Pipe Inlet 600mm dia | Nos | 36 |  |  |  | Md.Abudl Latif
67 | KISH/PW-15 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 |  |  |  | Md.Khalilur Rahman
68 | KISH/PW-15 | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 |  |  |  | Md.Khalilur Rahman
69 | KISH/PW-16 | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
70 | KISH/PW-16 | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 |  |  |  | Md.Khalilur Rahman
71 | KISH/PW-16 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
72 | KISH/PW-17 | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
73 | KISH/PW-17 | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 |  |  |  | Md.Khalilur Rahman
74 | KISH/PW-17 | Box Drainage Outlet-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
75 | KISH/PW-17 | Box Drainage Outlet-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
76 | KISH/PW-17 | Box Drainage Outlet-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
77 | KISH/PW-17 | Box Drainage Outlet-4 | Nos | 1 |  |  |  | Md.Khalilur Rahman
78 | KISH/PW-17 | Box Drainage Outlet-5 | Nos | 1 |  |  |  | Md.Khalilur Rahman
79 | KISH/PW-17 | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 |  |  |  | Md.Khalilur Rahman
80 | KISH/PW-17 | Block Road | Km |  |  |  |  | Md.Khalilur Rahman
81 | KISH/PW-17 | Irrigation Pipe Inlet-1 | Nos | 25 |  |  |  | Md.Khalilur Rahman
82 | KISH/PW-18 | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 |  |  |  | Md.Khalilur Rahman
83 | KISH/PW-18 | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 |  |  |  | Md.Khalilur Rahman
84 | KISH/PW-18 | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 |  |  |  | Md.Khalilur Rahman
85 | KISH/PW-18 | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 |  |  |  | Md.Khalilur Rahman
86 | KISH/PW-18 | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 |  |  |  | Md.Khalilur Rahman
87 | KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 |  |  |  | Md.Khalilur Rahman
88 | KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 |  |  |  | Md.Khalilur Rahman
89 | KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 |  |  |  | Md.Khalilur Rahman
90 | KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 |  |  |  | Md.Khalilur Rahman
91 | KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 |  |  |  | Md.Khalilur Rahman
103 | KISH/PW-21 | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 |  |  |  | Md.Khalilur Rahman
104 | KISH/PW-21 | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 |  |  |  | Md.Khalilur Rahman
105 | KISH/PW-21 | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 |  |  |  | Md.Khalilur Rahman
106 | KISH/PW-21 | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 |  |  |  | Md.Khalilur Rahman
107 | KISH/PW-22 | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 |  |  |  | Md.Khalilur Rahman
108 | KISH/PW-22 | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
109 | KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 |  |  |  | Md.Khalilur Rahman
110 | KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 |  |  |  | Md.Khalilur Rahman
111 | KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 |  |  |  | Md.Khalilur Rahman
112 | KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 |  |  |  | Md.Khalilur Rahman
113 | KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 |  |  |  | Md.Khalilur Rahman
114 | KISH/PW-22 | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 |  |  |  | Md.Khalilur Rahman
115 | KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 |  |  |  | Md.Khalilur Rahman
116 | KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 |  |  |  | Md.Khalilur Rahman
117 | KISH/PW-22 | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 |  |  |  | Md.Khalilur Rahman
118 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
119 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
120 | KISH/PW-22 | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 |  |  |  | Md.Khalilur Rahman
129 | KISH/PW-25 | Regulator 5-Vent-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
130 | KISH/PW-25 | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 |  |  |  | Md.Khalilur Rahman
131 | KISH/PW-25 | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Nos | 1 |  |  |  | Md.Khalilur Rahman
132 | KISH/PW-25 | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
133 | KISH/PW-25 | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 |  |  |  | Md.Khalilur Rahman
134 | KISH/PW-25 | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
135 | KISH/PW-25 | Box Sluice-1 | Nos | 1 |  |  |  | Md.Khalilur Rahman
136 | KISH/PW-25 | Irrigation Pipe Inlet 600mm dia | Nos | 15 |  |  |  | Md.Khalilur Rahman
1 | KISH/PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 |  |  |  | Munshi Zahirul Islam
2 | KISH/PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 |  |  |  | Munshi Zahirul Islam
3 | KISH/PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 |  |  |  | Munshi Zahirul Islam
4 | KISH/PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 |  |  |  | Munshi Zahirul Islam
5 | KISH/PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 |  |  |  | Munshi Zahirul Islam
6 | KISH/PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 |  |  |  | Munshi Zahirul Islam
62 | KISH/PW-13 | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 |  |  |  | Munshi Zahirul Islam
63 | KISH/PW-13 | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 |  |  |  | Munshi Zahirul Islam
64 | KISH/PW-13 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 |  |  |  | Munshi Zahirul Islam
65 | KISH/PW-14 | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 |  |  |  | Munshi Zahirul Islam
66 | KISH/PW-14 | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 |  |  |  | Munshi Zahirul Islam
92 | KISH/PW-19 | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 |  |  |  | Munshi Zahirul Islam
93 | KISH/PW-19 | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 |  |  |  | Munshi Zahirul Islam
128 | KISH/PW-24 | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 |  |  |  | Munshi Zahirul Islam
Munshi Zahirul Islam
Md. Amirul Islam
Md.Abudl Latif
Anil Chandra Roy
Md.Khalilur Rahman