## Regulator
Item No | Item Code | Description of Item | Unit | Unit Rate | Markhali Khal
1 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials from entire site and removing soil upto 15cm depth including uprooting stumps, jungle, cleaning, levelling, dressing etc. complete as per direction of Engineer in charge | sqm |  | 8274.48
2 | 04-100 | Manufacturing and supplying R.C.C boundary pillar, bench mark pillar and kilometer post in proportion 1:2:4, as per approved drawing and specifications, 110cm height, bottom dia 25cm and top dia 20cm, of which 15cm slanting and 50 level; with 6 nos. 10mm dia vertical rod and 8 nos. 6mm dia binder excluding the cost of M.S work or reinforcement but including the cost of form works, plastering top, finishing surface, curing with inscription of "BWDB, R.L./K.M." mark, as per approved size and shape in exposed surface etc. complete, as per direction of Engineer in charge. | nos |  | 4
3 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge. | nos |  | 4
4 | 04-320 | Supply of bamboo pegs 0.45m to 0.75m long and average dia. 6 cm, with saw cut top as per direction of Engineer in charge. | nos |  | 160
5 | 04-330 | Labour charge for fixing of bamboo pegs 0.45m to 0.75m long and average dia 6cm, as per direction of Engineer in charge. | nos |  | 160
6 | 12-100 | Installation of pizeometer including supply of 40mm G.I. pipe, brass strainer, socket, labour, by wash boring, lowering, fixing the elevation and providing cover on the top of the well etc. complete as per direction of Engineer in charge. | nos |  | 6
7 | 12-300 | Construction of sump well with dug holes of size 1.80 m x 2.0 m, laying in position the perforated empty diesel/petrol drum sheet of 1.00 m dia to a depth 1.5m having slot area of 1000 sq.cm/sqm, slot dia being 30mm each with supply of necessary shrouding materials comprising of 60% 40mm down graded khoa and 40% coarse sand of FM>=2.50 and placing those around and beneath the drum sheet having thickness of 40cm and 50cm respectively including necessary welding, fitting etc. complete as per direction of Engineer in charge. | nos |  | 10
8 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | cum |  | 22.65
9 | 16-560-30 | Shoring for slope protection of foundation trench, canal, embankment, road, pond etc. as per design slopes, grades including removal of spoils to a safe distance as per direction of Engineer in charge. By local hard wood ballah post of 6.0m length, 125mm dia, 1.0m c/c, and 2.0m drive with 6.0m long bamboo of average 75mm dia, @1.0m c/c and 2.0m drive with drum sheet walling and average 70mm dia half split bamboo batten @ 2.0m c/c fixed with nails. | sqm |  | 447.2
10 | 16-310-10 | For moving spoil earth upto a distance of 100m from the centre of the pit. | cum |  | 9746.45
11 | 40-440-20 | Capacity : 50 kg (2nd hand gunny bags) | cum |  | 1250
12 | 16-520-20 | (sand of FM>=1.50) | cum |  | 431.32
13 | 16-540-20 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. | cum |  | 1579.67
14 | 44-240-30 | U-shape, hot- rolled steel sheet pile width= 400mm to 600mm: height=>100mm, Th.=> 10.5: wt. per sqm of pile wall =>120 kg/m2: sectional modulus per one meter of pile wall width => 874 cm3/m. | M.ton |  | 27.46
15 | 44-320-20 | Above 10mm thick. | m |  | 97.24
16 | 72-540 | Epoxy paint 2 coats of approved colour and specification over a priming coat to gate, hoisting device and embedded metal parts including scraping out rust and old paint with chisel, scraper, steel wire brush & emery paper etc. complete in all respect including the cost of all materials as per direction of Engineer in charge. | m |  | 909.27
17 | 44-270-20 | U-type or any other type : Upto 4.50 m depth. | sqm |  | 211.64
18 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge. | sqm |  | 36.47
19 | 44-220-10 | Weighing minimum 1.0 kg per 6.50 sqm. | sqm |  | 485.1
20 | 40-610-20 | Well graded between 40mm to 20mm size. | cum |  | 75.26
21 | 40-610-30 | Well graded between 20mm to 5mm size. | cum |  | 75.26
22 | 40-650-30 | a) FM : 1.0to 1.5 | cum |  | 282.11
23 | 40-650-20 | a) FM : 1.5 to 2.0 | cum |  | 9.11
24 | 12-310-20 | by pump. | cum |  | 48937.98
25 | 28-120-20 | With 25mm down graded stone chips. | cum |  | 52.15
26 | 28-100-30 | with 25mm down graded stone shingles | cum |  | 1.84
27 | 36-150-10 | Vertical and inclined walls, columns, piers with 60-80mm dia barack bamboo props. | sqm |  | 1033.85
28 | 36-150-20 | Deck slab, operating deck slab, top slab of barrel upto 3.5m height with 60-80mm dia barack bamboo props | sqm |  | 25.42
29 | 36-150-60 | Footing, footing beams, girder beams, foundation slab with 60-80mm dia barack bamboo props | sqm |  | 142.75
30 | 76-120-10 | 8mm dia to 30mm dia | kg |  | 27384.1616
31 | 76-115-10 | 6mm dia | kg |  | 34.78
32 | 80-230-40 | 40mm dia G.I. pipe line. | m |  | 14.29
33 | 76-170 | M.S. Work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cutting, bending, welding, forging, drilling, revetting, embedding anchor bars, staging and fitting, fixing, local handling etc. comlpete with energy consumption and supply of labours including the cost of materials as per design, specification and direction of Engineer in charge. | kg |  | 4042.01
34 | 28-200-10 | With stone chips | cum |  | 461.23
35 | 4-600-10 | Providing cork sheet/polysterene sheet in expansion joints of concrete works including supply of all materials etc. complete as per direction of Engineer in charge. 25mm thick sheet. | sqm |  | 13.68
36 | 04-280-10 | 150 mm x 25 mm | m |  | 18.2
37 | 56-430 | Filling up the expansion joints by asphalt, sand and jute waste etc. complete including supply of all materials and as per direction of Engineer in charge. | m |  | 38
38 | 40-140-50 | Block size: 30cm x 30cm x 30cm | nos |  | 10970
39 | 40-140-40 | Block size: 40cm x 40cm x 20cm | nos |  | 7295
40 | 40-220-10 | Within 200m | cum |  | 264.82
41 | 40-220-20 | Beyond 200m | cum |  | 264.82
42 | 76-630-10 | 3 bulb type | m |  | 26
43 | 16-240 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge. | cum |  | 2961.06
44 | 76-240-40 | Size 1.95m x 1.65m. | nos |  | 4
45 | 76-260-20 | Labour charge for fitting and fixing of M.S. vertical lift gate/flap gate shutters of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/sluice and mending the damages with CC (1:2:4), removing the spoils etc.complete including the cost of all materials as per direction of Engineer in charge.Size 1.95m x 1.65m. | nos |  | 4
46 | 76-190 | Manufacturing, supplying and Installation of Padestal type lifting device for slide gate with 63mm dia threaded steel shaft, 146mm outer dia bronze nut, thrust bearing, steel bevel gear etc. as per approved design including supply of all components, labours with a prime coat of redoxide where necessary etc. complete including the cost of all materials as per specification and direction of Engineer in charge. | nos |  | 4
47 | 16-530 | Back filling in hydraulic structures and slope building in protective works including all leads and lifts with selected local soil in layer of 150mm including watering, ramming etc. complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in charge. | cum |  | 2385.02
48 | 16-600-10 | Earth work by Mechanical Excavator ( Long Boom ) in all kinds of soil in excavation/re-excavation of Channel/Canal/khal etc. Including disposal of spoil-soil upto 30m away from the point of excavation with rough dressing and leveling etc. Complete as per direction of Engineer in charge. | cum |  | 13486.13
49 | 68-130 | Supplying pressure treated wooden fall boards/stop logs of different sizes (not less than 15cm in depth) of sal, sundari, garjan, shishu or equivalent for regulator/ sluices, including fixing in position with eye hook etc. complete as per direction of Engineer in charge. | cum |  | 15.47
50 | MR | Supply and Installation of Name Plate | nos |  | 8
51 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/ canalbank/road etccompacted to 85%/90% maximum drydensity at optimum moisture content,with referenceto laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay,0-40% silt, 0-30% sand) within the initial lead of 30m & all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots & stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc.complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 m to 3 m height with 85% compaction. | cum |  | 2760
52 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75 mm thick good quality durba or charkanta sods of size 200 mm x 200 mm with all leads and lifts including ramming watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only) as per direction of Engineer in charge. | sqm |  | 1870

## Embankment.
Item No | Item Code | Description of Item | Unit | Quantity | Unit Rate
1 | Approved Rate | Preparation and mobilization of the Site for Construction of Submersible Embankment or other Structural Components in c/w "Haor Flood Management and Livelihood Improved Improvement Project(BWDB Part) as per Technical Specifications, including land lease, rental charges, obtaining permissions for work, developing work area, preparation of platform for temporary semi pucca site office(40sqm), CI Sheet labour sheds(200sqm), CI Sheet Stores(200sqm), supply of wooden & cane seated furniture etc. as specified and as per Contractor's Method Statement and as per direction of Engineer in charge. | LS | 1
2 | Approved Rate | Provide and maintain 1 (one) no. Engine boat with boatmen having sun and rainproof cover to facilitate supervision by the Engineer/Engineer's Representative during whole construction period of the work as per Technical Specification, Contractor’s Method Statement and as per direction of Engineer in charge. | Days | 60
3 | Approved Rate | Demobilization and clean-up of the site upon completion of the works, as per Specifications and Contractor's Method Statement and as per direction of Engineer in Charge | LS | 1
4 | Approved Rate | Providing and maintaining adequate portable water supply by installing 6 Nos. of tube well and sanitation facilities by installing 6 Nos. of sanitary latrines for usage of labours,officials and others for prevailing the hygenic and healthy environment at allover the working site As per direction of the Engineer in charge. | LS | 1
5 | Approved Rate | Mobilize, strengthen required land based construction equipment such as excavator, dump truck, chain dozer, vibro-compactor, and plants such as generator for site electrification, digital camera for taking photographs and digital video camera for recording/Taking photograph all sequences of works etc for keeping records of the Works by providing following information including transfer to site, complete for the purposes stated in the Technical Specification and Contractor’s Method Statement and as per direction of Engineer in charge. | LS | 1
6 | Approved Rate | Operate , maintain of plant and equipment such as generator for site electrification, for the purpose stated in the Technical Specification and in the Contractor’s Method Statement and as per direction of Engineer in charge. | LS | 1
7 | 04-150 | Manufacturing and supplying R.C.C. (1:2:4) BM Pillars of size 15cmx 15cmx75cm, with 40cmx40cmx10cm base having 3 nos.10mm dia MS.bar each way at base,4nos.10mm dia vertical bar and 8nos 6mm dia ring,excluding cost of M.S.works for reinforcement but including cost of form works, concreting, plastering at top, finishing surface, curing etc. complete, with inscription of "BWDB", on exposed surface etc. complete as per direction of Engineer in charge. | nos | 29
8 | 04-160 | Fixing in position B.M. pillars and kilometer posts of size 15cmx15cmx75cm with 40cmx40cmx10cm base, embedding 45cm below G.L. including carriage, earth cutting, backfilling, ramming, etc. complete as per direction of Engineer in charge. | nos | 29
9 | 48-130 | Biological protection of bare earth surface by Dholkalmi with minimum 50cm long sapling, planting @ not more than 30 cm apart including supplying, sizing, taping and nursing etc. complete as per direction of the Engineer in charge. | m | 282400
10 | 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | nos | 283
11 | 40-540-10 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >=8.0 cm in position etc. complete as per direction of Engineer in charge. Length : >=4.5 m to <=6.0m | nos | 1501
12 | 40-560-10 | Supplying, sizing and fitting in position 8.0 cm and above dia in size full barrack bamboo half split walling pieces with nails average 1.00 m apart including supply of all materials as per direction of Engineer in charge.Double Walling. | m | 1200
13 | 40-550-20 | Labour charge for driving barrack bamboo pins of diameter >=8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge.>=1.50 m to <=2.0 m drive, in water including necessary staging etc. as required | m | 2251.5
14 | 40-580 | Supplying and placing in position and fitting, fixing single layer tarjah double woven matting with necessary ties including the cost of all materials etc. complete as per direction of Engineer in charge. | Sqm | 1200
15 | 16-410-10 | Earth work by carried earth (by truck/boat or any other means) supplied at contractor's own cost (including royalty) in constructing/ resectioning of the embankment/ canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content with reference to laboratory density test AASHTO modified hammer, with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) beyond initial lead of 300m including throwing the spoils to profiles in layer not exceeding 230mm in thickness with clod breaking to maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, clearing jungles, bail out of water, rough dressing including 150mm cambering at the centre of crest with all leads and lifts complete (compaction will be done by the contractor with approved equipment including all ancillary charges for compaction and testing) as per direction of Engineer in charge.300m to 1.00 km.(85% compaction) | cum | #REF!
16 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/ canalbank/road etccompacted to 85%/90% maximum drydensity at optimum moisture content,with referenceto laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay,0-40% silt, 0-30% sand) within the initial lead of 30m & all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots & stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc.complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 m to 3 m height with 85% compaction. | Cum | #REF!
17 | 16-190 | Extra rate for every additional lead of 15 m or part thereof beyond the initial lead of 30m up to a maximum of 19 leads (3m neglected) for all kinds of earth work. 2 nos Lead (Quoted rate will be applicable for 2 nos lead) | 2 lead/Cum | #REF!
18 | 16-650-10 | Earth work by Mechanical Excavator (Long Boon) in constructing/ resectioning of embankment/canal bank/ road etc. compacted to 85%/90% maximum dry density at optimum moisture content, with reference to laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay, 0-40% silt, 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots and stumps of trees of girth upto 200mm from the ground, stripping/ploughing the base of embankment and borrow pit area, dug bailing, rough dressing including 150mm cambering at the centre of crest etc. complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 to 4 m height with 85% compaction. | cum | #REF!
19 | 16-300 | Royalty of specified earth taken from private land (with prior permission of the Executive Engineer on production of royalty deeds with the land owner) from the area to be selected by the contractor with mutual agreement. | cum | #REF!
20 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75 mm thick good quality durba or charkanta sods of size 200 mm x 200 mm with all leads and lifts including ramming watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only) as per direction of Engineer in charge. | Sqm | 249781
Sub-Total Cost(Embankment):
(B)Block Road
21 | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge. | cum | 1249.5
22 | Approved Rate/LGED | BP: Preperation of bed by cutting and filling including watering to bring moisture content ±2% of OMC & compacting by appropiate mechanical means etc to attain minimum compaction 98% of MDD (standard) to obtain a minimum soaked CBR 4% etc all complete as per direction of the E-I-C. | Sqm | 2380
23 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by manual labour using mallet/ vibro compactor including cost of all materials etc. complete as per design, drawing and direction of Engineer in charge (payment shall be made on compacted volume). | cum | 357
24 |  | Manufacturing and supplying of CC blocks in leanest mix (1:2:4) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge.
| Approved Rate | Block size: 30cm x 30cm x 30cm | nos | 26444
| Approved Rate | Block size: 100cm x 65cm x (10-15)cm | nos | 1700
25 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge. | Sqm | 2380
26 | 40-220-10 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.Within 200m | cum | 426.06
| 40-220-20 | Beyond 200m | cum | 426.06

## Block Road_rate
24 | 56-100 | 56-100 | Earth work in box cutting up to 1.00 m depth, in all kinds of soil with all leads, removing the spoils to a safe distance, including levelling and dressing, maintaining required cambering etc. complete, as per direction of Engineer in charge. | cum | 1249.5 | 135.051 | One Hundred and Thirty-Five point Zero Five One | 168746.224
25 | Approved Rate | Approved Rate | BP: Preperation of bed by cutting and filling including watering to bring moisture content ±2% of OMC & compacting by appropiate mechanical means etc to attain minimum compaction 98% of MDD (standard) to obtain a minimum soaked CBR 4% etc all complete as per direction of the E-I-C. | sqm | 2380 | 11.391 | Eleven point Three Nine One | 27110.58
26 | 56-110 | 56-110 | Construction of improved road sub-grade of sand (FM>=0.8) in maximum 150mm thick layer including dressing, levelling, ramming, watering, cambering and compacting to attain minimum CBR-8% by manual labour using mallet/ vibro compactor including cost of all materials etc. complete as per design, drawing and direction of Engineer in charge (payment shall be made on compacted volume). | cum | 357 | 733.121 | Seven Hundred and Thirty-Three point One Two One | 261724.197
27(a) | Approved Rate | Approved Rate | Manufacturing and supplying of CC blocks in leanest mix (1:2:4) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. | nos | 26444 | 475.001 | Four Hundred and Seventy-Five point Zero Zero One | 12560926.444
27(b) | Approved Rate | Approved Rate | Manufacturing and supplying of CC blocks in leanest mix (1:2:4) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 15.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. | nos | 1700 | 1200.001 | One Thousand Two Hundred point Zero Zero One | 2040001.7
28 | 24-310 | 24-310-10 | Flush pointing to brick works, in sand cement mortar (sand of FM>=1.3), including scaffolding, curing, raking out joints, clearing the surface etc. complete in all floors including the cost of all materials and as per direction of Engineer in charge. | sqm | 2380 | 162.471 | One Hundred and Sixty-Two point Four Seven One | 386680.98
29(a) | 40-220 | 40-220-10 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.Within 200m | cum | 426.06 | 1145.881 | One Thousand One Hundred and Forty-Five point Eight Eight One | 488214.059
29(a) | 40-220 | 40-220-20 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.Beyond 200m | cum | 426.06 | 2027.041 | Two Thousand AND Twenty-Seven point Zero Four One | 863641.088
16797045.272
167.97
[7 empty] | CC Block | 146.01

## Reg_rate
30 | 04-180 | 04-180 | Site preparation by manually removing all miscellaneous objectional materials from entire site and removing soil upto 15cm depth including uprooting stumps, jungle, cleaning, levelling, dressing etc. complete as per direction of Engineer in charge | sqm | 8274.48 | 27.721 | Twenty-Seven point Seven Two One | 229376.86
31 | 04-100 | 04-100 | Manufacturing and supplying R.C.C boundary pillar, bench mark pillar and kilometer post in proportion 1:2:4, as per approved drawing and specifications, 110cm height, bottom dia 25cm and top dia 20cm, of which 15cm slanting and 50 level; with 6 nos. 10mm dia vertical rod and 8 nos. 6mm dia binder excluding the cost of M.S work or reinforcement but including the cost of form works, plastering top, finishing surface, curing with inscription of "BWDB, R.L./K.M." mark, as per approved size and shape in exposed surface etc. complete, as per direction of Engineer in charge. | nos | 4 | 926.871 | Nine Hundred and Twenty-Six point Eight Seven One | 3707.484
32 | 04-110 | 04-110 | Fixing in position, boundary pillars/bench mark pillars/K.M. post etc. of size 110cm height, bottom dia 25cm and top dia 20cm, embedded 45cm below G.L. including carriage, earth cutting, filling, ramming, etc. complete as per direction of Engineer in charge. | nos | 4 | 47.911 | Forty-Seven point Nine One One | 191.644
33 | 04-320 | 04-320 | Supply of bamboo pegs 0.45m to 0.75m long and average dia. 6 cm, with saw cut top as per direction of Engineer in charge. | nos | 160 | 27.881 | Twenty-Seven point Eight Eight One | 4460.96
34 | 04-330 | 04-330 | Labour charge for fixing of bamboo pegs 0.45m to 0.75m long and average dia 6cm, as per direction of Engineer in charge. | Nos | 160 | 2.831 | Two point Eight Three One | 452.96
35 | 12-100 | 12-100 | Installation of pizeometer including supply of 40mm G.I. pipe, brass strainer, socket, labour, by wash boring, lowering, fixing the elevation and providing cover on the top of the well etc. complete as per direction of Engineer in charge. | nos | 6 | 2584.221 | Two Thousand Five Hundred and Eighty-Four point Two Two One | 15505.326
36 | 12-300 | 12-300 | Construction of sump well with dug holes of size 1.80 m x 2.0 m, laying in position the perforated empty diesel/petrol drum sheet of 1.00 m dia to a depth 1.5m having slot area of 1000 sq.cm/sqm, slot dia being 30mm each with supply of necessary shrouding materials comprising of 60% 40mm down graded khoa and 40% coarse sand of FM>=2.50 and placing those around and beneath the drum sheet having thickness of 40cm and 50cm respectively including necessary welding, fitting etc. complete as per direction of Engineer in charge. | Nos | 10 | 17211.171 | Seventeen Thousand Two Hundred and Eleven point One Seven One | 172111.71
37 | 16-220 | 16-220 | Earth work by manual labour with clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) in construction of cross bundh/ ring bundh as per design and specification with all leads and lifts, throwing the earth in layers not exceeding 150mm in thickness, including breaking clods, rough dressing, clearing the jungle, removing stumps, dug bailing and 75mm cambering etc. complete as per direction of Engineer in charge. | cum | 22.65 | 142.421 | One Hundred and Forty-Two point Four Two One | 3225.836
38 | 16-560 | 16-560-30 | Shoring for slope protection of foundation trench, canal, embankment, road, pond etc. as per design slopes, grades including removal of spoils to a safe distance as per direction of Engineer in charge. By local hard wood ballah post of 6.0m length, 125mm dia, 1.0m c/c, and 2.0m drive with 6.0m long bamboo of average 75mm dia, @1.0m c/c and 2.0m drive with drum sheet walling and average 70mm dia half split bamboo batten @ 2.0m c/c fixed with nails. | sqm | 447.2 | 913.691 | Nine Hundred and Thirteen point Six Nine One | 408602.615
39 | 16-310 | 16-310-10 | Earth work in excavation of foundation trenches in all kinds of soil as per layout plan of foundation excavation with all leads and lifts and placing the spoil earth for constructing the ring bundh/ cofferdam where necessary as per design and specification or disposing it to a safe distance including pushing, levelling, dressing, etc. complete as per direction of Engineer in charge. | cum | 9746.45 | 246.711 | Two Hundred and Forty-Six point Seven One One | 2404556.426
40 | 40-440 | 40-440-20 | "Supplying and filling empty gunny/synthetic bags as approved in design & drawing with sand/ earth available at site sewing the end with sutly, including carrying and placing in position within the site with supply of all materials as per direction of Engineer in charge. | cum | 1250 | 32.511 | Thirty-Two point Five One One | 40638.75
41 | 16-520 | 16-520-20 | Supplying and filling sand in foundation of hydraulic structures, buildings and in protective works with selected sand, in 150mm thick layer, including levelling, dressing, ramming, watering etc. complete (compacted to 50% relative density by manual labour using mallet/ vibro compactor) as per direction of Engineer in charge. | cum | 431.32 | 1420.061 | One Thousand Four Hundred and Twenty point Zero Six One | 612500.711
42 | 16-540 | 16-540-20 | Back filling in hydraulic structures including all leads and lifts in 150mm layer including watering, ramming compacting to 30% relative density etc. complete by compactor or any other suitable method as per direction of Engineer in charge. | cum | 1579.67 | 757.751 | Seven Hundred and Fifty-Seven point Seven Five One | 1196996.522
43 | 44-240 | 44-240-30 | Supplying at site U-shape hot rolled steel sheet piles of different sections as mentioned in the material specification of this manual as tabular form of Phosphorus = 00.04% (Maximum), Sulphur = 0.04% (Maximum), Copper = 0.25% (Minimum), Tensile strength => 490 N/mm2, Yield strength => 296 N/mm2, Elongation = 15% (Minimum) including all taxes, freights, incidental charges etc. complete as per direction of Engineer in charge. | M.ton | 27.46 | 250000.001 | Two Lakh Fifty Thousand point Zero Zero One | 6865000.027
44 | 44-320 | 44-320-20 | Cutting of steel sheet piles to design length and shape as per requirement in design and drawing and as per direction of Engineer in charge. | m | 97.24 | 45.871 | Forty-Five point Eight Seven One | 4460.496
45 | 72-540 | 72-540 | Epoxy paint 2 coats of approved colour and specification over a priming coat to gate, hoisting device and embedded metal parts including scraping out rust and old paint with chisel, scraper, steel wire brush & emery paper etc. complete in all respect including the cost of all materials as per direction of Engineer in charge. | m | 909.27 | 550.001 | Five Hundred and Fifty point Zero Zero One | 500099.409
46 | 44-270 | 44-270-20 | Driving steel sheet piles of various sections and weights of any type of soil, by monkey hammer including handling and placing in position, staging and supplying of all equipments like monkey hammer, pully, rope, bamboo, bullah etc. including correcting leaning beyond tolerance & other defects and any other incidental cost etc. complete (measurement will be taken on projected width x height) as per direction of Engineer in charge. | sqm | 211.64 | 1250.751 | One Thousand Two Hundred and Fifty point Seven Five One | 264708.942
47 | 44-310 | 44-310 | Supplying and placing 20mm thick hessian cloth impregnated with bitumen in expansion joints or on top of sheet piles as per specification and direction of Engineer in charge. | sqm | 36.47 | 461.801 | Four Hundred and Sixty-One point Eight Zero One | 16841.882
48 | 44-220 | 44-220-10 | Supplying and laying single layer polythene sheet in floor below cement concrete, RCC slab, on walls etc. complete in all respect as per direction of Engineer in charge. | sqm | 485.1 | 31.221 | Thirty-One point Two Two One | 15145.307
49(a) | 40-610 | 40-610-20 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: | cum | 75.26 | 3730.471 | Three Thousand Seven Hundred and Thirty point Four Seven One | 280755.247
49(b) | 40-610 | 40-610-30 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: | cum | 75.26 | 4076.091 | Four Thousand AND Seventy-Six point Zero Nine One | 306766.609
50 | 40-650 | 40-650-30 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. | cum | 282.11 | 1070.291 | One Thousand AND Seventy point Two Nine One | 301939.794
51 | 40-650 | 40-650-20 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge. | cum | 9.11 | 1575.841 | One Thousand Five Hundred and Seventy-Five point Eight Four One | 14355.912
52 | 12-310 | 12-310-20 | Bailing out of water with all leads and lifts by manual labour or pump, with all arrangements for protection of ring bund and side slopes of foundation pit against erosion or washout etc. complete actual volume of work will be measured by sounding method before starting the work) as per direction of Engineer in charge. | cum | 48937.98 | 6.131 | Six point One Three One | 300038.755
53 | 28-120 | 28-120-20 | Cement concrete in leanest mix 1:3:6 with sand of F.M.>=1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of form works etc complete as per direction of Engineer in charge | cum | 52.15 | 10954.481 | Ten Thousand Nine Hundred and Fifty-Four point Four Eight One | 571276.184
54 | 28-100 | 28-100-30 | Cement concrete in leanest mix 1:4:8 with sand of F.M.>=1.5, in foundation or floor, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials excluding the cost of form works etc complete as per direction of Engineer in charge. | cum | 1.84 | 8755.071 | Eight Thousand Seven Hundred and Fifty-Five point Zero Seven One | 16109.331
55(a) | 36-150 | 36-150-10 | Formwork for centering and water tight shuttering as per drawing with 14 BWG M.S. sheet, fitted and fixed with 40mmx40mmx6mm M .S. angle frame and 25mmx6mm F.I. bar stiffener, with necessary fabrication, welding, making the forms including fitting, fixing of steel forms with necessary ties, battens, struts, nuts & bolts, props etc. as per desired shape and size including levelling and removing the forms after specified period including the cost of all materials as per direction of Engineer in charge. | sqm | 1064.17 | 1200.001 | One Thousand Two Hundred point Zero Zero One | 1277005.064
55(b) | 36-150 | 36-150-20 | Deck slab, operating deck slab, top slab of barrel upto 3.5m height with 60-80mm dia barack bamboo props | sqm | 25.42 | 1300.001 | One Thousand Three Hundred point Zero Zero One | 33046.025
55(c) | 36-150 | 36-150-60 | Footing, footing beams, girder beams, foundation slab with 60-80mm dia barack bamboo props | sqm | 263.67 | 735.351 | Seven Hundred and Thirty-Five point Three Five One | 193889.998
56(a) | 76-120 | 76-120-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm² (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. | kg | 39753.59 | 85.001 | Eighty-Five point Zero Zero One | 3379094.904
56(b) | 76-115 | 76-115-10 | M.S. Work for reinforcement with deformed M.S. bar, fy=414 N/mm² (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. | kg | 34.78 | 85.001 | Eighty-Five point Zero Zero One | 2956.335
57 | 80-230 | 80-230-40 | Supplying, laying, fitting and fixing of different dia G.I. pipes with all special fittings, such as bends, elbows, sockets, tees, unions, jam nuts etc. including cutting foundation trenches upto required depth where necessary and filling the same with earth duly compacted, making holes in floors and walls and mending the damages, fixing in walls with holders and clips, including cutting threads, making necessary connection etc. all complete, and as per direction of Engineer in charge. | m | 14.29 | 232.931 | Two Hundred and Thirty-Two point Nine Three One | 3328.584
58 | 76-170 | 76-170 | M.S. Work in plates, angles, channels, flat bars, Tees etc. including fabricating, machining, cutting, bending, welding, forging, drilling, revetting, embedding anchor bars, staging and fitting, fixing, local handling etc. comlpete with energy consumption and supply of labours including the cost of materials as per design, specification and direction of Engineer in charge. | kg | 4042.01 | 225.001 | Two Hundred and Twenty-Five point Zero Zero One | 909456.292
59 | 28-200 | 28-200-10 | Reinforced Cement Concrete Work in leanest mix. 1:1.5:3 with 25mm down graded coarse aggregates and sand of FM>= 2.0 to FM >= 2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm2, including breaking, screening, grading and washing aggregates with clear water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge. | cum | 461.23 | 15000.001 | Fifteen Thousand point Zero Zero One | 6918450.461
60 | 04-600 | 04-600-10 | Providing cork sheet/polysterene sheet in expansion joints of concrete works including supply of all materials etc. complete as per direction of Engineer in charge. 25mm thick sheet. | sqm | 13.68 | 470.071 | Four Hundred and Seventy point Zero Seven One | 6430.571
61 | 04-280 | 04-280-10 | Constructing at site, cement mortar gauge on masonry wall, including engraving in meter, decimeter & centimeter, painting and figuring with black and red water proof paint, etc. complete as per direction of Engineer in charge. | m | 18.2 | 77.731 | Seventy-Seven point Seven Three One | 1414.704
62 | 56-430 | 56-430 | Filling up the expansion joints by asphalt, sand and jute waste etc. complete including supply of all materials and as per direction of Engineer in charge. | m | 38 | 165.951 | One Hundred and Sixty-Five point Nine Five One | 6306.138
63(a) | 40-140 | 40-140-50 | Manufacturing and supplying of CC blocks in leanest mix (1:3:6) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. | nos | 10970 | 355.001 | Three Hundred and Fifty-Five point Zero Zero One | 3894360.97
63(b) | 40-140 | 40-140-40 | Manufacturing and supplying of CC blocks in leanest mix (1:3:6) in volume, with cement, sand (FM>=1.5) and stone chips (40mmdown graded), to attain a minimum 28 days cylinder strength of 9.0 N/mm2 including grading, washing shingles, mixing, laying in forms, consolidation, curing for at least 21 days, including preparation of platform, shuttering in measureable stacks etc. complete including supply of all materials ( steel shutter to be used) as per direction of Enginnner in charge. | nos | 7295 | 450.001 | Four Hundred and Fifty point Zero Zero One | 3282757.295
64(a) | 40-220 | 40-220-10 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge | cum | 264.82 | 1145.881 | One Thousand One Hundred and Forty-Five point Eight Eight One | 303452.206
64(b) | 40-220 | 40-220-20 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge | cum | 264.82 | 2027.041 | Two Thousand AND Twenty-Seven point Zero Four One | 536800.998
65 | 76-630 | 76-630-10 | Supply and fitting fixing 23cm PVC water stops having minimum strength of 13.80 N/mm2 at 225% elongation and of approved quality in contraction and expansion joints with necessary arrangement for modification of shuttering and keeping the water stop in position etc as per design, specification and direction of Engineer in charge | m | 26 | 1133.751 | One Thousand One Hundred and Thirty-Three point Seven Five One | 29477.526
66 | 16-240 | 16-240 | Earth work by manual labour, in all kinds of soil in removing the cross bundh/ ring bundh, including all leads and lifts complete and placing the spoils to a safe distance, (minimun 15m apart from the bank) as per direction of Engineer in charge. | cum | 2961.06 | 142.471 | One Hundred and Forty-Two point Four Seven One | 421865.179
67 | 76-240 | 76-240-40 | Manufacturing & Supplying of M.S. Vertical Lift Gate shutter of 8mm thick M.S. skin plate and stiffener with minimum 75mmx75mmx10mm M.S. angle as frame, horizontal & vertical beam 75mmx25mmx12mm P-type rubber seal, fixed with 10mm dia x 63 .5mm M.S. counter shank bolts with nuts and 40mmx10mm M.S. strip as clamp drilled spaces @ 150mm c/c, stem attachment with proper thread, nut, cotter pin and washer as per approved design including the cost of all materials of proper grade & brand new with a prime coat of redoxide where necessary as per specification and direction of Engineer in charge. | nos | 4 | 150000.001 | One Lakh Fifty Thousand point Zero Zero One | 600000.004
68 | 76-260 | 76-260-20 | Labour charge for fitting and fixing of M.S. vertical lift gate/flap gate shutters of different size including making holes in concrete for hooking arrangements with supply of necessary materials, tools and other accessories required for fitting the same to regulator/sluice and mending the damages with CC (1:2:4), removing the spoils etc.complete including the cost of all materials as per direction of Engineer in charge.Size 1.95m x 1.65m. | nos | 4 | 27517.535 | Twenty-Seven Thousand Five Hundred and Seventeen point Five Three Five | 110070.14
69 | 76-190 | 76-190 | Manufacturing, supplying and Installation of Padestal type lifting device for slide gate with 63mm dia threaded steel shaft, 146mm outer dia bronze nut, thrust bearing, steel bevel gear etc. as per approved design including supply of all components, labours with a prime coat of redoxide where necessary etc. complete including the cost of all materials as per specification and direction of Engineer in charge. | nos | 4 | 125000.001 | One Lakh Twenty-Five Thousand point Zero Zero One | 500000.004
70 | 16-530 | 16-530 | Back filling in hydraulic structures and slope building in protective works including all leads and lifts with selected local soil in layer of 150mm including watering, ramming etc. complete compacted to 20% relative density by compactor or any other suitable method as per direction of Engineer in charge. | cum | 2385.02 | 159.491 | One Hundred and Fifty-Nine point Four Nine One | 380389.225
71 | 16-600 | 16-600-10 | Earth work by Mechanical Excavator ( Long Boom ) in all kinds of soil in excavation/re-excavation of Channel/Canal/khal etc. Including disposal of spoil-soil upto 30m away from the point of excavation with rough dressing and leveling etc. Complete as per direction of Engineer in charge. | cum | 13486.13 | 96.971 | Ninety-Six point Nine Seven One | 1307763.512 | D
72 | 68-130 | 68-130 | Supplying pressure treated wooden fall boards/stop logs of different sizes (not less than 15cm in depth) of sal, sundari, garjan, shishu or equivalent for regulator/ sluices, including fixing in position with eye hook etc. complete as per direction of Engineer in charge. | cum | 15.47 | 60966.401 | Sixty Thousand Nine Hundred and Sixty-Six point Four Zero One | 943150.223
73 | MR | MR | Supply and Installation of Name Plate | NOS | 8 | 13709.555 | Thirteen Thousand Seven Hundred and Nine point Five Five Five | 109676.44 | D
74 | 16-120 | 16-120-10 | Earth work by manual labour in constructing/ resectioning of embankment/ canalbank/road etccompacted to 85%/90% maximum drydensity at optimum moisture content,with referenceto laboratory density test AAHSTO modified hammer, with clayey soil(minm 30% clay,0-40% silt, 0-30% sand) within the initial lead of 30m & all lifts including throwing the spoils to profiles in layers not exceeding 230mm in thickness with clod breaking to a maximum size of 100mm, benching the side slopes, removing roots & stumps of trees of girth upto 200mm from the ground, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of crest etc.complete, including maintenance of the same for 6 months after completion, (compaction will be done by the contractor with approved equipment, including all ancillary charges for compaction and testing) as per direction of Engineer in charge. 0 m to 3 m height with 85% compaction. | cum | 2760 | 170.001 | One Hundred and Seventy point Zero Zero One | 469202.76 | D
75 | 48-100 | 48-100 | Fine dressing and close turfing of the slopes and the crest of embankment with 75 mm thick good quality durba or charkanta sods of size 200 mm x 200 mm with all leads and lifts including ramming watering until the turf grows properly, maintaining etc. complete (measurement will be given on well grown grass only) as per direction of Engineer in charge. | sqm | 1870 | 12.005 | Twelve point Zero Zero Five | 22449.35 | D
76 | NSI | NSI | Environmental Monitoring through Sample Collection and analysis such as Air quality test, Surface water test, Sound Level monitoring, Traffic signs and road navigation, safety provisions with first aid and medical Assistant as per direction of engineer in charge. | LS | 1 | 258152.401 | Two Lakh Fifty-Eight Thousand One Hundred and Fifty-Two point Four Zero One | 258152.401 | D
404.51
[6 empty] | Dediction | D | 21.67
382.84