## Stucture_Summary
Irrigation Inlet :82 Contract Value:756.57 Paid Bill:121.99 Amount Payable:634.58
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
17 | 17a | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 25 | 274.46 | 1 | 117.08 | OG | 157.38
20 | 20a | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 15 | 118.56 | 1 | 4.91 | OG | 113.65
20 | 20d | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 7 | 55.33 | 1 | 0 | OG | 55.33
20 | 20g | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 14 | 110.66 | 1 | 0 | OG | 110.66
22 | 22a | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | nos. | 6 | 72.88 | 1 | 0 | OG | 72.88
25 | 25a | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | nos. | 15 | 124.68 | 1 | 0 | OG | 124.68
Sub-Total Inlet |  |  |  |  | 82 | 756.57 |  | 121.99 |  | 634.58
Regulator:9 Contract Value:2031.23 Paid Bill:864.21 Amount Payable:1167.02
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
4 | 4a | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 | 3 | 179.54 | OG | 18.46
4 | 4b | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 | 3 | 231.82 | OG | 23.83
10 | 10a | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 114 | 3 | 14.22 | OG | 99.78
11 | 11a | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 | 3 | 134.1 | OG | 140.4
21 | 21a | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 | 3 | 0 | OG | 225
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Construction of 2-V Mozilla Khal Regulator | nos. | 1 | 298.3 | 3 | 0 | OG | 298.3
23 | 23b | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Construction of 2-V Noaparakhali Khal Regulator | nos. | 1 | 230.33 | 3 | 0 | OG | 230.33
25 | 25b | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 | 3 | 304.53 | OG | 92.43
Sub-Total Regulator |  |  |  |  | 9 | 1992.74 |  | 864.21 |  | 1128.53
Box Drainage Outlet:13 Contract Value:535.08 Paid Bill:233.70 Amount Payable:301.18
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
9 | 9c | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 77.25 | 4 | 22.46 | OG | 54.79
17 | 17a1 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 1 | 35.49 | 4 | 16.48 | OG | 19.01
| 17a2 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 1 | 35.49 | 4 | 16.48 | OG | 19.01
| 17a3 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 1 | 35.49 | 4 | 16.48 | OG | 19.01
| 17a4 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 1 | 35.49 | 4 | 16.48 | OG | 19.01
| 17a5 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 1 | 35.49 | 4 | 16.48 | OG | 19.01
20 | 20b | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
| 20e | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
| 20h1 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
| 20h2 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 1 | 42.6 | 4 | 32.21 | OG | 10.39
22 | 22b1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Box Drainage Outlet at Km 19.5 | nos. | 1 | 36.66 | 4 | 0 | OG | 36.66
| 22b2 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Box Drainage Outlet at Km 22.5 | nos. | 1 | 36.66 | 4 | 0 | OG | 36.66
| 22b3 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Box Drainage Outlet at Km 23.6 | nos. | 1 | 36.66 | 4 | 0 | OG | 36.66
Sub-Total Box Drainage Outlet |  |  |  |  | 13 | 535.08 |  | 233.7 |  | 301.38
Causeway:10 Contract Value:1865.695 Paid Bill:606.13 Amount Payable:1259.57
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
9 | 9a | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 193.13 | 5 | 56.15 | OG | 136.98
| 9b1 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width |  | 1 | 231.76 | 5 | 67.38 | OG | 164.38
| 9b2 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 1 | 231.76 | 5 | 67.38 | OG | 164.38
10 | 10b | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 1 | 152 | 5 | 18.96 | OG | 133.04
20 | 20c | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway at Chitra Khal | nos. | 1 | 133.79 | 5 | 88.79 | OG | 45
20 | 20f1 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway at Nabunpur Khal | nos. | 1 | 187.82 | 5 | 73.24 | OG | 114.58
20 | 20f2 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway at Dipjuri Khal | nos. | 1 | 181.18 | 5 | 131.39 | OG | 49.79
20 | 20i | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway at Sudhi Khal | nos. | 1 | 133.84 | 5 | 73.8 | OG | 60.04
22 | 22c | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 | 5 | 0 | OG | 194.91
25 | 25c | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 | 5 | 23.35 | OG | 126.795
Sub-Total Causeway |  |  |  |  | 10 | 1790.335 |  | 600.44 |  | 1189.895
Khal/River:75.856 km Contract Value:2515.06 Paid Bill:1104.20 Amount Payable:1410.09
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
6 | 6a1 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Katakhali Khal | Km | 3.8 | 69.51 | 7 | 63.5169 | OG | 5.9931
| 6a2 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Samarbari Khal | Km | 3.89 | 102.18 | 7 | 93.3701 | OG | 8.8099
| 6a3 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Mahinhandra Khal | Km | 0.9 | 28.84 | 7 | 26.3534 | OG | 2.4866
| 6a4 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Kata Khal | Km | 0.5 | 16.45 | 7 | 15.0317 | OG | 1.4183
| 6a5 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Kurigai Khal | Km | 7.35 | 231.8 | 7 | 211.8143 | OG | 19.9857
| 6a6 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Beri Gang | Km | 3.56 | 112.46 | 7 | 102.7637 | OG | 9.6963
12 | 12a1 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Lalpur Khal | Km | 3.99 | 166.7 | 7 | 43.8596 | OG | 122.8404
| 12a2 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Naluar Khal | Km | 0.6 | 17.47 | 7 | 4.5964 | OG | 12.8736
| 12a3 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Maherkona Khal | Km | 3 | 98.06 | 7 | 25.8 | OG | 72.26
| 12a4 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Nabinpur Khal | Km | 2.8 | 109.32 | 7 | 28.7626 | OG | 80.5574
| 12a5 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Jalalpur | Km | 0.367 | 4.3 | 7 | 1.1314 | OG | 3.1686
19 | 19a1 | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Bera Chapra River | Km | 15.82 | 540.2 | 7 | 165.3006 | OG | 374.8994
| 19a2 | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Ataplal River | Km | 7.111 | 428.3 | 7 | 131.0594 | OG | 297.2406
22 | 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Sajna Khal | Km | 1 | 21.69 | 7 | 0 |  | 21.69
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Chandpur Khal | Km | 0.7 | 32.74 | 7 | 0 |  | 32.74
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Baduti Khal | Km | 1 | 7.67 | 7 | 0 |  | 7.67
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Kanala Khal | Km | 0.584 | 9.84 | 7 | 0 |  | 9.84
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Kursi Khal | Km | 2.9 | 99.77 | 7 | 0 |  | 99.77
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Bamuna Khal | Km | 1.4 | 14.93 | 7 | 0 |  | 14.93
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Chouganga Khal | Km | 1.9 | 4.59 | 7 | 0 |  | 4.59
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Maora Khal | Km | 1.7 | 18.3 | 7 | 0 |  | 18.3
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Burimara Khal | Km | 0.439 | 5.51 | 7 | 0 |  | 5.51
25 | 25d1 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Bantai River | Km | 1.65 | 54.4 | 7 | 27.7267 |  | 26.6733
| 25d2 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Shankir Khal | Km | 8.895 | 320.03 | 7 | 163.1133 |  | 156.9167
Sub-Total Khal/River |  |  |  |  | 75.856 | 2515.06 |  | 1104.2 |  | 1410.86
Submersible Embankment:84.21 km Contract Value:3653.70 Paid Bill:1328.52 Amount Payable:2325.18
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
3 | 3a | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | Km | 10.383 | 533.94 | 11 | 432.69 | OG | 101.25
5 | 5a | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | Km | 12.214 | 577.36 | 11 | 349.59 | OG | 227.77
10 | 10c | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | Km | 11.98 | 617.94 | 11 | 211.56 | OG | 406.38
13 | 13a | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 10 | 576.67 | 11 | 86.55 | OG | 490.12
16 | 16a | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | Km | 14.12 | 511.3 | 11 | 248.13 | OG | 263.17
21 | 21b | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 10 | 478.31 | 11 | 0 | OG | 478.31
22 | 22e | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 11 | 252.89 | 11 | 0 | OG | 252.89
23 | 23a | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 4.51 | 105.29 | 11 | 0 | OG | 105.29
Sub-Total Submersible Embankment |  |  |  |  | 84.207 | 3653.7 |  | 1328.52 |  | 2325.18
[8 empty] | Inlet | 82 | 634.58
[8 empty] | Regulator | 9 | 1128.53
[8 empty] | Outlet | 13 | 307.63
[8 empty] | Causeway | 10 | 1259.57
[8 empty] | Khal/River | 74.61 | 1575.34
[8 empty] | Sub Emb | 84.21 | 2325.18
7230.83

## Khal
Khal/River:75.856 km Contract Value:2515.06 Paid Bill:1104.20 Amount Payable:1410.09
SL No | Comp No | Package Name | Component | Unit | Qnty | Contract Value | STC Code | Billed Amount | Current Status | Remaining Bill
6 | 6a1 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Katakhali Khal | Km | 3.8 | 69.51 | 7 | 63.5169 | OG | 5.9931
| 6a2 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Samarbari Khal | Km | 3.89 | 102.18 | 7 | 93.3701 | OG | 8.8099
| 6a3 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Mahinhandra Khal | Km | 0.9 | 28.84 | 7 | 26.3534 | OG | 2.4866
| 6a4 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Kata Khal | Km | 0.5 | 16.45 | 7 | 15.0317 | OG | 1.4183
| 6a5 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Kurigai Khal | Km | 7.35 | 231.8 | 7 | 211.8143 | OG | 19.9857
| 6a6 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Beri Gang | Km | 3.56 | 112.46 | 7 | 102.7637 | OG | 9.6963
12 | 12a1 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Lalpur Khal | Km | 3.99 | 166.7 | 7 | 43.8596 | OG | 122.8404
| 12a2 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Naluar Khal | Km | 0.6 | 17.47 | 7 | 4.5964 | OG | 12.8736
| 12a3 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Maherkona Khal | Km | 3 | 98.06 | 7 | 25.8 | OG | 72.26
| 12a4 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Nabinpur Khal | Km | 2.8 | 109.32 | 7 | 28.7626 | OG | 80.5574
| 12a5 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Jalalpur | Km | 0.367 | 4.3 | 7 | 1.1314 | OG | 3.1686
19 | 19a1 | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Bera Chapra River | Km | 15.82 | 540.2 | 7 | 165.3006 | OG | 374.8994
| 19a2 | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Ataplal River | Km | 7.111 | 428.3 | 7 | 131.0594 | OG | 297.2406
22 | 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Sajna Khal | Km | 1 | 21.69 | 7 | 0 |  | 21.69
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Chandpur Khal | Km | 0.7 | 32.74 | 7 | 0 |  | 32.74
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Baduti Khal | Km | 1 | 7.67 | 7 | 0 |  | 7.67
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Kanala Khal | Km | 0.584 | 9.84 | 7 | 0 |  | 9.84
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Kursi Khal | Km | 2.9 | 99.77 | 7 | 0 |  | 99.77
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Bamuna Khal | Km | 1.4 | 14.93 | 7 | 0 |  | 14.93
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Chouganga Khal | Km | 1.9 | 4.59 | 7 | 0 |  | 4.59
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Maora Khal | Km | 1.7 | 18.3 | 7 | 0 |  | 18.3
| 22d1 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Burimara Khal | Km | 0.439 | 5.51 | 7 | 0 |  | 5.51
25 | 25d1 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Bantai River | Km | 1.65 | 54.4 | 7 | 27.7267 |  | 26.6733
| 25d2 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Shankir Khal | Km | 8.895 | 320.03 | 7 | 163.1133 |  | 156.9167 | 1204.4845
Sub-Total Khal/River |  |  |  |  | 75.856 | 2515.06 |  | 1104.2 |  | 1410.86
[8 empty] | Inlet | 82 | 634.58
[8 empty] | Regulator | 9 | 1128.53
[8 empty] | Outlet | 13 | 307.63
[8 empty] | Causeway | 10 | 1259.57
[8 empty] | Khal/River | 74.61 | 1575.34
[8 empty] | Sub Emb | 84.21 | 2325.18
7230.83

## Immediate_Actions
Sl No | Pack Name | Structue Name | Length | Contract Value | STC Code | Bill Paid | Remaining Bill | FSE Name | Cell Phone No | Work Completion Probability | Value of Workdone | Value of work Payable | Required Immediate Action
1 | 3 | Const. of Submersible Embankment | 10.383 Km | 533.94 | 11 | 432.69 | 101.25 | Abul Latif | 01712840981 | 0-1:1km To Be Startted 1-9:8Km Complete 9-10.383:1.383 Km To be startted | 411.3956 | -21.2944 | 1.Immediate Start of Work in Some Places
2 | 5 | Const. of Submersible Embankment | 12.214 Km | 577.36 | 11 | 349.59 | 227.77 | Abdul Latif | 01712840981 | 0-4:4 Km Complete 4-5.3:1.3 Km On going 5.3-6.5:1.2 Km GAP due to River Erosion 6.5-9.0:2.5 Km 2nd Layer Complete 9-10:1Km 1st Layer 10-12:2Km Not Started | 361.6181 | 12.0281 | 1.Immediate Start of Work in Some Places
3 | 10 | Const. of Submersible Embankment | 11.98 Km | 617.94 | 11 | 211.56 | 406.38 | Amirul Islam | 01719255232 | 0:5:5Km Not Started Due to Local Problem 5-10:Completed 10-11.98Km:Not Started | 257.9 | 46.34 | 1.Immediate Start of Work in Some Places
4 | 12 | Lalpur Khal -3.99 Km | 3.99 Km | 166.7 | 7 | 43.86 | 122.84 | Amirul Islam | 01719255232 | Not Yet Started |  | -43.86 | 1.Immediate Start of Works
|  | Maherkona Khal-3.00 Km | 3.00 Km | 98.06 | 7 | 25.8 | 72.26 | Amirul Islam | 01719255232 | 3.00-1.50:1.5 Km Completed 1.50-0.00:On Going | 49.03 | 23.23 | 1.Expedite Work
|  | Nabinpur Khal-2.8 Km | 2.8 Km | 109.32 | 7 | 28.76 | 80.56 | Amirul Islam | 01719255232 | Complete | 109.32 | 80.56
5 | 13 | Const. of Submersible Embankment | 10 Km | 576.67 | 11 | 86.55 | 490.12 | Munshi | 01712696439 | 0-4:4Km LA Problem Not Started 4-6:2Km Completed 6-10:4km 3rd Layer | 288.34 | 201.79 | 1.Immediate Start of work in 0-4Km
6 | 16 | Const. of Submersible Embankment | 14.12 Km | 511.3 | 11 | 248.13 | 263.17 | Khalilur Rahman | 01764762777 |  |  | -248.13
7 | 19 | Bera Chapra River-15.82 Km | 15.82 Km | 540.2 | 7 | 165.3 | 374.9 | Munshi | 01712696439 | Mobiliztion Yet Not Completed | 0 | -165.3 | 1.Contractor is slothful. 2.Need Immediate Mobilization 3.If Not Mobilize Contract Termination 4.If Mobilize Deployment of Personnel for Daily Progress Monitoring
|  | Ataplal River-7.111 Km | 7.11 Km | 428.3 | 7 | 131.06 | 297.24 | Munshi | 01712696439 | Mobiliztion Yet Not Completed | 0 | -131.06 | 1.Contractor is slothful. 2.Need Immediate Mobilization 3.If Not Mobilize Contract Termination 4.If Mobilize Deployment of Personnel for Daily Progress Monitoring
8 | 20 | Const. of 4.0 m width Causeway at Chitra Khal | 4m | 133.79 | 5 | 88.79 | 45 | Abul Latif | 01712840981 | Block Placing Going On | 100.3425 | 11.5525
|  | Const. of 4.0 m width Causeway at Nabunpur Khal | 4m | 187.82 | 5 | 73.24 | 114.58 | Abul Latif | 01712840981 | Block Placing Going On | 140.865 | 67.625
|  | Const. of 4.0 m width Causeway at Dipjuri Khal | 4m | 181.18 | 5 | 131.39 | 49.79 | Abul Latif | 01712840981 | Block Placing Going On | 135.885 | 4.495
|  | Const. of 4.0 m width Causeway at Sudhi Khal | 4m | 133.84 | 5 | 73.8 | 60.04 | Abul Latif | 01712840981 | Block Manufacturing | 80.304 | 6.504 | 1.Immediate Start of CC Block Manufacturing
9 | 21 | Const. of Submersible Embankment | 10 Km | 478.31 | 11 | 0 | 478.31 | Khalilur Rahman | 01764762777 | Work Not Strated On But Excavator Mobilized | 0 | 0
10 | 22 | Box Drainage Outlet at Km 19.5 | 1-vent | 36.66 | 4 | 0 | 36.66 | Khalilur Rahman | 01764762777 | Work will be started soon | 0 | 0 | 1.Settingup Layout
|  | Box Drainage Outlet at Km 22.5 | 1-vent | 36.66 | 4 | 0 | 36.66 | Khalilur Rahman | 01764762777 | Work will be started soon | 0 | 0 | 1.Settingup Layout
|  | Box Drainage Outlet at Km 23.6 | 1-vent | 36.66 | 4 | 0 | 36.66 | Khalilur Rahman | 01764762777 | Work will be started soon | 0 | 0 | 1.Settingup Layout
|  | Const. of 4.0 m width Causeway | 4m | 194.91 | 5 | 0 | 194.91 | Khalilur Rahman | 01764762777 | Material is On Site work will be started soon. | 0 | 0 | 1.Settingup Layout
|  | Kursi Khal -2.9 Km | 2.9 Km | 99.97 | 7 | 0 | 99.97 | Khalilur Rahman | 01764762777 | Not Yet Started | 0 | 0 | 1.ImmediateStart of Work
|  | Const. of Submersible Embankment | 11 Km | 252.89 | 11 | 0 | 252.89 | Khalilur Rahman | 01764762777 | 1st Layer althrough | 68.97 | 68.97
11 | 23 | Construction of 2-V Mozilla Khal Regulator | 2-vent | 298.3 | 3 | 0 | 298.3 | Anil | 01715332085 | Work On Going | 119.32 | 119.32 | 1.Preparation of Realistic Work Programme to Finish The Work
|  | Construction of 2-V Noaparakhali Khal Regulator | 2-vent | 230.33 | 3 | 0 | 230.33 | Anil | 01715332085 | Work On Going | 92.132 | 92.132 | 1.Preparation of Realistic Work Programme to Finish The Work
|  | Const. of Submersible Embankment | 4.51 Km | 105.29 | 11 | 0 | 105.29 | Anil | 01715332085 | Althrough 1st Layer 2nd Layer Going on | 42.116 | 42.116
12 | 25 | Shankir Khal -8.895 Km | 8.895 Km | 320.03 | 7 | 163.11 | 156.92 | Khalilur Rahman | 01764762777 | 0-8:7.6 Km complete with 400m gap and 8-8.800:Yet to be started | 276.3895 | 113.2795 | 1.Immediate Completion of Work
|  | Const. of New Regulators 5 vent (1.50mx1.80m) | 5-Vent | 396.96 | 3 | 304.53 | 92.43 | Khalilur Rahman | 01764762777 | Structure Almost Complete | 297.72 | -6.81 | 1.Immediate Start of CC Block Manufacturing2.Due to Conbtractual Problem There is Dispute about CA for CCBlock whethere Shgringles or Crushed Stone To be Used 3.Work is pedding due to Indecision of Competent Authority
|  | Const. of 4.0 m width Causeway | 4m | 150.145 | 5 | 23.35 | 126.795 | Khalilur Rahman | 01764762777 |  | 120.116 | 96.766 | 1.Immediate Start of CC Block Manufacturing2.Due to Conbtractual Problem There is Dispute about CA for CCBlock whethere Shgringles or Crushed Stone To be Used 3.Work is pedding due to Indecision of Competent Authority
Sub-Total |  |  |  | 7433.535 |  | 2581.51 | 4852.025 |  |  |  | 2951.7637 | 370.2537

## Sheet2
374.9
297.24 | 672.14