## WBS
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS (2)
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | 0 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9