## FLOOD FUSE 30m
Task Name | Unit | Quantity | Equipment
Mobilization and Site Preparation | LS | 1
CC Block Manufacture(50X50X50) | Nos | 2669 | MM-2 | CC Block Manufacture(50X50X50)-2669 Nos
CC Block Manufacture(50X50X30) | Nos | 4795 | MM-2 | CC Block Manufacture(50X50X30)-4795 Nos
CC Block Manufacture(40X40X40) | Nos | 3653 | MM-2 | CC Block Manufacture(40X40X40)-3653 Nos
CC Block Manufacture(40X40X40) | Nos | 2655 | MM-2 | CC Block Manufacture(40X40X40)-2655 Nos
Ring Bundh construction (2052 cum) | cum | 2052 | MM-2 | Ring Bundh construction (2052 cum)-2052 cum
Excavation | cum | 2525 |  | Excavation-2525 cum
Embankment Construction | cum | 1771 |  | Embankment Construction-1771 cum
Placing Sand Filter | Cum | 361 |  | Placing Sand Filter-361 Cum
Placing Geotextile Filter | sqm | 2457 |  | Placing Geotextile Filter-2457 sqm
Placing Pea Gravel Filter | cum | 481 |  | Placing Pea Gravel Filter-481 cum
Placing CC Block | cum | 503.13 |  | Placing CC Block-503.13 cum
Ancilary Work for Site Completion | LS | 1

## FLOOD FUSE 15_4.52
Task Name | Unit | Quantity | Equipment
Mobilization and Site Preparation | LS | 1
CC Block Manufacture(50X50X50) | Nos | 1355 | MM-2 | CC Block Manufacture(50X50X50)-1355 Nos
CC Block Manufacture(50X50X30) | Nos | 4795 | MM-2 | CC Block Manufacture(50X50X30)-4795 Nos
CC Block Manufacture(40X40X40) | Nos | 1782 | MM-2 | CC Block Manufacture(40X40X40)-1782 Nos
CC Block Manufacture(40X40X40) | Nos | 3917 | MM-2 | CC Block Manufacture(40X40X40)-3917 Nos
Ring Bundh construction | cum | 1482 | MM-2 | Ring Bundh construction -1482 cum
Excavation | cum | 1192 |  | Excavation-1192 cum
Embankment Construction | cum | 1082 |  | Embankment Construction-1082 cum
Placing Sand Filter | Cum | 268 |  | Placing Sand Filter-268 Cum
Placing Geotextile Filter | sqm | 1838 |  | Placing Geotextile Filter-1838 sqm
Placing Pea Gravel Filter | cum | 357 |  | Placing Pea Gravel Filter-357 cum
Placing CC Block | cum | 630 |  | Placing CC Block-630 cum
Ancilary Work for Site Completion | LS | 1
b

## FLOOD FUSE 35.05
Task Name | Unit | Quantity | Equipment
Mobilization and Site Preparation | LS | 1
CC Block Manufacture(50X50X50) | Nos | 1355 | MM-2 | CC Block Manufacture(50X50X50)-1355 Nos
CC Block Manufacture(50X50X30) | Nos | 4795 | MM-2 | CC Block Manufacture(50X50X30)-4795 Nos
CC Block Manufacture(40X40X40) | Nos | 1782 | MM-2 | CC Block Manufacture(40X40X40)-1782 Nos
CC Block Manufacture(40X40X40) | Nos | 3917 | MM-2 | CC Block Manufacture(40X40X40)-3917 Nos
Ring Bundh construction | cum | 1482 | MM-2 | Ring Bundh construction -1482 cum
Excavation | cum | 1123 |  | Excavation-1123 cum
Embankment Construction | cum | 669 |  | Embankment Construction-669 cum
Placing Sand Filter | Cum | 242 |  | Placing Sand Filter-242 Cum
Placing Geotextile Filter | sqm | 1668 |  | Placing Geotextile Filter-1668 sqm
Placing Pea Gravel Filter | cum | 322 |  | Placing Pea Gravel Filter-322 cum
Placing CC Block | cum | 578 |  | Placing CC Block-578 cum
Ancilary Work for Site Completion | LS | 1
b

## 281_m_type_A
Task Name | Unit | Quantity | Equipment
Mobilization and Site Preparation | LS | 1
CC Block Manufacture(30X30X30) | Nos | 39933 | 4 | CC Block Manufacture(30X30X30)-39933 Nos
CC Block Manufacture(40X40X20) | Nos | 8701 | 4 | CC Block Manufacture(40X40X20)-8701 Nos
Embankment Construction | cum | 9880 | 2 | Embankment Construction-9880 cum
Placing Sand Filter | cum | 601 |  | Placing Sand Filter-601 cum
Placing Geotextile Filter | sqm | 6617 |  | Placing Geotextile Filter-6617 sqm
Placing Pea Gravel Filter | cum | 620 |  | Placing Pea Gravel Filter-620 cum
Placing CC Block | cum | 1492 |  | Placing CC Block-1492 cum
Ancilary Work for Site Completion | LS | 1 |  | Ancilary Work for Site Completion-1 LS

## Equipment Production Rate
| day/cum | cum/day
Ruller | 0.0013 | 769.2308
Excavator Long Boom | 0.0033 | 303.0303

## 80_m_type_A
Task Name | Unit | Quantity | Equipment
Mobilization and Site Preparation | LS | 1
CC Block Manufacture(30X30X30) | Nos | 4000 | 1 | CC Block Manufacture(30X30X30)-4000 Nos
CC Block Manufacture(40X40X20) | Nos | 1334 | 1 | CC Block Manufacture(40X40X20)-1334 Nos
Embankment Construction | cum | 292 | 1 | Embankment Construction-292 cum
Placing Sand Filter | cum | 60 |  | Placing Sand Filter-60 cum
Placing Geotextile Filter | sqm | 683 |  | Placing Geotextile Filter-683 sqm
Placing Pea Gravel Filter | cum | 62 |  | Placing Pea Gravel Filter-62 cum
Placing CC Block | cum | 164 |  | Placing CC Block-164 cum
Ancilary Work for Site Completion | LS | 1 |  | Ancilary Work for Site Completion-1 LS