## Slide 1: JICA’S APPRECIATION

## Slide 2: JICA’S APPRECIATION

## Slide 3: WHY DID WE GET APPRECIATION
For Accurate Representation of Flood Situation in the project area(Damage)
For Representation and Explaining in detail of Design of different type of protection work.
For Presentation of Activity plan for civil works next two dry seasons
Progress in agriculture component and plan for next FY
Presentations of civil works monitoring format

## Slide 4: Commitments Made to JICA
Commitments to JICA | Follow ups
1. Inclusion of Type B1 protective work for 200m pilot basis | Consultant had been notified to find suitable reach
2. Quality Monitoring Civil Work Plan | 1. QA format finalized 2. Specification drafted (Needs immediate finalization)
3. Improvement of Embankment Turfing | 1. No standard test could be identified 2. Only visual inspection.
4.Photos of condition after major construction activities shall be taken at a regular intervals, e.g. every 200 m, and added to the report | 1.Embankment compaction and turfing will be videographer by single continuous shot. 2.A drone with camera will be procured to picturize different scenarios of

## Slide 5: Commitments Made to JICA
Photos of condition after major construction activities shall be taken at a regular intervals, e.g. every 200 m, and added to the report.
In case of Type A:
  Before the construction of protection work
  Before applying 100mm thick sand layer
  After applying 100mm thick sand layer
  After applying Geotextile Filter Cloth
  After applying 100 m thick assorted filter
  After applying CC blocks

## Slide 6: Commitments Made to JICA

## Slide 7: Commitments Made to JICA
Shaping of embankment crest and slope in design level and in desired compaction.
Selection of turfing source.
Cutting and transporting turf in 250mmx250mmx75mm size.
Planting turf in embankment slope without any gap in staggered formation within February.
Continuous watering upto defects liability period.
Application of fertilizer in proportion N:P:K=16:5:12
Replanting if needed in any defect area.

## Slide 8: Work Program for 2020-21
Chart: BDT Crore
| Inlet | Reg Re-inst | Reg/ CW/BDO | Khal/River (New) | Khal/River (Rehab ) | Full Emb | Subm Emb (Rehab) | Subm Emb (New) | Rehabof Reg | WMG office | Threshing Floor | Gate
Total Target as Per 2nd RDPP | 116 | 5 | 112 | 338 | 109 | 68 | 62 | 263 | 7 | 30 | 5 | 86
Program | 50 | 3 | 30 | 75 | 34 | 7 | 8 | 50 | 4 | 13 | 3 | 19

## Slide 9: Activity Plan for Next TWO Years?

## Slide 10: Progress of Re-excavation of Khal/River (New Haor)

## Slide 11
Progress of Re-excavation of Khal/River (Rehab Haor)

## Slide 12: Progress of Construction of Submersible Embankment (New Haor)

## Slide 13: Yearwise Civil Works Expenditure

## Slide 14: Specification What Does It Contain?
How ,when and by whom measurement for Individual work Item will be given.
How ,when ,by whom and in what frequency Quality Assurance Tests for Individual work items will be performed.
Schedule of Tests for different work Items.

## Slide 15: How Measurement Will be Given
JMT Will Take All Measurement
Concerned Executive Engineer will check and recommend to PD for Approval
PD will Approve all measurement

## Slide 16: JOINT MEASUREMENT TEAM
Constituting Members | Designation
Concerned Sub-Divisional Engineer | Convener
Concerned SAE/SO. | Member
Concerned Field Inspector. | Member
Representative of the Contractor | Member
Concerned Field Supervision Engineer. | Member Secretary

## Slide 17
Submit Measurement Every 15days in standard format. (Annex-II: Standard Forms for Measurement)
Ensure Quality Control tests performed properly
Submit monthly quality control report for every site/reach/structure.
After Completion prepare a defect liability schedule
Measurement Work Scope of JMT

## Slide 18: Measurement Format for CC Block

## Slide 19
Measurement Format for RCC Work

## Slide 20
Measurement Format for Reinforcement

## Slide 21: Measurement Format for Earth Work

## Slide 22: Measurement Format for Earth Work

## Slide 23: Measurement Format for General Items Not Covered Above

## Slide 24: Summary of Measurement

## Slide 25: Standard Sampling and Testing for Embankment
Sl | Name of Test | Frequency of Test | Test Method
1 | Atterberg's Limit (Plastic Limit & Liquid Limit) | 1. For each source of fill materials 2. One Sample for each 10,000 Cum of fill material 3. Change in the Characteristics of the material noticed on visual examination. | ASTM D 4318 or Equivalent
2 | Grain Size Distribution | As stated above | ASTM D 422 or Equivalent
3 | Modified Proctor Test | As stated above | ASTM D 1557 & ASSTO T 180 D
4 | Moisture Content | I .For each 5000 cum of fill material 2. As per direction of the Project Manager. | ASTM D 4346 & ASTM D 4944 or V Equivalent
5 | Field Dry Density Test | 1. One Sample for each 1000 sqm of compacted surface in each layer 2. As per direction of the Project Manager. | AAHSTO T191 or Equivalent

## Slide 26: Standard Sampling and Testing for CC Block
Sl | Name of Test | Frequency of Test | Test Method
1 | Cement: Fineness Soundness Initial Setting Time and Final Setting Time Compressive Strength Tensile Strength Unit Weight | For each fresh Consignment arriving at Site For each 100 M. Ton As approved or directed by the Project Manager. | ASTM C786, ASTI C403, ISO 679:2009 or Equivalent
2 | Fine Aggregate (Sand) i) Fineness Modulus | 1(one) Sample for each 350 Cum or part thereof At least 1 Sample in a week As approved or directed by the Project Manager. | ASTM C 33 or Equivalent
3 | Coarse Aggregate (Stone Chips) Gradation Test | 1(one) Sample for each 700 Cum or part thereof At least 1 Sample in a week As approved or directed by the Project Manager. | ASTM C330, AASHTO T-85, BS- 812, ASTM C-535 or Equivalent
4 | Water Suitability of Water for Concrete Mixing | For Each source of Water As approved or directed by the Project Manager. | BS EN BS EN 1008:2002
5 | Concrete Concrete Core Test | Concrete Core Test will be carried out for at least 5000 CC or 150 cubic meter volume of block which ever is greater. As approved or directed by the Project Manager. | BS 1881, ASTM C-42 Or similar standard

## Slide 27: Standard Sampling and Testing for Geo Textile
Sl | Name of Test | Frequency of Test | Test Method
1 | Geotextile Filter Materials: |  | 
 | i. Opening Size 090 | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 12956
 | ii. Mass per unit area | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | BS EN 965
 | iii. CBR Puncture Resistance | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 12336
 | iv. Tensile Strength (machine direction- MD or cross machine direction-CMD) | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 10319

## Slide 28: Standard Sampling and Testing for Geo Textile
Sl | Name of Test | Frequency of Test | Test Method
 | Minimum thickness | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 9863
 | Grab Tensile Strength | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D 4632
 | Vertical Permeability under 2Kn/m2 & 200Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491
 | viii. Horizontal Permeability under 2Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491

## Slide 29: Standard Sampling and Testing for Geo Textile
Sl | Name of Test | Frequency of Test | Test Method
 | Minimum thickness | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 9863
 | Grab Tensile Strength | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D 4632
 | Vertical Permeability under 2Kn/m2 & 200Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491
 | viii. Horizontal Permeability under 2Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491

## Slide 30: Standard Sampling and Testing for Geo Textile
Sl | Name of Test | Frequency of Test | Test Method
 | Minimum thickness | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 9863
 | Grab Tensile Strength | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D 4632
 | Vertical Permeability under 2Kn/m2 & 200Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491
 | viii. Horizontal Permeability under 2Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491

## Slide 31: Total number of Test for SUNM-PW-07
Type A Protective Work Start: Finish: Length: Start of reporting period: Report Finished Date:
Work Item/Material | Unit | Work Executed/Material Consumed in Last 30 days | Name of Test | Relevant Test Standard | No of Test Required as Per Specification | No of Test Performed | No of Test Passing Threshold Value | No of Test Do Not Passing Threshold Value | Remarks
CC Block | Nos | 88751 | Compressive Strength by Core Cutting | ASTM C42 | 71 |  |  |  | 
Cement | Kg | 1355700 | Fineness Test | ASTM C786 | 14 |  |  |  | 
 |  |  | soundness Test | ASTM C151 | 14 |  |  |  | 
 |  |  | Setting Time | ASTM C403 | 14 |  |  |  | 
Fine Aggregate | cum | 2382 | Fineness Modulus | ASTM C127 | 7 |  |  |  | 
Coarse Aggregate | cum | 5199 | Gradation Test | ASTM C36 | 8 |  |  |  | 
Geo Textile Filter | sqm | 59363 | Opening Size O90 | EN ISO 12956 | 6 |  |  |  | 
 |  |  | Mass per unit area | BS EN 965 | 6 |  |  |  | 
 |  |  | CBR Puncture Resistance | EN ISO 12336 | 6 |  |  |  | 
 |  |  | Tensile Strength (machine direction-MD or cross machine direction-CMD) | EN ISO 10319 | 6 |  |  |  | 
 |  |  | Minimum thickness | EN ISO 9863 | 6 |  |  |  | 
 |  |  | Grab Tensile Strength | ASTM D 4632 | 6 |  |  |  | 
 |  |  | Vertical Permeability under 2Kn/m2 | ASTM D 4632 | 6 |  |  |  | 
 |  |  | Horizontal Permeability under 2Kn/m2 | ASTM D 4632 | 6 |  |  |  | 

## Slide 32: Total number of Test Required for SUNM-PW-07
Enclosure: Test Reports Stated Above.
This is to certify that all the tests has been performed as per relevant standard and work has been done with full conformity to specification.
Recommended By
Concerned Executive Engineer
Work Item/Material | Unit | Work Executed/Material Consumed in Last 30 days | Name of Test | Relevant Test Standard | No of Test Required as Per Specification | No of Test Performed | No of Test Passing Threshold Value | No of Test Do Not Passing Threshold Value | Remarks
Submersible Embankment Construction | cum | 51484 | Atterberg's Limit (Plastic Limit & Liquid Limit) | ASTM D 4318 | 6 |  |  |  | 
 |  |  | Grain Size Distribution | ASTM D6913 / D6913M | 6 |  |  |  | 
 |  |  | Modified Proctor Test | AASHTO T99 | 6 |  |  |  | 
 |  |  | Moisture Content | ASTM D2216 | 12 |  |  |  | 
 |  |  | Dry Density | ASTM D7263 | 138 |  |  |  | 
Sub-Divisional Engineer | Consultant Supervision Engineer | Representative of Contractor