## Slide 1: Assumptions and methodology
1)Site Distribution: Every Stretch of Embankment has been considered as an individual site. Every Khal/River has been considered as different site. Every Regulator/Causeway/Box Drainage outlet has been considered as different site. Irrigation inlet has been considered as Lot.
2) Data Collection: Data for Every Site has been collected from concerned Field Inspector appointed by Project authority.
3)Estimate Segregation: From official estimate and Quoted Tender Price by Contractor contract value for every site has been calculated . During preparation of site estimate, mobilization cost has been discarded.
3)Amount of Bill Paid: In absence of any reliable data on how much bill paid for every site, paid amount distributed proportionally as per prepared site estimate. But this will not effect the analysis as total bill paid for a package will remain same.
4) Projection and Value of Work done :For completed site, whole contract value has been considered as VWD. For projection present pace of work has been considered

## Slide 2: Acronyms
CV :Contract Value.
BP :Bill Paid.
RB :Remaining Bill.
VWD :Value of Work Done.
PVWD :Projected Value of Work Done.
PE :Projected Expenditure of This Financial Year.
P :Problematic Site. Work is not going on for any and all reasons.
C :Site Completed
OG :On Going Work

## Slide 3
Chart: Site Status Hobiganj
| Inlet | Regulator | Box | Causeway | Khal River(New) | Khal River(Old) | Sub Emb Rehab
Total Site | 1 | 8 | 9 | 6 | 10 | 5 | 6
Completed Site | 0 | 0 | 9 | 1 | 6 | 3 | 5
Ongoing Site | 0 | 4 | 0 | 4 | 2 | 0 | 0
Problemetic Site | 1 | 4 | 0 | 1 | 2 | 2 | 1
Total Site=45
Completed Site=24
Ongoing Site=10
Problematic=11

## Slide 4
Chart: Projection of Hobiganj
| HOBI/PW-01 | HOBI/PW-02 | HOBI/PW-04 | HOBI/PW-05 | HOBI/PW-06 | HOBI/PW-07
CV | 1521.4 | 1352.2486 | 1146.8 | 1316.5445 | 1581.7287 | 907.1377
BP | 718.56 | 586.4597 | 626.76 | 232.9399 | 917.2476 | 459.6703
RB | 802.84 | 765.7889 | 520.04 | 1083.6046 | 664.4811 | 447.4673
VWD | 1455.87 | 594.7198 | 721.03 | 622.6004 | 1420.2512 | 558.4809
PVWD | 1455.87 | 712.5858 | 882.92 | 816.9052 | 1521.4706 | 778.3051
PE | 737.31 | 126.1261 | 256.16 | 583.9652 | 604.223 | 318.6348
Total Projection FY_19_20=2626.42

## Slide 5
Chart: Site Status Sunam Gonj
| Inet | Regulator | Box Outlet | Cause Way | Khal/Riv New Haor | Sub Emb Const
Total Site | 2 | 4 | 8 | 10 | 21 | 2
Completed Site | 0 | 0 | 0 | 0 | 13 | 0
Ongoing | 0 | 4 | 4 | 6 | 6 | 1
Problematic | 2 | 0 | 4 | 4 | 2 | 1

## Slide 6
Chart: Projection of Sunamgonj
| SUNM/PW-01 | SUNM/PW-02 | SUNM/PW-03 | SUNM/PW-04 | SUNM/PW-05 | SUNM/PW-06
CV | 1462.001 | 1193.75 | 1682.1286 | 1564.32 | 1457.9869 | 1576.6466
BP | 618.109 | 150.11 | 312.5399 | 1037.6 | 0 | 823.0957
RB | 843.892 | 1043.64 | 1369.5886 | 526.72 | 1457.9869 | 753.551
VWD | 544.411 | 240.8 | 457.91 | 1181.06 | 767.4 | 1050.3542
PVWD | 642.39 | 471.53 | 732.7181 | 1334.36 | 1459.651 | 1383.5487
PE | 24.281 | 321.42 | 420.1782 | 296.76 | 1459.651 | 560.453

## Slide 7
Chart: Site Status Netrokona
| Inet | Reg(r) | Regulator(c) | Box Outlet | Khal(N) | Khal(R) | Full Emb Rehab | Sub Emb Rehab | Reg (RN)
Total Site | 1 | 1 | 5 | 2 | 7 | 15 | 3 | 6 | 1
Completed Site | 0 | 0 | 0 | 0 | 3 | 8 | 1 | 0 | 0
Ongoing Site | 0 | 0 | 4 | 0 | 3 | 2 | 2 | 1 | 0
Problemetic Site | 1 | 1 | 1 | 2 | 1 | 5 | 0 | 5 | 1

## Slide 8
Chart: Projection of Netrokona
| NETR/PW-01 | NETR/PW-02 | NETR/PW-03 | NETR/PW-04 | NETR/PW-05 | NETR/PW-06 | NETR/PW-07
CV | 1345.3447 | 948.8902 | 868.99 | 1500.9205 | 1189.18 | 631.3207 | 893.6768
BP | 428.86 | 343.5 | 289.1 | 501.7924 | 123.11 | 295.03 | 567.7
RB | 916.4847 | 605.3902 | 579.89 | 999.1281 | 1066.07 | 336.2907 | 325.9768
VWD | 563.76 | 514.26 | 295.41 | 961.5522 | 418.33 | 387.452 | 670.18
PVWD | 707.48 | 530.88 | 384.75 | 1021.2322 | 1131.93 | 432.472 | 670.18
PE | 278.62 | 187.38 | 95.65 | 519.4398 | 1008.82 | 137.442 | 102.48

## Slide 9
Chart: Site Status Netrokona
| Inet | Reg(r) | Regulator(c) | Box Outlet | Cause Way | Khal(N) | Khal(R) | Full Emb Rehab | Sub Emb Rehab | Sub Emb Const | Reg (RN)
Total Site | 4 | 1 | 17 | 19 | 16 | 38 | 20 | 3 | 12 | 4 | 1
Completed Site | 0 | 0 | 0 | 9 | 1 | 22 | 11 | 1 | 5 | 0 | 0
Ongoing | 0 | 0 | 12 | 4 | 10 | 11 | 2 | 2 | 1 | 2 | 0
Problematic | 4 | 1 | 5 | 6 | 5 | 5 | 7 | 0 | 6 | 2 | 1
Total Site=135
Completed Site=49
Ongoing site=44
Problematic=42

## Slide 10
Chart: Projection of Total
| CV | BP | RB | VWD | PVWD | PE
Habiganj | 7825.8595 | 3541.6375 | 4284.222 | 5372.9523 | 6168.0567 | 2626.4192
Sunamgonj | 8936.8331 | 2941.4546 | 5995.3785 | 4241.9352 | 6024.1978 | 3082.7432
Netrokona | 7378.3229 | 2549.0924 | 4829.2306 | 3810.9442 | 4878.9242 | 2329.8318
Total | 24141.0155 | 9032.1845 | 15108.831 | 13425.8317 | 17071.1786 | 8038.9941