## 17-18
Item wise Physical & Financial Progress
Economic Code | Item | As per 1st RDPP |  |  |  | Cumulative Physical & Financial Progress (up to June, 2017) |  |  |  |  | Physical & Financial Target during 2017-18 as per RADP |  |  |  |  | Physical & Financial Progress from 01-07-2017 to 30-06-2018) |  |  |  |  | Cumulative Physical & Financial Progress (up to 27 June, 2018) |  |  |  |  | IMED 05
|  | GOB (FE) | PA |  | Total | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Terget | Expend | RPA | DPA
|  |  | RPA | DPA |  |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total
(a) Revenue Component:
4700 | Salary & Allowance | [24 empty] | 25.28 | 25.28
4765 | Conveyance Allowance | 10 |  |  | 10 | L.S. | 0.43 |  |  | 0.43 | L.S. | 0.28 |  |  | 0.28 | L.S. | 0.28 |  |  | 0.28 | L.S. | 0.71 | 0 | 0 | 0.71
4769 | Overtime Allowance | 10 |  |  | 10 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 | 0 | 0 | 0
4795 | Other Allowance | 140 |  |  | 140 | L.S. | 0 |  |  | 0 | L.S. | 25 |  |  | 25 | L.S. | 25 |  |  | 25 | L.S. | 25 | 0 | 0 | 25
4700 | Supplies and Services
4801 | Travel Expenses (TA & DA for PMO & PIU) | 100 |  |  | 100 | L.S. | 27.88 |  |  | 27.88 | L.S. | 18 |  |  | 18 | L.S. | 17.96 |  |  | 17.96 | L.S. | 45.84 | 0 | 0 | 45.84 | 18 | 17.96
4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 |  |  | 245 | L.S. | 47.6 |  |  | 47.6 | L.S. | 35.5 |  |  | 35.5 | L.S. | 34.86 |  |  | 34.86 | L.S. | 82.46 | 0 | 0 | 82.46 | 35.5 | 34.86
4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 |  |  | 2596.27 | L.S. | 1016.1 |  |  | 1016.1 | L.S. | 338 |  |  | 338 | L.S. | 337.33 |  |  | 337.33 | L.S. | 1353.43 | 0 | 0 | 1353.43 | 338 | 337.33
4815 | Postage | 25 |  |  | 25 | L.S. | 0.18 |  |  | 0.18 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.4 | 0 | 0 | 0.4 | 0.42 | 0.42
4816 | Telephones/Telegram/Teleprinter | 25 |  |  | 25 | L.S. | 0.74 |  |  | 0.74 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.89 | 0 | 0 | 0.89
4817 | Telex/Fax/Internet | 25 |  |  | 25 | L.S. | 0.34 |  |  | 0.34 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.39 | 0 | 0 | 0.39
4818 | Registration Fee (Vehicles) | 15 |  |  | 15 | L.S. | 9.55 |  |  | 9.55 | L.S. | 5.5 |  |  | 5.5 | L.S. | 0 |  |  | 0 | L.S. | 9.55 | 0 | 0 | 9.55 | 5.5 | 0
4819 | Water | 10 |  |  | 10 | L.S. | 0.34 |  |  | 0.34 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.37 |  |  | 0.37 | L.S. | 0.71 | 0 | 0 | 0.71 | 2.9 | 2.68
4821 | Electricity | 15 |  |  | 15 | L.S. | 3.65 |  |  | 3.65 | L.S. | 2.5 |  |  | 2.5 | L.S. | 2.31 |  |  | 2.31 | L.S. | 5.96 | 0 | 0 | 5.96
4822 | Gas & Fuel | 200 |  |  | 200 | L.S. | 7.63 |  |  | 7.63 | L.S. | 4 |  |  | 4 | L.S. | 4 |  |  | 4 | L.S. | 11.63 | 0 | 0 | 11.63 | 22 | 22
4823 | Petrol and Lubricant | 150 |  |  | 150 | L.S. | 26.59 |  |  | 26.59 | L.S. | 18 |  |  | 18 | L.S. | 18 |  |  | 18 | L.S. | 44.59 | 0 | 0 | 44.59
4824 | Insurance/Bank Charges (including Vehicles) | 3 |  |  | 3 | L.S. | 0.84 |  |  | 0.84 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.22 |  |  | 0.22 | L.S. | 1.06 | 0 | 0 | 1.06 | 0.25 | 0.22
4827 | Printing & Binding | 35 |  |  | 35 | L.S. | 24.18 |  |  | 24.18 | L.S. | 6 |  |  | 6 | L.S. | 6 |  |  | 6 | L.S. | 30.18 | 0 | 0 | 30.18 | 6 | 6
4828 | Stationery, Seals & Stamps | 150 |  |  | 150 | L.S. | 19.94 |  |  | 19.94 | L.S. | 12 |  |  | 12 | L.S. | 11.99 |  |  | 11.99 | L.S. | 31.93 | 0 | 0 | 31.93 | 12 | 11.99
4831 | Books & Periodicals | 2 |  |  | 2 | L.S. | 0.13 |  |  | 0.13 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.18 | 0 | 0 | 0.18 | 0.05 | 0.05
4840 | Training Expenditure
| Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 238.54 |  | 238.54 | L.S. |  |  |  | 0 | L.S. | [9 empty] | L.S.
| Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 47.81 | 350.6 |  | 398.41 | L.S. |  | 39.08 |  | 39.08 | L.S. | 6.92 | 79.75 |  | 86.67 | L.S. | 6.8 | 79.75 |  | 86.55 | L.S. | 6.8 | 118.83 | 0 | 125.63 | 860.6 | 835.73 | 789.79
| Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 304 | 2229.34 |  | 2533.34 | L.S. |  | 199.49 |  | 199.49 | L.S. | 43.78 | 500.46 |  | 544.24 | L.S. | 24.64 | 500.25 |  | 524.89 | L.S. | 24.64 | 699.74 | 0 | 724.38
| Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 158.6 | 1163.08 |  | 1321.68 | L.S. |  | 119.7 |  | 119.7 | L.S. | 19.9 | 209.79 |  | 229.69 | L.S. | 14.5 | 209.79 |  | 224.29 | L.S. | 14.5 | 329.49 | 0 | 343.99
4851 | Casual labour/Job worker | 15 |  |  | 15 | L.S. | 4.71 |  |  | 4.71 | L.S. | 2 |  |  | 2 | L.S. | 2 |  |  | 2 | L.S. | 6.71 | 0 | 0 | 6.71 | 2 | 2
4854 | Consumable Stores | 25 |  |  | 25 | L.S. | 1.74 |  |  | 1.74 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. | 2.74 | 0 | 0 | 2.74 | 1 | 1
4874 | Consultancy : International - 71 M/M National - 324 M/M |  |  | 7901.4 | 7901.4 | L.S. |  |  | 3792.25 | 3792.25 | L.S. |  |  | 700 | 700 | L.S. |  |  | 689.33 | 689.33 | L.S. | 0 | 0 | 4481.58 | 4481.58 | 700 | 689.33 |  | 689.33
4883 | a) Honorarium/Fees/Remuneration (for different Committee) | 25 |  |  | 25 | L.S. | 3.23 |  |  | 3.23 | L.S. | 4.5 |  |  | 4.5 | L.S. | 4.5 |  |  | 4.5 | L.S. | 7.73 | 0 | 0 | 7.73 | 5 | 5
| b) Interim Evaluation | 10 |  |  | 10 | L.S. | 0.27 |  |  | 0.27 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.52 | 0 | 0 | 0.52
| c) Progress Monitoring | 10 |  |  | 10 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.55 | 0 | 0 | 0.55
4886 | Survey | 162 |  |  | 162 | L.S. | 25.09 |  |  | 25.09 | L.S. | 30 |  |  | 30 | L.S. | 30 |  |  | 30 | L.S. | 55.09 | 0 | 0 | 55.09 | 30 | 30
4888 | Computer Consumables | 50 |  |  | 50 | L.S. | 6.49 |  |  | 6.49 | L.S. | 6.5 |  |  | 6.5 | L.S. | 6.48 |  |  | 6.48 | L.S. | 12.97 | 0 | 0 | 12.97 | 6.5 | 6.48
4899 | Other Expenses: Salary of Manpower through Outsourcing | 1700 |  |  | 1700 | L.S. | 312.29 |  |  | 312.29 | L.S. | 263.25 |  |  | 263.25 | L.S. | 263.24 |  |  | 263.24 | L.S. | 575.53 | 0 | 0 | 575.53 | 263.25 | 263.24
4900 | Repair, Maintenance & Rehabilitation
4901 | Motor Vehicles | 100 |  |  | 100 | L.S. | 18.95 |  |  | 18.95 | L.S. | 22 |  |  | 22 | L.S. | 21.99 |  |  | 21.99 | L.S. | 40.94 | 0 | 0 | 40.94 | 85.75 | 72.49
4906 | Furnitures & Fixtures | 15 |  |  | 15 | L.S. | 1.23 |  |  | 1.23 | L.S. | 1 |  |  | 1 | L.S. | 0.98 |  |  | 0.98 | L.S. | 2.21 | 0 | 0 | 2.21
4911 | Computers & office equipments | 25 |  |  | 25 | L.S. | 1.35 |  |  | 1.35 | L.S. | 2 |  |  | 2 | L.S. | 2 |  |  | 2 | L.S. | 3.35 | 0 | 0 | 3.35
4916 | Machineries & Equipments | 25 |  |  | 25 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.72 | 0 | 0 | 0.72
4921 | Office Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 0 |  |  | 0 | L.S. | 11 |  |  | 11 | L.S. | 9.98 |  |  | 9.98 | L.S. | 9.98 | 0 | 0 | 9.98
4923 | Residential Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 0 |  |  | 0 | L.S. | 11 |  |  | 11 | L.S. | 8.95 |  |  | 8.95 | L.S. | 8.95 | 0 | 0 | 8.95
4932 | Engineering Equipments | 25 |  |  | 25 | L.S. | 0.39 |  |  | 0.39 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.89 | 0 | 0 | 0.89
4947 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 43.5 | 319 |  | 362.5 | L.S. | 7.16 | 52.54 |  | 59.7 | L.S. | 4 | 30 |  | 34 | L.S. | 2.68 | 21.66 |  | 24.34 | L.S. | 9.84 | 74.2 | 0 | 84.04 |  |  | 21.66
4976 | Water Transport : Repair of Speedboat(s) | 10 |  |  | 10 | L.S. | 0.9 |  |  | 0.9 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.75 |  |  | 0.75 | L.S. | 1.65 | 0 | 0 | 1.65
4991 | Others : Repair & Maintenance | 25 |  |  | 25 | L.S. |  |  |  | 0 | L.S. | 3 |  |  | 3 | L.S. | 2.5 |  |  | 2.5 | L.S. | 2.5 | 0 | 0 | 2.5
| Sub-total : (a) Revenue Component: | 6572.18 | 4300.56 | 7901.4 | 18774.14 |  | 1570.44 | 410.81 | 3792.25 | 5773.5 |  | 900 | 820 | 700 | 2420 |  | 863.28 | 811.45 | 689.33 | 2364.06 |  | 2433.72 | 1222.26 | 4481.58 | 8137.56 | 2420 | 2364.06 | 811.45 | 689.33
(b) Capital Component:
6800 | Acquisition of Assets:
6807 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 |  |  | 702.5 | 7 nos. | 484.9 |  |  | 484.9 | 3 nos. | 217.6 |  |  | 217.6 |  | 122 |  |  | 122 | 7 nos. | 606.9 | 0 | 0 | 606.9 | 226.35 | 130
| Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 68.25 |  |  | 68.25 | 30 nos. | 42.22 |  |  | 42.22 | 5 nos. | 8.75 |  |  | 8.75 | 3 nos. | 8 |  |  | 8 | 33 nos. | 50.22 | 0 | 0 | 50.22
6809 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 100 |  |  | 100 | 3 nos. | 40.29 |  |  | 40.29 | 1 no. | 21 |  |  | 21 | 1 no. | 21 |  |  | 21 | 4 nos. | 61.29 | 0 | 0 | 61.29 | 21 | 21
6813 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 |  |  | 8.97 | 7 nos. | 8.95 |  |  | 8.95 |  |  |  |  | 0 |  | 0 |  |  | 0 | 7 nos. | 8.95 | 0 | 0 | 8.95 | 0 | 0
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 5 |  |  | 5 | 2 nos. | 0.79 |  |  | 0.79 |  |  |  |  | 0 |  | 0 |  |  | 0 | 2 nos. | 0.79 | 0 | 0 | 0.79
6814 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 |  |  | 20.5 | 11 nos. | 16.7 |  |  | 16.7 | 6 no. | 3.8 |  |  | 3.8 |  | 3.48 |  |  | 3.48 | 11 nos. | 20.18 | 0 | 0 | 20.18 | 17.3 | 13.5
| Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 |  |  | 6 |  | 0 |  |  | 0 | 1 no. | 2.5 |  |  | 2.5 | 1 no. | 2.13 |  |  | 2.13 | 1 no. | 2.13 | 0 | 0 | 2.13
| Engineering Laboratory Equipments for Kishoregonj WD Division | 50 |  |  | 50 |  | 0 |  |  | 0 | L.S. | 11 |  |  | 11 | L.S. | 7.89 |  |  | 7.89 | L.S. | 7.89 | 0 | 0 | 7.89
6815 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.5 |  |  | 19.5 | 27 nos. | 17.2 |  |  | 17.2 | 3 nos. | 2.3 |  |  | 2.3 | 3 no. | 2.27 |  |  | 2.27 | 30 nos. | 19.47 | 0 | 0 | 19.47 | 7.3 | 6.33
| Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 |  |  | 13.75 | 7 nos. | 6.73 |  |  | 6.73 | 4 nos. | 4 |  |  | 4 | 4 no. | 3.15 |  |  | 3.15 | 11 nos. | 9.88 | 0 | 0 | 9.88
| A3 Combo Printer 2 no ( PMO) | 1.5 |  |  | 1.5 | 1 no. | 0.2 |  |  | 0.2 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. | 0.2 | 0 | 0 | 0.2
| Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 |  |  | 5.25 | 7 nos. | 3.17 |  |  | 3.17 | 4 nos. | 1 |  |  | 1 | 4 no. | 0.91 |  |  | 0.91 | 11 nos. | 4.08 | 0 | 0 | 4.08
6821 | Furnitures & Fixtures | 50 |  |  | 50 | L.S. | 25.39 |  |  | 25.39 | L.S. | 10 |  |  | 10 | L.S. | 9.96 |  |  | 9.96 | L.S. | 35.35 | 0 | 0 | 35.35 | 14 | 11.96
6869 | Aircooler | 15 |  |  | 15 | 4 nos. | 3.77 |  |  | 3.77 | 4 nos. | 4 |  |  | 4 | L.S. | 2 |  |  | 2 | 4 nos. | 5.77 | 0 | 0 | 5.77
6900 | Acquisition/Purchase of lands and landed properties of Assets:
6901 | Land Acquisition ( 408 hectare) | 24000 |  |  | 24000 | L.S. | 4649.65 |  |  | 4649.65 | L.S. | 5794.05 |  |  | 5794.05 | L.S. | 5794.05 |  |  | 5794.05 | L.S. | 10443.7 | 0 | 0 | 10443.7 | 5794.05 | 5794.05
7000 | Construction and Works:
7036 | Irrigation Infrastructures : | [24 empty] | 8500 | 7523.9 | 6542.04
7036 | Construction of Irrigation Inlet (New Haors) | 151.32 | 1109.68 |  | 1261 |  |  |  |  | 0
7041 | Drainage Structures : | [8 empty] | 0
7041 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 181.8 | 1333.2 |  | 1515 |  |  |  |  | 0
7041 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 2437.32 | 17873.68 |  | 20311 | 5 nos. (Part) | 38.11 | 255.04 |  | 293.15 | 20 nos. (Part) | 450 | 3300 |  | 3750 | 7 nos. (Part) | 411.86 | 2362.04 |  | 2773.9 | 15 nos. (Part) | 449.97 | 2617.08 | 0 | 3067.05
7041 | Re-excavation of Khal/River (New Haors) | 1167.48 | 8561.52 |  | 9729 | 8 Km. | 40.49 | 308.67 |  | 349.16 | 120 Km. (Part) | 100 | 740 |  | 840 | 112 Km. (Part) | 100 | 740 |  | 840 | 108 Km. (Part) | 140.49 | 1048.67 | 0 | 1189.16
Others
7081 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 301.8 | 2213.2 |  | 2515 |  |  |  |  | 0
7081 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 306 | 2244 |  | 2550 |  |  |  |  | 0
7081 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 214.2 | 1570.8 |  | 1785 |  |  |  |  | 0
7081 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 1434.3 | 10518.2 |  | 11952.5 | 10 Km. | 40.43 | 296.48 |  | 336.91 | 100 Km. (Part) | 470 | 3440 |  | 3910 | 90 Km. (Part) | 470 | 3440 |  | 3910 | 90 Km. (Part) | 510.43 | 3736.48 | 0 | 4246.91
7081 | Rehabilitation of Regulator (New Haors) | 19.92 | 146.08 |  | 166 |  |  |  |  | 0
7081 | Construction of WMG Office | 165.6 | 1214.4 |  | 1380 |  |  |  |  | 0
7081 | O & M during Construction | 200 |  |  | 200 |  |  |  |  | 0
| Sub-total : (b) Capital Component: | 31645.96 | 46784.76 | 0 | 78430.72 |  | 5418.99 | 860.19 | 0 | 6279.18 |  | 7100 | 7480 | 0 | 14580 |  | 6958.7 | 6542.04 | 0 | 13500.74 |  | 12377.69 | 7402.23 | 0 | 19779.92 | 14580 | 13500.74 | 6542.04 | 0
| Total Cost (a+b) : | 38218.14 | 51085.32 | 7901.4 | 97204.86 |  | 6989.43 | 1271 | 3792.25 | 12052.68 |  | 8000 | 8300 | 700 | 17000 |  | 7821.98 | 7353.49 | 689.33 | 15864.8 |  | 14811.41 | 8624.49 | 4481.58 | 27917.48 | 17000 | 15864.8 | 7353.49 | 689.33
| (c) Physical Contingency ( Lump sum): | 100 | 158 |  | 258
| (d) Price Contingency (Lump sum): | 100.76 | 301.38 |  | 402.14 | [22 empty] | 8042.82
| Grand Total : (a)+(b)+(c)+(d): | 38418.9 | 51544.7 | 7901.4 | 97865 |  | 6989.43 | 1271 | 3792.25 | 12052.68 |  | 8000 | 8300 | 700 | 17000 |  | 7821.98 | 7353.49 | 689.33 | 15864.8 |  | 14811.41 | 8624.49 | 4481.58 | 27917.48
[17 empty] | 97.77% | 88.6% | 98.48% | 93.32%

## 18-19
Item wise Physical & Financial Progress
Economic Code | Item | As per 1st RDPP |  |  |  | Cumulative Physical & Financial Progress (up to June, 20158) |  |  |  |  | Physical & Financial Target during 2018-19 as per ADP |  |  |  |  | Physical & Financial Target during 2018-19 as per RADP |  |  |  |  | Physical & Financial Progress from 01-07-2018 to 31-01-2019) |  |  |  |  | Cumulative Physical & Financial Progress up to current month (up to November, 2018) |  |  |  |  | IMED 05
|  | GOB (FE) | PA |  | Total | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Physical | Financial |  |  |  | Terget | Expend | RPA | DPA
|  |  | RPA | DPA |  |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total |  | GOB | RPA | DPA | Total
(a) Revenue Component:
| Salary & Allowance | [29 empty] | 12.3 | 7.06
3111302 | Conveyance Allowance | 10 |  |  | 10 | L.S. | 0.71 | 0 | 0 | 0.71 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.3 |  |  | 0.3 | L.S. | 0.17 |  |  | 0.17 | L.S. | 0.88 | 0 | 0 | 0.88
3111327 | Overtime Allowance | 10 |  |  | 10 | L.S. | 0 | 0 | 0 | 0 | L.S. |  |  |  | 0 | L.S. |  |  |  | 0 | L.S. | 0 |  |  | 0 | L.S. | 0 | 0 | 0 | 0
3111338 | Other Allowance | 140 |  |  | 140 | L.S. | 25 | 0 | 0 | 25 | L.S. | 14 |  |  | 14 | L.S. | 12 |  |  | 12 | L.S. | 6.89 |  |  | 6.89 | L.S. | 31.89 | 0 | 0 | 31.89
Supplies and Services
3241101 | Travel Expenses (TA & DA for PMO & PIU) | 100 |  |  | 100 | L.S. | 45.84 | 0 | 0 | 45.84 | L.S. | 18 |  |  | 18 | L.S. | 15 |  |  | 15 | L.S. | 6.68 |  |  | 6.68 | L.S. | 52.52 | 0 | 0 | 52.52 | 15 | 6.68
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 |  |  | 245 | L.S. | 82.46 | 0 | 0 | 82.46 | L.S. | 34.25 |  |  | 34.25 | L.S. | 34.25 |  |  | 34.25 | L.S. | 22.81 |  |  | 22.81 | L.S. | 105.27 | 0 | 0 | 105.27 | 34.25 | 22.81
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 |  |  | 2596.27 | L.S. | 1353.43 | 0 | 0 | 1353.43 | L.S. | 252.44 |  |  | 252.44 | L.S. | 254.1 |  |  | 254.1 | L.S. | 109.5 |  |  | 109.5 | L.S. | 1462.93 | 0 | 0 | 1462.93 | 254.1 | 109.5
3211119 | Postage | 25 |  |  | 25 | L.S. | 0.4 | 0 | 0 | 0.4 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.22 |  |  | 0.22 | L.S. | 0.62 | 0 | 0 | 0.62 | 0.65 | 0.33
3211120 | Telephones/Telegram/Teleprinter | 25 |  |  | 25 | L.S. | 0.89 | 0 | 0 | 0.89 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.06 |  |  | 0.06 | L.S. | 0.95 | 0 | 0 | 0.95
3211117 | Telex/Fax/Internet | 25 |  |  | 25 | L.S. | 0.39 | 0 | 0 | 0.39 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.44 | 0 | 0 | 0.44
3221104 | Registration Fee (Vehicles) | 15 |  |  | 15 | L.S. | 9.55 | 0 | 0 | 9.55 | L.S. | 5.45 |  |  | 5.45 | L.S. | 3 |  |  | 3 | L.S. | 2.8 |  |  | 2.8 | L.S. | 12.35 | 0 | 0 | 12.35 | 3 | 2.8
3211115 | Water | 10 |  |  | 10 | L.S. | 0.71 | 0 | 0 | 0.71 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.4 |  |  | 0.4 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.96 | 0 | 0 | 0.96 | 3.6 | 2.06
3211113 | Electricity | 15 |  |  | 15 | L.S. | 5.96 | 0 | 0 | 5.96 | L.S. | 2.5 |  |  | 2.5 | L.S. | 3.2 |  |  | 3.2 | L.S. | 1.81 |  |  | 1.81 | L.S. | 7.77 | 0 | 0 | 7.77
3243102 | Gas & Fuel | 200 |  |  | 200 | L.S. | 11.63 | 0 | 0 | 11.63 | L.S. | 4 |  |  | 4 | L.S. | 6 |  |  | 6 | L.S. | 3.24 |  |  | 3.24 | L.S. | 14.87 | 0 | 0 | 14.87 | 26 | 16.17
3243101 | Petrol and Lubricant | 150 |  |  | 150 | L.S. | 44.59 | 0 | 0 | 44.59 | L.S. | 18 |  |  | 18 | L.S. | 20 |  |  | 20 | L.S. | 12.93 |  |  | 12.93 | L.S. | 57.52 | 0 | 0 | 57.52
3221108 | Insurance/Bank Charges (including Vehicles) | 3 |  |  | 3 | L.S. | 1.06 | 0 | 0 | 1.06 | L.S. | 0.25 |  |  | 0.25 | L.S. | 0.15 |  |  | 0.15 | L.S. | 0.1 |  |  | 0.1 | L.S. | 1.16 | 0 | 0 | 1.16 | 0.15 | 0.1
3255102 | Printing & Binding | 35 |  |  | 35 | L.S. | 30.18 | 0 | 0 | 30.18 | L.S. | 4 |  |  | 4 | L.S. | 4 |  |  | 4 | L.S. | 3.13 |  |  | 3.13 | L.S. | 33.31 | 0 | 0 | 33.31 | 4 | 3.13
3255104 | Stationery, Seals & Stamps | 150 |  |  | 150 | L.S. | 31.93 | 0 | 0 | 31.93 | L.S. | 15 |  |  | 15 | L.S. | 18 |  |  | 18 | L.S. | 13.6 |  |  | 13.6 | L.S. | 45.53 | 0 | 0 | 45.53 | 18 | 13.6
3211127 | Books & Periodicals | 2 |  |  | 2 | L.S. | 0.18 | 0 | 0 | 0.18 | L.S. | 0.05 |  |  | 0.05 | L.S. | 0.1 |  |  | 0.1 | L.S. | 0.04 |  |  | 0.04 | L.S. | 0.22 | 0 | 0 | 0.22 | 0.1 | 0.04
3231201 | Training Expenditure
| Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 238.54 |  | 238.54 | L.S. |  |  |  | 0 | L.S. |  |  |  |  | L.S. | [9 empty] | L.S.
| Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 47.81 | 350.6 |  | 398.41 | L.S. | 6.8 | 118.83 | 0 | 125.63 | L.S. | 10.41 | 93.68 |  | 104.09 | L.S. | 20.1 | 155 |  | 175.1 | L.S. | 6.55 | 67.85 |  | 74.4 | L.S. | 13.35 | 186.68 | 0 | 200.03 | 1065.65 | 710.89 | 648.31 |  |  | 77.1023 | 9.2523
| Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 304 | 2229.34 |  | 2533.34 | L.S. | 24.64 | 699.74 | 0 | 724.38 | L.S. | 59.38 | 534.47 |  | 593.85 | L.S. | 78 | 583 |  | 661 | L.S. | 40.95 | 424.31 |  | 465.26 | L.S. | 65.59 | 1124.05 | 0 | 1189.64 |  |  |  |  | 648.31 | 482.1705 | 57.8605
| Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 158.6 | 1163.08 |  | 1321.68 | L.S. | 14.5 | 329.49 | 0 | 343.99 | L.S. | 23.54 | 211.85 |  | 235.39 | L.S. | 27.55 | 202 |  | 229.55 | L.S. | 15.08 | 156.15 |  | 171.23 | L.S. | 29.58 | 485.64 | 0 | 515.22 | [5 empty] | 177.4432 | 21.2932
3211109 | Casual labour/Job worker | 15 |  |  | 15 | L.S. | 6.71 | 0 | 0 | 6.71 | L.S. | 4 |  |  | 4 | L.S. | 4.25 |  |  | 4.25 | L.S. | 2.68 |  |  | 2.68 | L.S. | 9.39 | 0 | 0 | 9.39 | 4.25 | 2.68
3256103 | Consumable Stores | 25 |  |  | 25 | L.S. | 2.74 | 0 | 0 | 2.74 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. |  |  |  | 0 | L.S. | 2.74 | 0 | 0 | 2.74 | 1 | 0
3257101 | Consultancy : International - 71 M/M National - 324 M/M |  |  | 7901.4 | 7901.4 | L.S. | 0 | 0 | 4481.58 | 4481.58 | L.S. |  |  | 500 | 500 | L.S. |  |  | 700 | 700 | L.S. |  |  | 262.68 | 262.68 | L.S. | 0 | 0 | 4744.26 | 4744.26 | 700 | 262.68 |  | 262.68
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 25 |  |  | 25 | L.S. | 7.73 | 0 | 0 | 7.73 | L.S. | 5 |  |  | 5 | L.S. | 5 |  |  | 5 | L.S. | 3.26 |  |  | 3.26 | L.S. | 10.99 | 0 | 0 | 10.99 | 7 | 3.26
| b) Interim Evaluation | 10 |  |  | 10 | L.S. | 0.52 | 0 | 0 | 0.52 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. |  |  |  | 0 | L.S. | 0.52 | 0 | 0 | 0.52
| c) Progress Monitoring | 10 |  |  | 10 | L.S. | 0.55 | 0 | 0 | 0.55 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. |  |  |  | 0 | L.S. | 0.55 | 0 | 0 | 0.55
3257104 | Survey | 162 |  |  | 162 | L.S. | 55.09 | 0 | 0 | 55.09 | L.S. | 30 |  |  | 30 | L.S. | 30 |  |  | 30 | L.S. | 21.01 |  |  | 21.01 | L.S. | 76.1 | 0 | 0 | 76.1 | 30 | 21.01
3255101 | Computer Consumables | 50 |  |  | 50 | L.S. | 12.97 | 0 | 0 | 12.97 | L.S. | 6.5 |  |  | 6.5 | L.S. | 7.5 |  |  | 7.5 | L.S. | 6.45 |  |  | 6.45 | L.S. | 19.42 | 0 | 0 | 19.42 | 7.5 | 6.45
3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 |  |  | 1700 | L.S. | 575.53 | 0 | 0 | 575.53 | L.S. | 300 |  |  | 300 | L.S. | 300 |  |  | 300 | L.S. | 171.17 |  |  | 171.17 | L.S. | 746.7 | 0 | 0 | 746.7 | 300 | 171.17
Repair, Maintenance & Rehabilitation
3258101 | Motor Vehicles | 100 |  |  | 100 | L.S. | 40.94 | 0 | 0 | 40.94 | L.S. | 20 |  |  | 20 | L.S. | 21 |  |  | 21 | L.S. | 12.55 |  |  | 12.55 | L.S. | 53.49 | 0 | 0 | 53.49 | 63.45 | 31.98
3258102 | Furnitures & Fixtures | 15 |  |  | 15 | L.S. | 2.21 | 0 | 0 | 2.21 | L.S. | 1 |  |  | 1 | L.S. | 1 |  |  | 1 | L.S. | 0.32 |  |  | 0.32 | L.S. | 2.53 | 0 | 0 | 2.53
3258103 | Computers & office equipments | 25 |  |  | 25 | L.S. | 3.35 | 0 | 0 | 3.35 | L.S. | 2 |  |  | 2 | L.S. | 2 |  |  | 2 | L.S. | 0.91 |  |  | 0.91 | L.S. | 4.26 | 0 | 0 | 4.26
3258105 | Machineries & Equipments | 25 |  |  | 25 | L.S. | 0.72 | 0 | 0 | 0.72 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.14 |  |  | 0.14 | L.S. | 0.86 | 0 | 0 | 0.86
3258107 | Office Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 9.98 | 0 | 0 | 9.98 | L.S. | 5 |  |  | 5 | L.S. | 6 |  |  | 6 | L.S. | 9.91 |  |  | 9.91 | L.S. | 19.89 | 0 | 0 | 19.89
3258106 | Residential Building : Repair & Maintenance | 20 |  |  | 20 | L.S. | 8.95 | 0 | 0 | 8.95 | L.S. | 5 |  |  | 5 | L.S. | 10 |  |  | 10 | L.S. | 4.98 |  |  | 4.98 | L.S. | 13.93 | 0 | 0 | 13.93
3258105 | Engineering Equipments | 25 |  |  | 25 | L.S. | 0.89 | 0 | 0 | 0.89 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.5 |  |  | 0.5 | L.S. | 0.18 |  |  | 0.18 | L.S. | 1.07 | 0 | 0 | 1.07
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 43.5 | 319 |  | 362.5 | L.S. | 9.84 | 74.2 | 0 | 84.04 | L.S. | 1.36 | 10 |  | 11.36 | L.S. | 1.7 | 10 |  | 11.7 | L.S. |  |  |  | 0 | L.S. | 9.84 | 74.2 | 0 | 84.04 |  |  | 0
3258128 | Water Transport : Repair of Speedboat(s) | 10 |  |  | 10 | L.S. | 1.65 | 0 | 0 | 1.65 | L.S. | 0.75 |  |  | 0.75 | L.S. | 0.75 |  |  | 0.75 | L.S. |  |  |  | 0 | L.S. | 1.65 | 0 | 0 | 1.65
3258107 | Others : Repair & Maintenance | 25 |  |  | 25 | L.S. | 2.5 | 0 | 0 | 2.5 | L.S. | 3 |  |  | 3 | L.S. | 10 |  |  | 10 | L.S. | 2.99 |  |  | 2.99 | L.S. | 5.49 | 0 | 0 | 5.49
| Sub-total : (a) Revenue Component: | 6572.18 | 4300.56 | 7901.4 | 18774.14 |  | 2433.72 | 1222.26 | 4481.58 | 8137.56 |  | 850 | 850 | 500 | 2200 |  | 900 | 950 | 700 | 2550 |  | 483.41 | 648.31 | 262.68 | 1394.4 |  | 2917.13 | 1870.57 | 4744.26 | 9531.96 | 2550 | 1394.4 | 648.31 | 262.68
(b) Capital Component:
Acquisition of Assets:
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 |  |  | 702.5 | 9 nos. | 606.9 | 0 | 0 | 606.9 | 1 no. | 95.6 |  |  | 95.6 | 1 no. | 95.6 |  |  | 95.6 |  |  |  |  | 0 | 7 nos. | 606.9 | 0 | 0 | 606.9 | 95.6 | 0
| Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 68.25 |  |  | 68.25 | 35 nos. | 50.22 | 0 | 0 | 50.22 |  |  |  |  | 0 |  |  |  |  | 0 | 3 nos. |  |  |  | 0 | 33 nos. | 50.22 | 0 | 0 | 50.22
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 100 |  |  | 100 | 4 nos. | 61.29 | 0 | 0 | 61.29 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. |  |  |  | 0 | 4 nos. | 61.29 | 0 | 0 | 61.29 | 0 | 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 |  |  | 8.97 | 7 nos. | 8.95 | 0 | 0 | 8.95 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 7 nos. | 8.95 | 0 | 0 | 8.95 | 0 | 0
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 5 |  |  | 5 | 2 nos. | 0.79 | 0 | 0 | 0.79 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2 nos. | 0.79 | 0 | 0 | 0.79
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 |  |  | 20.5 | 11 nos. | 20.18 | 0 | 0 | 20.18 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 11 nos. | 20.18 | 0 | 0 | 20.18 | 2 | 0
| Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 |  |  | 6 | 1 no. | 2.13 | 0 | 0 | 2.13 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. |  |  |  | 0 | 1 no. | 2.13 | 0 | 0 | 2.13
| Engineering Laboratory Equipments for Kishoregonj WD Division | 50 |  |  | 50 | L.S. | 7.89 | 0 | 0 | 7.89 | L.S. | 2 |  |  | 2 | L.S. | 2 |  |  | 2 | L.S. |  |  |  | 0 | L.S. | 7.89 | 0 | 0 | 7.89
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.5 |  |  | 19.5 | 30 nos. | 19.47 | 0 | 0 | 19.47 |  |  |  |  | 0 |  |  |  |  | 0 | 3 no. |  |  |  | 0 | 30 nos. | 19.47 | 0 | 0 | 19.47 | 0 | 0
| Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 |  |  | 13.75 | 11 nos. | 9.88 | 0 | 0 | 9.88 |  |  |  |  | 0 |  |  |  |  | 0 | 4 no. |  |  |  | 0 | 11 nos. | 9.88 | 0 | 0 | 9.88
| A3 Combo Printer 2 no ( PMO) | 1.5 |  |  | 1.5 | 1 no. | 0.2 | 0 | 0 | 0.2 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1 no. | 0.2 | 0 | 0 | 0.2
| Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 |  |  | 5.25 | 11 nos. | 4.08 | 0 | 0 | 4.08 |  |  |  |  | 0 |  |  |  |  | 0 | 4 no. |  |  |  | 0 | 11 nos. | 4.08 | 0 | 0 | 4.08
4112314 | Furnitures & Fixtures | 50 |  |  | 50 | L.S. | 35.35 | 0 | 0 | 35.35 | L.S. | 10 |  |  | 10 | L.S. | 10 |  |  | 10 | L.S. | 5.97 |  |  | 5.97 | L.S. | 41.32 | 0 | 0 | 41.32 | 14 | 5.97
4112303 | Aircooler | 15 |  |  | 15 | 4 nos. | 5.77 | 0 | 0 | 5.77 | 4 nos. | 4 |  |  | 4 | 4 nos. | 4 |  |  | 4 | L.S. |  |  |  | 0 | 4 nos. | 5.77 | 0 | 0 | 5.77
Acquisition/Purchase of lands and landed properties of Assets:
4141101 | Land Acquisition ( 470 hectare) | 24000 |  |  | 24000 | L.S. | 10443.7 | 0 | 0 | 10443.7 | L.S. | 7852.4 |  |  | 7852.4 | L.S. | 8287.4 |  |  | 8287.4 | L.S. | 730.52 |  |  | 730.52 | L.S. | 11174.22 | 0 | 0 | 11174.22 | 8287.4 | 730.52
Construction and Works:
4111306 | Irrigation Infrastructures : | [29 empty] | 12051 | 3931.58 | 3382.27
4111306 | Construction of Irrigation Inlet (New Haors) | 151.32 | 1109.68 |  | 1261 |  |  |  |  | 0 | 50 (F)+25 (P) nos. | 90 | 610 |  | 700 | 50 (F)+25 (P) nos. | 75 | 460 |  | 535
4111307 | Drainage Structures : | [8 empty] | 0
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 181.8 | 1333.2 |  | 1515 |  |  |  |  | 0 | 5 nos. (Part) | 90 | 610 |  | 700 | 5 nos. (Part) | 75 | 450 |  | 525
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 2437.32 | 17873.68 |  | 20311 | 15 nos. (Part) | 449.97 | 2617.08 | 0 | 3067.05 | 20 (F)+40 (P) nos. | 600 | 4000 |  | 4600 | 20 (F)+40 (P) nos. | 450 | 2700 |  | 3150 | 7 nos. (Part) | 146.28 | 900.65 |  | 1046.93 | 15 nos. (Part) | 596.25 | 3517.73 | 0 | 4113.98
4111307 | Re-excavation of Khal/River (New Haors) | 1167.48 | 8561.52 |  | 9729 | 108 Km. (Part) | 140.49 | 1048.67 | 0 | 1189.16 | 100 (F)+100 (P) Km. | 750 | 5000 |  | 5750 | 100 (F)+100 (P) Km. | 650 | 4000 |  | 4650 | 112 Km. (Part) | 151.85 | 935 |  | 1086.85 | 108 Km. (Part) | 292.34 | 1983.67 | 0 | 2276.01
Others
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 301.8 | 2213.2 |  | 2515 |  |  |  |  | 0 | 50 (F)+60 (P) Km. | 100 | 700 |  | 800 | 50 (F)+60 (P) Km. | 65 | 400 |  | 465
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 306 | 2244 |  | 2550 |  |  |  |  | 0 | 35 (F)+30 (P) Km. | 90 | 610 |  | 700 | 35 (F)+30 (P) Km. | 65 | 400 |  | 465 | 5 Km. (Part) | 58.7 | 360.59 |  | 419.29
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 214.2 | 1570.8 |  | 1785 |  |  |  |  | 0 | 25 (F)+25 (P) Km. | 75 | 525 |  | 600 | 25 (F)+25 (P) Km. | 50 | 300 |  | 350
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 1434.3 | 10518.2 |  | 11952.5 | 90 Km. (Part) | 510.43 | 3736.48 | 0 | 4246.91 | 80 (F)+110 (P) Km. | 370 | 2455 |  | 2825 | 80 (F)+110 (P) Km. | 250 | 1500 |  | 1750 | 90 Km. (Part) | 192.48 | 1186.03 |  | 1378.51 | 90 Km. (Part) | 702.91 | 4922.51 | 0 | 5625.42
4111201 | Rehabilitation of Regulator (New Haors) | 19.92 | 146.08 |  | 166 |  |  |  |  | 0 | 3 (F)+2 (P) nos. | 10 | 65 |  | 75 | 3 (F)+2 (P) nos. | 10 | 65 |  | 75
4111201 |  | 165.6 | 1214.4 |  | 1380 |  |  |  |  | 0 | 5 (F)+5 (P) nos. | 11 | 75 |  | 86 | 5 (F)+5 (P) nos. | 11 | 75 |  | 86
4111201 | O & M during Construction | 200 |  |  | 200 |  |  |  |  | 0
| Sub-total : (b) Capital Component: | 31645.96 | 46784.76 | 0 | 78430.72 |  | 12377.69 | 7402.23 | 0 | 19779.92 |  | 10150 | 14650 | 0 | 24800 |  | 10100 | 10350 | 0 | 20450 |  | 1285.8 | 3382.27 | 0 | 4668.07 |  | 13663.49 | 10784.5 | 0 | 24447.99 | 20450 | 4668.07 | 3382.27 | 0
| Total Cost (a+b) : | 38218.14 | 51085.32 | 7901.4 | 97204.86 |  | 14811.41 | 8624.49 | 4481.58 | 27917.48 |  | 11000 | 15500 | 500 | 27000 |  | 11000 | 11300 | 700 | 23000 |  | 1769.21 | 4030.58 | 262.68 | 6062.47 |  | 16580.62 | 12655.07 | 4744.26 | 33979.95 | 23000 | 6062.47 | 4030.58 | 262.68
| (c) Physical Contingency ( Lump sum): | 100 | 158 |  | 258
| (d) Price Contingency (Lump sum): | 100.76 | 301.38 |  | 402.14 | [27 empty] | 4293.26
| Grand Total : (a)+(b)+(c)+(d): | 38418.9 | 51544.7 | 7901.4 | 97865 |  | 14811.41 | 8624.49 | 4481.58 | 27917.48 |  | 11000 | 15500 | 500 | 27000 |  | 11000 | 11300 | 700 | 23000 |  | 1769.21 | 4030.58 | 262.68 | 6062.47 |  | 16580.62 | 12655.07 | 4744.26 | 33979.95
[22 empty] | 16.08% | 35.67% | 37.53% | 26.36%

## Sheet4
msjwMœ-4
mgq-wfwËK Kg©-cwiKíbv
gš¿Yvjq/wefvM t- | cvwb m¤ú` gš¿Yvjq
ev¯ÍevqbKvix ms¯’v t- | evsjv‡`k cvwb Dbœqb †evW©
cÖK‡íi bvg I †KvW bs t- | nvIi GjvKvq eb¨v e¨e¯’vcbv I Rxeb hvÎvi gvb Dbœqb (evcvD‡ev Ask ) (HFMLIP) ‡KvW bs - 5135 | [9 empty] | (j¶ UvKvq)
wWwcwc/ wcwc eivÏ Abyhvqx |  | 2017-2018 A_© erm‡ii eivÏ Abyhvqx j¶¨gvÎv |  |  | Kv‡Ri AMÖMÖwZ Ryb/2017 ch©šÍ |  |  | j¶¨gvÎv RyjvB/2017 n‡Z ‡m‡Þt/2017 ch©šÍ |  |  | gšÍe¨
Kv‡Ri A‡½i bvg | eivÏ
|  | ‡fŠZ | Avw_©K | w¯‹g msL¨v | ‡fŠZ | Avw_©K | w¯‹g msL¨v | ‡fŠZ | Avw_©K | w¯‹g msL¨v | gšÍe¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
K) ivR¯^ e¨q t | [10 empty] | 1g wKw¯Íi mgq ch©šÍ wRIwei ivR¯^ Lv‡Z PjwZ A_© eQ‡ii jÿ¨gvÎvi GK PZz_©vsk A_© Aegyw³i cÖ¯Íve Kiv n‡jv Ges g~jab Lv‡Z ¯úxW †evU e¨ZxZ ‡gvUimvB‡Kj I Ab¨vb¨ hš¿cvwZi m¤ú~b© AskB µq Kiv n‡e Ges c~Z© wbg©vY KvR MZ A_© eQi n‡Z Avi¤¢ nIqvq GLv‡Z 1g wKw¯Í‡Z †ekx A_© e¨q n‡e weavq GB Lv‡Z Rwg AwaMÖn‡bi e¨q Kg †`wL‡q wRIwe g~jab Lv‡Zi jÿ¨gvÎvI GK PZz_©vs‡ki mgvb A_© Aegyw³i cÖ¯Íve Kiv n‡jv¦ myZivs 1g wKw¯Í‡Z wRIwe Lv‡Z 2750.00 jÿ UvKv Aegy³ Kivi cÖ¯Íve Kiv n‡jv¦ (ivR¯^-175.00+g~jab 2575.00) |  |  | Lv‡Zi †KvW I weeiY |  | ev‡RU 15-16 | eivÏK…Z A_© (1g wKw¯Í) | eivÏK…Z A_© (2q wKw¯Í) | ‡gvU Znwej Aegyw³ (1g I 2q wKw¯Í)
fvZvw` (4700)
hvZvqvZ fvZv (4765) | 10 | 1 `dv | 0.2 |  |  | 0.43 |  | 1 `dv | 0.05 |  |  | 0.3 | 0.25 | 4765-hvZvqvZ fvZv | 10 | 0.5 | 12500 | 12500 | 25000 | 0.05
AwaKvj fvZv (4769) | 50 | 1 `dv | 0 |  |  | 0 |  | 1 `dv | 0 |  |  | 0.125 | 0.125 | 4769-AwaKvj fvZv | 50 | 0.5 | 12500 |  | 12500 | 0
Dc-‡gvU fvZvw` t | 60 | 0 | 0.2 |  |  | 0.43 |  | 0 | 0.05
mieivn I †mev (4800)
ågb e¨q (wcGgI I wcAvBBD `ß‡ii wUGI wWG) (4801) | 100 | 1 `dv | 20 |  |  | 27.88 |  | 1 `dv | 5 |  |  | 12 | 5 | 4801-ågb fvZv | 100 | 10 | 250000 | 250000 | 500000 | 7
Awdm fvov t wcGgI `ß‡ii (3,500 etdzt) 8eQ‡ii Rb¨(4806) | 378 | 1 `dv | 35.5 |  |  | 47.6 |  | 1 `dv | 9 |  |  | 17.5 | 17.5 | 4806-Awdm fvov | 378 | 35 | 875000 | 875000 | 1750000 | 0
Ab¨vb¨ Kit(civgk©K‡`i AvqKi, AvDU‡mwms Rbe‡ji †eZb, evox fvov, Mvoxi U¨v·-‡Uv‡Kb, wdU‡bm BZ¨vw`) (4814) | 2396.27 | 1 `dv | 301.5 |  |  | 1016.1 |  | 1 `dv | 76 |  |  | 489.475 | 367.7 | 4814-Ab¨vb¨ Ki | 2396.27 | 735.4 | 18385000 | 18385000 | 36770000 | 121.775
WvK‡hvMv‡hvM (4815) | 25 | 1 `dv | 0.15 |  |  | 0.18 |  | 1 `dv | 0.04 |  |  | 0.25 | 0.25 | 4815-WvK †hvMv‡hvM | 25 | 0.5 | 12500 | 12500 | 25000 | 0
‡Uwj‡dvb/‡UwjMÖvg/‡UwjwcÖ›Uvi (4816) | 25 | 1 `dv | 0.3 |  |  | 0.74 |  | 1 `dv | 0.1 |  |  | 0.3 | 0.25 | 4816-‡Uwj‡dvb/‡UwjMÖvg/‡UwjwcÖ›Uvi | 25 | 0.5 | 12500 | 12500 | 25000 | 0.05
‡U‡j·/d¨v·/B›Uvi‡bU (4817) | 25 | 1 `dv | 0.1 |  |  | 0.34 |  | 1 `dv | 0 |  |  | 0.5 | 0.5 | 4817-‡U‡j·/d¨v·/B-‡gBj | 25 | 1 | 25000 | 25000 | 50000 | 0
Mvoxi †iwRt wd (4818) | 10 | 1 `dv |  |  |  | 9.55 | [5 empty] | 8.9 | 8.9 | 4818-Mvox †iwR‡÷ªkb wd | 10 | 8.9 | 222500 | 667000 | 890000 | 0
cvwb (4819) | 10 | 1 `dv | 0.25 |  |  | 0.34 |  | 1 `dv | 0.06 |  |  | 0.25 | 0.25 | 4819-cvwb | 10 | 0.5 | 12500 | 12500 | 25000 | 0
we`y¨r (4821) | 15 | 1 `dv | 2 |  |  | 3.65 |  | 1 `dv | 0.5 |  |  | 2 | 1 | 4821-we`y¨r | 15 | 2 | 50000 | 50000 | 100000 | 1
M¨vm Ges R¡vjvbx (4822) | 200 | 1 `dv | 4 |  |  | 7.63 |  | 1 `dv | 1 |  |  | 3.75 | 3.75 | 4822-M¨vm I R¡vjvbx | 200 | 15 | 375000 |  | 375000 | 0
R¡vjvbx I jyweªK¨v›U (4823) | 150 | 1 `dv | 18 |  |  | 26.59 |  | 1 `dv | 4.5 |  |  | 7 | 5 | 4823-‡c‡Uªvj I jyweªK¨v›U | 150 | 10 | 250000 | 250000 | 500000 | 2
BÝy‡iÝ/e¨vsK PvR© (Mvox mn) (4824) | 3 | 1 `dv | 0.1 |  |  | 0.84 |  | 1 `dv | 0.05 |  |  | 1.5 | 1.25 | 4824-BÝy‡iÝ/e¨vsK PvR© (Mvoxmn) | 3 | 2.5 | 62500 | 62500 | 125000 | 0.25
gy`ªY I cÖKvkbv (4827) | 25 | 1 `dv | 0.8 |  |  | 24.18 |  | 1 `dv | 0.2 |  |  | 7 | 5 | 4827-wcÖw›Us Ges cvewj‡Kkb | 25 | 5 | 125000 | 375000 | 500000 | 2
‡÷kbvix wmj I ›U¨v¤ú (4828) | 150 | 1 `dv | 14 |  |  | 19.94 |  | 1 `dv | 3.5 |  |  | 7 | 5.25 | 4828-‡÷kbvix, wmj I ÷¨v¤úm | 150 | 7 | 175000 | 350000 | 525000 | 1.75
eBcÎ (4831) | 2 | 1 `dv | 0.1 |  |  | 0.13 | [5 empty] | 0.1 | 0.1 | 4831-eBcÎ | 2 | 0.2 | 5000 | 5000 | 10000 | 0
cÖwkÿY e¨q (4840)
GKwU we‡`‡k cÖwkÿY †Kvm©(08 Rb) I GKwU we‡`‡k Öwkÿv mdi (10 Rb) | 238.54
¯’vbxq cÖwkÿYt K) IGÛGg g¨vbyqvj(evcvD‡ev Kg©KZv‡`i) Ges L) cvwb e¨ve¯’vcbv ms¯’v (WMO) | 78
Agriculture Promotion Support Sub-project (APSS) t Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme | 1815.8
Small Scale Income Generation Sub-project (SGSP): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme | 298
K¨Ryqvj †jevi/Re IqvKvi (4851) | 10 | 1 `dv | 2 |  |  | 4.71 |  | 1 `dv | 0.5 |  |  | 2.3 | 2 | 4851-Pzw³wfwËK Kg©Pvix/Kvh© mnKvix | 10 | 4 | 100000 | 100000 | 200000 | 0.3
KbwRD‡gej †÷vi (4854) | 25 | 1 `dv | 1 |  |  | 1.74 |  | 1 `dv | 0.25 |  |  | 1 | 1 | 4854-KbwRD‡gej †÷vi | 25 | 2 | 50000 | 50000 | 100000 | 0
civgk©K †mev (4874) | 7901.4 | [11 empty] | 0 | 4874-civgk©K †mev | 7901.4 | 900 |  |  | 0 | 0
m¤§vbx/wd/m¤§vbx fvZv (4883) (w÷qvwis KwgwU, wcBwm, wUBwmwcGgwm BZ¨vw`) | 25 | 1 `dv | 1.5 |  |  | 3.23 |  | 1 `dv | 0.4 |  |  | 3 | 3 | 4883-m¤§vbx/wd/m¤§vbx fvZv | 25 | 3 | 150000 | 150000 | 300000 | 0
Interim Evaluation (4883) | 10 | 1 `dv | 0.5 |  |  | 0.27 |  | 1 `dv | 0.1 |  |  | 0 | 0 | Interim Evaluation | 10 | 1 |  |  | 0 | 0
Progress Monitoring (4883) | 10 | 1 `dv | 0.5 |  |  | 0.3 |  | 1 `dv | 0.1 |  |  | 0 | 0 | Progress Monitoring | 10 | 2 |  |  | 0 | 0
mv‡f© (4886) | 162 | 1 `dv | 30 |  |  | 25.09 |  | 1 `dv | 6.5 |  |  | 11.5 | 11.5 | 4886-mv‡f© | 162 | 46 | 1150000 |  | 1150000 | 0
Kw¤úDUvi KbwRD‡gej (4888) | 50 | 1 `dv | 5 |  |  | 6.49 |  | 1 `dv | 1.25 |  |  | 1.5 | 1 | 4888-Kw¤úDUvi KbwRD‡gej | 50 | 2 | 50000 | 50000 | 100000 | 0.5
Ab¨vb¨ e¨q t AvDU‡mvwm©s Rbe‡ji †eZb (4899) | 912.29 | 1 `dv | 235 |  |  | 312.29 |  | 1 `dv | 60 |  |  | 64 | 50 | 4899-Ab¨vb¨ e¨q: AvDtRbe‡ji †eZb | 912.29 | 400 | 1000000 | 4000000 | 5000000 | 14
Dc-‡gvU mieivn I †mev t | 15050.3 | 0 | 672.3 |  |  | 1539.81 |  | 0 | 169.05
‡givgZ, msiÿY I c~be©vmb (4900)
†gvUi hvbevnb †givgZ (Mvox) (4901) | 100 | 1 `dv | 15 |  |  | 18.95 |  | 1 `dv | 3.65 |  |  | 6 | 2 | 4901-Mvox | 100 | 2 | 50000 | 150000 | 200000 | 4
Avmeve cÎ †givgZ I msi¶b (4906) | 15 | 1 `dv | 1 |  |  | 1.23 | [5 empty] | 0.5 | 0.5 | 4906-AvmevecÎ | 15 | 1 | 25000 | 25000 | 50000 | 0
Kw¤úDUvi I Awdm miÄvg ‡givgZ I msi¶b (4911) | 25 | 1 `dv | 2 |  |  | 1.35 |  | 1 `dv | 0.5 |  |  | 0.5 | 0.5 | 4911-Kw¤úDUvi I Awdm BKzBc‡g›Um | 25 | 1 | 25000 | 25000 | 50000 | 0
hš¿cvwZ I miÄvg †givgZ msi¶b (4916) | 25 | 1 `dv | 0.5 |  |  | 0.28 | [5 empty] | 0.5 | 0.5 | 4916-‡gwkbvix I BKzBc‡g›Um | 25 | 1 | 25000 | 25000 | 50000 | 0
cÖ‡KŠkj BKzBc‡g›Um (4932) | 25 | 1 `dv | 0.5 |  |  | 0.39 | [5 empty] | 0.25 | 0.25 | 4932-cÖ‡KŠkj BKzBc‡g›Um | 25 | 0.5 | 12500 | 12500 | 25000 | 0
wb®‹vkb KvVv‡gv (4947)
‡i¸‡jUi Gi †MU †givgZ I cwieZ©b (98wU) | 295.75 |  | 7.5 |  |  | 7.16 |  | 1 `dv | 1.75
Rjhvb t ¯úxW‡evU †givgZ (4976) | 10 | 1 `dv | 1 |  |  | 0.9 | [5 empty] | 1 | [7 empty] | 1
Dc-‡gvU ‡givgZ, msiÿY I c~be©vmb t | 495.75 | 0 | 27.5 |  |  | 30.26 |  | 0 | 5.9
ivR¯^ Dc-‡gvU (K) t | 15606.05 | 0 | 700 |  |  | 1570.5 |  | 0 | 175 |  |  | 650 | 494.325 | ‡gvU ivR¯^ e¨qt | 12869.96 | 2200 | 23500000 | 25932000 | 49432500 | 155.675 | 650
L) g~jab e¨q t
m¤ú` msMÖn t (6800) | [12 empty] | 0 | [6 empty] | 155.675
†gvUihvb (6807)
Rxc Mvox (cÖMwZi ˆZix 2500 wmwmi †P‡q †ekx) -1 wU cÖKí cwiPvj‡Ki e¨env‡ii Rb¨ Ges RxcMvox (cÖMwZi ˆZix 2200 wmwm n‡Z 2500 wmwm ch©šÍ) (4-WD)-6 wU (PMO-2wU, wK‡kviMÄ-1wU, ‡bÎ‡Kvbv-1wU, mybvgMÄ-1wU, nweMÄ-1wU I eªvþYevwoqv-1wU) (6807) | 702.5 |  |  |  |  | 484.9 |  |  | 0 |  |  |  | 145 | 6807-Mvoxt Rxc Mvox | 702.5 | 200 | 14500000 |  | 14500000
‡gvUimvB‡Kj 35wU (PMO-2wU, wK‡kviMÄ-12wU, ‡bÎ‡Kvbv-6wU, mybvgMÄ-6wU, nweMÄ-6wU I eªvþYevwoqv-6wU) (6807) | 68.25 | 5wU | 8.75 |  |  | 42.22 |  | 5wU | 8.75 |  |  |  | 10 | 6807-‡gvUi mvB‡Kj | 68.25 | 40 | 1000000 |  | 1000000
BwÄb I cÖ‡qvRbxq hš¿vskmn ¯úxW‡evU (55 Ak¦kw³i 5wU) (6809) | 100 | 2wU | 30 |  |  | 40.29 | [6 empty] | 30 | 6809-Rjhvbt BwÄb cÖ‡qvRbxq | 100 | 100 | 0 | 3000000 | 3000000
d‡UvKwcqvi 7wU (PMO-2wU, wK‡kviMÄ-1wU, ‡bÎ‡Kvbv-1wU, mybvgMÄ-1wU, nweMÄ-1wU I eªvþYevwoqv-1wU) (6813) | 8.97 |  |  |  |  | 8.95 | [6 empty] | 3.5 | 6813-‡gwkbvix I Ab¨vb¨ (d7) | 8.97 | 5 | 50000 | 300000 | 350000
d¨v· 7wU (PMO-2wU, wK‡kviMÄ-1wU, ‡bÎ‡Kvbv-1wU, mybvgMÄ-1wU, nweMÄ-1wU I eªvþYevwoqv-1wU) (6813) | 5 |  |  |  |  | 0.79 | [6 empty] | 0 | d¨v·-7wU | 5 | 2 |  |  | 0
cÖ‡KŠkj BKzBc‡g›Um | [12 empty] | 11 | 6814-cÖ‡KŠkj BKzBc‡g›Um, mv‡f© BKzt |  |  | 50000 | 1050000 | 1100000
mv‡f© BKzBc‡g›Um (wWwRUvj †j‡fwjs BÝUªy‡g›Um 5wU, †UvUvj †÷kb 2wU I n¨vÛ †nì wRwcGm 10wU) (6814) | 20.5 | 6wU | 3.8 |  |  | 16.7 |  | 6wU | 3.8 |  |  |  | 0 | 6814-mv‡f© BKzBc‡g›Um | 20.5 | 10 |  |  | 0
‡bUIqvwK©s BKzBc‡g›Um 6wU (PMO-1wU, wK‡kviMÄ-1wU, ‡bÎ‡Kvbv-1wU, mybvgMÄ-1wU, nweMÄ-1wU I eªvþYevwoqv-1wU) (6814) | 6 | [11 empty] | 0 | 6814-‡bUIqvwK©s BKzBc‡g›Um | 6 | 3 |  |  | 0
Kw¤úDUvi I cÖ‡qvRbxq hš¿vsk | [12 empty] | 16.5 | 6815-Kw¤úDUvi I cÖ‡qvRbxq hš¿vsk |  |  | 1650000 |  | 1650000
†W¯‹Uc Kw¤úDUvi - 30wU (Project Management Office-9wU, cÖavb cwiKíbv `ßi - 3wU, cÖavb cÖ‡KŠkjx bKkv - 3wU, hyM¥ cÖavb cwiKíbv - 2wU, wnmve iÿY cwi`ßi - 2wU, wK‡kviMÄ-3wU, ‡bÎ‡Kvbv-2wU, mybvgMÄ-2wU, nweMÄ-2wU I eªvþYevwoqv-2wU) (6815) | 19.5 | 3 wU | 2.3 |  |  | 17.2 |  | 3 wU | 2.3 |  |  |  | 0 | ‡W¯‹Uc Kw¤úDUvi- 30wU | 19.5 | 13 |  |  | 0
j¨vcUc Kw¤úDUvi - 11wU (Project Management Office-6wU, wK‡kviMÄ-1wU, ‡bÎ‡Kvbv-1wU, mybvgMÄ-1wU, nweMÄ-1wU I eªvþYevwoqv-1wU) (6815) | 13.75 | 4 wU | 4 |  |  | 6.73 |  | 4 wU | 4 |  |  |  | 0 | j¨vcUc-11wU | 13.75 | 6 |  |  | 0
(A3 K‡¤^v wcÖ›Uvi - 1wU (Project Management Office) (6815) | 1.5 |  |  |  |  | 0.2 |  |  | 0 |  |  |  | 0 | K‡¤^v wcÖ›Uvi-1wU | 1.5 | 1 |  |  | 0
‡jmvi wcÖ›Uvi - 7wU (PMO-2wU, wK‡kviMÄ-1wU, ‡bÎ‡Kvbv-1wU, mybvgMÄ-1wU, nweMÄ-1wU I eªvþYevwoqv-1wU) (6815) | 5.25 |  |  |  |  | 3.17 |  |  | 0 |  |  |  | 0 | ‡jRvi wcÖ›Uvi-7wU | 5.25 | 1 |  |  | 0
AvmevecÎ (6821) | 50 | 1 `dv | 10 |  |  | 25.39 |  | 1 `dv | 4 |  |  |  | 7.5 | 6821-AvmevecÎ msMÖn | 50 | 10 | 250000 | 500000 | 750000
GqviKzjvi (6869) | 15 | 4 wU | 4 |  |  | 3.77 |  | 4 wU | 4 |  |  |  | 0 | 6869-GqviKzjvi | 15 | 5 |  |  | 0
Rwg AwaMÖnb/µq t (6900) | [12 empty] | 0 | 6901-Rwg AwaMÖnb (408 †n±i) | 30334.2 | 304 | 0 |  | 0
Rwg AwaMÖnb (408 ‡n±i) (6901) | 30334.2 | 150 †nt | 9227.15 |  |  | 4649.65 |  | 65 †nt | 1998.15 |  |  |  | 223.5 | ‡gvUt †gvU g~jab e¨q | 31350.42 | 700 | 17500000 | 4850000 | 22350000
wbg©vY KvR t (7000) | [12 empty] | 717.82 | ‡gvU= | 44220.38 | 2900 | 41000000 | 30782000 | 71782000
wb®‹vkb KvVv‡gv (7041) | [12 empty] | 0
‡i¸‡jUi c~bt¯’vcb/wbg©vY (5wU) (7041) | 942 | [11 empty] | 0
bZzb ‡i¸‡jUi ¯’vcb/wbg©vY (42wU) (7041) | 19850 | 32 wU ‡i¸‡jUi I 11 wU KRI‡q (Ask) | 450 |  |  | 38.11 |  | 32 wU ‡i¸‡jUi I 11 wU KRI‡q (Ask) | 225 |  |  |  | 0
Lvj c~btLbb (bZzb nvIo) 266.00 wKwg (7041) | 2659 | 180 wKwg (Ask) | 90 |  |  | 40.49 |  | 180 wKwg (Ask) | 90 |  |  |  | 0
Ab¨vb¨ (7081) | [12 empty] | 0
Lvj c~btLbb (nvIo c~be©vmb) 75.40 wKwg (7081) | 378
euva c~be©vmb (c~Y©) 1.55 wKwg (7081) | 63
euva c~be©vmb (WzešÍ) 8.09 wKwg (7081) | 178.5
euva wbg©vY (WzešÍ) 342.30 wKwg (7081) | 14758.55 | 150 wKwg (Ask) | 470 |  |  | 40.43 |  | 150 wKwg (Ask) | 235
g~jab Dc-‡gvU (L) t | 70179.47 |  | 10300 |  |  | 5418.99 |  |  | 2575
Dc-‡gvU (K+L) | 85785.52 |  | 11000 |  |  | 6989.49 |  |  | 2750
(M) wdwRKvj Kw›U‡RbwÝ | 2857.84
(N) cÖvBP Kw›U‡RbwÝ | 10694.36
| 13552.2 |  | 0 |  |  | 0 |  |  | 0
me©-‡gvU (K+L+M+N) t | 99337.72 |  | 11000 |  |  | 6989.49 |  |  | 2750
wmwbqi mnKvix mwPe |  |  |  | (‡gvt dLiæj Av‡e`xb)
cvwb m¤ú` gš¿Yvjq |  |  |  | cÖKí cwiPvjK
nvIi GjvKvq eb¨v e¨e¯’vcbv I Rxeb
hvÎvi gvb Dbœqb cÖKí
evcvD‡ev, XvKv¦

## Sheet5
8.0 Economic code wise comparison of cost summary between the Original DPP and proposed Revised DPP | [27 empty] | (BDT in Lakh)
Economic Code | Economic Sub-Code | Sub-Code wise component description | Original approved DPP | [8 empty] | Proposed 1st Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(a) Revenue Component:
4700 | Allowances
| 4765 | Conveyance Allowance |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
| 4769 | Overtime Allowance |  | 1 Item | 50 | 50 | [6 empty] | 1 Item | 10 | 10 | [7 empty] | -40 | -40
| 4795 | Other Allowance |  | 1 Item | [8 empty] | 1 Item | 140 | 140 | [7 empty] | 140 | 140
4800 | Supplies and Services
| 4801 | Travel Expenses (TA & DA for PMO & PIU) |  | 1 Item | 100 | 100 | [6 empty] | 1 Item | 100 | 100
| 4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | 1 Item | 378 | 378 | [6 empty] | 1 Item | 245 | 245 | [7 empty] | -133 | -133
| 4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 1 Item | 2396.27 | 2396.27 | [6 empty] | 1 Item | 2596.27 | 2596.27 | [7 empty] | 200 | 200
| 4815 | Postage |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4816 | Telephones/Telegram/Teleprinter |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4817 | Telex/Fax/Internet |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4818 | Registration Fee (Vehicles) |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 15 | 15 | [7 empty] | 5 | 5
| 4819 | Water |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
| 4821 | Electricity |  | 1 Item | 15 | 15 | [6 empty] | 1 Item | 15 | 15
| 4822 | Gas & Fuel |  | 1 Item | 200 | 200 | [6 empty] | 1 Item | 200 | 200
| 4823 | Petrol and Lubricant |  | 1 Item | 150 | 150 | [6 empty] | 1 Item | 150 | 150
| 4824 | Insurance/Bank Charges (including Vehicles) |  | 1 Item | 3 | 3 | [6 empty] | 1 Item | 3 | 3
| 4827 | Printing & Binding |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 35 | 35 | [7 empty] | 10 | 10
| 4828 | Stationery, Seals & Stamps |  | 1 Item | 150 | 150 | [6 empty] | 1 Item | 150 | 150
| 4831 | Books & Periodicals |  | 1 Item | 2 | 2 | [6 empty] | 1 Item | 2 | 2
| 4840 | Training Expenditure
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 1 Item | 238.54 |  |  | 238.54 |  |  |  |  | 1 Item | 238.54 |  |  | 238.54
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  |  | 78 |  |  | 78 | [5 empty] | 398.41 | 47.81 |  | 350.6 | [5 empty] | 320.41 | 47.81 |  | 272.6
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1815.8 |  |  | 1815.8 | [5 empty] | 2533.34 | 304 |  | 2229.34 | [5 empty] | 717.54 | 304 |  | 413.54
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 298 |  |  | 298 | [5 empty] | 1321.68 | 158.6 |  | 1163.08 | [5 empty] | 1023.68 | 158.6 |  | 865.08
| 4851 | Casual labour/Job worker |  |  | 10 | 10 | [6 empty] | 1 Item | 15 | 15 | [7 empty] | 5 | 5
| 4854 | Consumable Stores |  |  | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4874 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | MM | 71+324 | 7901.4 |  |  | 5904.6 | 1996.8 |  |  | MM | 71+324 | 7901.4 |  |  |  | 7901.4 |  |  |  |  | 0 |  |  | -5904.6 | 5904.6
| 4883 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
|  | b) Interim Evaluation |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
|  | c) Progress Monitoring |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
| 4886 | Survey |  | 1 Item | 162 | 162 | [6 empty] | 1 Item | 162 | 162
| 4888 | Computer Consumables |  | 1 Item | 50 | 50 | [6 empty] | 1 Item | 50 | 50
| 4899 | Other Expenses: Salary of Manpower through Outsourcing |  | 1 Item | 912.29 | 912.29 | [6 empty] | 1 Item | 1700 | 1700 | [7 empty] | 787.71 | 787.71
4900 | Repair, Maintenance & Rehabilitation
| 4901 | Motor Vehicles |  | L.S. | 100 | 100 | [6 empty] | L.S. | 100 | 100
| 4906 | Furnitures & Fixtures |  | L.S. | 15 | 15 | [6 empty] | L.S. | 15 | 15
| 4911 | Computers & office equipments |  | L.S. | 25 | 25 | [6 empty] | L.S. | 25 | 25
| 4916 | Machineries & Equipments |  | L.S. | 25 | 25 | [6 empty] | L.S. | 25 | 25
| 4921 | Office Building : Repair & Maintenance |  | L.S. | [8 empty] | L.S. | 20 | 20 | [7 empty] | 20 | 20
| 4923 | Residential Building : Repair & Maintenance |  | L.S. | [8 empty] | L.S. | 20 | 20 | [7 empty] | 20 | 20
| 4932 | Engineering Equipments |  | L.S. | 25 | 25 | [6 empty] | L.S. | 25 | 25
| 4947 | Drainage Structures :
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | 98 | 295.75 | 14.75 |  | 281 |  |  |  | Nos. | 104 | 362.5 | 43.5 |  | 319 | [5 empty] | 66.75 | 28.75 |  | 38
| 4976 | Water Transport : Repair of Speedboat(s) | Nos. | 5 | 10 | 10 | [5 empty] | Nos. | 5 | 10 | 10
| 4991 | Others : Repair & Maintenance | [10 empty] | L.S. | 25 | 25 | [7 empty] | 25 | 25
Sub-total : (a) Revenue Component: |  |  |  |  | 15606.05 | 4993.31 |  | 8615.94 | 1996.8 |  |  |  |  | 18774.14 | 6572.18 |  | 4300.56 | 7901.4 |  |  |  |  | 3168.09 | 1578.87 |  | -4315.38 | 5904.6
Economic Code | Economic Sub-Code | Sub-Code wise component description | Original approved DPP | [8 empty] | Proposed 1st Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(b) Capital Component:
6800 | Acquisition of Assets:
| 6807 | Motor Vehicle :
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 | 702.5 | 702.5 | [5 empty] | Nos. | 10 | 702.5 | 702.5
|  | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 35 | 68.25 | 68.25 | [5 empty] | Nos. | 35 | 68.25 | 68.25
| 6809 | Water Transport :
|  | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | Nos. | 5 | 100 | 100 | [5 empty] | Nos. | 6 | 100 | 100
| 6813 | Mechinary & Other Equipment
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 | 8.97 | 8.97 | [5 empty] | Nos. | 7 | 8.97 | 8.97
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 | 5 | 5 | [5 empty] | Nos. | 7 | 5 | 5
| 6814 | Engineering Equipments
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 17 | 20.5 | 20.5 | [5 empty] | Nos. | 17 | 20.5 | 20.5
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 6 | 6 | 6 | [5 empty] | Nos. | 6 | 6 | 6
|  | Engineering Laboratory Equipments for Kishoregonj WD Division | [10 empty] | L.S. | 50 | 50 | [7 empty] | 50 | 50
| 6815 | Computers & Accessories
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos. | 30 | 19.5 | 19.5 | [5 empty] | Nos. | 30 | 19.5 | 19.5
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 11 | 13.75 | 13.75 | [5 empty] | Nos. | 11 | 13.75 | 13.75
|  | A3 Combo Printer 2 no ( PMO) | Nos. | 1 | 1.5 | 1.5 | [5 empty] | Nos. | 2 | 1.5 | 1.5
|  | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 | 5.25 | 5.25 | [5 empty] | Nos. | 11 | 5.25 | 5.25
| 6821 | Furnitures & Fixtures |  | L.S. | 50 | 50 | [6 empty] | L.S. | 50 | 50
| 6869 | Aircooler |  |  | 15 | 15 | [5 empty] | Nos. | 15 | 15 | 15 | [16 empty] | Ori |  |  | Pro |  | Diff
6900 |  | Acquisition/Purchase of lands and landed properties of Assets:
| 6901 | Land Acquisition ( 408 hectare) | ha. | 408 ha. | 30334.2 | 30334.2 | [5 empty] | ha. | 470 | 24000 | 24000 | [7 empty] | -6334.2 | -6334.2 | [6 empty] | #REF! | #REF! | #REF! | 50 | 371 | 421 | #REF!
7000 |  | Construction and Works:
| 7036 | Irrigation Infrastructures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
|  | Construction of Irrigation Inlet (New Haors) | Nos. | [8 empty] | Nos. | 131 | 1261 | 151.32 |  | 1109.68 | [5 empty] | 1261 | 151.32 |  | 1109.68
| 7041 | Drainage Structures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
|  | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | Nos. | 5 | 942 | 46.5 |  | 895.5 |  |  |  | Nos. | 7 (2+5) | 1515 | 181.8 |  | 1333.2 | [5 empty] | 573 | 135.3 |  | 437.7 |  |  |  | #DIV/0! | 978.5 | 18871.5 | 19850 | 3398 | 24917 | 28315 | 8465
|  | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 42 | 19850 | 978.5 |  | 18871.5 |  |  |  | Nos. | 137 (57+35+ 1+44) | 20311 | 2437.32 |  | 17873.68 | [5 empty] | 461 | 1458.82 |  | -997.82 |  |  |  | #DIV/0! | 131 | 2528 | 2659 | 455 | 3337 | 3792 | 1133
|  | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | Km. | 266 | 2659 | 131 |  | 2528 |  |  |  | Km | 318.2 | 9729 | 1167.48 |  | 8561.52 | [5 empty] | 7070 | 1036.48 |  | 6033.52 |  |  |  | #REF!
| 7081 | Others | [27 empty] | #DIV/0! | 18 | 360 | 378 | 65 | 475.36 | 540.36 | 162.36
|  | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | Km. | 75.4 | 378 | 18 |  | 360 |  |  |  | Km | 143 | 2515 | 301.8 |  | 2213.2 | [5 empty] | 2137 | 283.8 |  | 1853.2 |  |  |  | #DIV/0! | 3 | 60 | 63 | 11 | 80 | 91 | 28
|  | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | Km. | 1.55 | 63 | 3 |  | 60 |  |  |  | Km | 84.31 | 2550 | 306 |  | 2244 | [5 empty] | 2487 | 303 |  | 2184 |  |  |  | #DIV/0! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
|  | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | Km. | 8.09 | 178.5 | 8.25 |  | 170.25 |  |  |  | Km | 87.03 | 1785 | 214.2 |  | 1570.8 | [5 empty] | 1606.5 | 205.95 |  | 1400.55 |  |  |  | #DIV/0!
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km. | 342.3 | 14758.55 | 726.6 |  | 14031.95 |  |  |  | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | [5 empty] | -2806.05 | 707.7 |  | -3513.75 |  |  |  | #REF!
|  | Rehabilitation of Regulator (New Haors) | Nos. | [8 empty] | Nos. | 8 | 166 | 19.92 |  | 146.08 | [5 empty] | 166 | 19.92 |  | 146.08 |  |  |  | #REF! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
|  | Construction of WMG Office | Nos. | [8 empty] | Nos. | 60 | 1380 | 165.6 |  | 1214.4 | [5 empty] | 1380 | 165.6 |  | 1214.4 |  |  |  |  | 726.6 | 14031.95 | 14758.55 | 2526 | 18527 | 21053 | 6294.45
|  | O & M during Construction |  | L.S. | [8 empty] | L.S. | 200 | 200 | [7 empty] | 200 | 200 | [6 empty] | #REF! | #REF! | #REF! | 6889 | 50521.36 | 57410.36 | #REF!
Sub-total : (b) Capital Component: |  |  |  |  | 70179.47 | 33262.27 |  | 36917.2 | [5 empty] | 78430.72 | 31645.96 |  | 46784.76 | [5 empty] | 8251.25 | -1616.31 |  | 9867.56 | 0
Total Cost (a+b) : |  |  |  |  | 85785.52 | 38255.58 |  | 45533.14 | 1996.8 |  |  |  |  | 97204.86 | 38218.14 |  | 51085.32 | 7901.4 |  |  |  |  | 11419.34 | -37.44 |  | 5552.18 | 5904.6
(c) Physical Contingency ( Lump sum): |  |  |  | L.S. | 2857.84 | 393.04 |  | 2464.8 | [5 empty] | 258 | 100 |  | 158 | [5 empty] | -2599.84 | -293.04 |  | -2306.8
(d) Price Contingency (Lump sum): |  |  |  | L.S. | 10694.36 | 1243 |  | 9451.36 | [5 empty] | 402.14 | 100.76 |  | 301.38 | [5 empty] | -10292.22 | -1142.24 |  | -9149.98
|  | Grand Total : (a)+(b)+(c)+(d): |  |  | 99337.72 | 39891.62 |  | 57449.3 | 1996.8 |  |  |  |  | 97865 | 38418.9 |  | 51544.7 | 7901.4 |  |  |  |  | -1472.72 | -1472.72 |  | -5904.6 | 5904.6
* DOSA, CONTASA, SAFE, IMPREST etc.
|  |  |  | c+d | 39124.8 | 1926.6 |  | 37198.2 | [5 empty] | 53527 | 6423.24 |  | 47103.76 |  |  | 0 |  |  | 14402.2 | 4496.64 |  | 9905.56
|  |  |  | Phy.Works | 39124.8 | 1926.6 |  | 37198.2 |  |  |  |  | Phy.Works | 53727 | 6623.24 |  | 47103.76 |  |  | 0 |  | Phy.Works | 14602.2 | 4696.64 |  | 9905.56
|  |  |  | c+d+works |  | 3853.2 |  | 74396.4 | [6 empty] | 13046.48 |  | 94207.52 |  |  | 0
|  |  |  | other |  | 36038.42 |  | 2430.34 | [8 empty] | 3981.56
[8 empty] | 76826.74 | [8 empty] | 98189.08
[9 empty] | Reh | [7 empty] | Reh | 0
[9 empty] | New | [7 empty] | New | #REF!
[5 empty] | 2191.8 | [8 empty] | 4253.43 |  |  | 3743.02 | 0
#REF!

## Sheet6
Training Vat & Tax (4840)
Allocation in RADP | Probable Expenditure | Expenditure
Code 4840 | (9.5% of Total) | Code 4814 | Code 4840 | Total | Remaining | Residue Code 4840
70.44 | 81.88 | 40.52 | 38.63 | 79.15 | 2.73 | 29.08

## Sheet7
Details of expense : GoB Revenue | [5 empty] | Taka in Lakh
Code | Items | RADP Allocation | Expenditure upto 27-06-2018 | Expected Expenditure upto 28-06-2018 | Balance | Remarks
4840 | Training | 70.6 | 38.63 | 41.36 | 29.24
4814 | Vat & Tax and others | 338 | 361.9 | 340.88 | -2.88
4899 | Others (O/S salary etc.) | 263.25 | 239.9 | 258.92 | 4.33
4883 | Honorarium | 5 | 3.92 |  | 5
4818 | Registration Fee (Veh.) | 5.5 |  |  | 5.5
4884 | Survey | 30 | 18.77 |  | 30
4901 | Motor Veh. Repair | 22 | 17.09 |  | 22
Details of expense : GoB Capital
6807 | Motor Veh. | 217.6 | 0 | 122 | 95.6
7041 | New Regulators | 450 | 190.46 | 190.46 | 259.54
7041 | Khal/River | 100 | 100 | 100 | 0
7081 | S. Embankment | 470 | 457.68 | 457.68 | 12.32