## Sheet1
of scope of works as per preperatory survey & MOD with the scope of works in detail planning review report.
Descripition of Item | 1st Revised DPP |  |  |  | Proposed 2nd Revised DPP |  |  |  | Difference |  |  |  | Reason for revision
| Physical Qty/Unit | GOB (EE) | Project Aid | Total | Physical Qty/Unit | GOB (EE) | Project Aid | Total | Physical Qty/Unit | GOB (EE) | Project Aid | Total
|  |  | RPA |  |  |  | RPA |  |  |  | RPA
|  |  | Special Account* |  |  |  | Special Account* |  |  |  | Special Account*
APSS, SIGS & Training
1. Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 1 Item | 47.81 | 350.6 | 398.41 | 1 Item | 64.39 | 472.19 | 536.58 |  | 16.58 | 121.59 | 138.17 | Provision has been kept for 100 nos. Water Management Gropu (WMG) in preparatory survey on upper Meghna River Basin Watershed Management Improvement Project prepared by Nippon Koei co. Ltd and Minutes of Discussion of HFM&LIP. Now the detail houshold survey has been carried out in 22 haor sub-projects out of 29 and WMG formation has been formulated. Accoording to the baseline survey the required numbers of WMG hasve been increased and total planned number of WMG is now 380. Itemof works as well as number of APSS & SIGS activities in Agriculture Promotion Support Sub-Project (APSS) and Small-Scale Income Generation Sub-Project (SIGS) have also been increased. (Detail Information's) and Small-Scale Income Generation's related to APSS & SIGS are attached here as Annexure-II). So over all total cost have increased for training of WMG, APSS & SIGS related activities, the objective of the project will be effectivly achieved
2. Agriculture Promotion Support Sub-Project (APSS): Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility support and Technology Development Programme. | 1 Item | 304 | 2229.34 | 2533.34 | 1 Item | 375.07 | 2774.73 | 3149.8 |  | 71.07 | 545.39 | 616.46
3. Small scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme,Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme | 1 Item | 158.6 | 1163.08 | 1321.68 | 1 Item | 158.6 | 1163.08 | 1321.68 |  | 0 | 0 | 0
Construction Works
Drainage Structures:
Repair/Replacement of Regulator Gates and other related works | 104 Nos | 43.5 | 319 | 362.5 | 104 Nos | 43.5 | 319 | 362.5 | 0 Nos | 0 | 0 | 0
Construction of Irrigation Inlet (New Haors) | 131 Nos | 151.32 | 1109.68 | 1261 | 130 Nos | 183.6296 | 1128.0104 | 1311.64 | -1 Nos | 32.3096 | 18.3304 | 50.64 | Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost and total cost have have been increased.
Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 7 Nos | 181.8 | 1333.2 | 1515 | 2 Nos | 58.3268 | 358.2932 | 416.62 | -5 Nos | -123.4732 | -974.9068 | -1098.38 | Cost decrease due to detail investigation & review of the rehabilition works.
Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 137 Nos | 2437.32 | 17873.68 | 20311 | 122 Nos | 2689.7976 | 16523.0424 | 19212.84 | -15 Nos | 252.4776 | -1350.6376 | -1098.16 | No of Structre was decreased.Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost increased but total cost have have been decreased due to drop in numbers of structure.
Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | 318 Km | 1167.48 | 8561.52 | 9729 | 342.105 Km | 1392.7424 | 8555.4176 | 9948.16 | 24.105 Km | 225.2624 | -6.1024 | 219.16 | Length of Canal (New Haors) has been increased.Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost and total cost have have been increased.
Others:
Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | 143 Km | 301.8 | 2213.2 | 2515 | 109.27 Km | 392.9492 | 2413.8308 | 2806.78 | -33.73 Km | 91.1492 | 200.6308 | 291.78 | Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost and total cost have have been increased.
Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | 84.31 Km | 306 | 2244 | 2550 | 69.11 Km | 245.5978 | 1508.6722 | 1754.27 | -15.20 Km | -60.4022 | -735.3278 | -795.73 | Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost have been increased but total cost have reduced due to drop in quantity.
Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | 87.03 Km | 214.2 | 1570.8 | 1785 | 58.272 Km | 211.2264 | 1297.5336 | 1508.76 | -28.76 Km | -2.9736 | -273.2664 | -276.24 | Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost have been increased but total cost have reduced due to drop in quantity.
Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 263.24 Km | 1434.3 | 10518.2 | 11952.5 | 240.472 Km | 1515.1962 | 9307.6338 | 10822.83 | -22.77 Km | 80.8962 | -1210.5662 | -1129.67 | Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost have been increased but total cost have reduced due to drop in quantity.
Rehabilitation of Regulator (New Haors) | 8 Nos | 19.92 | 146.08 | 166 | 7 Nos | 21.5768 | 132.5432 | 154.12 | -1 Nos | 1.6568 | -13.5368 | -11.88 | Detailed field investigation was conducted.To meet the actual field condtion designs have been changed from original Dpp Drawing.As such unit cost have been increased but total cost have reduced due to drop in quantity.
Embankment Slope Protection Work | 0 Km | 0 | 0 | 0 | 27.25 Km | 731.14 | 4419.29 | 5150.43 | 27.25 Km | 731.14 | 4419.29 | 5150.43 | Due to severe wind and wave action erosion in submersible embankment is very common.This piloting work is taken to find out the effective and economical measure for protection of slope of submersible embankment.Outcome of this piloting will be very helpful in futre.
Thershing Floor Construction | 0 Nos | 0 | 0 | 0 | 20 Nos | 126 | 774 | 900 | 20 Nos | 126 | 774 | 900 | In Haor area due to scarecity of Highland farmer's face great difficulty in threshing of Boro rice after harvest of said crop.Construction of threshing floor will help in mitigation of this crisis and will enhance their economical condtion directly.
Construction of WMG Training Centre | 60 Nos | 165.6 | 1214.4 | 1380 | 60 Nos | 336 | 2064 | 2400 | 0 Nos | 170.4 | 849.6 | 1020 | In Haor Area High Land for Building construction is scarce.Prevoius Design of Building was in Brick Masonry Structure whixh is unsuitable for Low Land.Hence Design was changed to RCC Frame Structure that can be easily constructed on filled low land.So cost in this item was increased
O & M during Construction | LS | 200 | 0 | 200 | LS | 200 | 0 | 200 | LS | 0 | 0 | 0

## Sheet2
536.58 | 64.39 |  | 472.19
3125.56 | 375.07 |  | 2750.49
1321.68 | 158.6 |  | 1163.08
| Total | Gob |  | RPA
Inlet | 1311.64 | 183.6296 |  | 1128.0104
Reg Rhab | 416.62 | 58.3268 |  | 358.2932
| 19212.84 | 2689.7976 |  | 16523.0424
| 9948.16 | 1392.7424 |  | 8555.4176
| 2806.78 | 392.9492 |  | 2413.8308
| 1754.27 | 245.5978 |  | 1508.6722 | 0 Km | 0 | 0 | 0 | 27.25 Km | 126 | 774 | 900 | 27.25 Km | 126 | 774 | 900
| 1508.76 | 211.2264 |  | 1297.5336
| 10822.83 | 1515.1962 |  | 9307.6338
| 154.12 | 21.5768 |  | 132.5432
| 5222.43 | 731.14 |  | 4491.29
| 900 | 126 |  | 774
| 2400 | 336 |  | 2064
| 200 | 200 |  | 0

## Sheet3
Thershing Floor Construction
126 | 774 | 900