## Annex2Df
| Code | Description | rindex | Unit Cost | Quantity | TotalCost | Weight | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2020-21-P | 2021-22-P | Investment_Cost_Index | Total_upto_19_20 | Remaining | EC_FACTOR
0 | 3111302 | Conveyance Allowance | 10 | 5 | 0 | 5 | 0 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.58 | 0.42 | 9 | 1.51 | 3.49 | 0.902
1 | 3111327 | Overtime Allowance | 11 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.63 | 0.37 | 10 | 0 | 10 | 0.902
2 | 3111338 | Other Allowance | 12 | 140 | 0 | 140 | 0 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.6 | 0.4 | 11 | 50.61 | 89.39 | 0.902
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 14 | 120 | 0 | 120 | 0 | 0.991 | 11.909 | 14.98 | 17.96 | 12.7 | 15 | 28.8052 | 17.6548 | 0.62 | 0.38 | 13 | 73.54 | 46.46 | 0.902
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 15 | 245 | 0 | 245 | 0 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.25 | 58.3296 | 35.7504 | 0.62 | 0.38 | 14 | 150.92 | 94.08 | 0.812
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 16 | 2596.27 | 0 | 2596.27 | 0 | 223.746 | 464.654 | 327.7 | 337.33 | 249.75 | 359.08 | 367.7258 | 266.2842 | 0.58 | 0.42 | 15 | 1962.26 | 634.01 | 0.812
6 | 3211119 | Postage | 17 | 5 | 0 | 5 | 0 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.5 | 2.1634 | 1.5666 | 0.58 | 0.42 | 16 | 1.27 | 3.73 | 0.812
7 | 3211120 | Telephones/Telegram/Teleprinter | 18 | 5 | 0 | 5 | 0 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.2 | 2.3363 | 1.4937 | 0.61 | 0.39 | 17 | 1.17 | 3.83 | 0.812
8 | 3211117 | Telex/Fax/Internet | 19 | 5 | 0 | 5 | 0 | 0.249 | 0.001 | 0.09 | 0.05 | 0.05 | 0.2 | 2.4416 | 1.9184 | 0.56 | 0.44 | 18 | 0.64 | 4.36 | 0.812
9 | 3221104 | Registration Fee (Vehicles) | 20 | 20 | 0 | 20 | 0 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 1 | 4.4604 | 2.6196 | 0.63 | 0.37 | 19 | 12.92 | 7.08 | 0.812
10 | 3211115 | Water | 21 | 5 | 0 | 5 | 0 | 0 | 0.11 | 0.23 | 0.37 | 0.4 | 0.45 | 2.0984 | 1.3416 | 0.61 | 0.39 | 20 | 1.56 | 3.44 | 0.812
11 | 3211113 | Electricity | 22 | 20 | 0 | 20 | 0 | 0.187 | 1.683 | 1.78 | 2.31 | 2.78 | 3.5 | 4.268 | 3.492 | 0.55 | 0.45 | 21 | 12.24 | 7.76 | 0.812
12 | 3243102 | Gas & Fuel | 23 | 100 | 0 | 100 | 0 | 0.938 | 3.692 | 3 | 4 | 5.89 | 6 | 46.6528 | 29.8272 | 0.61 | 0.39 | 22 | 23.52 | 76.48 | 0.812
13 | 3243101 | Petrol and Lubricant | 24 | 200 | 0 | 200 | 0 | 0.625 | 6.995 | 18.97 | 18 | 20 | 20 | 65.7837 | 49.6263 | 0.57 | 0.43 | 23 | 84.59 | 115.41 | 0.72
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 25 | 3 | 0 | 3 | 0 | 0.081 | 0.749 | 0.01 | 0.22 | 0.1 | 0.15 | 0.9295 | 0.7605 | 0.55 | 0.45 | 24 | 1.31 | 1.69 | 0.902
15 | 3255102 | Printing & Binding | 26 | 50 | 0 | 50 | 0 | 0.196 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.3574 | 5.9826 | 0.61 | 0.39 | 25 | 34.66 | 15.34 | 0.812
16 | 3255104 | Stationery, Seals & Stamps | 27 | 120 | 0 | 120 | 0 | 0.968 | 6.972 | 11.2 | 12.79 | 17.98 | 20 | 31.5567 | 18.5333 | 0.63 | 0.37 | 26 | 69.91 | 50.09 | 0.812
17 | 3211127 | Books & Periodicals | 28 | 2 | 0 | 2 | 0 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.58 | 0.42 | 27 | 0.48 | 1.52 | 0.812
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 30 | 238.54 | 0 | 238.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.54 | 0 | 1 | 0 | 29 | 0 | 238.54 | 0.902
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 31 | 536.58 | 0 | 536.58 | 0 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 196.17 | 23.346 | 15.564 | 0.6 | 0.4 | 30 | 497.67 | 38.91 | 0.902
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 32 | 3139.8 | 0 | 3139.8 | 0 | 0 | 0 | 199.49 | 524.89 | 622.25 | 677.14 | 703.0989 | 412.9311 | 0.63 | 0.37 | 31 | 2023.77 | 1116.03 | 0.902
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 33 | 1321.68 | 0 | 1321.68 | 0 | 0 | 0 | 119.7 | 224.29 | 234.21 | 246.66 | 273.251 | 223.569 | 0.55 | 0.45 | 32 | 824.86 | 496.82 | 0.902
22 | 3211109 | Casual labour/Job worker | 34 | 22 | 0 | 22 | 0 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.5 | 4.6748 | 2.8652 | 0.62 | 0.38 | 33 | 14.46 | 7.54 | 0.902
23 | 3256103 | Consumable Stores | 35 | 15 | 0 | 15 | 0 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.58 | 0.42 | 34 | 6.74 | 8.26 | 0.812
24 | 3257101 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | 36 | 0 | 71+234 | 7901.4 | 0 | 849.675 | 1819.425 | 1123.15 | 689.33 | 686.43 | 500 | 1362.3679 | 871.0221 | 0.61 | 0.39 | 35 | 5668.01 | 2233.39 | 0.902
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 37 | 30 | 0 | 30 | 0 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 5 | 7.1166 | 5.1534 | 0.58 | 0.42 | 36 | 17.73 | 12.27 | 0.902
26 | 3111332 | b) Interim Evaluation | 38 | 10 | 0 | 10 | 0 | 0 | 0 | 0.27 | 0.25 | 0.77 | 1 | 7.71 | 0 | 1 | 0 | 37 | 2.29 | 7.71 | 0.902
27 | 3111332 | c) Progress Monitoring | 39 | 10 | 0 | 10 | 0 | 0 | 0 | 0.3 | 0.25 | 0.75 | 1 | 4.774 | 2.926 | 0.62 | 0.38 | 38 | 2.3 | 7.7 | 0.902
28 | 3257104 | Survey | 40 | 200 | 0 | 200 | 0 | 0 | 7.62 | 17.47 | 30 | 29.93 | 50 | 37.0386 | 27.9414 | 0.57 | 0.43 | 39 | 135.02 | 64.98 | 0.902
29 | 3255101 | Computer Consumables | 41 | 60 | 0 | 60 | 0 | 0.491 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.2415 | 13.2885 | 0.55 | 0.45 | 40 | 30.47 | 29.53 | 0.902
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 42 | 1700 | 0 | 1700 | 0 | 0 | 84.32 | 227.97 | 263.24 | 299.93 | 300 | 298.9878 | 225.5522 | 0.57 | 0.43 | 41 | 1175.46 | 524.54 | 0.86
31 | 3258101 | Motor Vehicles | 44 | 125 | 0 | 125 | 0 | 0.983 | 5.967 | 12 | 21.99 | 20.46 | 15 | 26.73 | 21.87 | 0.55 | 0.45 | 43 | 76.4 | 48.6 | 0.86
32 | 3258102 | Furnitures & Fixtures | 45 | 10 | 0 | 10 | 0 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 2 | 2.88 | 1.92 | 0.6 | 0.4 | 44 | 5.2 | 4.8 | 0.86
33 | 3258103 | Computers & office equipments | 46 | 15 | 0 | 15 | 0 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.59 | 0.41 | 45 | 8.34 | 6.66 | 0.86
34 | 3258105 | Machineries & Equipments | 47 | 10 | 0 | 10 | 0 | 0 | 0.21 | 0.01 | 0.5 | 0.5 | 2 | 4.1358 | 2.6442 | 0.61 | 0.39 | 46 | 3.22 | 6.78 | 0.86
35 | 3258107 | Office Building : Repair & Maintenance | 48 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.59 | 0.41 | 47 | 19.98 | 5.02 | 0.765
36 | 3258106 | Residential Building : Repair & Maintenance | 49 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 8.95 | 5.58 | 5 | 11.8726 | 8.5974 | 0.58 | 0.42 | 48 | 19.53 | 20.47 | 0.765
37 | 3258105 | Engineering Equipments | 50 | 20 | 0 | 20 | 0 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.55 | 0.45 | 49 | 3.39 | 16.61 | 0.86
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 52 | 294.34 | 86 | 294.34 | 0 | 0 | 0 | 59.7 | 24.34 | 10.99 | 58.25 | 88.8678 | 52.1922 | 0.63 | 0.37 | 51 | 153.28 | 141.06 | 0.812
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 53 | 5 | 0 | 5 | 0 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.75 | 1.1346 | 0.7254 | 0.61 | 0.39 | 52 | 3.14 | 1.86 | 0.812
40 | 3258107 | Others : Repair & Maintenance | 54 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 2.5 | 4.98 | 3 | 16.5312 | 12.9888 | 0.56 | 0.44 | 53 | 10.48 | 29.52 | 0.902
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 59 | 70.25 | 10 | 702.5 | 0 | 346.3 | 138.6 | 0 | 122 | 0 | 95.6 | 0 | 0 | 0 | 0 | 58 | 702.5 | 0 | 0.68
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 60 | 1.52 | 45 | 68.25 | 0 | 5.825 | 26.315 | 10.08 | 8 | 0 | 0 | 18.03 | 0 | 1 | 0 | 59 | 50.22 | 18.03 | 0.68
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 62 | 15.5 | 4 | 62 | 0 | 0 | 0 | 40.29 | 21 | 0 | 0 | 0.71 | 0 | 1 | 0 | 61 | 61.29 | 0.71 | 0.68
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 64 | 1.28 | 7 | 8.97 | 0 | 3.726 | 2.744 | 2.48 | 0 | 0 | 0 | 0.02 | 0 | 1 | 0 | 63 | 8.95 | 0.02 | 0.812
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 0.14 | 7 | 1 | 0 | 0.796 | 0 | 0 | 0 | -0.006 | 0 | 0.21 | 0 | 1 | 0 | 64 | 0.79 | 0.21 | 0.812
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 67 | 60.5 | 17 | 60.5 | 0 | 0 | 5.55 | 11.15 | 3.48 | 0 | 0 | 40.32 | 0 | 1 | 0 | 66 | 20.18 | 40.32 | 0.68
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 68 | 0.5 | 6 | 3 | 0 | 0 | 0 | 0 | 2.13 | 0 | 0 | 0.87 | 0 | 1 | 0 | 67 | 2.13 | 0.87 | 0.68
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 69 | 0 | L.S | 50 | 0 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 35.51 | 0 | 1 | 0 | 68 | 14.49 | 35.51 | 0.68
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 71 | 0.66 | 37 | 24.5 | 0 | 3.879 | 7.141 | 6.18 | 2.27 | 0 | 0 | 5.03 | 0 | 1 | 0 | 70 | 19.47 | 5.03 | 0.812
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 72 | 0.86 | 16 | 13.75 | 0 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 3.87 | 0 | 1 | 0 | 71 | 9.88 | 3.87 | 0.812
51 | 4112202 | A3 Combo Printer 2 nos ( PMO) | 73 | 0.3 | 5 | 1.5 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1 | 0 | 72 | 0.2 | 1.3 | 0.812
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 74 | 0.38 | 14 | 5.25 | 0 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 1.17 | 0 | 1 | 0 | 73 | 4.08 | 1.17 | 0.812
53 | 4112314 | Furnitures & Fixtures | 75 | 50 | LS | 50 | 0 | 7.96 | 8.44 | 8.99 | 9.96 | 9.97 | 0 | 2.9016 | 1.7784 | 0.62 | 0.38 | 74 | 45.32 | 4.68 | 0.812
54 | 4112303 | Aircooler | 76 | 1 | 15 | 15 | 0 | 0 | 0 | 3.77 | 2 | 3.96 | 4 | 0.7747 | 0.4953 | 0.61 | 0.39 | 75 | 13.73 | 1.27 | 0.812
55 | 4141101 | Land Acquisition ( 470 hectare) | 78 | 46.81 | 470 | 22000 | 0 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 2049.42 | 5626.98 | 0 | 1 | 0 | 77 | 16373.02 | 5626.98 | 0.902
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 81 | 9.56 | 127 | 1213.55 | 0 | 0 | 0 | 0 | 0 | 116.72 | 490.33 | 333.575 | 272.925 | 0.55 | 0.45 | 80 | 607.05 | 606.5 | 0.902
57 | 4111307 | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 83 | 255.32 | 5 | 1276.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778.7382 | 497.8818 | 0.61 | 0.39 | 82 | 0 | 1276.62 | 0.765
58 | 4111307 | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 84 | 157.05 | 114 | 17903.93 | 0 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 8105.58 | 2229.3609 | 1425.3291 | 0.61 | 0.39 | 83 | 14249.24 | 3654.69 | 0.765
59 | 4111307 | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | 85 | 29.46 | 342.584 | 10091.78 | 0 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 3936.68 | 83.2996 | 60.3204 | 0.58 | 0.42 | 84 | 9948.16 | 143.62 | 0.761
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | 87 | 28.87 | 108.974 | 3145.78 | 0 | 0 | 0 | 0 | 0 | 455.04 | 900.73 | 1020.3057 | 769.7043 | 0.57 | 0.43 | 86 | 1355.77 | 1790.01 | 0.761
61 | 4111201 | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | 88 | 25.11 | 67.11 | 1684.96 | 0 | 0 | 0 | 0 | 0 | 452.46 | 913.26 | 181.9668 | 137.2732 | 0.57 | 0.43 | 87 | 1365.72 | 319.24 | 0.761
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | 89 | 27.08 | 57.912 | 1568.07 | 0 | 0 | 0 | 0 | 0 | 341.85 | 657.55 | 358.2621 | 210.4079 | 0.63 | 0.37 | 88 | 999.4 | 568.67 | 0.761
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 90 | 0 | 254.207 | 16526.21 | 0 | 0 | 0 | 336.91 | 3910 | 1880.15 | 4650.77 | 3506.5118 | 2241.8682 | 0.61 | 0.39 | 89 | 10777.83 | 5748.38 | 0.761
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 91 | 22.02 | 7 | 154.12 | 0 | 0 | 0 | 0 | 0 | 73.26 | 0 | 50.1332 | 30.7268 | 0.62 | 0.38 | 90 | 73.26 | 80.86 | 0.761
65 | 4111201 | Threshing Floor Construction | 92 | 45 | 20 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 351 | 0.61 | 0.39 | 91 | 0 | 900 | 2.761
66 | 4111201 | Construction of WMG Office | 93 | 35 | 60 | 2100 | 0 | 0 | 0 | 0 | 0 | 42.09 | 348.14 | 1008.7643 | 701.0057 | 0.59 | 0.41 | 92 | 390.23 | 1709.77 | 0.765
67 | 4111201 | O & M during Construction | 94 | 0 | 2 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 258 | 0.57 | 0.43 | 93 | 0 | 600 | 0.761
68 | 0 | (c) Physical Contingency ( Lump sum): | 97 | 0 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.54 | 95.46 | 0.63 | 0.37 | 96 | 0 | 258 | 0.765
69 | 0 | (d) Price Contingency (Lump sum): | 98 | 0 | 0 | 402.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.177 | 180.963 | 0.55 | 0.45 | 97 | 0 | 402.14 | 0

## Annex9Df
| Code | Description | rindex | Total-cum | GoB-cum | RPA-cum | DPA-cum | Total-19-20 | GoB-19-20 | RPA-19-20 | DPA-19-20 | Total-20-21 | GoB-20-21 | RPA-20-21 | DPA-20-21 | Total-21-22 | GoB-21-22 | RPA-21-22 | DPA-21-22 | Total-DPP-Cost | Total-Phased-Cost-1 | Total-Phased-GoB | Total-Phased-RPA | Total-Phased-DPA | Total-Phased-Cost-2 | Check1 | Check2
0 | 3111302 | Conveyance Allowance | 11 | 1.01 | 1.01 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.0242 | 2.0242 | 0 | 0 | 1.4658 | 1.4658 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
1 | 3111327 | Overtime Allowance | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 6.3 | 0 | 0 | 3.7 | 3.7 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
2 | 3111338 | Other Allowance | 13 | 36.61 | 36.61 | 0 | 0 | 14 | 14 | 0 | 0 | 53.634 | 53.634 | 0 | 0 | 35.756 | 35.756 | 0 | 0 | 140 | 140 | 140 | 0 | 0 | 140 | 0 | 0
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 15 | 58.54 | 58.54 | 0 | 0 | 15 | 15 | 0 | 0 | 28.8052 | 28.8052 | 0 | 0 | 17.6548 | 17.6548 | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 120 | 1.4211e-14 | 1.4211e-14
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 16 | 116.67 | 116.67 | 0 | 0 | 34.25 | 34.25 | 0 | 0 | 58.3296 | 58.3296 | 0 | 0 | 35.7504 | 35.7504 | 0 | 0 | 245 | 245 | 245 | 0 | 0 | 245 | 0 | 0
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 17 | 1603.18 | 1603.18 | 0 | 0 | 359.08 | 359.08 | 0 | 0 | 367.7258 | 367.7258 | 0 | 0 | 266.2842 | 266.2842 | 0 | 0 | 2596.27 | 2596.27 | 2596.27 | 0 | 0 | 2596.27 | 0 | 0
6 | 3211119 | Postage | 18 | 0.77 | 0.77 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.1634 | 2.1634 | 0 | 0 | 1.5666 | 1.5666 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
7 | 3211120 | Telephones/Telegram/Teleprinter | 19 | 0.97 | 0.97 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 2.3363 | 2.3363 | 0 | 0 | 1.4937 | 1.4937 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
8 | 3211117 | Telex/Fax/Internet | 20 | 0.44 | 0.44 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 2.4416 | 2.4416 | 0 | 0 | 1.9184 | 1.9184 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
9 | 3221104 | Registration Fee (Vehicles) | 21 | 11.92 | 11.92 | 0 | 0 | 1 | 1 | 0 | 0 | 4.4604 | 4.4604 | 0 | 0 | 2.6196 | 2.6196 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | -3.5527e-15 | -3.5527e-15
10 | 3211115 | Water | 22 | 1.11 | 1.11 | 0 | 0 | 0.45 | 0.45 | 0 | 0 | 2.0984 | 2.0984 | 0 | 0 | 1.3416 | 1.3416 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
11 | 3211113 | Electricity | 23 | 8.74 | 8.74 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 4.268 | 4.268 | 0 | 0 | 3.492 | 3.492 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0
12 | 3243102 | Gas & Fuel | 24 | 17.52 | 17.52 | 0 | 0 | 6 | 6 | 0 | 0 | 46.6528 | 46.6528 | 0 | 0 | 29.8272 | 29.8272 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 100 | 0 | 0
13 | 3243101 | Petrol and Lubricant | 25 | 64.59 | 64.59 | 0 | 0 | 20 | 20 | 0 | 0 | 65.7837 | 65.7837 | 0 | 0 | 49.6263 | 49.6263 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 200 | 0 | 0
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 26 | 1.16 | 1.16 | 0 | 0 | 0.15 | 0.15 | 0 | 0 | 0.9295 | 0.9295 | 0 | 0 | 0.7605 | 0.7605 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 4.4409e-16 | 4.4409e-16
15 | 3255102 | Printing & Binding | 27 | 34.16 | 34.16 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 9.3574 | 9.3574 | 0 | 0 | 5.9826 | 5.9826 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 0
16 | 3255104 | Stationery, Seals & Stamps | 28 | 49.91 | 49.91 | 0 | 0 | 20 | 20 | 0 | 0 | 31.5567 | 31.5567 | 0 | 0 | 18.5333 | 18.5333 | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 120 | 0 | 0
17 | 3211127 | Books & Periodicals | 29 | 0.28 | 0.28 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0.8816 | 0.8816 | 0 | 0 | 0.6384 | 0.6384 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.54 | 0 | 238.54 | 0 | 0 | 0 | 0 | 0 | 238.54 | 238.54 | 0 | 238.54 | 0 | 238.54 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 32 | 301.5 | 22.54 | 278.96 | 0 | 196.17 | 21.0294 | 175.1406 | 0 | 23.346 | 2.5027 | 20.8433 | 0 | 15.564 | 1.6685 | 13.8955 | 0 | 536.58 | 536.58 | 47.7406 | 488.8394 | 0 | 536.58 | 0 | 0
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 33 | 1346.63 | 80.34 | 1266.29 | 0 | 677.14 | 72.5894 | 604.5506 | 0 | 703.0989 | 75.3722 | 627.7267 | 0 | 412.9311 | 44.2662 | 368.6649 | 0 | 3139.8 | 3139.8 | 272.5678 | 2867.2322 | 0 | 3139.8 | -4.5475e-13 | -4.5475e-13
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 34 | 578.2 | 35.47 | 542.73 | 0 | 246.66 | 26.442 | 220.218 | 0 | 273.251 | 29.2925 | 243.9585 | 0 | 223.569 | 23.9666 | 199.6024 | 0 | 1321.68 | 1321.68 | 115.1711 | 1206.5089 | 0 | 1321.68 | 0 | 0
22 | 3211109 | Casual labour/Job worker | 35 | 10.96 | 10.96 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 4.6748 | 4.6748 | 0 | 0 | 2.8652 | 2.8652 | 0 | 0 | 22 | 22 | 22 | 0 | 0 | 22 | 0 | 0
23 | 3256103 | Consumable Stores | 36 | 3.74 | 3.74 | 0 | 0 | 3 | 3 | 0 | 0 | 4.7908 | 4.7908 | 0 | 0 | 3.4692 | 3.4692 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
24 | 3257101 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | 37 | 5168.01 | 0 | 0 | 5168.01 | 500 | 0 | 0 | 500 | 1362.3679 | 0 | 0 | 1362.3679 | 871.0221 | 0 | 0 | 871.0221 | 7901.4 | 7901.4 | 0 | 0 | 7901.4 | 7901.4 | 0 | 0
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 38 | 12.73 | 12.73 | 0 | 0 | 5 | 5 | 0 | 0 | 7.1166 | 7.1166 | 0 | 0 | 5.1534 | 5.1534 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 0
26 | 3111332 | b) Interim Evaluation | 39 | 1.29 | 1.29 | 0 | 0 | 1 | 1 | 0 | 0 | 7.71 | 7.71 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
27 | 3111332 | c) Progress Monitoring | 40 | 1.3 | 1.3 | 0 | 0 | 1 | 1 | 0 | 0 | 4.774 | 4.774 | 0 | 0 | 2.926 | 2.926 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
28 | 3257104 | Survey | 41 | 85.02 | 85.02 | 0 | 0 | 50 | 50 | 0 | 0 | 37.0386 | 37.0386 | 0 | 0 | 27.9414 | 27.9414 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 200 | 5.6843e-14 | 5.6843e-14
29 | 3255101 | Computer Consumables | 42 | 20.47 | 20.47 | 0 | 0 | 10 | 10 | 0 | 0 | 16.2415 | 16.2415 | 0 | 0 | 13.2885 | 13.2885 | 0 | 0 | 60 | 60 | 60 | 0 | 0 | 60 | 0 | 0
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 43 | 875.46 | 875.46 | 0 | 0 | 300 | 300 | 0 | 0 | 298.9878 | 298.9878 | 0 | 0 | 225.5522 | 225.5522 | 0 | 0 | 1700 | 1700 | 1700 | 0 | 0 | 1700 | 0 | 0
31 | 3258101 | Motor Vehicles | 45 | 61.4 | 61.4 | 0 | 0 | 15 | 15 | 0 | 0 | 26.73 | 26.73 | 0 | 0 | 21.87 | 21.87 | 0 | 0 | 125 | 125 | 125 | 0 | 0 | 125 | 0 | 0
32 | 3258102 | Furnitures & Fixtures | 46 | 3.2 | 3.2 | 0 | 0 | 2 | 2 | 0 | 0 | 2.88 | 2.88 | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
33 | 3258103 | Computers & office equipments | 47 | 5.34 | 5.34 | 0 | 0 | 3 | 3 | 0 | 0 | 3.9294 | 3.9294 | 0 | 0 | 2.7306 | 2.7306 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
34 | 3258105 | Machineries & Equipments | 48 | 1.22 | 1.22 | 0 | 0 | 2 | 2 | 0 | 0 | 4.1358 | 4.1358 | 0 | 0 | 2.6442 | 2.6442 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
35 | 3258107 | Office Building : Repair & Maintenance | 49 | 19.98 | 19.98 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9618 | 2.9618 | 0 | 0 | 2.0582 | 2.0582 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 25 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | 50 | 14.53 | 14.53 | 0 | 0 | 5 | 5 | 0 | 0 | 11.8726 | 11.8726 | 0 | 0 | 8.5974 | 8.5974 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
37 | 3258105 | Engineering Equipments | 51 | 1.39 | 1.39 | 0 | 0 | 2 | 2 | 0 | 0 | 9.1355 | 9.1355 | 0 | 0 | 7.4745 | 7.4745 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 53 | 95.03 | 10.83 | 84.2 | 0 | 58.25 | 8.5744 | 49.6756 | 0 | 88.8678 | 13.0813 | 75.7865 | 0 | 52.1922 | 7.6827 | 44.5095 | 0 | 294.34 | 294.34 | 40.1684 | 254.1716 | 0 | 294.34 | 0 | -5.6843e-14
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 54 | 2.39 | 2.39 | 0 | 0 | 0.75 | 0.75 | 0 | 0 | 1.1346 | 1.1346 | 0 | 0 | 0.7254 | 0.7254 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | -8.8818e-16 | -8.8818e-16
40 | 3258107 | Others : Repair & Maintenance | 55 | 7.48 | 7.48 | 0 | 0 | 3 | 3 | 0 | 0 | 16.5312 | 16.5312 | 0 | 0 | 12.9888 | 12.9888 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 60 | 606.9 | 606.9 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702.5 | 702.5 | 702.5 | 0 | 0 | 702.5 | 0 | 0
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 61 | 50.22 | 50.22 | 0 | 0 | 0 | 0 | 0 | 0 | 18.03 | 18.03 | 0 | 0 | 0 | 0 | 0 | 0 | 68.25 | 68.25 | 68.25 | 0 | 0 | 68.25 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 63 | 61.29 | 61.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 62 | 62 | 0 | 0 | 62 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 8.95 | 8.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 8.97 | 8.97 | 8.97 | 0 | 0 | 8.97 | 1.7764e-15 | 1.7764e-15
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 66 | 0.796 | 0.796 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.006 | 1.006 | 0 | 0 | 1.006 | -0.006 | -0.006
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 68 | 20.18 | 20.18 | 0 | 0 | 0 | 0 | 0 | 0 | 40.32 | 40.32 | 0 | 0 | 0 | 0 | 0 | 0 | 60.5 | 60.5 | 60.5 | 0 | 0 | 60.5 | 0 | 0
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 69 | 2.13 | 2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87 | 0.87 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 70 | 9.49 | 9.49 | 0 | 0 | 5 | 5 | 0 | 0 | 35.51 | 35.51 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 0
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 72 | 19.47 | 19.47 | 0 | 0 | 0 | 0 | 0 | 0 | 5.03 | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 | 24.5 | 24.5 | 24.5 | 0 | 0 | 24.5 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 73 | 9.88 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 3.87 | 3.87 | 0 | 0 | 0 | 0 | 0 | 0 | 13.75 | 13.75 | 13.75 | 0 | 0 | 13.75 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 nos ( PMO) | 74 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 75 | 4.08 | 4.08 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 5.25 | 5.25 | 0 | 0 | 5.25 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | 76 | 45.32 | 45.32 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9016 | 2.9016 | 0 | 0 | 1.7784 | 1.7784 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 0
54 | 4112303 | Aircooler | 77 | 9.73 | 9.73 | 0 | 0 | 4 | 4 | 0 | 0 | 0.7747 | 0.7747 | 0 | 0 | 0.4953 | 0.4953 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | 79 | 14323.6 | 14323.6 | 0 | 0 | 2049.42 | 2049.42 | 0 | 0 | 5626.98 | 5626.98 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 22000 | 0 | 0 | 22000 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 82 | 116.72 | 16.34 | 100.38 | 0 | 490.33 | 68.6462 | 421.6838 | 0 | 333.575 | 46.7005 | 286.8745 | 0 | 272.925 | 38.2095 | 234.7155 | 0 | 1213.55 | 1213.55 | 169.8962 | 1043.6538 | 0 | 1213.55 | 0 | -2.2737e-13
57 | 4111307 | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778.7382 | 109.0233 | 669.7149 | 0 | 497.8818 | 69.7035 | 428.1783 | 0 | 1276.62 | 1276.62 | 178.7268 | 1097.8932 | 0 | 1276.62 | 0 | 0
58 | 4111307 | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 85 | 6143.66 | 889.49 | 5254.17 | 0 | 8105.58 | 1134.7812 | 6970.7988 | 0 | 2229.3609 | 312.1105 | 1917.2504 | 0 | 1425.3291 | 199.5461 | 1225.783 | 0 | 17903.93 | 17903.93 | 2535.9278 | 15368.0022 | 0 | 17903.93 | 0 | 0
59 | 4111307 | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | 86 | 6011.48 | 791.08 | 5220.4 | 0 | 3936.68 | 551.1352 | 3385.5448 | 0 | 83.2996 | 11.6619 | 71.6377 | 0 | 60.3204 | 8.4449 | 51.8755 | 0 | 10091.78 | 10091.78 | 1362.322 | 8729.458 | 0 | 10091.78 | 0 | 0
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | 88 | 455.04 | 64.36 | 390.68 | 0 | 900.73 | 126.1022 | 774.6278 | 0 | 1020.3057 | 142.8428 | 877.4629 | 0 | 769.7043 | 107.7586 | 661.9457 | 0 | 3145.78 | 3145.78 | 441.0636 | 2704.7164 | 0 | 3145.78 | 4.5475e-13 | 0
61 | 4111201 | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | 89 | 452.46 | 63.49 | 388.97 | 0 | 913.26 | 127.8564 | 785.4036 | 0 | 181.9668 | 25.4754 | 156.4914 | 0 | 137.2732 | 19.2182 | 118.055 | 0 | 1684.96 | 1684.96 | 236.04 | 1448.92 | 0 | 1684.96 | 0 | 2.2737e-13
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | 90 | 341.85 | 48.84 | 293.01 | 0 | 657.55 | 92.057 | 565.493 | 0 | 358.2621 | 50.1567 | 308.1054 | 0 | 210.4079 | 29.4571 | 180.9508 | 0 | 1568.07 | 1568.07 | 220.5108 | 1347.5592 | 0 | 1568.07 | 0 | 2.2737e-13
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 91 | 6127.06 | 779.02 | 5348.04 | 0 | 4650.77 | 651.1078 | 3999.6622 | 0 | 3506.5118 | 490.9117 | 3015.6001 | 0 | 2241.8682 | 313.8615 | 1928.0067 | 0 | 16526.21 | 16526.21 | 2234.901 | 14291.309 | 0 | 16526.21 | -3.638e-12 | 0
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 92 | 73.26 | 9.77 | 63.49 | 0 | 0 | 0 | 0 | 0 | 50.1332 | 7.0186 | 43.1146 | 0 | 30.7268 | 4.3018 | 26.425 | 0 | 154.12 | 154.12 | 21.0904 | 133.0296 | 0 | 154.12 | 0 | 0
65 | 4111201 | Threshing Floor Construction | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 76.86 | 472.14 | 0 | 351 | 49.14 | 301.86 | 0 | 900 | 900 | 126 | 774 | 0 | 900 | 0 | 0
66 | 4111201 | Construction of WMG Office | 94 | 42.09 | 5.47 | 36.62 | 0 | 348.14 | 48.7396 | 299.4004 | 0 | 1008.7643 | 141.227 | 867.5373 | 0 | 701.0057 | 98.1408 | 602.8649 | 0 | 2100 | 2100 | 293.5774 | 1806.4226 | 0 | 2100 | 0 | 0
67 | 4111201 | O & M during Construction | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 47.88 | 294.12 | 0 | 258 | 36.12 | 221.88 | 0 | 600 | 600 | 84 | 516 | 0 | 600 | 0 | 0
68 | 0 | (c) Physical Contingency ( Lump sum): | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.54 | 162.54 | 0 | 0 | 95.46 | 95.46 | 0 | 0 | 258 | 258 | 258 | 0 | 0 | 258 | 0 | 0
69 | 0 | (d) Price Contingency (Lump sum): | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.177 | 221.177 | 0 | 0 | 180.963 | 180.963 | 0 | 0 | 402.14 | 402.14 | 402.14 | 0 | 0 | 402.14 | 0 | 0

## Civil_Works_Cost
| Code | Description | rindex | unit | Quantity | GOB | RPA | DPA | TOTAL | Unitcost | Tindex
0 | 4111306 | Construction of Irrigation Inlet (New Haors) | 58 | Nos | 127 | 169.897 | 1043.653 | 0 | 1213.55 | 9.5555 | 2
1 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 59 | Nos | 5 | 178.7268 | 1097.8932 | 0 | 1276.62 | 255.324 | 3
2 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 60 | Nos | 114 | 2506.5502 | 15397.3798 | 0 | 17903.93 | 157.052 | 4
3 | 4111307 | Re-excavation of Khal/River (New Haors) | 61 | Km | 342.584 | 1412.8492 | 8678.9308 | 0 | 10091.78 | 29.4578 | 5
4 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 62 | Km | 108.974 | 440.4092 | 2705.3708 | 0 | 3145.78 | 28.8673 | 6
5 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 63 | Km | 67.11 | 235.8944 | 1449.0656 | 0 | 1684.96 | 25.1074 | 7
6 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 64 | Km | 57.912 | 219.5298 | 1348.5402 | 0 | 1568.07 | 27.0768 | 8
7 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 65 | Km | 254.207 | 2313.6694 | 14212.5406 | 0 | 16526.21 | 65.0108 | 9
8 | 4111201 | Rehabilitation of Regulator (New Haors) | 66 | Nos | 7 | 21.5768 | 132.5432 | 0 | 154.12 | 22.0171 | 10
9 | 4111201 | Threshing Floor Construction | 67 | Nos | 20 | 126 | 774 | 0 | 900 | 45 | 11
10 | 4111201 | Construction of WMG Office | 68 | Nos | 60 | 294 | 1806 | 0 | 2100 | 35 | 12
11 | 3258114 | Gate Repair By M&E | 40 | Nos | 86 | 41.2076 | 253.1324 | 0 | 294.34 | 3.4226 | 13
12 | 4111201 | O&M During Construction | 69 | LS | 1 | 600 | 0 | 0 | 600 | 600 | 14

## Code-wise-comaprison
| Code | Description | Quantity_1st | GOB_1st | RPA_1st | DPA_1st | TOTAL_1st | rindex | Quantity_2nd | GOB_2nd | RPA_2nd | DPA_2nd | TOTAL_2nd | Quantity_diff | GOB_Diff | RPA_diff | DPA_diff | TOTAL_diff | Tindex | annex2_input_index | annex9_input_index | UintCost | units | Distribution _code
0 | 3111302 | Conveyance Allowance | 0 | 10 | 0 | 0 | 10 | 12 | 0 | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 2 | 2 | 2 | 5 |  | 1
1 | 3111327 | Overtime Allowance | 0 | 10 | 0 | 0 | 10 | 13 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 10 |  | 1
2 | 3111338 | Other Allowance | 0 | 140 | 0 | 0 | 140 | 14 | 0 | 140 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 140 |  | 1
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 0 | 100 | 0 | 0 | 100 | 16 | 0 | 120 | 0 | 0 | 120 | 0 | 20 | 0 | 0 | 20 | 5 | 5 | 5 | 120 |  | 1
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 0 | 245 | 0 | 0 | 245 | 17 | 0 | 245 | 0 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 245 |  | 1
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 0 | 2596.27 | 0 | 0 | 2596.27 | 18 | 0 | 2596.27 | 0 | 0 | 2596.27 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 2596.27 |  | 1
6 | 3211119 | Postage | 0 | 25 | 0 | 0 | 25 | 19 | 0 | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 8 | 8 | 8 | 5 |  | 1
7 | 3211120 | Telephones/Telegram/Teleprinter | 0 | 25 | 0 | 0 | 25 | 20 | 0 | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 9 | 9 | 9 | 5 |  | 1
8 | 3211117 | Telex/Fax/Internet | 0 | 25 | 0 | 0 | 25 | 21 | 0 | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 10 | 10 | 10 | 5 |  | 1
9 | 3221104 | Registration Fee (Vehicles) | 0 | 15 | 0 | 0 | 15 | 22 | 0 | 20 | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 5 | 11 | 11 | 11 | 20 |  | 1
10 | 3211115 | Water | 0 | 10 | 0 | 0 | 10 | 23 | 0 | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 12 | 12 | 12 | 5 |  | 1
11 | 3211113 | Electricity | 0 | 15 | 0 | 0 | 15 | 24 | 0 | 20 | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 5 | 13 | 13 | 13 | 20 |  | 1
12 | 3243102 | Gas & Fuel | 0 | 200 | 0 | 0 | 200 | 25 | 0 | 100 | 0 | 0 | 100 | 0 | -100 | 0 | 0 | -100 | 14 | 14 | 14 | 100 |  | 2
13 | 3243101 | Petrol and Lubricant | 0 | 150 | 0 | 0 | 150 | 26 | 0 | 200 | 0 | 0 | 200 | 0 | 50 | 0 | 0 | 50 | 15 | 15 | 15 | 200 |  | 2
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 0 | 3 | 0 | 0 | 3 | 27 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 3 |  | 1
15 | 3255102 | Printing & Binding | 0 | 35 | 0 | 0 | 35 | 28 | 0 | 50 | 0 | 0 | 50 | 0 | 15 | 0 | 0 | 15 | 17 | 17 | 17 | 50 |  | 1
16 | 3255104 | Stationery, Seals & Stamps | 0 | 150 | 0 | 0 | 150 | 29 | 0 | 120 | 0 | 0 | 120 | 0 | -30 | 0 | 0 | -30 | 18 | 18 | 18 | 120 |  | 1
17 | 3211127 | Books & Periodicals | 0 | 2 | 0 | 0 | 2 | 30 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19 | 2 |  | 1
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 0 | 0 | 238.54 | 0 | 238.54 | 32 | 0 | 238.54 | 0 | 0 | 238.54 | 0 | 238.54 | -238.54 | 0 | 0 | 20 | 20 | 20 | 238.54 |  | 3
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 0 | 47.81 | 350.6 | 0 | 398.41 | 33 | 0 | 64.39 | 472.19 | 0 | 536.58 | 0 | 16.58 | 121.59 | 0 | 138.17 | 21 | 21 | 21 | 536.58 |  | 3
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 0 | 304 | 2229.34 | 0 | 2533.34 | 34 | 0 | 375.07 | 2764.73 | 0 | 3139.8 | 0 | 71.07 | 535.39 | 0 | 606.46 | 22 | 22 | 22 | 3139.8 |  | 3
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 0 | 158.6 | 1163.08 | 0 | 1321.68 | 35 | 0 | 158.6 | 1163.08 | 0 | 1321.68 | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 23 | 1321.68 |  | 3
22 | 3211109 | Casual labour/Job worker | 0 | 15 | 0 | 0 | 15 | 36 | 0 | 22 | 0 | 0 | 22 | 0 | 7 | 0 | 0 | 7 | 24 | 24 | 24 | 22 |  | 1
23 | 3256103 | Consumable Stores | 0 | 25 | 0 | 0 | 25 | 37 | 0 | 15 | 0 | 0 | 15 | 0 | -10 | 0 | 0 | -10 | 25 | 25 | 25 | 15 |  | 1
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | 71+234 | 0 | 0 | 7901.4 | 7901.4 | 38 | 71+234 | 0 | 0 | 7901.4 | 7901.4 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 26 | 0 |  | 4
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 0 | 25 | 0 | 0 | 25 | 39 | 0 | 30 | 0 | 0 | 30 | 0 | 5 | 0 | 0 | 5 | 27 | 27 | 27 | 30 |  | 1
26 | 3111332 | b) Interim Evaluation | 0 | 10 | 0 | 0 | 10 | 40 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 28 | 10 |  | 1
27 | 3111332 | c) Progress Monitoring | 0 | 10 | 0 | 0 | 10 | 41 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 29 | 10 |  | 1
28 | 3257104 | Survey | 0 | 162 | 0 | 0 | 162 | 42 | 0 | 200 | 0 | 0 | 200 | 0 | 38 | 0 | 0 | 38 | 30 | 30 | 30 | 200 |  | 1
29 | 3255101 | Computer Consumables | 0 | 50 | 0 | 0 | 50 | 43 | 0 | 60 | 0 | 0 | 60 | 0 | 10 | 0 | 0 | 10 | 31 | 31 | 31 | 60 |  | 1
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 0 | 1700 | 0 | 0 | 1700 | 44 | 0 | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 1700 |  | 1
31 | 3258101 | Motor Vehicles | 0 | 100 | 0 | 0 | 100 | 46 | 0 | 125 | 0 | 0 | 125 | 0 | 25 | 0 | 0 | 25 | 33 | 33 | 33 | 125 |  | 5
32 | 3258102 | Furnitures & Fixtures | 0 | 15 | 0 | 0 | 15 | 47 | 0 | 10 | 0 | 0 | 10 | 0 | -5 | 0 | 0 | -5 | 34 | 34 | 34 | 10 |  | 5
33 | 3258103 | Computers & office equipments | 0 | 25 | 0 | 0 | 25 | 48 | 0 | 15 | 0 | 0 | 15 | 0 | -10 | 0 | 0 | -10 | 35 | 35 | 35 | 15 |  | 5
34 | 3258105 | Machineries & Equipments | 0 | 25 | 0 | 0 | 25 | 49 | 0 | 10 | 0 | 0 | 10 | 0 | -15 | 0 | 0 | -15 | 36 | 36 | 36 | 10 |  | 5
35 | 3258107 | Office Building : Repair & Maintenance | 0 | 20 | 0 | 0 | 20 | 50 | 0 | 25 | 0 | 0 | 25 | 0 | 5 | 0 | 0 | 5 | 37 | 37 | 37 | 25 |  | 5
36 | 3258106 | Residential Building : Repair & Maintenance | 0 | 20 | 0 | 0 | 20 | 51 | 0 | 40 | 0 | 0 | 40 | 0 | 20 | 0 | 0 | 20 | 38 | 38 | 38 | 40 |  | 5
37 | 3258105 | Engineering Equipments | 0 | 25 | 0 | 0 | 25 | 52 | 0 | 20 | 0 | 0 | 20 | 0 | -5 | 0 | 0 | -5 | 39 | 39 | 39 | 20 |  | 5
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 0 | 43.5 | 319 | 0 | 362.5 | 54 | 86 | 41.2076 | 253.1324 | 0 | 294.34 | 0 | -2.2924 | -65.8676 | 0 | -68.16 | 40 | 40 | 40 | 294.34 |  | 8
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 0 | 10 | 0 | 0 | 10 | 55 | 0 | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 41 | 41 | 41 | 5 |  | 5
40 | 3258107 | Others : Repair & Maintenance | 0 | 25 | 0 | 0 | 25 | 56 | 0 | 40 | 0 | 0 | 40 | 0 | 15 | 0 | 0 | 15 | 42 | 42 | 42 | 40 |  | 5
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 10 | 702.5 | 0 | 0 | 702.5 | 68 | 10 | 702.5 | 0 | 0 | 702.5 | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 43 | 70.25 |  | 6
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 35 | 68.25 | 0 | 0 | 68.25 | 69 | 45 | 68.25 | 0 | 0 | 68.25 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 1.52 |  | 6
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 4 Nos.) | 6 | 100 | 0 | 0 | 100 | 71 | 4 | 62 | 0 | 0 | 62 | 0 | -38 | 0 | 0 | -38 | 45 | 45 | 45 | 15.5 |  | 6
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 7 | 8.97 | 0 | 0 | 8.97 | 73 | 7 | 8.97 | 0 | 0 | 8.97 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 46 | 1.28 |  | 6
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 7 | 5 | 0 | 0 | 5 | 74 | 7 | 1 | 0 | 0 | 1 | 0 | -4 | 0 | 0 | -4 | 47 | 47 | 47 | 0.14 |  | 6
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos,RTK GPS with Base and Rover Station 1 set) | 17 | 20.5 | 0 | 0 | 20.5 | 76 | 17 | 60.5 | 0 | 0 | 60.5 | 0 | 40 | 0 | 0 | 40 | 48 | 48 | 48 | 60.5 |  | 6
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 | 6 | 0 | 0 | 6 | 77 | 6 | 3 | 0 | 0 | 3 | 0 | -3 | 0 | 0 | -3 | 49 | 49 | 49 | 0.5 |  | 6
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | L.S | 50 | 0 | 0 | 50 | 78 | L.S | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 |  | 6
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 30 | 19.5 | 0 | 0 | 19.5 | 80 | 37 | 24.5 | 0 | 0 | 24.5 | 0 | 5 | 0 | 0 | 5 | 51 | 51 | 51 | 0.66 |  | 6
50 | 4112202 | Laptop Computer -16 nos (PMO 7 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No,Chief Water Management 1 No) | 11 | 13.75 | 0 | 0 | 13.75 | 81 | 16 | 13.75 | 0 | 0 | 13.75 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 0.86 |  | 6
51 | 4112202 | A3 Combo Printer 5 no ( PMO) | 2 | 1.5 | 0 | 0 | 1.5 | 82 | 5 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 53 | 0.3 |  | 6
52 | 4112202 | Laser Printer- 14 nos. (PMO 9 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 11 | 5.25 | 0 | 0 | 5.25 | 83 | 14 | 5.25 | 0 | 0 | 5.25 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 54 | 0.38 |  | 6
53 | 4112314 | Furnitures & Fixtures | LS | 50 | 0 | 0 | 50 | 84 | LS | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 50 |  | 6
54 | 4112303 | Aircooler | 15 | 15 | 0 | 0 | 15 | 85 | 15 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 56 | 1 |  | 6
55 | 4141101 | Land Acquisition ( 470 hectare) | 470 | 24000 | 0 | 0 | 24000 | 87 | 470 | 22000 | 0 | 0 | 22000 | 0 | -2000 | 0 | 0 | -2000 | 57 | 57 | 57 | 46.81 |  | 7
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 131 | 151.32 | 1109.68 | 0 | 1261 | 90 | 127 | 169.897 | 1043.653 | 0 | 1213.55 | 0 | 18.577 | -66.027 | 0 | -47.45 | 58 | 58 | 58 | 9.56 |  | 8
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 7(2+5) | 181.8 | 1333.2 | 0 | 1515 | 92 | 5 | 178.7268 | 1097.8932 | 0 | 1276.62 | 0 | -3.0732 | -235.3068 | 0 | -238.38 | 59 | 59 | 59 | 255.32 |  | 8
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 137(57+35+14) | 2437.32 | 17873.68 | 0 | 20311 | 93 | 114 | 2506.5502 | 15397.3798 | 0 | 17903.93 | 0 | 69.2302 | -2476.3002 | 0 | -2407.07 | 60 | 60 | 60 | 157.05 |  | 8
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 318 | 1167.48 | 8561.52 | 0 | 9729 | 94 | 342.584 | 1412.8492 | 8678.9308 | 0 | 10091.78 | 0 | 245.3692 | 117.4108 | 0 | 362.78 | 61 | 61 | 61 | 29.46 |  | 8
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 143 | 301.8 | 2213.2 | 0 | 2515 | 96 | 108.974 | 440.4092 | 2705.3708 | 0 | 3145.78 | 0 | 138.6092 | 492.1708 | 0 | 630.78 | 62 | 62 | 62 | 28.87 |  | 8
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 84.31 | 306 | 2244 | 0 | 2550 | 97 | 67.11 | 235.8944 | 1449.0656 | 0 | 1684.96 | 0 | -70.1056 | -794.9344 | 0 | -865.04 | 63 | 63 | 63 | 25.11 |  | 8
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 87.03 | 214.2 | 1570.8 | 0 | 1785 | 98 | 57.912 | 219.5298 | 1348.5402 | 0 | 1568.07 | 0 | 5.3298 | -222.2598 | 0 | -216.93 | 64 | 64 | 64 | 27.08 |  | 8
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 263.24 | 1434.3 | 10518.2 | 0 | 11952.5 | 12515.6856 | 254.207 | 4527.399 | 11998.811 | 0 | 16526.21 | 0 | 3093.099 | 1480.611 | 0 | 4573.71 | 65 | 65 | 65 | 0 |  | 8
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 8 | 19.92 | 146.08 | 0 | 166 | 100 | 7 | 21.5768 | 132.5432 | 0 | 154.12 | 0 | 1.6568 | -13.5368 | 0 | -11.88 | 66 | 66 | 66 | 22.02 |  | 8
65 | 4111201 | Threshing Floor Construction | 0 | 0 | 0 | 0 | 0 | 101 | 20 | 126 | 774 | 0 | 900 | 0 | 126 | 774 | 0 | 900 | 67 | 67 | 67 | 45 |  | 8
66 | 4111201 | Construction of WMG Office | 60 | 165.6 | 1214.4 | 0 | 1380 | 102 | 60 | 294 | 1806 | 0 | 2100 | 0 | 128.4 | 591.6 | 0 | 720 | 68 | 68 | 68 | 35 |  | 8
67 | 4111201 | O&M During Construction | L.S | 200 | 0 | 0 | 200 | 103 | 2 | 600 | 0 | 0 | 600 | 0 | 400 | 0 | 0 | 400 | 69 | 69 | 69 | 0 |  | 8
68 |  | (c) Physical Contingency ( Lump sum): | 0 | 100 | 158 | 0 | 258 | 106 | 0 | 100 | 158 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 70 | 0 |  | 9
69 |  | (d) Price Contingency (Lump sum): | 0 | 100.76 | 301.38 | 0 | 402.14 | 107 | 0 | 100.76 | 301.38 | 0 | 402.14 | 0 | 0 | 0 | 0 | 0 | 71 | 71 | 71 | 0 |  | 9