## DPP_ALLOC
Code | Description | Imed_Code | GOB | RPA | DPA | TOTAL
3111302 | Conveyance Allowance | REV_1 | 10 |  |  | 10
3111327 | Overtime Allowance | REV_1 | 10 |  |  | 10
3111338 | Other Allowance | REV_1 | 140 |  |  | 140
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 100 |  |  | 100
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 245 |  |  | 245
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 2596.27 |  |  | 2596.27
3211119 | Postage | REV_5 | 25 |  |  | 25
3211120 | Telephones/Telegram/Teleprinter | REV_5 | 25 |  |  | 25
3211117 | Telex/Fax/Internet | REV_5 | 25 |  |  | 25
3221104 | Registration Fee (Vehicles) | REV_6 | 15 |  |  | 15
3211115 | Water | REV_7 | 10 |  |  | 10
3211113 | Electricity | REV_7 | 15 |  |  | 15
3243102 | Gas & Fuel | REV_8 | 200 |  |  | 200
3243101 | Petrol and Lubricant | REV_8 | 150 |  |  | 150
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 3 |  |  | 3
3255102 | Printing & Binding | REV_10 | 35 |  |  | 35
3255104 | Stationery, Seals & Stamps | REV_11 | 150 |  |  | 150
3211127 | Books & Periodicals | REV_12 | 2 |  |  | 2
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 |  | 238.54 |  | 238.54
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 47.81 | 350.6 |  | 398.41
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 304 | 2229.34 |  | 2533.34
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 158.6 | 1163.08 |  | 1321.68
3211109 | Casual labour/Job worker | REV_15 | 15 |  |  | 15
3256103 | Consumable Stores | REV_16 | 25 |  |  | 25
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 |  |  | 7901.4 | 7901.4
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 25 |  |  | 25
| b) Interim Evaluation | REV_18 | 10 |  |  | 10
| c) Progress Monitoring | REV_18 | 10 |  |  | 10
3257104 | Survey | REV_19 | 162 |  |  | 162
3255101 | Computer Consumables | REV_20 | 50 |  |  | 50
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 1700 |  |  | 1700
3258101 | Motor Vehicles | REV_22 | 100 |  |  | 100
3258102 | Furnitures & Fixtures | REV_22 | 15 |  |  | 15
3258103 | Computers & office equipments | REV_22 | 25 |  |  | 25
3258105 | Machineries & Equipments | REV_22 | 25 |  |  | 25
3258107 | Office Building : Repair & Maintenance | REV_22 | 20 |  |  | 20
3258106 | Residential Building : Repair & Maintenance | REV_22 | 20 |  |  | 20
3258105 | Engineering Equipments | REV_22 | 25 |  |  | 25
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 43.5 | 319 |  | 362.5
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 10 |  |  | 10
3258107 | Others : Repair & Maintenance | REV_22 | 25 |  |  | 25
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 702.5 |  |  | 702.5
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 68.25 |  |  | 68.25
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 100 |  |  | 100
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 8.97 |  |  | 8.97
| Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 5 |  |  | 5
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 20.5 |  |  | 20.5
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 6 |  |  | 6
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 50 |  |  | 50
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 19.5 |  |  | 19.5
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 13.75 |  |  | 13.75
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 1.5 |  |  | 1.5
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 5.25 |  |  | 5.25
4112314 | Furnitures & Fixtures | CAP_6 | 50 |  |  | 50
4112303 | Aircooler | CAP_6 | 15 |  |  | 15
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 24000 |  |  | 24000
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 151.32 | 1109.68 |  | 1261
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 181.8 | 1333.2 |  | 1515
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 2437.32 | 17873.68 |  | 20311
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 1167.48 | 8561.52 |  | 9729
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 301.8 | 2213.2 |  | 2515
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 306 | 2244 |  | 2550
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 214.2 | 1570.8 |  | 1785
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 1434.3 | 10518.2 |  | 11952.5
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 19.92 | 146.08 |  | 166
4111201 | Construction of WMG Office | CAP_8 | 165.6 | 1214.4 |  | 1380
4111201 | O&M During Construction | CAP_8 | 200 | 0 |  | 200
XXXXX1 | Physical Contingency | C | 100 | 158 | 0 | 258
XXXXX2 | Price Contingency | D | 100.76 | 301.38 | 0 | 402.14

## Modified
fvZvw` |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
1 | 3111302 (4765) | hvZvqvZ | 1 |  | 1190 | 2980 | 3100 | 2350 | 900 | 2990 | 3000 | 3200 | 3200 | 4540 | 2550 | 30000 | 0.3
|  | Overtime Allowance | 2
2 | 3111338 (4795) | Ab¨vb¨ fvZv | 3 |  |  | 187532 | 166152 | 25290 | 71716 | 124531 | 100593 | 1755 | 162524 | 99783 | 221164 | 1161040 | 11.6104
3 | 3241101 (4801) | ågY e¨q | 4 |  | 22050 | 21000 | 210353 | 95660 | 103704 | 51075 | 163847 | 41460 | 31950 | 108809 | 319053 | 1168961 | 11.6896
4 | 3211129 (4806) | Awdm fvovi Rb¨ | 5 |  | 570140 | 285070 | 285070 | 285070 | 285070 | 285070 | 285070 | 285070 | 285070 | 285070 | 285070 | 3420840 | 34.2084
5 | 3821103 (4814) | Ab¨vb¨ Ki | 6 |  | 1011737 | 427396 | 613578 | 666447 | 422336 | 4909127.35 | 2558511.49 | 683323 | 487785 | 5164536.74 | 8315140.07 | 25259917.65 | 252.5992
6 | 3211119 (4815) | WvK †hvMv‡hvM | 7 |  | 4600 | 4042 | 2599 | 4445 | 2415 | 3571 | 316 | 575 | 799 | 2473 | 11224 | 37059 | 0.37059
7 | 3211120 (4816) | ‡Uwj‡dvb/†UwjMÖvg/†UwjwcÖ›Uvi | 8 | Aug: 1070; Sep: 2536; Feb: 3596; May: 2052 | 9254 | 0.09254
8 | 3211117 (4817) | ‡U‡j·/d¨v·/B›Uvi‡bU | 9 | Sep: 2782; Jan: 1070 | 3852 | 0.03852
9 | 3221108 (4818) | Mvoxi †iwRt wd | 10 | Sep: 130000; Dec: 149505; Jun: 67600 | 347105 | 3.471
10 | 3211115 (4819) | cvwb | 11 |  |  | 9437 | 2840 | 3218 |  | 6654 | 3570 |  | 7141 | 3895 | 4003 | 40758 | 0.40758
11 | 3211113 (4821) | we`y¨r | 12 |  |  | 84107 | 31511 | 24703 |  | 29239 | 11604 |  | 29639 | 32759 | 33610 | 277172 | 2.7717
12 | 3243102 (4822) | M¨vm I R¡vjvbx | 13 |  | 25607 | 78383 | 24502 | 26619 | 24783 | 112989 | 23263 | 12947 | 70736 | 23959 | 118726 | 542514 | 5.4251
13 | 3243101 (4823) | ‡cUªj Ges jyweª‡K›U | 14 |  |  | 322021 | 300217 | 99107 | 152572 | 168772 | 259167 | 99052 | 162103 | 128387 | 299064 | 1990462 | 19.9046
14 | 3221108 (4824) | BÝy‡iÝ/e¨vsK PvR© (Mvoxmn) | 15 | Aug: 7642; Nov: 414; Jan: 748; Feb: 1392 | 10196 | 0.10196
15 | 3255102 (4827) | wcÖw›Us Ges cvewj‡Kkb | 16 | Oct: 294870; Feb: 17700; Mar: 14040; May: 9945; Jun: 30420 | 366975 | 3.6698
16 | 3255104 (4828) | ‡÷kbvix wmj I ÷¨v¤ú | 17 |  | 45142 | 89929 | 52018 | 475223 | 48709 | 547334 | 101451 | 45925 | 25022 | 39055 | 65270 | 1535078 | 15.3508
17 | 3211127 (4831) | eBcÎ | 18 | Aug: 1049; Sep: 1616; Dec: 556; Jan: 255; Mar: 546; May: 503; Jun: 5383 | 9908 | 0.09908
18 | 3231201 (4840-1) | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 19 |  | 203182 | 1018536 | 1018411 | 1199977 | 1100843 | 1291269 | 425551 | 281018 | 652268 | 709568 | 1291838 | 9192461 | 91.9246
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 20
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 21
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 22
20 | 3211109 (4851) | Pzw³ wfwËK Kg©Pvix/Kvh© mnKvix | 23 |  |  | 120865 | 9200 | 46000 | 18400 | 18400 | 55200 |  | 64400 | 66700 | 25500 | 424665 | 4.2466
21 | 3256103 (4854) | KbwRD‡gej †÷vi | 24 | [12 empty] | 0 | 0
22 | 3257101 4874 | civgk©K †mev | 25 | [12 empty] | 0 | 0
|  | a) Honorarium/Fees/Remuneration (for different Committee) | 26
|  | b) Interim Evaluation | 27
23 | 3111332 (4883) | c) Progress Monitoring | 28 | Aug: 44996; Oct: 244800; Jan: 36000; Apr: 114400; Jun: 111600 | 551796 | 5.518
24 | 3257104 (4886) | mv‡f© | 29 | Jan: 920290; Feb: 1180921 | 2101211 | 21.0121
25 | 3255101 (4888) | Kw¤úDUvi KbwRD‡gej | 30 |  | 2467 | 159105 | 7020 | 109960 | 13910 | 346060 | 6955 | 4280 |  | 13910 | 100220 | 763887 | 7.6389
26 | 3256101 (4899) | Ab¨vb¨ e¨qt AvDU‡mvwm©s Rbe‡ji †eZb | 31 |  | 3244866 | 2108542 | 2426265 | 2494743 | 2114977 | 2349827.5 | 2377780 | 2562245 | 1780096 | 6038892 | 2494811 | 29993044.5 | 299.9304
27 | 3258101 (4901) | Mvox | 32 |  | 32770 | 135828 | 378388 | 120761 | 108513 | 233292 | 245919 | 29483 | 89692 | 31448 | 94361 | 1500455 | 15.0046
28 | 3258102 (4906) | AvmevecÎ | 33 | Sep: 6420; Nov: 18036; Feb: 8755; Apr: 5350; Jun: 10700 | 49261 | 0.49261
29 | 3258103 (4911) | Kw¤úDUvi I Awdm BKzBc‡g›Um | 34 |  | 13525 | 12075 | 6048 | 21474 | 1153 | 11942 | 24950 | 13910 | 13910 | 55162 | 255 | 174404 | 1.744
30 | 3258105 (4916) | ‡gwkbvix I BKzBc‡g›Um | 35 | Sep: 14338; Apr: 8111; Jun: 11289 | 33738 | 0.33738
31 | 3258107 (4921) | Awdm feb †givgZ I msi¶Y | 36 | Feb: 991329 | 991329 | 9.9133
32 | 3258106 (4923) | AvevwmK feb †givgZ I msi¶Y | 37 | Feb: 498316 | 498316 | 4.9832
33 | 3258105 (4932) | cÖ‡KŠkj BKzBc‡g›Um | 38 | Sep: 12840; Oct: 4860; Mar: 4280; Apr: 11235; Jun: 16692 | 49907 | 0.49907
36 | 4947-5 | ‡i¸‡jUi Gi †MU †givgZ I cwieZ©b (98wU) | 39 | [12 empty] | 0 | 0
37 | 3258128 (4976) | Rjhvbt ¯úxW‡evU †givgZ | 40 | [12 empty] | 0 | 0
38 | 3258107 (4991) | Ab¨vb¨t †givgZ I msi¶Y | 41 | Feb: 299446 | 299446 | 2.9945
39 | 4112101 (6807) | Mvoxt Rxc Mvox | 42 | [12 empty] | 0 | 0
40 | 4112101 (6807) | ‡gvUi mvB‡Kj | 43 | [12 empty] | 0 | 0
|  | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 44
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 45
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 46
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 47
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 48
41 | 4112304 (6814) | cÖ‡KŠkj BKzBc‡g›Um | 49 | [12 empty] | 0 | 0
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 50
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 51
|  | A3 Combo Printer 2 no ( PMO) | 52
|  | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 53
43 | 4112314 (6821) | AvmevecÎ msMÖn | 54 | Nov: 298000; Jan: 298700 | 596700 | 5.967
44 | 4112303 (6869) | GqviKzjvi | 55 | Jun: 100000 | 100000 | 1
45 | 4141101 (6901) | Rwg AwaMÖnY (470 †n±i) | 56 | Feb: 73052523.76; Jun: 314937476.24 | 387990000 | 3879.9
46 | 4111306 (7041) | Bwi‡Mkb Bb‡jU wbg©vY (bZzb nvIi) (131wU) | 57 | [12 empty] | 0 | 0
47 | 4111307 (7041-1) | †i¸‡jUi/KRI‡q cybt¯’vcb/wbg©vY (cybe©vmb Dc-cÖK‡í)(7wU) | 58 | [12 empty] | 0 | 0
48 | 4111307 (7041-5) | bZzb †i¸‡jUi/KRI‡q/eªxR/e· †Wª‡bR AvDU‡jU ¯’vcb/wbg©vY (bZzb nvIi) (137wU) | 59 | [12 empty] | 0 | 0
49 | 4111307 (7041-1) | Lvj cybtLbb (bZzb nvIi) 318.20 wKwg | 60 | Dec: 3024266; Jan: 6409950.01; Feb: 18129813.79; Mar: 18684853.86; Apr: 8693118.76; May: 18782497.47; Jun: 4042646.48 | 77767146.37 | 777.6715
50 | 4111201 | Lvj cybtLbb (cybe©vmb cybe©vmb Dc-cÖKí) 143.00 wKwg | 61 | Dec: 1725298.82; Jan: 10220826.42; Feb: 19965856.21; Mar: 10391217.06; Apr: 6847826.86; May: 1817779.46; Jun: 4390702.3 | 55359507.13 | 553.5951
51 |  | euva cybe©vmb (c~Y©) (cybe©vmb Dc-cÖKí) 84.31 wKtwgt | 62 | [12 empty] | 0 | 0
52 |  | euva cybe©vmb (Wzeš—) cybe©vmb Dc-cÖKí) 87.01 wKwg | 63 | [12 empty] | 0 | 0
53 |  | euva cybe©vmb (Wzeš—) (bZzb nvIi) 263.24 wKwg | 64 | [12 empty] | 0 | 0
54 |  | euva wbg©vY (Wzeš—) 342.30 wKwg | 65 | [12 empty] | 0 | 0
55 |  | †i¸‡jUi cybe©vmb (bZzb nvIi) (8wU) | 66 | [12 empty] | 0 | 0
56 |  | WMG Awdm wbg©vY (60wU) | 67 | [12 empty] | 0 | 0
|  | †gvU e¨qt |  |  | 5232033 | 5237380 | 6081802 | 6017497 | 9369626.82 | 28379982.28 | 120796396.25 | 33159179.92 | 19546376.62 | 33421723.67 | 337406368.09 | 604648365.65 | 6046.4837
| 1g wKw¯— | 275000000
| 2q wKw¯— | 275000000
| 3q wKw¯— | 109250000
4_© wKw¯—
|  | 659250000 | [13 empty] | 659250000
604648365.65
54601634.35
Note on M7: hp:Environent()

## Monthly_19_20_GOB
Code | Description | Imed_Code | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
3111302 | Conveyance Allowance | REV_1 | Aug: 4650; Sep: 5000; Oct: 5000; Nov: 5100
3111327 | Overtime Allowance | REV_1 | Oct: 0
3111338 | Other Allowance | REV_1 | Oct: 362147; Nov: 122607
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | Sep: 91434; Oct: 120270; Nov: 105930
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | Aug: 570140; Sep: 285070; Oct: 285070; Nov: 285070
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | Aug: 852263; Sep: 668538; Oct: 633392; Nov: 175528
3211119 | Postage | REV_5 | Aug: 1438; Sep: 1725; Oct: 1581
3211120 | Telephones/Telegram/Teleprinter | REV_5 | Sep: 6178; Oct: 0
3211117 | Telex/Fax/Internet | REV_5 | Sep: 2190; Oct: 0
3221104 | Registration Fee (Vehicles) | REV_6 | Sep: 0; Oct: 0
3211115 | Water | REV_7 | Aug: 2820; Sep: 6411; Oct: 0
3211113 | Electricity | REV_7 | Aug: 37257; Sep: 67934; Oct: 30428
3243102 | Gas & Fuel | REV_8 | Sep: 26648; Oct: 13820; Nov: 112742
3243101 | Petrol and Lubricant | REV_8 | Aug: 129500; Sep: 168858; Oct: 118371; Nov: 97513
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | Oct: 0
3255102 | Printing & Binding | REV_10 | Aug: 14000; Sep: 1404; Oct: 14625; Nov: 11700
3255104 | Stationery, Seals & Stamps | REV_11 | Aug: 49597; Sep: 329458; Oct: 5207; Nov: 333170
3211127 | Books & Periodicals | REV_12 | Aug: 575; Sep: 219; Oct: 1358; Nov: 5588
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | Oct: 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | Oct: 77343
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | Oct: 364148; Nov: 1010517
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | Oct: 0
3211109 | Casual labour/Job worker | REV_15 | Sep: 36800; Oct: 0; Nov: 51750
3256103 | Consumable Stores | REV_16 | Oct: 0
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | Oct: 0
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | Sep: 69575; Oct: 0
3111332 | b) Interim Evaluation | REV_18 | Oct: 0
3111332 | c) Progress Monitoring | REV_18 | Oct: 0
3257104 | Survey | REV_19 | Oct: 303360
3255101 | Computer Consumables | REV_20 | Aug: 13365; Sep: 240670; Oct: 316303; Nov: 28470
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | Aug: 3070966; Sep: 2043145; Oct: 2136764; Nov: 464684
3258101 | Motor Vehicles | REV_22 | Aug: 8468; Sep: 25598; Oct: 48488; Nov: 16096
3258102 | Furnitures & Fixtures | REV_22 | Oct: 0
3258103 | Computers & office equipments | REV_22 | Oct: 0
3258105 | Machineries & Equipments | REV_22 | Aug: 7642; Sep: 411; Oct: 16500; Nov: 3819
3258107 | Office Building : Repair & Maintenance | REV_22 | Oct: 0
3258106 | Residential Building : Repair & Maintenance | REV_22 | Oct: 0
3258105 | Engineering Equipments | REV_22 | Aug: 5650; Sep: 18886; Oct: 6570
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | Oct: 0; Nov: 28740
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | Oct: 0
3258107 | Others : Repair & Maintenance | REV_22 | Oct: 0
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | Oct: 0
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | Oct: 0
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | Oct: 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | Oct: 0
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | Oct: 0
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | Oct: 0
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | Oct: 0
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | Oct: 0
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | Oct: 0
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | Oct: 0
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | Oct: 0
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | Oct: 0
4112314 | Furnitures & Fixtures | CAP_6 | Oct: 0
4112303 | Aircooler | CAP_6 | Oct: 0
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | Oct: 0
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | Oct: 0
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | Oct: 0
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | Oct: 0
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | Oct: 0
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | Oct: 0
4111201 | Construction of WMG Office | CAP_8 | Oct: 0
4111201 | O&M During Construction | CAP_8 | Oct: 0
XXXXX1 | Physical Contingency | C
XXXXX2 | Price Contingency | D
Note on L7: hp:Environent()

## Monthly_19_20_RPA
Code | Description | Imed_Code | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
3111302 | Conveyance Allowance | REV_1
3111327 | Overtime Allowance | REV_1
3111338 | Other Allowance | REV_1
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4
3211119 | Postage | REV_5
3211120 | Telephones/Telegram/Teleprinter | REV_5
3211117 | Telex/Fax/Internet | REV_5
3221104 | Registration Fee (Vehicles) | REV_6
3211115 | Water | REV_7
3211113 | Electricity | REV_7
3243102 | Gas & Fuel | REV_8
3243101 | Petrol and Lubricant | REV_8
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9
3255102 | Printing & Binding | REV_10
3255104 | Stationery, Seals & Stamps | REV_11
3211127 | Books & Periodicals | REV_12
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | Oct: 592925
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | Oct: 2568938; Nov: 8237334
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | Oct: 0
3211109 | Casual labour/Job worker | REV_15
3256103 | Consumable Stores | REV_16
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18
3111332 | b) Interim Evaluation | REV_18
3111332 | c) Progress Monitoring | REV_18
3257104 | Survey | REV_19
3255101 | Computer Consumables | REV_20
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21
3258101 | Motor Vehicles | REV_22
3258102 | Furnitures & Fixtures | REV_22
3258103 | Computers & office equipments | REV_22
3258105 | Machineries & Equipments | REV_22
3258107 | Office Building : Repair & Maintenance | REV_22
3258106 | Residential Building : Repair & Maintenance | REV_22
3258105 | Engineering Equipments | REV_22
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22
3258128 | Water Transport : Repair of Speedboat(s) | REV_22
3258107 | Others : Repair & Maintenance | REV_22
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5
4112314 | Furnitures & Fixtures | CAP_6
4112303 | Aircooler | CAP_6
4141101 | Land Acquisition ( 470 hectare) | CAP_7
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8
4111201 | Construction of WMG Office | CAP_8
4111201 | O&M During Construction | CAP_8
XXXXX1 | Physical Contingency | C
XXXXX2 | Price Contingency | D

## Monthly_19_20_DPA
Code | Description | Imed_Code | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
3111302 | Conveyance Allowance | REV_1 | Aug: 0; Sep: 0; Oct: 0
3111327 | Overtime Allowance | REV_1 | Aug: 0; Sep: 0; Oct: 0
3111338 | Other Allowance | REV_1 | Aug: 0; Sep: 0; Oct: 0
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | Aug: 0; Sep: 0; Oct: 0
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | Aug: 0; Sep: 0; Oct: 0
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | Aug: 0; Sep: 0; Oct: 0
3211119 | Postage | REV_5 | Aug: 0; Sep: 0; Oct: 0
3211120 | Telephones/Telegram/Teleprinter | REV_5 | Aug: 0; Sep: 0; Oct: 0
3211117 | Telex/Fax/Internet | REV_5 | Aug: 0; Sep: 0; Oct: 0
3221104 | Registration Fee (Vehicles) | REV_6 | Aug: 0; Sep: 0; Oct: 0
3211115 | Water | REV_7 | Aug: 0; Sep: 0; Oct: 0
3211113 | Electricity | REV_7 | Aug: 0; Sep: 0; Oct: 0
3243102 | Gas & Fuel | REV_8 | Aug: 0; Sep: 0; Oct: 0
3243101 | Petrol and Lubricant | REV_8 | Aug: 0; Sep: 0; Oct: 0
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | Aug: 0; Sep: 0; Oct: 0
3255102 | Printing & Binding | REV_10 | Aug: 0; Sep: 0; Oct: 0
3255104 | Stationery, Seals & Stamps | REV_11 | Aug: 0; Sep: 0; Oct: 0
3211127 | Books & Periodicals | REV_12 | Aug: 0; Sep: 0; Oct: 0
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | Aug: 0; Sep: 0; Oct: 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | Aug: 0; Sep: 0; Oct: 0
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | Aug: 0; Sep: 0; Oct: 0
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | Aug: 0; Sep: 0; Oct: 0
3211109 | Casual labour/Job worker | REV_15 | Aug: 0; Sep: 0; Oct: 0
3256103 | Consumable Stores | REV_16 | Aug: 0; Sep: 0; Oct: 0
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | Aug: 0; Sep: 0; Oct: 13863000; Nov: 0
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | Aug: 0; Sep: 0; Oct: 0
3111332 | b) Interim Evaluation | REV_18 | Aug: 0; Sep: 0; Oct: 0
3111332 | c) Progress Monitoring | REV_18 | Aug: 0; Sep: 0; Oct: 0
3257104 | Survey | REV_19 | Aug: 0; Sep: 0; Oct: 0
3255101 | Computer Consumables | REV_20 | Aug: 0; Sep: 0; Oct: 0
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | Aug: 0; Sep: 0; Oct: 0
3258101 | Motor Vehicles | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258102 | Furnitures & Fixtures | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258103 | Computers & office equipments | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258105 | Machineries & Equipments | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258107 | Office Building : Repair & Maintenance | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258106 | Residential Building : Repair & Maintenance | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258105 | Engineering Equipments | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | Aug: 0; Sep: 0; Oct: 0
3258107 | Others : Repair & Maintenance | REV_22 | Aug: 0; Sep: 0; Oct: 0
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | Aug: 0; Sep: 0; Oct: 0
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | Aug: 0; Sep: 0; Oct: 0
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | Aug: 0; Sep: 0; Oct: 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | Aug: 0; Sep: 0; Oct: 0
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | Aug: 0; Sep: 0; Oct: 0
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | Aug: 0; Sep: 0; Oct: 0
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | Aug: 0; Sep: 0; Oct: 0
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | Aug: 0; Sep: 0; Oct: 0
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | Aug: 0; Sep: 0; Oct: 0
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | Aug: 0; Sep: 0; Oct: 0
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | Aug: 0; Sep: 0; Oct: 0
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | Aug: 0; Sep: 0; Oct: 0
4112314 | Furnitures & Fixtures | CAP_6 | Aug: 0; Sep: 0; Oct: 0
4112303 | Aircooler | CAP_6 | Aug: 0; Sep: 0; Oct: 0
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | Aug: 0; Sep: 0; Oct: 0
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111201 | Construction of WMG Office | CAP_8 | Aug: 0; Sep: 0; Oct: 0
4111201 | O&M During Construction | CAP_8 | Aug: 0; Sep: 0; Oct: 0
XXXXX1 | Physical Contingency | C
XXXXX2 | Price Contingency | D
Note on L7: hp:Environent()

## Monthly_19_20_Target
Code | Description | Imed_Code | DPP_Alloc_Total | DPP_Alloc_GOB | DPP_Alloc_RPA | DPP_Alloc_DPA | Upto_Last_FY_Total | Upto_Last_FY_GOB | Upto_Last_FY_RPA | Upto_Last_FY_DPA | Target_Total | Target_GOB | Target_RPA | Target_DPA
3111302 | Conveyance Allowance | REV_1 | 10 | 10 |  |  | 1.01 | 1.01 |  |  | 0.5 | 0.5
3111327 | Overtime Allowance | REV_1 | 10 | 10 |  |  | 0 | 0 |  |  | 0 | 0
3111338 | Other Allowance | REV_1 | 140 | 140 |  |  | 36.61 | 36.61 |  |  | 14 | 14
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 100 | 100 |  |  | 58.54 | 58.54 |  |  | 15 | 15
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 245 | 245 |  |  | 116.67 | 116.67 |  |  | 34.25 | 34.25
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 2596.27 | 2596.27 |  |  | 1603.18 | 1603.18 |  |  | 359.08 | 359.08
3211119 | Postage | REV_5 | 25 | 25 |  |  | 0.77 | 0.77 |  |  | 0.5 | 0.5
3211120 | Telephones/Telegram/Teleprinter | REV_5 | 25 | 25 |  |  | 0.97 | 0.97 |  |  | 0.2 | 0.2
3211117 | Telex/Fax/Internet | REV_5 | 25 | 25 |  |  | 0.44 | 0.44 |  |  | 0.2 | 0.2
3221104 | Registration Fee (Vehicles) | REV_6 | 15 | 15 |  |  | 11.92 | 11.92 |  |  | 1 | 1
3211115 | Water | REV_7 | 10 | 10 |  |  | 1.11 | 1.11 |  |  | 0.45 | 0.45
3211113 | Electricity | REV_7 | 15 | 15 |  |  | 8.74 | 8.74 |  |  | 3.5 | 3.5
3243102 | Gas & Fuel | REV_8 | 200 | 200 |  |  | 17.52 | 17.52 |  |  | 6 | 6
3243101 | Petrol and Lubricant | REV_8 | 150 | 150 |  |  | 64.59 | 64.59 |  |  | 20 | 20
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 3 | 3 |  |  | 1.16 | 1.16 |  |  | 0.15 | 0.15
3255102 | Printing & Binding | REV_10 | 35 | 35 |  |  | 34.16 | 34.16 |  |  | 0.5 | 0.5
3255104 | Stationery, Seals & Stamps | REV_11 | 150 | 150 |  |  | 49.91 | 49.91 |  |  | 20 | 20
3211127 | Books & Periodicals | REV_12 | 2 | 2 |  |  | 0.28 | 0.28 |  |  | 0.2 | 0.2
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 238.54 |  | 238.54 |  | 0 | 0 |  |  | 0 | 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 398.41 | 47.81 | 350.6 |  | 301.5 | 22.54 | 278.96 |  | 196.17 | 21.02 | 175.15
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 2533.34 | 304 | 2229.34 |  | 1346.63 | 80.34 | 1266.29 |  | 677.14 | 72.55 | 604.59
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 1321.68 | 158.6 | 1163.08 |  | 578.2 | 35.47 | 542.73 |  | 246.66 | 26.4 | 220.26
3211109 | Casual labour/Job worker | REV_15 | 15 | 15 |  |  | 10.96 | 10.96 |  |  | 3.5 | 3.5
3256103 | Consumable Stores | REV_16 | 25 | 25 |  |  | 3.74 | 3.74 |  |  | 3 | 3
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 7901.4 |  |  | 7901.4 | 5168.01 | 0 | 0 | 5168.01 | 500 | 0 | 0 | 500
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 25 | 25 |  |  | 12.73 | 12.73 |  |  | 5 | 5
3111332 | b) Interim Evaluation | REV_18 | 10 | 10 |  |  | 1.29 | 1.29 |  |  | 1 | 1
3111332 | c) Progress Monitoring | REV_18 | 10 | 10 |  |  | 1.3 | 1.3 |  |  | 1 | 1
3257104 | Survey | REV_19 | 162 | 162 |  |  | 85.02 | 85.02 |  |  | 50 | 50
3255101 | Computer Consumables | REV_20 | 50 | 50 |  |  | 20.47 | 20.47 |  |  | 10 | 10
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 1700 | 1700 |  |  | 875.46 | 875.46 |  |  | 300 | 300
3258101 | Motor Vehicles | REV_22 | 100 | 100 |  |  | 61.4 | 61.4 |  |  | 15 | 15
3258102 | Furnitures & Fixtures | REV_22 | 15 | 15 |  |  | 3.2 | 3.2 |  |  | 2 | 2
3258103 | Computers & office equipments | REV_22 | 25 | 25 |  |  | 5.34 | 5.34 |  |  | 3 | 3
3258105 | Machineries & Equipments | REV_22 | 25 | 25 |  |  | 1.22 | 1.22 |  |  | 2 | 2
3258107 | Office Building : Repair & Maintenance | REV_22 | 20 | 20 |  |  | 19.98 | 19.98 |  |  | 0 | 0
3258106 | Residential Building : Repair & Maintenance | REV_22 | 20 | 20 |  |  | 14.53 | 14.53 |  |  | 5 | 5
3258105 | Engineering Equipments | REV_22 | 25 | 25 |  |  | 1.39 | 1.39 |  |  | 2 | 2
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 362.5 | 43.5 | 319 |  | 95.03 | 10.83 | 84.2 |  | 58.25 | 8.25 | 50 | 0
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 10 | 10 |  |  | 2.39 | 2.39 |  |  | 0.75 | 0.75
3258107 | Others : Repair & Maintenance | REV_22 | 25 | 25 |  |  | 7.48 | 7.48 |  |  | 3 | 3
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 702.5 | 702.5 |  |  | 606.9 | 606.9 |  |  | 95.6 | 95.6
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 68.25 | 68.25 |  |  | 50.22 | 50.22
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 100 | 100 |  |  | 61.29 | 61.29
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 8.97 | 8.97 |  |  | 8.95 | 8.95
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 5 | 5 |  |  | 0.79 | 0.79
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 20.5 | 20.5 |  |  | 20.18 | 20.18
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 6 | 6 |  |  | 2.13 | 2.13
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 50 | 50 |  |  | 9.49 | 9.49 |  |  | 5 | 5
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 19.5 | 19.5 |  |  | 19.47 | 19.47
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 13.75 | 13.75 |  |  | 9.88 | 9.88
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 1.5 | 1.5 |  |  | 0.2 | 0.2
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 5.25 | 5.25 |  |  | 4.08 | 4.08
4112314 | Furnitures & Fixtures | CAP_6 | 50 | 50 |  |  | 45.32 | 45.32
4112303 | Aircooler | CAP_6 | 15 | 15 |  |  | 9.73 | 9.73 |  |  | 4 | 4
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 24000 | 24000 |  |  | 14323.6 | 14323.6 |  |  | 2049.42 | 2049.42
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 1261 | 151.32 | 1109.68 |  | 116.72 | 16.34 | 100.38 |  | 490.33 | 68.65 | 421.68
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 1515 | 181.8 | 1333.2 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 20311 | 2437.32 | 17873.68 |  | 6143.66 | 898.49 | 5254.17 |  | 8105.58 | 1134.84 | 6970.74 | 0
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 9729 | 1167.48 | 8561.52 |  | 6011.48 | 791.08 | 5220.4 |  | 3956.08 | 553.88 | 3402.2 | 0
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 2515 | 301.8 | 2213.2 |  | 455.04 | 64.36 | 390.68 |  | 900.73 | 126.11 | 774.62 | 0
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 2550 | 306 | 2244 |  | 452.46 | 63.49 | 388.97 |  | 913.26 | 127.86 | 785.4 | 0
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 1785 | 214.2 | 1570.8 |  | 341.85 | 48.84 | 293.01 |  | 657.55 | 92.06 | 565.49 | 0
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 11952.5 | 1434.3 | 10518.2 |  | 6127.06 | 779.02 | 5348.04 |  | 4914.31 | 688.04 | 4226.27 | 0
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 166 | 19.92 | 146.08 |  | 73.26 | 9.77 | 63.49 |  | 0 | 0 | 0 | 0
4111201 | Construction of WMG Office | CAP_8 | 1380 | 165.6 | 1214.4 |  | 42.09 | 5.47 | 36.62 |  | 348.14 | 44.54 | 303.6 | 0
4111201 | O&M During Construction | CAP_8 | 200 | 200 | 0 |  | 0 | 0 | 0 |  | 0 | 0
XXXXX1 | Physical Contingency | C | 258 | 100 | 158 | 0
XXXXX2 | Price Contingency | D | 402.14 | 100.76 | 301.38 | 0

## Codes
code | rindex
REV_1 | 5 | 0
REV_2 | 6 | 1
REV_3 | 7 | 2
REV_4 | 8 | 3
REV_5 | 9 | 4
REV_6 | 10 | 5
REV_7 | 11 | 6
REV_8 | 12 | 7
REV_9 | 13 | 8
REV_10 | 14 | 9
REV_11 | 15 | 10
REV_12 | 16 | 11
REV_13 | 17 | 12
REV_14 | 18 | 13
REV_15 | 19 | 14
REV_16 | 20 | 15
REV_17 | 21 | 16
REV_18 | 22 | 17
REV_19 | 23 | 18
REV_20 | 24 | 19
REV_21 | 25 | 20
REV_22 | 26 | 21
CAP_1 | 29 | 22
CAP_2 | 30 | 23
CAP_3 | 31 | 24
CAP_4 | 32 | 25
CAP_5 | 33 | 26
CAP_6 | 34 | 27
CAP_7 | 35 | 28
CAP_8 | 36 | 29
C | 42 | 30
D | 43 | 31

## Physical
code | Description | Physical_last_fy | Curyr_Target | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
REV_1 | Allowances
REV_2 | Travel expences
REV_3 | Office rent for PMO
REV_4 | Misc. taxes | 0.8% | 0.4% | Aug: 0.01%; Sep: 0.05%; Oct: 0.1%; Nov: 0.1%
REV_5 | Postage, telephone, Internate, Fax, telex etc.
REV_6 | Registration Fees (Vehicles)
REV_7 | Water & Elecricity
REV_8 | Gas & Fuel and Petrol & Lubricant
REV_9 | Insurance/Bank Charges (incl.Veh.)
REV_10 | Printing & Binding
REV_11 | Stationary
REV_12 | Books & periodical
REV_13 | Overseas Training
REV_14 | Local Training | 2% | 1% | Oct: 0.05%; Nov: 0.1%
REV_15 | Casual labour/Job worker
REV_16 | Consumable Stores
REV_17 | Consultancy | 2% | 1% | Oct: 0.3%; Nov: 0.3%
REV_18 | Honorarium/Fees/ Remuneration
REV_19 | Survey
REV_20 | Computer Consumables
REV_21 | Other expenses, Out sourcing Staff Salary | 1.2% | 0.6% | Nov: 0.25%
REV_22 | Repair & Maintenance of Vehicles, furniture, computers & other structure
CAP_1 | Motor Vehicle | 1% | 1%
CAP_2 | Water Transport
CAP_3 | Machinary & other equipment
CAP_4 | Engineering equipment
CAP_5 | Computer & Accessories
CAP_6 | Furniture & fixture and Aircooler
CAP_7 | Land acquisition | 7% | 3%
CAP_8 | Construction Works | 21% | 19% | Aug: 1%; Sep: 1.5%; Oct: 3%; Nov: 4.25%
C | Physical Contingency
D | Price Contingency

## Fund_releasae
Code | Description | Imed_Code | Total | 1stQ | 2ndQ | 3rdQ | 4thQ
3111302 | Conveyance Allowance | REV_1 | 0.1 | 0.1
3111327 | Overtime Allowance | REV_1 | 0 | 0
3111338 | Other Allowance | REV_1 | 3.5 | 3.5
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 3.75 | 3.75
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 8.56 | 8.56
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 89.77 | 89.77
3211119 | Postage | REV_5 | 0.13 | 0.13
3211120 | Telephones/Telegram/Teleprinter | REV_5 | 0.05 | 0.05
3211117 | Telex/Fax/Internet | REV_5 | 0.05 | 0.05
3221104 | Registration Fee (Vehicles) | REV_6 | 0.25 | 0.25
3211115 | Water | REV_7 | 0.11 | 0.11
3211113 | Electricity | REV_7 | 0.88 | 0.88
3243102 | Gas & Fuel | REV_8 | 1.5 | 1.5
3243101 | Petrol and Lubricant | REV_8 | 5 | 5
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 0.04 | 0.04
3255102 | Printing & Binding | REV_10 | 0.13 | 0.13
3255104 | Stationery, Seals & Stamps | REV_11 | 5 | 5
3211127 | Books & Periodicals | REV_12 | 0.05 | 0.05
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 0 | 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 30 | 30
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 0 | 0
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 0 | 0
3211109 | Casual labour/Job worker | REV_15 | 0.88 | 0.88
3256103 | Consumable Stores | REV_16 | 0.75 | 0.75
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 0 | 0
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 1.75 | 1.75
3111332 | b) Interim Evaluation | REV_18 | 0 | 0
3111332 | c) Progress Monitoring | REV_18 | 0 | 0
3257104 | Survey | REV_19 | 12.5 | 12.5
3255101 | Computer Consumables | REV_20 | 2.5 | 2.5
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 75 | 75
3258101 | Motor Vehicles | REV_22 | 3.75 | 3.75
3258102 | Furnitures & Fixtures | REV_22 | 0.5 | 0.5
3258103 | Computers & office equipments | REV_22 | 0.75 | 0.75
3258105 | Machineries & Equipments | REV_22 | 0.5 | 0.5
3258107 | Office Building : Repair & Maintenance | REV_22 | 1.25 | 1.25
3258106 | Residential Building : Repair & Maintenance | REV_22 | 0 | 0
3258105 | Engineering Equipments | REV_22 | 0.5 | 0.5
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 2.06 | 2.06
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 0.19 | 0.19
3258107 | Others : Repair & Maintenance | REV_22 | 0.75 | 0.75
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 0 | 0
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 0 | 0
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 0 | 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 0 | 0
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 0 | 0
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 0 | 0
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 0 | 0
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 5 | 5
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 0 | 0
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 0 | 0
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 0 | 0
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 0 | 0
4112314 | Furnitures & Fixtures | CAP_6 | 0 | 0
4112303 | Aircooler | CAP_6 | 4 | 4
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 0 | 0
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 17.16 | 17.16
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 536.53 | 536.53
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 261.87 | 261.87
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 31.53 | 31.53
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 31.97 | 31.97
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 23.02 | 23.02
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 325.29 | 325.29
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 0 | 0
4111201 | Construction of WMG Office | CAP_8 | 11.13 | 11.13
4111201 | O&M During Construction | CAP_8 | 0 | 0
XXXXX1 | Physical Contingency | C
XXXXX2 | Price Contingency | D

## Sheet4
code | Description |  | June,19 | June,18
REV_4 | Misc. taxes | 0.8% | 0.4% | 0.4%
REV_14 | Local Training | 2% | 1% | 1%
REV_17 | Consultancy | 2% | 1% | 1%
REV_21 | Other expenses, Out sourcing Staff Salary | 1.2% | 0.6% | 0.6%
REV_19 | Survey | 0% | 0% | 0%
Captial
CAP_1 | Motor Vehicle | 1% | 0% | 1%
CAP_2 | Water Transport | 0% | 0% | 0%
CAP_3 | Machinary & other equipment | 0% | 0% | 0%
CAP_4 | Engineering equipment | 0% | 0% | 0%
CAP_5 | Computer & Accessories | 0% | 0% | 0%
CAP_6 | Furniture & fixture and Aircooler | 0% | 0% | 0%
CAP_7 | Land acquisition | 7% | 1% | 6%
CAP_8 | Construction Works | 21% | 12% | 9%
|  | 35% | 16% | 19%

## DPP_TO_IMED
Eocde | Description | Imedcode
3111302 | Conveyance Allowance | REV_1
3111327 | Overtime Allowance | REV_1
3111338 | Other Allowance | REV_1
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4
3211119 | Postage | REV_5
3211120 | Telephones/Telegram/Teleprinter | REV_5
3211117 | Telex/Fax/Internet | REV_5
3221104 | Registration Fee (Vehicles) | REV_6
3211115 | Water | REV_7
3211113 | Electricity | REV_7
3243102 | Gas & Fuel | REV_8
3243101 | Petrol and Lubricant | REV_8
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9
3255102 | Printing & Binding | REV_10
3255104 | Stationery, Seals & Stamps | REV_11
3211127 | Books & Periodicals | REV_12
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14
3211109 | Casual labour/Job worker | REV_15
3256103 | Consumable Stores | REV_16
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18
3111332 | b) Interim Evaluation | REV_18
3111332 | c) Progress Monitoring | REV_18
3257104 | Survey | REV_19
3255101 | Computer Consumables | REV_20
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21
3258101 | Motor Vehicles | REV_22
3258102 | Furnitures & Fixtures | REV_22
3258103 | Computers & office equipments | REV_22
3258105 | Machineries & Equipments | REV_22
3258107 | Office Building : Repair & Maintenance | REV_22
3258106 | Residential Building : Repair & Maintenance | REV_22
3258105 | Engineering Equipments | REV_22
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22
3258128 | Water Transport : Repair of Speedboat(s) | REV_22
3258107 | Others : Repair & Maintenance | REV_22
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5
4112314 | Furnitures & Fixtures | CAP_6
4112303 | Aircooler | CAP_6
4141101 | Land Acquisition ( 470 hectare) | CAP_7
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8
4111201 | Construction of WMG Office | CAP_8
4111201 | O&M During Construction | CAP_8
XXXXX1 | Physical Contingency | C
XXXXX2 | Price Contingency | D

## Imed_df
code | rindex | Dpp_alloc_total | Dpp_alloc_gob | Dpp_alloc_rpa | Dpp_alloc_dpa | Upto_last_fy_total | Upto_last_fy_gob | Upto_last_fy_rpa | Upto_last_fy_dpa | Target_curr_fy_total | Target_curr_fy_gob | Target_curr_fy_rpa | Target_curr_fy_dpa | Achiv_up_cur_month_total | Achiv_up_cur_month_gob | Achiv_up_cur_month_rpa | Achiv_up_cur_month_dpa | Achiv_up_prev_month_total | Achiv_up_prev_month_gob | Achiv_up_prev_month_rpa | Achiv_up_prev_month_dpa | fund_release | phy_upto_lastyr | phy_target | phy_curmonth | phy_prevmonth
REV_1 | 5
REV_2 | 6
REV_3 | 7
REV_4 | 8
REV_5 | 9
REV_6 | 10
REV_7 | 11
REV_8 | 12
REV_9 | 13
REV_10 | 14
REV_11 | 15
REV_12 | 16
REV_13 | 17
REV_14 | 18
REV_15 | 19
REV_16 | 20
REV_17 | 21
REV_18 | 22
REV_19 | 23
REV_20 | 24
REV_21 | 25
REV_22 | 26
CAP_1 | 29
CAP_2 | 30
CAP_3 | 31
CAP_4 | 32
CAP_5 | 33
CAP_6 | 34
CAP_7 | 35
CAP_8 | 36
C | 42
D | 43

## Quaterly_df
Imed_Code | Q1_F | Q2_F | Q3_F | Q4_F | Q1_Phy | Q2_Phy | Q3_Phy | Q4_Phy
REV_1
REV_2
REV_3
REV_4
REV_5
REV_6
REV_7
REV_8
REV_9
REV_10
REV_11
REV_12
REV_13
REV_14
REV_15
REV_16
REV_17
REV_18
REV_19
REV_20
REV_21
REV_22
CAP_1
CAP_2
CAP_3
CAP_4
CAP_5
CAP_6
CAP_7
CAP_8
C
D

## Category_cost
item | rindexc | Up_to_Last_fy | Up_to_curr_month | Total
consultantcy | 2
physicalworks | 3
Livelihood | 4
LA | 5
Tax and Vat | 6
Goods | 7
Office Administration | 8