## Previous_data
Code | Description | Imed_Code | Dpp_allocation | Weight | Prev_Progress_Fin | Prev_Progress_Phy | Cur_Tar_Fin | Cur_Tar_Phy
3111302 | Conveyance Allowance | REV_1 | 10 | 0.02 | 0.71 | 0.00142 | 0.3 | 0.0006
3111327 | Overtime Allowance | REV_1 | 10 | 0.02 | 0 | 0 | 0 | 0
3111338 | Other Allowance | REV_1 | 140 | 0.23 | 25 | 0.041071 | 14 | 0.023
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 100 | 0.17 | 45.84 | 0.077928 | 18 | 0.0306
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 245 | 0.41 | 82.46 | 0.13799 | 34.25 | 0.057316
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 2596.27 | 4.33 | 1353.43 | 2.2572 | 252.44 | 0.42101
3211119 | Postage | REV_5 | 25 | 0.04 | 0.4 | 0.00064 | 0.22 | 0.000352
3211120 | Telephones/Telegram/Teleprinter | REV_5 | 25 | 0.04 | 0.89 | 0.001424 | 0.15 | 0.00024
3211117 | Telex/Fax/Internet | REV_5 | 25 | 0.04 | 0.39 | 0.000624 | 0.05 | 8e-05
3221104 | Registration Fee (Vehicles) | REV_6 | 15 | 0.03 | 9.55 | 0.0191 | 5.45 | 0.0109
3211115 | Water | REV_7 | 10 | 0.02 | 0.71 | 0.00142 | 0.4 | 0.0008
3211113 | Electricity | REV_7 | 15 | 0.03 | 5.96 | 0.01192 | 2.5 | 0.005
3243102 | Gas & Fuel | REV_8 | 200 | 0.33 | 11.63 | 0.019189 | 4 | 0.0066
3243101 | Petrol and Lubricant | REV_8 | 150 | 0.25 | 44.59 | 0.074317 | 18 | 0.03
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 3 | 0.01 | 1.06 | 0.0035333 | 0.25 | 0.00083333
3255102 | Printing & Binding | REV_10 | 35 | 0.06 | 30.18 | 0.051737 | 4 | 0.0068571
3255104 | Stationery, Seals & Stamps | REV_11 | 150 | 0.25 | 31.93 | 0.053217 | 15 | 0.025
3211127 | Books & Periodicals | REV_12 | 2 | 0 | 0.18 | 0 | 0.05 | 0
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 238.54 | 0.53 | 0 | 0 |  | 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 398.41 | 0.89 | 125.63 | 0.28064 | 104.09 | 0.23252
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 2533.34 | 5.64 | 724.38 | 1.6127 | 593.85 | 1.3221
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 1321.68 | 2.94 | 343.99 | 0.76519 | 235.39 | 0.52361
3211109 | Casual labour/Job worker | REV_15 | 15 | 0.25 | 6.71 | 0.11183 | 4 | 0.066667
3256103 | Consumable Stores | REV_16 | 25 | 0.42 | 2.74 | 0.046032 | 1 | 0.0168
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 7901.4 | 10 | 4481.58 | 5.6719 | 500 | 0.6328
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 25 | 0.42 | 7.73 | 0.12986 | 5 | 0.084
3111332 | b) Interim Evaluation | REV_18 | 10 | 0.17 | 0.52 | 0.00884 | 1 | 0.017
3111332 | c) Progress Monitoring | REV_18 | 10 | 0.17 | 0.55 | 0.00935 | 1 | 0.017
3257104 | Survey | REV_19 | 162 | 2.7 | 55.09 | 0.91817 | 30 | 0.5
3255101 | Computer Consumables | REV_20 | 50 | 0.83 | 12.97 | 0.2153 | 6.5 | 0.1079
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 1700 | 2.84 | 575.53 | 0.96147 | 300 | 0.50118
3258101 | Motor Vehicles | REV_22 | 100 | 0.48 | 40.94 | 0.19651 | 20 | 0.096
3258102 | Furnitures & Fixtures | REV_22 | 15 | 0.07 | 2.21 | 0.010313 | 1 | 0.0046667
3258103 | Computers & office equipments | REV_22 | 25 | 0.12 | 3.35 | 0.01608 | 2 | 0.0096
3258105 | Machineries & Equipments | REV_22 | 25 | 0.12 | 0.72 | 0.003456 | 0.5 | 0.0024
3258107 | Office Building : Repair & Maintenance | REV_22 | 20 | 0.1 | 9.98 | 0.0499 | 5 | 0.025
3258106 | Residential Building : Repair & Maintenance | REV_22 | 20 | 0.1 | 8.95 | 0.04475 | 5 | 0.025
3258105 | Engineering Equipments | REV_22 | 25 | 0.12 | 0.89 | 0.004272 | 0.5 | 0.0024
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 362.5 | 1.73 | 84.04 | 0.40107 | 11.36 | 0.054215
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 10 | 0.05 | 1.65 | 0.00825 | 0.75 | 0.00375
3258107 | Others : Repair & Maintenance | REV_22 | 25 | 0.12 | 2.5 | 0.012 | 3 | 0.0144
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 702.5 | 2.73 | 606.9 | 2.3585 | 95.6 | 0.37151
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 68.25 | 0.27 | 50.22 | 0.19867 | 0 | 0
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 100 | 1 | 61.29 | 0.6129 | 0 | 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 8.97 | 0.21 | 8.95 | 0.20953 | 0 | 0
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 5 | 0.11 | 0.79 | 0.01738 | 0 | 0
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 20.5 | 0.47 | 20.18 | 0.46266 | 0 | 0
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 6 | 0.14 | 2.13 | 0.0497 | 0 | 0
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 50 | 1.15 | 7.89 | 0.18147 | 2 | 0.046
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 19.5 | 0.45 | 19.47 | 0.44931 | 0 | 0
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 13.75 | 0.32 | 9.88 | 0.22993 | 0 | 0
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 1.5 | 0.03 | 0.2 | 0.004 | 0 | 0
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 5.25 | 0.12 | 4.08 | 0.093257 | 0 | 0
4112314 | Furnitures & Fixtures | CAP_6 | 50 | 0.77 | 35.35 | 0.54439 | 10 | 0.154
4112303 | Aircooler | CAP_6 | 15 | 0.23 | 5.77 | 0.088473 | 4 | 0.061333
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 24000 | 10 | 10443.7 | 4.3515 | 7852.4 | 3.2718
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 1261 | 1.06 | 0 | 0 | 700 | 0.58842
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 1515 | 1.27 | 0 | 0 | 700 | 0.5868
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 20311 | 17.09 | 3067.05 | 2.5807 | 4600 | 3.8705
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 9729 | 8.19 | 1189.16 | 1.0011 | 5750 | 4.8404
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 2515 | 2.12 | 0 | 0 | 800 | 0.67435
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 2550 | 2.15 | 0 | 0 | 700 | 0.5902
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 1785 | 1.5 | 0 | 0 | 600 | 0.5042
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 11952.5 | 10.06 | 4246.91 | 3.5745 | 2825 | 2.3777
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 166 | 0.14 | 0 | 0 | 178.46 | 0.15051
4111201 | Construction of WMG Office | CAP_8 | 1380 | 1.16 | 0 | 0 | 86 | 0.07229
4111201 | O&M During Construction | CAP_8 | 200 | 0.17 | 0 | 0 | 0 | 0
[6 empty] | 31.2385 |  | 23.0383 | 54.2768