## Sheet1
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
| Monthly Implementation Progress Review meeting of ADP included Project of the year 2019-2020 |  |  |  |  | IMED 05/2003 (Revised)
Monthly Progress Report
Reporting Period: Nov/2019
| Name of the Ministry/Division/Organization |  |  | : Ministry of Water Resources /
Bangladesh Water Development Board (BWDB)
(In Lakh Taka)
| Name of the Project | Allocation for the year 2019-2020 |  |  | Taka released | Expenditure upto Reporting Period: Reporting Period: Nov/2019& % of allocation
|  | Total | Taka | Project Aid (RPA) |  | Total | Taka(GoB) | Project Aid (RPA)
a) Main Programme :
| “Haor Flood Management and Livelihood Improvement Project (BWDB part)” | 25000.00 | 6000.00 | 19000.00 (18500.00) | 1500.00 | 383.12 | 163.85 | 219.28 (80.65)
| Sub Total : | 25000.00 | 6000.00 | 19000.00 (18500.00) | 1500.00 | 383.12 | 163.85 | 219.28 (80.65)
b) Technical Assistance
Sub Total :
c) Organization's Self Financed Programme :
Sub Total :
d) Food Aided Programme :
4333.38
4603.73
Sub Total :
| Grand Total : | 25000.00 | 6000.00 | 19000.00 (18500.00) | 1500.00 | 383.12 | 163.85 | 219.28 (80.65)

## Sheet2
| Monthly Implementation Progress Review meeting of ADP included Project of the year 2019-2020 | [7 empty] | IMED 05/2003 (Revised)
Reporting Period: Nov/2019 | [8 empty] | Monthly Progress Report
Name of the Ministry/Division/Organization |  |  |  | : Ministry of Water Resources /
Bangladesh Water Development Board (BWDB)
1 | Name of the Project |  | : Haor Flood Management and Livelihood Improvement Project (BWDB part)
2 | Objectives of the Project |  | : The main objectives of the project are:
(a) Rehabilitating and constructing the flood management facilities and
(b) Implementing agriculture promotion activities.
3 | Implementation Period |  | : a) Original : July,2014 to June,2022
b) Revised :- July, 2014 to June, 2022
4 | Location of the Project |  | : Kishoreganj, Mymensingh, Netrokona, Sunamganj, Habiganj and Brahmanbaria District
5 | Source of Funding (with amount) |  |  | :JICA Loan (Loan No.. BD P-80) (Total-97865.00, PA-59446.10, GoB-38418.90)
6 | Estimated Cost |  |  | : |  |  |  |  | (In Lakh Taka)
[5 empty] | Total | Taka(GoB) | Project Aid (RPA) |  | Physical(% of Total Project)
a) i. Original |  |  |  | : | 99337.72 | 39891.62 | 59446.10(51544.70)
b) ii. Revised |  |  |  | : | 97865.00 | 38418.90 | 59446.10(51544.70)
c) Cumulative Progress upto last
|  | Jun-19 |  | : | 45560.70 | 21133.75 | 24435.95(19267.94) |  | 54%
d) Current year Revised allocation
and Physical Target |  |  |  | : | 25000.00 | 6000.00 | 19000.00(18500.00) |  | 26%
e) Progress of current month |  |  |  | : | 75.62 | 26.60 | 49.03(49.03) |  | 1.55% |  |  | -3803.66 | -717.68 | 17643%
f) Progress upto the current | [11 empty] | 1298.44 | 1298.44
month of the year |  |  |  | : | 383.12 | 163.85 | 219.28(80.65) |  | 5%
g) Fund released upto the current | [11 empty] | 4420.69
month |  |  |  | : | [7 empty] | 4006.25
7 | Quarterly Financial |  |  | :
and Physical | [8 empty] | (In Lakh Taka)
|  |  | 1st Quarter |  |  | 2nd Quarter |  | 3rd Quarter |  | 4th Quarter |  |  | 383.12 | 163.85 | 11329.88 | 10643.45
|  |  | Financial |  | Physical | Financial | Physical | Financial | Physical | Financial | Physical |  | 11562.02 | 2948.3 | 8884.19 | 8480.01
| a) Target : |  | 5000 |  | 3% | 7500 | 3% | 7500 | 6% | 5000 | 7% |  | -11178.9 | -2784.45 | 2445.69 | 2163.44
| b) Achievement : |  | 88.64 |  | 1.55% | 294.48 | 3.45% | [5 empty] | 383.12 | 6313.62 | 11329.88 | 10643.45
[13 empty] | 11562.02 | 2948.3 | 8884.19 | 8480.01
[13 empty] | -11178.9 | 3365.32 | 2445.69 | 2163.44
[13 empty] | 6593 | 17643.22
[13 empty] | 11329.88 | -88.64
[13 empty] | 17922.88 | -294.48
0
17260.1

## Sheet3
8 | Target and Achievement of the main Components of the Project: | [6 empty] | (In Lakh Taka)
Sl. No. | Work components as Per RDPP (With quantity) | Estimated Cost | Achievement upto last June |  | Revised Target of the current year |  | Progress upto the month of Reporting Period: Nov/2019 of the current year
|  |  | Financial | Physical (% of the component) | Financial | Physical (% of the component) | Financial | Physical (% of the component)
A. | Revenue Component
1 | Allowances | 160 | 37.62 | - | 14.5 | - | 5.045 | -
2 | Travel expences | 100 | 58.54 | - | 15 | - | 3.1763 | -
3 | Office rent for PMO | 245 | 116.67 | - | 34.25 | - | 14.2535 | -
4 | Misc. taxes | 2596.27 | 1603.18 | 1.2% | 359.08 | 0.4% | 23.2972 | 0.1%
5 | Postage, telephone, Internate, Fax, telex etc. | 75 | 2.18 | - | 0.9 | - | 0.13112 | -
6 | Registration Fees (Vehicles) | 15 | 11.92 | - | 1 | - | 0 | -
7 | Water & Elecricity | 25 | 9.85 | - | 3.95 | - | 1.4485 | -
8 | Gas & Fuel and Petrol & Lubricant | 350 | 82.11 | - | 26 | - | 6.6745 | -
9 | Insurance/Bank Charges (incl.Veh.) | 3 | 1.16 | - | 0.15 | - | 0 | -
10 | Printing & Binding | 35 | 34.16 | - | 0.5 | - | 0.41729 | - | 242.23
11 | Stationary | 150 | 49.91 | - | 20 | - | 7.1743 | - | 860.03
12 | Books & periodical | 2 | 0.28 | - | 0.2 | - | 0.0774 | - | 7478.2
13 | Overseas Training | 238.54 | 0 | - | 0 | - | 0 | - | 8580.46
14 | Local Training | 4253.43 | 2226.33 | 3% | 1119.97 | 1% | 88.3855 | 0.1% | 11130.71
15 | Casual labour/Job worker | 15 | 10.96 | - | 3.5 | - | 3.7117 | - | 2550.25
16 | Consumable Stores | 25 | 3.74 | - | 3 | - | 0 | - | 1
17 | Consultancy | 7901.4 | 5168.01 | 3% | 500 | 1% | 138.63 | 0.3% | 2.53
18 | Honorarium/Fees/ Remuneration | 45 | 15.32 | - | 7 | - | 0.69575 | - | 2553.78
19 | Survey | 162 | 85.02 | - | 50 | - | 3.0336 | -
20 | Computer Consumables | 50 | 20.47 | - | 10 | - | 5.9881 | -
21 | Other expenses, Out sourcing Staff Salary | 1700 | 875.46 | 1.8% | 300 | 0.6% | 77.1556 | 0.25%
22 | Repair & Maintenance of Vehicles, furniture, computers & other structure | 627.5 | 211.96 | - | 91 | - | 3.8293 | -
| SubTotal A: | 18774.14 | 10624.85 | 9% | 2560 | 3% | 383.1248 | 0.75%
B. | Capital Component
1 | Motor Vehicle | 770.75 | 657.12 | 1% | 95.6 | 1% | 0 | -
2 | Water Transport | 100 | 61.29 | - | 0 | - | 0 | -
3 | Machinary & other equipment | 13.97 | 9.74 | - | 0 | - | 0 | -
4 | Engineering equipment | 76.5 | 31.8 | - | 5 | - | 0 | -
5 | Computer & Accessories | 40 | 33.63 | - | 0 | - | 0 | -
6 | Furniture & fixture and Aircooler | 65 | 55.05 | - | 4 | - | 0
7 | Land acquisition | 24000 | 14323.6 | 8% | 2049.42 | 3% | 0 | -
8 | Construction Works | 53364.5 | 19763.62 | 36% | 20285.98 | 19% | 0 | 4.25% | 11.6
| SubTotal B: | 78430.72 | 34935.85 | 45% | 22440 | 23% | 0 | 4.25% | 14
| Total A + B: | 97204.86 | 45560.7 | 54% | 25000 | 26% | 383.1248 | 5%
Sl. No. | Work components as Per RDPP (With quantity) | Estimated Cost | Achievement upto last June |  | Revised Target of the current year |  | Progress upto the month of Reporting Period: Nov/2019 of the current year
|  |  | Financial | Physical (% of the component) | Financial | Physical (% of the component) | Financial | Physical (% of the component)
C. | Physical Contingency | 258 | 0 |  | 0 | - | 0 | -
D. | Price Contingency | 402.14 | 0 |  | 0 | - | 0 | -
| Grand Total (A+B+C+D): | 97865 | 45560.7 | 54% | 25000 | 26% | 383.1248 | 5% | 244.4948
9. Reasons for the delay of | [8 empty] | 23000
Project implementation |  |  | : N/A | [5 empty] | 8287.4
14712.6
10. Existing problems of | [8 empty] | 3879.9
Implementation of the project |  |  |  | : N/A |  |  |  |  | 18592.5
1
2.53
18595.03
[6 empty] | Project Director |  |  | 23000
[6 empty] | Haor Flood Management and |  |  | -8287.4
[6 empty] | Livelihood Improvement Project. |  |  | 3879.9
[6 empty] | BWDB, Dhaka. |  |  | 3.53
18596.03