## imed_df
| code | rindex | Dpp_alloc_total | Dpp_alloc_gob | Dpp_alloc_rpa | Dpp_alloc_dpa | Upto_last_fy_total | Upto_last_fy_gob | Upto_last_fy_rpa | Upto_last_fy_dpa | Target_curr_fy_total | Target_curr_fy_gob | Target_curr_fy_rpa | Target_curr_fy_dpa | Achiv_up_cur_month_total | Achiv_up_cur_month_gob | Achiv_up_cur_month_rpa | Achiv_up_cur_month_dpa | Achiv_up_prev_month_total | Achiv_up_prev_month_gob | Achiv_up_prev_month_rpa | Achiv_up_prev_month_dpa | fund_release | phy_upto_lastyr | phy_target | phy_curmonth | phy_prevmonth
0 | REV_1 | 5 | 160 | 160 | 0 | 0 | 37.62 | 37.62 | 0 | 0 | 14.5 | 14.5 | 0 | 0 | 6.4377 | 6.4377 | 0 | 0 | 5.045 | 5.045 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0
1 | REV_2 | 6 | 100 | 100 | 0 | 0 | 58.54 | 58.54 | 0 | 0 | 15 | 15 | 0 | 0 | 4.5304 | 4.5304 | 0 | 0 | 3.1763 | 3.1763 | 0 | 0 | 3.75 | 0 | 0 | 0 | 0
2 | REV_3 | 7 | 245 | 245 | 0 | 0 | 116.67 | 116.67 | 0 | 0 | 34.25 | 34.25 | 0 | 0 | 17.1072 | 17.1072 | 0 | 0 | 14.2535 | 14.2535 | 0 | 0 | 8.56 | 0 | 0 | 0 | 0
3 | REV_4 | 8 | 2596.27 | 2596.27 | 0 | 0 | 1603.18 | 1603.18 | 0 | 0 | 359.08 | 359.08 | 0 | 0 | 71.4953 | 71.4953 | 0 | 0 | 28.4169 | 28.4169 | 0 | 0 | 89.77 | 0.012 | 0.004 | 0.002 | 0.001
4 | REV_5 | 9 | 75 | 75 | 0 | 0 | 2.18 | 2.18 | 0 | 0 | 0.9 | 0.9 | 0 | 0 | 0.17541 | 0.17541 | 0 | 0 | 0.11952 | 0.11952 | 0 | 0 | 0.23 | 0 | 0 | 0 | 0
5 | REV_6 | 10 | 15 | 15 | 0 | 0 | 11.92 | 11.92 | 0 | 0 | 1 | 1 | 0 | 0 | 0.06085 | 0.06085 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0
6 | REV_7 | 11 | 25 | 25 | 0 | 0 | 9.85 | 9.85 | 0 | 0 | 3.95 | 3.95 | 0 | 0 | 2.1098 | 2.1098 | 0 | 0 | 1.4485 | 1.4485 | 0 | 0 | 0.99 | 0 | 0 | 0 | 0
7 | REV_8 | 12 | 350 | 350 | 0 | 0 | 82.11 | 82.11 | 0 | 0 | 26 | 26 | 0 | 0 | 11.0328 | 11.0328 | 0 | 0 | 6.6745 | 6.6745 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0
8 | REV_9 | 13 | 3 | 3 | 0 | 0 | 1.16 | 1.16 | 0 | 0 | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0 | 0 | 0
9 | REV_10 | 14 | 35 | 35 | 0 | 0 | 34.16 | 34.16 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0.41729 | 0.41729 | 0 | 0 | 0.41729 | 0.41729 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0
10 | REV_11 | 15 | 150 | 150 | 0 | 0 | 49.91 | 49.91 | 0 | 0 | 20 | 20 | 0 | 0 | 10.608 | 10.608 | 0 | 0 | 7.1743 | 7.1743 | 0 | 0 | 5 | 0 | 0 | 0 | 0
11 | REV_12 | 16 | 2 | 2 | 0 | 0 | 0.28 | 0.28 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0.03003 | 0.03003 | 0 | 0 | 0.0274 | 0.0274 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0
12 | REV_13 | 17 | 238.54 | 0 | 238.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | REV_14 | 18 | 4253.43 | 510.41 | 3743.02 | 0 | 2226.33 | 138.35 | 2087.98 | 0 | 1119.97 | 119.97 | 1000 | 0 | 145.2956 | 14.8459 | 130.4497 | 0 | 88.3855 | 9.6993 | 78.6862 | 0 | 30 | 0.03 | 0.01 | 0.002 | 0.001
14 | REV_15 | 19 | 15 | 15 | 0 | 0 | 10.96 | 10.96 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 0.8855 | 0.8855 | 0 | 0 | 0.8855 | 0.8855 | 0 | 0 | 0.88 | 0 | 0 | 0 | 0
15 | REV_16 | 20 | 25 | 25 | 0 | 0 | 3.74 | 3.74 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0
16 | REV_17 | 21 | 7901.4 | 0 | 0 | 7901.4 | 5168.01 | 0 | 0 | 5168.01 | 500 | 0 | 0 | 500 | 138.63 | 0 | 0 | 138.63 | 138.63 | 0 | 0 | 138.63 | 0 | 0.03 | 0.01 | 0.003 | 0.003
17 | REV_18 | 22 | 45 | 45 | 0 | 0 | 15.32 | 15.32 | 0 | 0 | 7 | 7 | 0 | 0 | 1.2753 | 1.2753 | 0 | 0 | 0.69575 | 0.69575 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0
18 | REV_19 | 23 | 162 | 162 | 0 | 0 | 85.02 | 85.02 | 0 | 0 | 50 | 50 | 0 | 0 | 3.0336 | 3.0336 | 0 | 0 | 3.0336 | 3.0336 | 0 | 0 | 12.5 | 0 | 0 | 0 | 0
19 | REV_20 | 24 | 50 | 50 | 0 | 0 | 20.47 | 20.47 | 0 | 0 | 10 | 10 | 0 | 0 | 5.9981 | 5.9981 | 0 | 0 | 5.9981 | 5.9981 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
20 | REV_21 | 25 | 1700 | 1700 | 0 | 0 | 875.46 | 875.46 | 0 | 0 | 300 | 300 | 0 | 0 | 170.7923 | 170.7923 | 0 | 0 | 144.9222 | 144.9222 | 0 | 0 | 75 | 0.018 | 0.006 | 0.0035 | 0.0025
21 | REV_22 | 26 | 627.5 | 308.5 | 319 | 0 | 211.96 | 127.76 | 84.2 | 0 | 91 | 41 | 50 | 0 | 37.7176 | 8.2569 | 29.4608 | 0 | 3.8293 | 1.8687 | 1.9607 | 0 | 10.25 | 0 | 0 | 0 | 0
22 | CAP_1 | 29 | 770.75 | 770.75 | 0 | 0 | 657.12 | 657.12 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | 0
23 | CAP_2 | 30 | 100 | 100 | 0 | 0 | 61.29 | 61.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | CAP_3 | 31 | 13.97 | 13.97 | 0 | 0 | 9.74 | 9.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | CAP_4 | 32 | 76.5 | 76.5 | 0 | 0 | 31.8 | 31.8 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
26 | CAP_5 | 33 | 40 | 40 | 0 | 0 | 33.63 | 33.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | CAP_6 | 34 | 65 | 65 | 0 | 0 | 55.05 | 55.05 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
28 | CAP_7 | 35 | 24000 | 24000 | 0 | 0 | 14323.6 | 14323.6 | 0 | 0 | 2049.42 | 2049.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.03 | 0 | 0
29 | CAP_8 | 36 | 53364.5 | 6579.74 | 46784.76 | 0 | 19763.62 | 2676.86 | 17095.76 | 0 | 20285.98 | 2835.98 | 17450 | 0 | 123.8713 | 15.4839 | 108.3874 | 0 | 0 | 0 | 0 | 0 | 1238.5 | 0.36 | 0.19 | 0.0525 | 0.0425
30 | C | 42 | 258 | 100 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | D | 43 | 402.14 | 100.76 | 301.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Rev | 10624.85 | 3284.66 | 2172.18 | 5168.01 | 2560 | 1010 | 1050 | 500 | 627.6328 | 329.0924 | 159.9105 | 138.63
[6 empty] | Captital | 34935.85 | 17849.09 | 17095.76 | 0 | 22440 | 4990 | 17450 | 0 | 123.8713 | 15.4839 | 108.3874 | 0
[7 empty] | 45560.7 | 21133.75 | 19267.94 | 5168.01 | 25000 | 6000 | 18500 | 500 | 751.5041 | 344.5763 | 268.2978 | 138.63

## cum_gob
| Ecode | Description | Imedcode | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Q1 | Q2 | Q3 | Q4
0 | 3111302 | Conveyance Allowance | REV_1 | 0 | 0.0465 | 0.0965 | 0.1465 | 0.1975 | 0.2475 | 0.2475 | 0.2475 | 0.2475 | 0.2475 | 0.2475 | 0.2475 | 0.0965 | 0.2475 | 0.2475 | 0.2475
1 | 3111327 | Overtime Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 3111338 | Other Allowance | REV_1 | 0 | 0 | 0 | 3.6215 | 4.8475 | 6.1902 | 6.1902 | 6.1902 | 6.1902 | 6.1902 | 6.1902 | 6.1902 | 0 | 6.1902 | 6.1902 | 6.1902
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 0 | 0 | 0.91434 | 2.117 | 3.1763 | 4.5304 | 4.5304 | 4.5304 | 4.5304 | 4.5304 | 4.5304 | 4.5304 | 0.91434 | 4.5304 | 4.5304 | 4.5304
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 0 | 5.7014 | 8.5521 | 11.4028 | 14.2535 | 17.1072 | 17.1072 | 17.1072 | 17.1072 | 17.1072 | 17.1072 | 17.1072 | 8.5521 | 17.1072 | 17.1072 | 17.1072
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 0 | 8.5226 | 15.2081 | 21.542 | 28.4169 | 71.4953 | 71.4953 | 71.4953 | 71.4953 | 71.4953 | 71.4953 | 71.4953 | 15.2081 | 71.4953 | 71.4953 | 71.4953
6 | 3211119 | Postage | REV_5 | 0 | 0.01438 | 0.03163 | 0.04744 | 0.06584 | 0.12173 | 0.12173 | 0.12173 | 0.12173 | 0.12173 | 0.12173 | 0.12173 | 0.03163 | 0.12173 | 0.12173 | 0.12173
7 | 3211120 | Telephones/Telegram/Teleprinter | REV_5 | 0 | 0 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178 | 0.03178
8 | 3211117 | Telex/Fax/Internet | REV_5 | 0 | 0 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219 | 0.0219
9 | 3221104 | Registration Fee (Vehicles) | REV_6 | 0 | 0 | 0 | 0 | 0 | 0.06085 | 0.06085 | 0.06085 | 0.06085 | 0.06085 | 0.06085 | 0.06085 | 0 | 0.06085 | 0.06085 | 0.06085
10 | 3211115 | Water | REV_7 | 0 | 0.0282 | 0.09231 | 0.09231 | 0.09231 | 0.25741 | 0.25741 | 0.25741 | 0.25741 | 0.25741 | 0.25741 | 0.25741 | 0.09231 | 0.25741 | 0.25741 | 0.25741
11 | 3211113 | Electricity | REV_7 | 0 | 0.37257 | 1.0519 | 1.3562 | 1.3562 | 1.8524 | 1.8524 | 1.8524 | 1.8524 | 1.8524 | 1.8524 | 1.8524 | 1.0519 | 1.8524 | 1.8524 | 1.8524
12 | 3243102 | Gas & Fuel | REV_8 | 0 | 0 | 0.26648 | 0.40468 | 1.5321 | 1.8161 | 1.8161 | 1.8161 | 1.8161 | 1.8161 | 1.8161 | 1.8161 | 0.26648 | 1.8161 | 1.8161 | 1.8161
13 | 3243101 | Petrol and Lubricant | REV_8 | 0 | 1.295 | 2.9836 | 4.1673 | 5.1424 | 9.2166 | 9.2166 | 9.2166 | 9.2166 | 9.2166 | 9.2166 | 9.2166 | 2.9836 | 9.2166 | 9.2166 | 9.2166
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3255102 | Printing & Binding | REV_10 | 0 | 0.14 | 0.15404 | 0.30029 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.41729 | 0.15404 | 0.41729 | 0.41729 | 0.41729
16 | 3255104 | Stationery, Seals & Stamps | REV_11 | 0 | 0.49597 | 3.7906 | 3.8426 | 7.1743 | 10.608 | 10.608 | 10.608 | 10.608 | 10.608 | 10.608 | 10.608 | 3.7906 | 10.608 | 10.608 | 10.608
17 | 3211127 | Books & Periodicals | REV_12 | 0 | 0.00575 | 0.00794 | 0.02152 | 0.0274 | 0.03003 | 0.03003 | 0.03003 | 0.03003 | 0.03003 | 0.03003 | 0.03003 | 0.00794 | 0.03003 | 0.03003 | 0.03003
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 0 | 0 | 0 | 0.77343 | 2.1137 | 2.186 | 2.186 | 2.186 | 2.186 | 2.186 | 2.186 | 2.186 | 0 | 2.186 | 2.186 | 2.186
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 0 | 0 | 0 | 3.6415 | 6.9852 | 12.0596 | 12.0596 | 12.0596 | 12.0596 | 12.0596 | 12.0596 | 12.0596 | 0 | 12.0596 | 12.0596 | 12.0596
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 0 | 0 | 0 | 0 | 0.60036 | 0.60036 | 0.60036 | 0.60036 | 0.60036 | 0.60036 | 0.60036 | 0.60036 | 0 | 0.60036 | 0.60036 | 0.60036
22 | 3211109 | Casual labour/Job worker | REV_15 | 0 | 0 | 0.368 | 0.368 | 0.8855 | 0.8855 | 0.8855 | 0.8855 | 0.8855 | 0.8855 | 0.8855 | 0.8855 | 0.368 | 0.8855 | 0.8855 | 0.8855
23 | 3256103 | Consumable Stores | REV_16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 0 | 0 | 0.69575 | 0.69575 | 0.69575 | 1.2753 | 1.2753 | 1.2753 | 1.2753 | 1.2753 | 1.2753 | 1.2753 | 0.69575 | 1.2753 | 1.2753 | 1.2753
26 | 3111332 | b) Interim Evaluation | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3111332 | c) Progress Monitoring | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3257104 | Survey | REV_19 | 0 | 0 | 0 | 3.0336 | 3.0336 | 3.0336 | 3.0336 | 3.0336 | 3.0336 | 3.0336 | 3.0336 | 3.0336 | 0 | 3.0336 | 3.0336 | 3.0336
29 | 3255101 | Computer Consumables | REV_20 | 0 | 0.14365 | 2.5503 | 5.7134 | 5.9981 | 5.9981 | 5.9981 | 5.9981 | 5.9981 | 5.9981 | 5.9981 | 5.9981 | 2.5503 | 5.9981 | 5.9981 | 5.9981
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 38.3871 | 63.9264 | 93.4543 | 119.0521 | 144.9222 | 170.7923 | 170.7923 | 170.7923 | 170.7923 | 170.7923 | 170.7923 | 170.7923 | 93.4543 | 170.7923 | 170.7923 | 170.7923
31 | 3258101 | Motor Vehicles | REV_22 | 0 | 0.08468 | 0.34066 | 0.82554 | 0.9865 | 1.7246 | 1.7246 | 1.7246 | 1.7246 | 1.7246 | 1.7246 | 1.7246 | 0.34066 | 1.7246 | 1.7246 | 1.7246
32 | 3258102 | Furnitures & Fixtures | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 3258103 | Computers & office equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 2.0582 | 2.0582 | 2.0582 | 2.0582 | 2.0582 | 2.0582 | 2.0582 | 0 | 2.0582 | 2.0582 | 2.0582
34 | 3258105 | Machineries & Equipments | REV_22 | 0 | 0.07642 | 0.08053 | 0.24553 | 0.28372 | 0.45443 | 0.45443 | 0.45443 | 0.45443 | 0.45443 | 0.45443 | 0.45443 | 0.08053 | 0.45443 | 0.45443 | 0.45443
35 | 3258107 | Office Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 3258105 | Engineering Equipments | REV_22 | 0 | 0.0565 | 0.24536 | 0.31106 | 0.31106 | 0.31106 | 0.31106 | 0.31106 | 0.31106 | 0.31106 | 0.31106 | 0.31106 | 0.24536 | 0.31106 | 0.31106 | 0.31106
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 0 | 0 | 0 | 0 | 0.2874 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 3.7086 | 0 | 3.7086 | 3.7086 | 3.7086
39 | 3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 3258107 | Others : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 4112303 | Aircooler | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 15.4839 | 15.4839 | 15.4839 | 15.4839 | 15.4839 | 15.4839 | 15.4839 | 0 | 15.4839 | 15.4839 | 15.4839
59 | 4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 4111201 | Construction of WMG Office | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 4111201 | O&M During Construction | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | XXXXX1 | Physical Contingency | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | XXXXX2 | Price Contingency | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## cum_rpa
| Ecode | Description | Imedcode | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Q1 | Q2 | Q3 | Q4
0 | 3111302 | Conveyance Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3111327 | Overtime Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 3111338 | Other Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 3211119 | Postage | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 3211120 | Telephones/Telegram/Teleprinter | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 3211117 | Telex/Fax/Internet | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 3221104 | Registration Fee (Vehicles) | REV_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 3211115 | Water | REV_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 3211113 | Electricity | REV_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3243102 | Gas & Fuel | REV_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3243101 | Petrol and Lubricant | REV_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3255102 | Printing & Binding | REV_10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 3255104 | Stationery, Seals & Stamps | REV_11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 3211127 | Books & Periodicals | REV_12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 0 | 0 | 0 | 5.9292 | 16.549 | 17.0718 | 17.0718 | 17.0718 | 17.0718 | 17.0718 | 17.0718 | 17.0718 | 0 | 17.0718 | 17.0718 | 17.0718
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 0 | 0 | 0 | 25.6894 | 54.633 | 105.8736 | 105.8736 | 105.8736 | 105.8736 | 105.8736 | 105.8736 | 105.8736 | 0 | 105.8736 | 105.8736 | 105.8736
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 0 | 0 | 0 | 0 | 7.5043 | 7.5043 | 7.5043 | 7.5043 | 7.5043 | 7.5043 | 7.5043 | 7.5043 | 0 | 7.5043 | 7.5043 | 7.5043
22 | 3211109 | Casual labour/Job worker | REV_15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 3256103 | Consumable Stores | REV_16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 3111332 | b) Interim Evaluation | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3111332 | c) Progress Monitoring | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3257104 | Survey | REV_19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 3255101 | Computer Consumables | REV_20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 3258101 | Motor Vehicles | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 3258102 | Furnitures & Fixtures | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 3258103 | Computers & office equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 3258105 | Machineries & Equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 3258107 | Office Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 3258105 | Engineering Equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 0 | 0 | 0 | 0 | 1.9607 | 29.4608 | 29.4608 | 29.4608 | 29.4608 | 29.4608 | 29.4608 | 29.4608 | 0 | 29.4608 | 29.4608 | 29.4608
39 | 3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 3258107 | Others : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 4112303 | Aircooler | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 108.3874 | 108.3874 | 108.3874 | 108.3874 | 108.3874 | 108.3874 | 108.3874 | 0 | 108.3874 | 108.3874 | 108.3874
59 | 4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 4111201 | Construction of WMG Office | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 4111201 | O&M During Construction | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | XXXXX1 | Physical Contingency | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | XXXXX2 | Price Contingency | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## cum_dpa
| Ecode | Description | Imedcode | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Q1 | Q2 | Q3 | Q4
0 | 3111302 | Conveyance Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3111327 | Overtime Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 3111338 | Other Allowance | REV_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 3211119 | Postage | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 3211120 | Telephones/Telegram/Teleprinter | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 3211117 | Telex/Fax/Internet | REV_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 3221104 | Registration Fee (Vehicles) | REV_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 3211115 | Water | REV_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 3211113 | Electricity | REV_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3243102 | Gas & Fuel | REV_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3243101 | Petrol and Lubricant | REV_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3255102 | Printing & Binding | REV_10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 3255104 | Stationery, Seals & Stamps | REV_11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 3211127 | Books & Periodicals | REV_12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 3211109 | Casual labour/Job worker | REV_15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 3256103 | Consumable Stores | REV_16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | 0 | 0 | 0 | 138.63 | 138.63 | 138.63 | 138.63 | 138.63 | 138.63 | 138.63 | 138.63 | 138.63 | 0 | 138.63 | 138.63 | 138.63
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 3111332 | b) Interim Evaluation | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3111332 | c) Progress Monitoring | REV_18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3257104 | Survey | REV_19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 3255101 | Computer Consumables | REV_20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 3258101 | Motor Vehicles | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 3258102 | Furnitures & Fixtures | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 3258103 | Computers & office equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 3258105 | Machineries & Equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 3258107 | Office Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 3258105 | Engineering Equipments | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 3258107 | Others : Repair & Maintenance | REV_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 4112303 | Aircooler | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | CAP_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 4111201 | Construction of WMG Office | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 4111201 | O&M During Construction | CAP_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | XXXXX1 | Physical Contingency | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | XXXXX2 | Price Contingency | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## quarterly
| Imed_Code | Q1_F | Q2_F | Q3_F | Q4_F | Q1_Phy | Q2_Phy | Q3_Phy | Q4_Phy | Diff_progress
0 | REV_1 | 0.0965 | 6.4377 | 6.4377 | 6.4377 | 0 | 0 | 0 | 0 | 6.3412
1 | REV_2 | 0.91434 | 4.5304 | 4.5304 | 4.5304 | 0 | 0 | 0 | 0 | 3.6161
2 | REV_3 | 8.5521 | 17.1072 | 17.1072 | 17.1072 | 0 | 0 | 0 | 0 | 8.5551
3 | REV_4 | 15.2081 | 71.4953 | 71.4953 | 71.4953 | 0.0005 | 0.002 | 0.002 | 0.002 | 56.2872
4 | REV_5 | 0.08531 | 0.17541 | 0.17541 | 0.17541 | 0 | 0 | 0 | 0 | 0.0901
5 | REV_6 | 0 | 0.06085 | 0.06085 | 0.06085 | 0 | 0 | 0 | 0 | 0.06085
6 | REV_7 | 1.1442 | 2.1098 | 2.1098 | 2.1098 | 0 | 0 | 0 | 0 | 0.96556
7 | REV_8 | 3.2501 | 11.0328 | 11.0328 | 11.0328 | 0 | 0 | 0 | 0 | 7.7827
8 | REV_9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | REV_10 | 0.15404 | 0.41729 | 0.41729 | 0.41729 | 0 | 0 | 0 | 0 | 0.26325
10 | REV_11 | 3.7906 | 10.608 | 10.608 | 10.608 | 0 | 0 | 0 | 0 | 6.8175
11 | REV_12 | 0.00794 | 0.03003 | 0.03003 | 0.03003 | 0 | 0 | 0 | 0 | 0.02209
12 | REV_13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | REV_14 | 0 | 145.2956 | 145.2956 | 145.2956 | 0 | 0.002 | 0.002 | 0.002 | 145.2956
14 | REV_15 | 0.368 | 0.8855 | 0.8855 | 0.8855 | 0 | 0 | 0 | 0 | 0.5175
15 | REV_16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | REV_17 | 0 | 138.63 | 138.63 | 138.63 | 0 | 0.003 | 0.003 | 0.003 | 138.63
17 | REV_18 | 0.69575 | 1.2753 | 1.2753 | 1.2753 | 0 | 0 | 0 | 0 | 0.5796
18 | REV_19 | 0 | 3.0336 | 3.0336 | 3.0336 | 0 | 0 | 0 | 0 | 3.0336
19 | REV_20 | 2.5503 | 5.9981 | 5.9981 | 5.9981 | 0 | 0 | 0 | 0 | 3.4477
20 | REV_21 | 93.4543 | 170.7923 | 170.7923 | 170.7923 | 0 | 0.0035 | 0.0035 | 0.0035 | 77.338
21 | REV_22 | 0.66655 | 37.7176 | 37.7176 | 37.7176 | 0 | 0 | 0 | 0 | 37.0511
22 | CAP_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | CAP_2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | CAP_3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | CAP_4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | CAP_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | CAP_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | CAP_7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | CAP_8 | 0 | 123.8713 | 123.8713 | 123.8713 | 0.015 | 0.0525 | 0.0525 | 0.0525 | 123.8713
30 | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| REV | 130.9381 | 627.6328 | 627.6328 | 627.6328 | 0.0005 | 0.0105 | 0.0105 | 0.0105 | 496.6947
| CAPITAL | 0 | 123.8713 | 123.8713 | 123.8713 | 0.015 | 0.0525 | 0.0525 | 0.0525 | 123.8713
| TOTAL | 130.9381 | 751.5041 | 751.5041 | 751.5041 | 0.0155 | 0.063 | 0.063 | 0.063 | 620.5659 | 0.0475